## Dashboard IPBB
Milestone | Scope
| Swap | % | New | %
00. Migration Done | 1 | 4.167% | 0 | 0%
01. Checklist Go no Go Migration | 1 | 4.167% | 0 | 0%
01a. Integration Done | 2 | 8.333% | 0 | 0%
02. Power On | 3 | 12.5% | 0 | 0%
02a. Installation Done | 3 | 12.5% | 0 | 0%
02a. Permit Install Release | 3 | 0.8475% | 0 | 0%
02b. Permit Install Submit | 3 | 12.5% | 0 | 0%
03. Material On Delivery | 3 | 12.5% | 0 | 0%
04. Material On Region | 3 | 12.5% | 0 | 0%
05. Delivery Transfer | 3 | 12.5% | 0 | 0%
06. RFI | 4 | 16.67% | 0 | 0%
07. DRM Done | 21 | 87.5% | 0 | 0%
08. eTSS Approve XLS | 0 | 0% | 0 | 0%
08a. eTSS Approve ZTE | 4 | 16.67% | 0 | 0%
08b. eTSS Upload | 21 | 87.5% | 0 | 0%
09. Survey Done | 24 | 100% | 0 | 0%
09. Permit Survey Approve
09b. Permit Survey Submit
10. PO Batch 1 Total | 24 | 100% | 1 | 100%

## Summary IPBB
|  |  | Values |  |  |  |  | JAW-JT-KDL-3487 | SN Mangkang
Tower ID | Sites Name | Site Type | Survey Total | eTT Approve ZTE |  |  |  | JAW-JT-MGG-1158 | Magelang
JAW-JT-CLP-0425 | Gandrung Mangu | 2.AG | 1 |  | ccsi |  |  | JAW-JT-PKL-1319
JAW-JT-DMK-0602 | Gadjah Demak | 2.AG | 1 |  | Mingze |  |  | JAW-JT-PTI-1520
JAW-JT-KDL-3487 | SN Mangkang | 3.lv C | 2 |  | GPA |  |  | JAW-JT-PWT-1716
|  | 4.PS | 2 |  |  | JAW-JT-CLP-0425 | Gandrung Mangu | JAW-JT-SKH-1923
JAW-JT-MGG-1158 | Magelang | 2.AG | 1 | 1 | GPA | JAW-JT-PBG-1276 | Purbalingga | JAW-JT-TGL-2600
JAW-JT-PBG-1276 | Purbalingga | 2.AG | 1 |  | ccsi | JAW-JT-PWT-1716 | Purwokerto | JAW-YO-BTL-0074
JAW-JT-PWD-1579 | Purwodadi | 2.AG | 1 |  | Mingze | JAW-JT-SLT-2171 | Tingkir Salatiga | JAW-YO-SMN-0149
JAW-JT-PWT-1716 | Purwokerto | 3.lv C | 1 |  | GPA |  |  | JAW-YO-WNO-0012
JAW-JT-SKH-1923 | SN Solo | 2.AG | 1 |  | GPA |  |  | JAW-YO-YYK-0492
JAW-JT-PKL-1319 | Pekalongan | 2.AG | 1 |  | GPA
JAW-JT-PTI-1520 | Juwana | 2.AG | 1 |  | GPA
JAW-JT-SLT-2171 | Tingkir Salatiga | 2.AG | 1 |  | ccsi | JAW-JT-DMK-0602 | Gadjah Demak
JAW-JT-SMG-3485 | SN Gombel | 2.AG | 1 |  |  | JAW-JT-PWD-1579 | Purwodadi
JAW-JT-TGL-2600 | Tegal | 2.AG | 1 |  | GPA | JAW-JT-UNR-2703 | Karangjati
JAW-JT-UNR-2703 | Karangjati | 2.AG | 1 |  | Mingze | JAW-YO-WAT-0365 | Wates
JAW-YO-BTL-0074 | Imogiri | 2.AG | 1 |  | GPA
JAW-YO-SMN-0149 | Tempel | 2.AG | 1 | 1 | GPA
JAW-YO-WAT-0365 | Wates | 2.AG | 1 |  | Mingze
JAW-YO-WNO-0012 | Wonosari | 2.AG | 1 |  | GPA
JAW-YO-YYK-0492 | Pathuk | 3.lv C | 1 |  | GPA
|  | 4.PS | 2
Grand Total |  |  | 24 | 2

## IPBB Req Material (hidden)
Unique | Tower ID | Sites Name | Long | Lat | City | TP Name | TP ID | Subcon
Swap_JAW-JT-PTI-1520_01 | JAW-JT-PTI-1520 | Juwana | 111.1446 | -6.7188 | Pati | Protelindo | JAW-CJV-0283-X-P | GPA
8SPlus | 2
3SPlus | 1

## IPBB
Vendor | Region | Unique | Tower ID | Sites Name | Site Info | Long | Lat | City | TP Name | TP ID | exist info | Hostname | IP Address | Existing Device | Existing Vendor | New Info | Propose Scope | Scope Uniq | Code | BOQ Type | Final Type | Site Type | Batch | Permit Survey TP Request | Permit Survey MS Request | Permit Survey Request Status | Permit Survey TP Release | Permit Survey MS Release | Permit Survey Release Status | Subcon Survey | Survey Plan | Survey Actual | TSSR Submit by Subcon | eTSS Review Status | TSSR Approved by ZTE | TSSR Approved by XLS | DRM Date | RFI Status | Depedency | Initial LDM | RFI Date | DT Date | Material in WH Region | DO Request | DO Release | Permit Install TP Request | Permit Install MS Request | Permit Install Request Status | Permit Install TP Release | Permit Install MS Release | Permit Install Release Status | MOS Plan | Mos Actual | Subcon Install | Install Plan | Install Actual | Power On Date | MOP Submit | XLWO Release Date | XLWO Number | RFC Release Date | RFC Number | Integration Plan | Integration Actual | Checklist Go no Go | Migration Plan | Migration Actual | Final LDM | Upload to MATRA | Dismantle Date | Inbound Plan | Inbound Actual | ATP Plan | ATP Actual | RCA
ZTE | Central Java | Swap_JAW-JT-SMG-3485_01 | JAW-JT-SMG-3485 | SN Gombel |  | 110.4175 | -7.09636111111111 | Kota Semarang | NO TP NAME | NO TP ID |  | AG-SMSGB-01H | 112.215.186.119 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _01 | M6000-8S Plus | M6000-8S Plus | 2.AG | 1 | [6 empty] | GPA |  | 2025-10-28 | 2025-11-04 | Reviewing |  |  | 2025-11-05 | NY RFI | Need Modernize Rectifier & Battery
ZTE | Central Java | Swap_JAW-JT-CLP-0425_01 | JAW-JT-CLP-0425 | Gandrung Mangu |  | 108.8552 | -7.5253 | Cilacap | PT CENTRATAMA MENARA INDONESIA | JAW-JT-CLP-0425 |  | AG-SMGDM-01H | 202.152.246.146 | NE40E-M2K-B | Huawei |  | Swap | Swap_ | _01 | M6000-3S Plus | M6000-3S Plus | 2.AG | 1 | [6 empty] | CCSI | 2025-10-25 | 2025-10-25 | 2025-10-31 | Reviewing |  |  | 2025-11-04 | NY RFI | Need Modernization Battery
ZTE | Central Java | Swap_JAW-JT-KDL-3487_01 | JAW-JT-KDL-3487 | SN Mangkang |  | 110.270188888889 | -6.96536111111111 | Kendal | NO TP NAME | NO TP ID |  | C-SMSMK-01H | 202.152.246.86 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _01 | M6000-8SE | M6000-8SE | 3.lv C | 1 | [6 empty] | GPA | 2025-10-26 | 2025-10-28 | 2025-10-29 | Reviewing |  |  | 2025-11-04 | NY RFI | Need Upgrade PLN, Need Reloc ACPDB, Rebalancing load PLN, Need Add Battery
ZTE | Central Java | Swap_JAW-JT-KDL-3487_2 | JAW-JT-KDL-3487 | SN Mangkang |  | 110.270188888889 | -6.96536111111111 | Kendal | NO TP NAME | NO TP ID |  | C-SMSMK-02H | 202.152.247.220 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _2 | M6000-8SE | M6000-8SE | 3.lv C | 1 | [6 empty] | GPA | 2025-10-26 | 2025-10-28 | 2025-10-29 | #N/A |  |  | 2025-11-04 | NY RFI | Need Upgrade PLN, Need Reloc ACPDB, Rebalancing load PLN, Need Add Battery
ZTE | Central Java | Swap_JAW-JT-KDL-3487_3 | JAW-JT-KDL-3487 | SN Mangkang |  | 110.270188888889 | -6.96536111111111 | Kendal | NO TP NAME | NO TP ID |  | PS-SMSMK-01H | 202.152.246.117 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _3 | M6000-4SE | M6000-4SE | 4.PS | 1 | [6 empty] | GPA | 2025-10-26 | 2025-10-28 | 2025-10-29 | #N/A |  |  | 2025-11-04 | NY RFI | Need Upgrade PLN, Need Reloc ACPDB, Rebalancing load PLN, Need Add Battery
ZTE | Central Java | Swap_JAW-JT-KDL-3487_4 | JAW-JT-KDL-3487 | SN Mangkang |  | 110.270188888889 | -6.96536111111111 | Kendal | NO TP NAME | NO TP ID |  | PS-SMSMK-02H | 202.152.246.118 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _4 | M6000-4SE | M6000-4SE | 4.PS | 1 | [6 empty] | GPA | 2025-10-26 | 2025-10-28 | 2025-10-29 | #N/A |  |  | 2025-11-04 | NY RFI | Need Upgrade PLN, Need Reloc ACPDB, Rebalancing load PLN, Need Add Battery
ZTE | Central Java | Swap_JAW-YO-SMN-0149_01 | JAW-YO-SMN-0149 | Tempel |  | 110.3268 | -7.6508 | Sleman | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JAW-JGJ-0079-X-P |  | AG-YGTPL-01H | 202.152.247.168 | NE40E-M2K-B | Huawei |  | Swap | Swap_ | _01 | M6000-3S Plus | M6000-3S Plus | 2.AG | 1 | [6 empty] | GPA |  | 2025-10-21 | 2025-10-29 | Reviewing | 2025-10-21 |  | 2025-10-21 | RFI | Waiting MOCN Implementation |  | 2025-10-21 | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | 2025-11-11 | 2025-11-11 | GPA |  | 2025-11-11 | 2025-11-13 | Done | Done | Done | Done | Done | Done | 2025-11-13 | 2025-11-21 |  | 2025-11-23
ZTE | Central Java | Swap_JAW-JT-MGG-1158_01 | JAW-JT-MGG-1158 | Magelang |  | 110.2269 | -7.4796 | Kota Magelang | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JAW-CJV-0262-X-P |  | AG-SMMGL-01H | 202.152.246.18 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _01 | M6000-8S Plus | M6000-8S Plus | 2.AG | 1 | [6 empty] | GPA |  | 2025-10-23 | 2025-10-29 | Reviewing | 2025-10-21 |  | 2025-10-21 | RFI |  |  | 2025-10-21 | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | 2025-11-05 | 2025-11-08 | GPA |  | 2025-11-10 | 2025-11-23 | Done | Done | Done | Done | Done | Done | 2025-11-23
ZTE | Central Java | Swap_JAW-JT-SKH-1923_01 | JAW-JT-SKH-1923 | SN Solo |  | 110.8363 | -7.68366944444444 | Sukoharjo | NO TP NAME | NO TP ID |  | AG-YGSNS-01H | 202.152.246.41 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _01 | M6000-8S Plus | M6000-8S Plus | 2.AG | 1 | [6 empty] | GPA | 2025-10-25 | 2025-10-25 | 2025-10-29 | Reviewing |  |  | 2025-11-04 | NY RFI | Need Replace Battery, Need Add Module Recti, Need Repair Genset
ZTE | Central Java | Swap_JAW-YO-YYK-0492_01 | JAW-YO-YYK-0492 | Pathuk |  | 110.3595 | -7.7893 | Kota Yogyakarta | PT XL Axiata | JAW-YO-YYK-0492 |  | C-YGPTH-01H | 112.215.186.72 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _01 | M6000-8SE | M6000-8SE | 3.lv C | 1 | [6 empty] | GPA | 2025-10-26 | 2025-10-29 | 2025-10-29 | Reviewing |  |  | 2025-11-04 | NY RFI | Need Upgrade & Modernize Rectifier, Need add Battery
ZTE | Central Java | Swap_JAW-YO-YYK-0492_2 | JAW-YO-YYK-0492 | Pathuk |  | 110.3595 | -7.7893 | Kota Yogyakarta | PT XL Axiata | JAW-YO-YYK-0492 |  | PS-YGPTH-01H | 202.152.247.207 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _2 | M6000-4SE | M6000-4SE | 4.PS | 1 | [6 empty] | GPA | 2025-10-26 | 2025-10-29 | 2025-10-29 | #N/A |  |  | 2025-11-04 | NY RFI | Need Upgrade & Modernize Rectifier, Need add Battery
ZTE | Central Java | Swap_JAW-YO-YYK-0492_3 | JAW-YO-YYK-0492 | Pathuk |  | 110.3595 | -7.7893 | Kota Yogyakarta | PT XL Axiata | JAW-YO-YYK-0492 |  | PS-YGPTH-02H | 202.152.247.208 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _3 | M6000-4SE | M6000-4SE | 4.PS | 1 | [6 empty] | GPA | 2025-10-26 | 2025-10-29 | 2025-10-29 | #N/A |  |  | 2025-11-04 | NY RFI | Need Upgrade & Modernize Rectifier, Need add Battery
ZTE | Central Java | Swap_JAW-JT-PBG-1276_01 | JAW-JT-PBG-1276 | Purbalingga |  | 109.3623 | -7.3873 | Purbalingga | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JAW-CJV-0290-X-P |  | AG-SMPBL-01H | 202.152.246.19 | NetEngine 8000 M8 | Huawei |  | Swap | Swap_ | _01 | M6000-3S Plus | M6000-3S Plus | 2.AG | 1 | [6 empty] | CCSI |  | 2025-10-24 | 2025-10-31 | Reviewing |  |  | 2025-11-04 | NY RFI | Need Upgrade PLN, Need Add Module Recti, Need Add AC, Need Modernize Battery
ZTE | Central Java | Swap_JAW-JT-PKL-1319_01 | JAW-JT-PKL-1319 | Pekalongan |  | 109.664 | -6.8909 | Kota Pekalongan | PT XL Axiata | JAW-JT-PKL-1319 |  | AG-SMPKL-01H | 112.215.48.53 | NetEngine 8000 M14 | Huawei |  | Swap | Swap_ | _01 | M6000-3S Plus | M6000-8S Plus | 2.AG | 1 | [6 empty] | GPA | 2025-10-25 | 2025-10-25 |  | #N/A |  |  | 2025-10-29 | NY RFI | Need Swap Battery
ZTE | Central Java | Swap_JAW-JT-SLT-2171_01 | JAW-JT-SLT-2171 | Tingkir Salatiga |  | 110.5156 | -7.3627 | Kota Salatiga | PT CENTRATAMA MENARA INDONESIA | JAW-JT-SLT-2171 |  | AG-SMTKR-01H | 202.152.247.182 | NE40E-M2K-B | Huawei |  | Swap | Swap_ | _01 | M6000-3S Plus | M6000-8S Plus | 2.AG | 1 | [6 empty] | CCSI |  | 2025-10-24 | 2025-10-31 | Reviewing |  |  | 2025-10-27 | NY RFI | Need Upgrade PLN Need Add AC Need Upgrade Genset
ZTE | Central Java | Swap_JAW-JT-DMK-0602_01 | JAW-JT-DMK-0602 | Gadjah Demak |  | 110.7173 | -6.8738 | Demak | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JAW-CJV-0247-X-P |  | AG-SMGJH-01H | 202.152.247.184 | NetEngine 8000 M8 | Huawei |  | Swap | Swap_ | _01 | #N/A | M6000-3S Plus | 2.AG | 1 | [6 empty] | Mingze |  | 2025-10-27 | 2025-10-31 | Reviewing | 2025-08-11 |  | 2025-11-04 | RFI
ZTE | Central Java | Swap_JAW-JT-PWD-3478_01 | JAW-JT-PWD-3478 | Purwodadi |  | 110.917 | -7.0717 | Grobogan | PT XL Axiata | JAW-JT-PWD-3478 |  | AG-SMPWD-01H | 202.152.246.40 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _01 | M6000-8S Plus | M6000-8S Plus | 2.AG | 1 | [6 empty] | Mingze |  | 2025-10-27 |  | #N/A |  |  | 2025-11-05 | NY RFI | Need Modernize Rectifier & Battery, Need Repair AC |  |  | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | 2025-11-12 | 2025-11-12 | Mingze |  | 2025-11-12 | 2025-11-23 | Done | Done | Done | Done | Done
ZTE | Central Java | Swap_JAW-YO-WNO-0012_01 | JAW-YO-WNO-0012 | Wonosari |  | 110.5969 | -7.9688 | Wonosari | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JAW-JGJ-0067-H-P |  | AG-YGWNS-01H | 202.152.247.165 | NE40E-M2K-B | Huawei |  | Swap | Swap_ | _01 | M6000-3S Plus | M6000-3S Plus | 2.AG | 1 | [6 empty] | GPA |  | 2025-10-23 | 2025-10-29 | Reviewing
ZTE | Central Java | Swap_JAW-JT-TGL-2600_01 | JAW-JT-TGL-2600 | Tegal |  | 109.143 | -6.8618 | Kota Tegal | PT XL Axiata | JAW-JT-TGL-2600 |  | AG-SMTGL-01H | 202.152.247.212 | NetEngine 8000 M14 | Huawei |  | Swap | Swap_ | _01 | M6000-8S Plus | M6000-8S Plus | 2.AG | 1 | [6 empty] | GPA | 2025-10-25 | 2025-10-25 |  | #N/A |  |  | 2025-10-29 | NY RFI | Need Swap Battery
ZTE | Central Java | Swap_JAW-JT-PTI-1520_01 | JAW-JT-PTI-1520 | Juwana |  | 111.1446 | -6.7188 | Pati | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JAW-CJV-0283-X-P |  | AG-SMJWN-01H | 202.152.247.185 | NetEngine 8000 M8 | Huawei |  | Swap | Swap_ | _01 | #N/A | M6000-3S Plus | 2.AG | 1 | [6 empty] | GPA |  | 2025-10-24 | 2025-11-04 | Reviewing |  |  | 2025-10-28 | RFI |  | 2025-10-28
ZTE | Central Java | Swap_JAW-JT-PWT-1716_01 | JAW-JT-PWT-1716 | Purwokerto |  | 109.2214 | -7.4218 | Banyumas | PT XL Axiata | XL |  | C-SMPRW-01H | 112.215.48.39 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _01 | M6000-8SE | M6000-8SE | 3.lv C | 1 | [6 empty] | GPA |  | 2025-10-24 | 2025-11-04 | Reviewing | 2025-08-11 |  | 2025-11-05 | NY RFI | Need Modernize Rectifier & Battery, Need AC
ZTE | Central Java | Swap_JAW-YO-WAT-0365_01 | JAW-YO-WAT-0365 | Wates |  | 110.1609 | -7.8573 | Kulon Progo | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JAW-YO-WAT-0365 |  | AG-YGWAT-01H | 112.215.48.51 | NetEngine 8000 M8 | Huawei |  | Swap | Swap_ | _01 | M6000-3S Plus | M6000-3S Plus | 2.AG | 1 | [6 empty] | Mingze |  | 2025-10-29 | 2025-11-04 | Reviewing
ZTE | Central Java | Swap_JAW-YO-BTL-0074_01 | JAW-YO-BTL-0074 | Imogiri |  | 110.382 | -7.9223 | Bantul | PT CENTRATAMA MENARA INDONESIA | JAW-YO-BTL-0074 |  | AG-YGIMG-01H | 202.152.247.166 | NetEngine 8000 M8 | Huawei |  | Swap | Swap_ | _01 | M6000-3S Plus | M6000-8S Plus | 2.AG | 1 | [6 empty] | GPA |  | 2025-10-24 | 2025-10-31 | Reviewing |  |  | 2025-10-30 | NY RFI | Need Upgrade PLN Need Upgrade & Replace Battery
ZTE | Central Java | Swap_JAW-JT-UNR-2703_01 | JAW-JT-UNR-2703 | Karangjati |  | 110.4226 | -7.1818 | Semarang | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JAW-CJV-0295-X-P |  | AG-SMKRJ-01H | 112.215.48.52 | NetEngine 8000 M14 | Huawei |  | Swap | Swap_ | _01 | M6000-3S Plus | M6000-3S Plus | 2.AG | 1 | [6 empty] | Mingze |  | 2025-10-26 | 2025-10-31 | Reviewing
ZTE | Central Java | New_JAW-YO-YYK-0492_01 | JAW-YO-YYK-0492 | Pathuk |  | 110.3595 | -7.7893 | Kota Yogyakarta | PT XL Axiata | JAW-YO-YYK-0492 |  | C-YGPTH-02H |  | NE40E-X8A(V8) | Huawei |  | New | New_ | _01 | M6000-8SE | M6000-8SE | 3.lv C | [7 empty] | GPA |  |  |  | #N/A

## IPRAN Req Material (hidden)
Uniq ID | ScopeID | NewXLS ID | SiteName | Region | Provice | City | Lat | Long | Scope Update | Type | Class Type | Subcon | Pic | Phone
Swap_JAW-JT-PWT-1716_2 | Swap_JAW-JT-PWT-1716 | JAW-JT-PWT-1716 | Mpls - Purwokerto | Central Java | Jawa Tengah | Banyumas | -7.4218 | 109.2214 | Swap | Type C | PAG | GPA | Andriyana | +62 896-9026-4421
Swap_JAW-JT-PWT-1773_1 | Swap_JAW-JT-PWT-1773 | JAW-JT-PWT-1773 | Kembaran | Central Java | Jawa Tengah | Banyumas | -7.4028 | 109.2861 | Swap | Type C | PAG | GPA | Andriyana | +62 896-9026-4421
Uniq ID | ScopeID | NewXLS ID | SiteName | Region | City | Lat | Long | SOW | Type | Site Type | Subcon | PIC | Phone
Swap_JAW-JT-JPA-0651_1 | Swap_JAW-JT-JPA-0651 | JAW-JT-JPA-0651 | Pecangaan | Central Java | Jepara | -6.7307 | 110.723 | Swap Only | Type B | MA | GIT | Rudi Hartono | +62 882-9359-7647
Swap_JAW-JT-PTI-1497_1 | Swap_JAW-JT-PTI-1497 | JAW-JT-PTI-1497 | Tayu | Central Java | Pati | -6.5364 | 111.0546 | Swap Only | Type B | MA | GIT | Rudi Hartono | +62 882-9359-7647
Swap_JAW-JT-JPA-0629_1 | Swap_JAW-JT-JPA-0629 | JAW-JT-JPA-0629 | Tahunan | Central Java | Jepara | -6.6204 | 110.6881 | Swap Only | Type B | MA | GIT | Rudi Hartono | +62 882-9359-7647

## Fishbone
|  |  |  | Swap Done | 99
|  | Mos + Install | 99 | NY Swap | 7 | Plan 23 Nov 2025
Swap
157
|  | NY Mos + Install | 58 | Plan W48 | 59
IPRAN Nov Target
245
| New Fiber | Plan W46 | 26
| 88 | Plan W47 | 30
|  | Plan W48 | 32

## FTTS Site
RING ID LMS | TOWER ID A | Site Name A | TOWERI ID B | Site Name B | FLP PARTNER | Span ID LMS | Tower Owner Group A | Tower Owner B | Kota / Kabupaten | Termination Status A | Termination Status B | SPAN STATUS | RING Status | Ring Type | RFS Actual Date | MoP Status | MMP Status | Subcon | Assignment | DO Req | DO Release | Plan Visit | Visit | Jumpering NE | Jumpering FE | RFM Status | Remark
R0000019821 | JAW-JT-JPA-0713 | KERSO_JEPARA | JAW-JT-JPA-0621 | Kedung | PT IFORTE SOLUSI INFOTEK | S000054242 | NON TBG | PT CENTRATAMA MENARA INDONESIA | JEPARA | 13b. TERMINATION ODP ACPDP | 13. TERMINATION DONE | 09. TERMINATION WORK | 10. READY ATP / RFS | Star | 2025-11-09 | MoP NY Prepare | Ok Proceed | GCI | Done |  |  |  | 2025-11-20 | 2025-11-20 | 2025-11-20 | RFM
R0000019823 | JAW-JT-JPA-8420 | SF-ZSMG_1948-Mindahan Batealit | JAW-JT-JPA-0660 | BATEALIT | PT IFORTE SOLUSI INFOTEK | S000054244 | TBG GROUP | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JEPARA | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | Star | 2025-11-09 | MoP NY Prepare | MMP Issue - Hold | GCI | Done
R0000019831 | JAW-JT-JPA-8337 | SF-ZSMG_1654-JEPARA | JAW-JT-JPA-3402 | Tahunan Tahunan | PT IFORTE SOLUSI INFOTEK | S000054252 | NON TBG | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JEPARA | 13b. TERMINATION ODP ACPDP | 13. TERMINATION DONE | 09. TERMINATION WORK | 10. READY ATP / RFS | Star | 2025-11-09 | MoP NY Prepare | Ok Proceed | GCI | Done |  |  |  | 2025-11-20 |  |  |  | NE Access Issue, No ODP at FE
R0000019833 | JAW-JT-JPA-8316 | SF-ZSMG_1747-DEMAAN JEPARA | JAW-JT-JPA-0617 | DEMAAN JEPARA | PT IFORTE SOLUSI INFOTEK | S000054254 | NON TBG | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JEPARA | 13b. TERMINATION ODP ACPDP | 13. TERMINATION DONE | 09. TERMINATION WORK | 10. READY ATP / RFS | Star | 2025-11-09 | MoP NY Prepare | Ok Proceed | GCI | Done |  |  |  | 2025-11-20 | 2025-11-20 | 2025-11-20 | RFM
R0000019873 | JAW-JT-PWD-8505 | SF-ZSMG2_0003-GROBOKAN GABUS | JAW-JT-PWD-1619 | 3G_GABUS_GABUS | PT IFORTE SOLUSI INFOTEK | S000054395 | TBG GROUP | PT GIHON TELEKOMUNIKASI INDONESIA | GROBOGAN | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 | MoP NY Prepare | MMP Issue - Hold | GCI | Done
R0000019876 | JAW-JT-PWD-8499 | SF-ZSMG_2115-Ngaringan II | JAW-JT-PWD-0150 | 3G_GAGAAN_KUNDURAN | PT IFORTE SOLUSI INFOTEK | S000054398 | NON TBG | PT TOWER BERSAMA | GROBOGAN | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 | MoP NY Prepare | MMP Issue - Hold | GCI | Done
R0000019879 | JAW-JT-PWD-8413 | SF-ZSMG_2690-GROBOGAN GROBOGAN 2 | JAW-JT-PWD-1582 | Grobogan | PT IFORTE SOLUSI INFOTEK | S000054401 | TBG GROUP | PT SOLUSI TUNAS PRATAMA TBK | GROBOGAN | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 | MOP Submitted | MMP Issue - Hold | GCI | Done
R0000019881 | JAW-JT-PWD-8523 | SF-ZSMG_1635-Plumpung Kemadoh Batur | JAW-JT-PWD-1599 | Gn.Gading Kemahduhbatur | PT IFORTE SOLUSI INFOTEK | S000054403 | TBG GROUP | PT TOWER BERSAMA | GROBOGAN | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 | MOP Submitted | MMP Issue - Hold | GCI | Done
R0000019884 | JAW-JT-PWD-8517 | SF-ZSMG2_0226-Grogolan Sambirejo D | JAW-JT-PWD-1600 | Tanjungrejo Wirosari (Collocation Tower) | PT IFORTE SOLUSI INFOTEK | S000054406 | NON TBG | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | GROBOGAN | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 | MOP Submitted | Ok Proceed | GCI | Done |  |  |  | 2025-11-21 |  | 2025-11-21 |  | NE NY Jumpering
R0000019975 | JAW-JT-UNR-2548 | COKROAMINOTO UNGARAN | JAW-JT-UNR-2689 | Ungaran Kota | PT IFORTE SOLUSI INFOTEK | S000054598 | NON TBG | PT DAYAMITRA TELEKOMUNIKASI | SEMARANG | 13. TERMINATION DONE | 13. TERMINATION DONE | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 | MoP NY Prepare | Ok Proceed | GCI | Done |  |  |  | 2025-11-21 |  | 2025-11-21 |  | NE NY Jumpering
R0000019981 | JAW-JT-UNR-8443 | SF-ZSMG_1582-Candirejo | JAW-JT-UNR-2688 | Candirejo Ungaran | PT IFORTE SOLUSI INFOTEK | S000054604 | TBG GROUP | PT TOWER BERSAMA | SEMARANG | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 | MoP NY Prepare | MMP Issue - Hold | GCI | Done
R0000019991 | JAW-JT-UNR-2551 | RANDUGUNTING_RELOCATION | JAW-JT-UNR-2704 | 3G Harjosari | PT IFORTE SOLUSI INFOTEK | S000054614 | NON TBG | PT DAYAMITRA TELEKOMUNIKASI | SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 | MoP NY Prepare | Ok Proceed | GCI | Done | [7 empty] | Team Changing
R0000019997 | JAW-JT-UNR-8447 | SF-ZSMG_1591-Banaran Ambarawa | JAW-JT-UNR-2682 | Kota Ambarawa Relocation | PT IFORTE SOLUSI INFOTEK | S000054620 | TBG GROUP | PT SOLUSINDO KREASI PRATAMA | SEMARANG | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 | MoP NY Prepare | MMP Issue - Hold | GCI | Done
R0000020053 | JAW-JT-SMG-0617 | TUGU INDUSTRI SEMARANG | JAW-JT-SMG-2327 | Site Ngaliyan | PT IFORTE SOLUSI INFOTEK | S000054676 | NON TBG | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 | MOP Submitted | Ok Proceed | GCI | Done |  |  |  | 2025-11-20 | 2025-11-20 | 2025-11-19 | RFM
R0000020055 | JAW-JT-SMG-2316 | GAMBILANGU | JAW-JT-SMG-2318 | WONOSARI NGALIAN | PT IFORTE SOLUSI INFOTEK | S000054678 | TBG GROUP | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | KOTA SEMARANG | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 | MOP Submitted | MMP Issue - Hold | GCI | Done
R0000020062 | JAW-JT-SMG-8495 | SF-ZSMG_1006-TANGGULMAS | JAW-JT-SMG-2407 | PANGGUNG KIDUL | PT IFORTE SOLUSI INFOTEK | S000054685 | NON TBG | PT SOLUSINDO KREASI PRATAMA | KOTA SEMARANG | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 | MOP Submitted | MMP Issue - Hold | GCI | Done
R0000020068 | JAW-JT-SMG-2957 | MANGUNHARJOTUGU | JAW-JT-SMG-2323 | Mangkang Wetan 3G | PT IFORTE SOLUSI INFOTEK | S000054691 | NON TBG | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 | MOP Submitted | Ok Proceed | GCI | Done |  |  |  | 2025-11-20 | 2025-11-19 | 2025-11-19 | RFM
R0000020087 | JAW-JT-SMG-0602 | WARU PEDALANGAN BANYUMANIK | JAW-JT-SMG-2459 | Padangsari Semarang | PT IFORTE SOLUSI INFOTEK | S000054710 | NON TBG | PT TOWER BERSAMA | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 | MOP Submitted | Ok Proceed | GCI | Done |  |  |  | 2025-11-20 |  |  |  | No ODP at NE, FE MMP TBG
R0000020098 | JAW-JT-SMG-0531 | Maera Sari | JAW-JT-SMG-2509 | 3G UNDIP Tembalang | PT IFORTE SOLUSI INFOTEK | S000054721 | TBG GROUP | PT DAYAMITRA TELEKOMUNIKASI | KOTA SEMARANG | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 | MOP Submitted | MMP Issue - Hold | GCI | Done
R0000020102 | JAW-JT-SMG-2510 | Bulusan Tembalang | JAW-JT-SMG-3473 | LTE_TIRTO_AGUNG_RELOCATION | PT IFORTE SOLUSI INFOTEK | S000054725 | NON TBG | PT EDOTCO INFRASTRUKTUR INDONESIA | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13. TERMINATION DONE | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 | MOP Submitted | Ok Proceed | GCI | Done |  |  |  | 2025-11-20 |  | 2025-11-20 |  | No ODP at NE
R0000020110 | JAW-JT-SMG-2317 | Wonoplumbon Kendal | JAW-JT-SMG-2322 | Mijen Semarang | PT IFORTE SOLUSI INFOTEK | S000054733 | NON TBG | PT SOLUSI TUNAS PRATAMA TBK | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 | MoP NY Prepare | Ok Proceed | GCI | Done |  |  |  | 2025-11-21 | 2025-11-21 | 2025-11-21 | RFM
R0000020111 | JAW-JT-SMG-2353 | SADENG GUNUNG PATI | JAW-JT-SMG-2346 | 3G_PUNGANGAN_GUNUNGPATI | PT IFORTE SOLUSI INFOTEK | S000054734 | TBG GROUP | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | KOTA SEMARANG | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-02 | MOP Submitted | MMP Issue - Hold | GCI | Done
R0000020133 | JAW-JT-SMG-2951 | BRINGIN NGALIYAN | JAW-JT-SMG-2336 | Kadung Pane | PT IFORTE SOLUSI INFOTEK | S000054756 | TBG GROUP | PT SOLUSI TUNAS PRATAMA TBK | KOTA SEMARANG | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 | MoP NY Prepare | MMP Issue - Hold | GCI | Done
R0000020137 | JAW-JT-SMG-0547 | BERINGIN NGALIYAN RELOCATION | JAW-JT-SMG-2336 | Kadung Pane | PT IFORTE SOLUSI INFOTEK | S000054760 | TBG GROUP | PT SOLUSI TUNAS PRATAMA TBK | KOTA SEMARANG | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 | MoP NY Prepare | MMP Issue - Hold | GCI | Done
R0000020141 | JAW-JT-SMG-2324 | Gondoriyo Ngaliyan | JAW-JT-SMG-2336 | Kadung Pane | PT IFORTE SOLUSI INFOTEK | S000054764 | TBG GROUP | PT SOLUSI TUNAS PRATAMA TBK | KOTA SEMARANG | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 | MOP Submitted | MMP Issue - Hold | GCI | Done
R0000020333 | JAW-JT-PWD-8425 | SF-ZSMG2_0621-PURWODADI UTR | JAW-JT-PWD-1572 | Kuripan Purwodadi | PT IFORTE SOLUSI INFOTEK | S000055170 | NON TBG | PT PERSADA SOKKA TAMA | GROBOGAN | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK | 10. READY ATP / RFS | Star | 2025-11-09 | MoP NY Prepare | Ok Proceed | GCI | Done | [7 empty] | Team Changing
R0000019814 | JAW-JT-JPA-8392 | SF-ZSMG_2840-Paren Mayong B | JAW-JT-JPA-0649 | 3G KALIPUCANG WETAN | PT IFORTE SOLUSI INFOTEK | S000054235 | PT INTI BANGUN SEJAHTERA | NON TBG | JEPARA | 13b. TERMINATION ODP ACPDP | 13. TERMINATION DONE | 09. TERMINATION WORK |  | Star | 2025-11-17 | MoP NY Prepare | Ok Proceed | Mingze | Need Email | 1
R0000019819 | JAW-JT-JPA-8383 | SF-ZSMG_2877-Banyuputih Kalinyamatan A1 | JAW-JT-JPA-0603 | Pendosawalan | PT IFORTE SOLUSI INFOTEK | S000054240 | PT INTI BANGUN SEJAHTERA | NON TBG | JEPARA | 13b. TERMINATION ODP ACPDP | 13. TERMINATION DONE | 09. TERMINATION WORK |  | Star | 2025-11-17 | MoP NY Prepare | Ok Proceed | Mingze | Need Email | 2
R0000019836 | JAW-JT-JPA-8360 | SF-ZSMG2_0024-Kedungsarimulyo | JAW-JT-JPA-0601 | Kedungsarimulyo | PT IFORTE SOLUSI INFOTEK | S000054257 | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | NON TBG | JEPARA | 13b. TERMINATION ODP ACPDP | 13. TERMINATION DONE | 09. TERMINATION WORK |  | Star | 2025-11-17 | MoP NY Prepare | Ok Proceed | Mingze | Need Email | 3
R0000019871 | JAW-JT-PWD-8399 | SF-ZSMG2_0099-Mangonan B@1 | JAW-JT-PWD-1565 | Brati | PT IFORTE SOLUSI INFOTEK | S000054393 | PT INTI BANGUN SEJAHTERA | NON TBG | GROBOGAN | 13. TERMINATION DONE | 13. TERMINATION DONE | 09. TERMINATION WORK |  | Star | 2025-11-17 | MoP NY Prepare | Ok Proceed | Mingze | Need Email | 1
R0000019875 | JAW-JT-PWD-8381 | SF-ZSMG_2952-Wolo F1 | JAW-JT-PWD-1558 | Penawangan | PT IFORTE SOLUSI INFOTEK | S000054397 | PT INTI BANGUN SEJAHTERA | NON TBG | GROBOGAN | 13. TERMINATION DONE | 13. TERMINATION DONE | 09. TERMINATION WORK |  | Star | 2025-11-17 | MoP NY Prepare | Ok Proceed | Mingze | Need Email | 2
R0000019885 | JAW-JT-PWD-8568 | SF-ZSMG_2947-Sukoharjo Kradenan D | JAW-JT-PWD-1613 | Kuwu | PT IFORTE SOLUSI INFOTEK | S000054407 | PT INTI BANGUN SEJAHTERA | NON TBG | GROBOGAN | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK |  | Star | 2025-11-17 | MoP NY Prepare | Ok Proceed | Mingze | Need Email | 3
R0000019976 | JAW-JT-UNR-8478 | SF-ZSMG_1757-KALIREJO CITY | JAW-JT-UNR-2702 | Kutilangsari Ungaran | PT IFORTE SOLUSI INFOTEK | S000054599 | PT INTI BANGUN SEJAHTERA | NON TBG | SEMARANG | 13. TERMINATION DONE | 13. TERMINATION DONE | 09. TERMINATION WORK |  | Star | 2025-11-17 | MoP NY Prepare | Ok Proceed | GPA | Need Email
R0000019978 | JAW-JT-UNR-8462 | SF-ZSMG_2516-Letjend S Parman Ungaran | JAW-JT-UNR-2684 | 3G Ungaran Selatan | PT IFORTE SOLUSI INFOTEK | S000054601 | PT DAYAMITRA TELEKOMUNIKASI | NON TBG | SEMARANG | 13. TERMINATION DONE | 13. TERMINATION DONE | 09. TERMINATION WORK |  | Star | 2025-11-17 | MoP NY Prepare | Ok Proceed | GPA | Need Email
R0000020017 | JAW-JT-SMG-0590 | Lotte Semarang | JAW-JT-SMG-2511 | Katamso Lamper Lor (Regular) | PT IFORTE SOLUSI INFOTEK | S000054640 | PT BINA MITRA SEHATI | NON TBG | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK |  | Star | 2025-11-17 | MoP NY Prepare | Ok Proceed | GPA | Need Email
R0000020082 | JAW-JT-SMG-0609 | JL. RAYASEMARANG BOJA TAMBANGAN | JAW-JT-SMG-2322 | Mijen Semarang | PT IFORTE SOLUSI INFOTEK | S000054705 | PT EPID MENARA ASSETCO | NON TBG | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK |  | Star | 2025-11-17 | MoP NY Prepare | Ok Proceed | GPA | Need Email
R0000020084 | JAW-JT-SMG-0603 | RASAMALA RAYA SRONDOL | JAW-JT-SMG-2459 | Padangsari Semarang | PT IFORTE SOLUSI INFOTEK | S000054707 |  |  | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP |  |  | Star | 2025-11-17 | MoP NY Prepare | Ok Proceed | GPA | Need Email
R0000020086 | JAW-JT-SMG-2542 | Bukit Kencana II 3G | JAW-JT-SMG-2559 | Meteseh | PT IFORTE SOLUSI INFOTEK | S000054709 | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | NON TBG | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK |  | Star | 2025-11-17 | MoP NY Prepare | Ok Proceed | GPA | Need Email
R0000020090 | JAW-JT-SMG-0544 | Transmart Setiabudi Semarang | JAW-JT-SMG-2422 | ADA_DEPT_STORE | PT IFORTE SOLUSI INFOTEK | S000054713 | PT DHOST TELEKOMUNIKASI NUSANTARA | NON TBG | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK |  | Star | 2025-11-17 | MoP NY Prepare | Ok Proceed | GPA | Need Email
R0000020093 | JAW-JT-SMG-8466 | SF-ZSMG_0643-SRONDOL | JAW-JT-SMG-2422 | ADA_DEPT_STORE | PT IFORTE SOLUSI INFOTEK | S000054716 | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | NON TBG | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK |  | Star | 2025-11-17 | MoP NY Prepare | Ok Proceed | GPA | Need Email
R0000020096 | JAW-JT-SMG-2543 | 3G_METESEH_TEMBALANG | JAW-JT-SMG-2559 | Meteseh | PT IFORTE SOLUSI INFOTEK | S000054719 | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | NON TBG | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK |  | Star | 2025-11-17 | MoP NY Prepare | Ok Proceed | GPA | Need Email
R0000020145 | JAW-JT-SMG-0622 | MANYARAN RELOCATION | JAW-JT-SMG-2368 | Kalibanteng Kidul | PT IFORTE SOLUSI INFOTEK | S000054768 | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | NON TBG | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13. TERMINATION DONE | 09. TERMINATION WORK |  | Star | 2025-11-17 | MoP NY Prepare | Ok Proceed | GPA | Need Email

## Dashboard
Milestone | Scope | [7 empty] | Milestone | Scope
| Swap | % | New | % | Modernize | % | Service Migration | % |  | Swap | %
00. Migration Done | 101 | 28.53% | 0 | 0% | 0 | 0% | 0 | 0% | 00. Inbound | 64 | 64.65%
01. Integration Done | 101 | 28.53% | 0 | 0% | 0 | 0% | 0 | 0% | 01. Dismantle | 92 | 92.93%
02. Installation Done | 101 | 28.53% | 1 | 0.1179% | 0 | 0% | 0 | 0% | 02. Migration Done | 101 | 102%
02a. Permit Install Release | 101 | 28.53% | 1 | 0.1179% | 0 | 0% | 0 | 0%
02b. Permit Install Submit | 101 | 28.53% | 1 | 0.1179% | 0 | 0% | 0 | 0%
03. Material On Delivery | 101 | 28.53% | 1 | 0.1179% | 0 | 0% | 0 | 0%
04. Material On Region | 120 | 33.9% | 1 | 0.1179% | 2 | 6.452% | 0 | 0%
05. Delivery Transfer | 120 | 33.9% | 1 | 0.1179% | 2 | 6.452% | 0 | 0%
06. RFI | 101 | 28.53% | 0 | 0% | 0 | 0% | 0 | 0%
07. DRM Done | 279 | 78.81% | 539 | 63.56% | 0 | 0% | 0 | 0%
08. eTSS Approve XLS | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
08a. eTSS Approve ZTE | 242 | 68.36% | 22 | 2.594% | 1 | 3.226% | 0 | 0%
08b. eTSS Upload | 256 | 72.32% | 44 | 5.189% | 2 | 6.452% | 0 | 0%
09. Survey Done | 268 | 75.71% | 60 | 7.075% | 2 | 6.452% | 0 | 0%
09. Permit Survey Approve
09b. Permit Survey Submit
10. PO Batch 1 Total | 354 | 100% | 848 | 100% | 31 | 100% | 3 | 100%

## Summary IPRAN (hidden)
Monthly | October | [19 empty] | Assignment | (blank)
[8 empty] | Assignment | (All) | [11 empty] | Scope Update | New
SOW | Total Site | Survey Done | eTSS Submit | eTSS Approve ZTE | eTSS Approve XLS |  |  | Scope Update | (All) | [6 empty] | Assignment | (Multiple Items) |  |  |  | Site Status | (All)
New | 91 | [14 empty] | Scope Update | (Multiple Items) |  |  |  | Subcon Plan | (Multiple Items)
Service Migration | 3 | [6 empty] | Count of NewXLS ID | Subcon Plan | [6 empty] | Site Status | (All) |  |  |  | Prior Survey | 1
Swap | 163 | 71 | 17 |  |  |  |  | City | CCSI | GCI | GIT | GPA | Mingze | YPTT | Grand Total
Grand Total | 257 | 71 | 17 |  |  |  |  | Banjarnegara | 3 | [5 empty] | 3 | Count of NewXLS ID | New Weekly Mig |  |  |  | Count of NewXLS ID |  | Site Type
[8 empty] | Bantul | 2 | [5 empty] | 2 | Subcon Install | 46 | 47 | 48 | Grand Total | Ring | City | PAG | #N/A | Grand Total
[8 empty] | Banyumas |  |  |  | 3 |  |  | 3 | GCI | 1 |  | 2 | 3 | (blank) | Demak | 2 | 3 | 5
[8 empty] | Blora | 1 | [5 empty] | 1 | GPA | 16 | 10 | 14 | 40 |  | Grobogan |  | 3 | 3
Monthly | (All) | [6 empty] | Boyolali | [5 empty] | 25 | 25 | Mingze | 4 | 4 | 8 | 16 |  | Jepara |  | 2 | 2
Monthly HQ | (All) | [6 empty] | Brebes |  |  |  | 17 |  |  | 17 | YPTT | 7 | 2 | 6 | 15 |  | Kudus |  | 4 | 4
Assignment | Done | [6 empty] | Cilacap | 1 | [5 empty] | 1 | GIT |  | 6 | 6 | 12 | Grand Total |  | 2 | 12 | 14
[8 empty] | Demak |  |  | 13 | 55 |  | 5 | 73 | Grand Total | 28 | 22 | 36 | 86
SOW | Total Site | Survey Done | eTSS Submit | DRM Done | eTSS Approve ZTE | eTSS Approve XLS | GAP | Grobogan |  |  | 2 | 50 |  | 3 | 55
GIT | 60 | 58 | 55 | 58 | 54 |  | 2 | Jepara |  |  | 8 |  | 21 | 2 | 31
GPA | 160 | 140 | 120 | 139 | 115 |  | 20 | Karanganyar |  | 3 |  |  | 3 | 5 | 11
YPTT | 88 | 66 | 66 | 84 | 61 |  | 22 | Kendal | 1 |  |  | 8 |  |  | 9
CCSI | 28 | 19 | 18 | 19 | 17 |  | 9 | Klaten |  |  |  |  | 4 | 7 | 11
Mingze | 43 | 8 | 4 | 41 | 4 |  | 35 | Kota Magelang |  |  | 2 |  |  |  | 2
GCI | 23 | 23 | 13 | 23 | 10 |  | 0 | Kota Salatiga |  |  | 3 |  |  |  | 3 | XLWO Number | (Multiple Items)
Grand Total | 402 | 314 | 276 | 364 | 261 |  |  | Kota Semarang | 2 |  | 3 | 3 |  | 15 | 23 | Migration Actual | (blank)
[8 empty] | Kota Surakarta | 7 |  |  |  |  | 9 | 16
[8 empty] | Kota Tegal |  |  |  | 2 |  |  | 2 | Count of NewXLS ID | New Plan 2
[8 empty] | Kota Yogyakarta | 6 |  |  |  |  | 2 | 8 | Ring | 2025-11-10 | (blank) | Grand Total
[8 empty] | Kudus |  |  | 21 |  |  | 4 | 25 | Central Java Ring 25C | 1 |  | 1
[8 empty] | Magelang |  |  | 1 |  |  |  | 1 | Central Java Ring 25E |  | 1 | 1
[8 empty] | Pati |  |  |  | 28 | 1 |  | 29 | Grand Total | 1 | 1 | 2
[8 empty] | Pemalang | 3 |  | 1 |  |  |  | 4
[8 empty] | Purbalingga | 1 |  | 2 |  |  |  | 3
[8 empty] | Semarang | 1 |  | 9 |  | 3 |  | 13
[8 empty] | Sleman | [5 empty] | 1 | 1
[8 empty] | Sragen |  | 20 |  |  |  |  | 20
[8 empty] | Sukoharjo |  |  |  |  | 11 | 12 | 23
[8 empty] | Tegal |  |  | 2 |  |  |  | 2
|  | Values | [5 empty] | Grand Total | 28 | 23 | 67 | 166 | 43 | 90 | 417
Scope | New Ring ID Fiber | Total Site | RFS
New | R0000019804 | 22
| R0000019850 | 20
| R0000019851 | 22
| R0000019852 | 16
| R0000019853 | 15
| R0000019854 | 17
| R0000020168 | 16 | 2
| R0000020393 | 19
| R0000020394 | 15
| R0000020395 | 21
| R0000020396 | 19
| R0000020397 | 12 | 2
| R0000020398 | 15
| R0000020399 | 15
| R0000020400 | 18
| R0000020401 | 15
| R0000020402 | 19
| R0000020403 | 20 | 1 | 19
| R0000020404 | 11
| R0000020475 | 21
| R0000020477 | 21
| R0000019802 | 21 | 4 | 17
| R0000019803 | 20 | 6 | 14
| R0000018247 | 3
| R0000020469 | 13
| R0000020470 | 18
| R0000020468 | 6
| R0000020471 | 15
| R0000020472 | 21
| R0000019967 | 10
| R0000019968 | 11
| R0000020473 | 20
| R0000020476 | 9
| R0000020375 | 18
| R0000019970 | 8
| R0000020319 | 18
| R0000020320 | 17
| R0000020330 | 4
| #N/A | 8
Grand Total |  | 609 | 15

## IPRAN
Batch | Order | Status | Uniq ID | ScopeID | NewXLS ID | Region | Province | City | Lat | Long | Scope | SOW | Scope Update | Type | Site Type | Tower ID | SiteName | TP Name | TP ID | Ring | NE Name | IP Address | Hardware Model/Version | Exsisting HW Vendor | Material Source | Detail | Site Status | Priority | New Chasis | Leased FO Partner | SPK Status | New Ring ID Fiber |  | Span ID Fiber 1 | Span ID Fiber 2 | Ring ID Fiber Status | RFS Plan | RFS Week Plan | RFS Actual | XC | P1 Fiber | MMP Status | 5G Priority | Subcon Survey | Survey Plan | Survey Week | Monthly | Monthly HQ | Survey Year | Survey Actual | TSSR Submit by Subcon | TSSR Remark | TSSR Approve ZTE | TSSR Approve XLS | DRM | DRM Status | RFI Status | Remark Survey | DT | Material in WH | DO Req | DO Release | MOS Plan | MOS Actual | Permit Install TP Submit | Permit Install MS Submit |  |  | Permit Status Submit | Permit Install TP Release | Permit Install MS Release | Permit Status Release | Subcon Install | Install Plan | Weekly Install | Install Actual | MOP Submit | XLWO Release | XLWO Number | RFC Number | Integration Plan | Integration Actual | Migration Plan | Weekly Mig | New Mig Plan | New Weekly Mig | X | New Plan 2 | New Week Plan 2 | Y | Migration Actual | Assignment | Prior Survey | Y | Monthly Target | Dismantle Date | LDM Upload | Inbound Date
1 | 1 | CLEAR | Modernize_JAW-YO-SMN-8408_1 | Modernize_JAW-YO-SMN-8408 | JAW-YO-SMN-8408 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.7416 | 110.3918 | Swap | Swap Only | Modernize | Type B | MA | ZYKT_0233 | #N/A |  |  | #N/A | YKT_6150_ZTE_1111 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-19 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-SMG-8658_1 | Modernize_JAW-JT-SMG-8658 | JAW-JT-SMG-8658 | Central Java | Jawa Tengah | Kota Semarang | -6.9638 | 110.4709 | Swap | Swap Only | Modernize | Type B | MA | ZSMG_0668 | #N/A |  |  | #N/A | SMG_6150_ZSMG_0668 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-19 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-SMG-8473_1 | Modernize_JAW-JT-SMG-8473 | JAW-JT-SMG-8473 | Central Java | Jawa Tengah | Kota Semarang | -6.9647 | 110.4119 | Swap | Swap Only | Modernize | Type B | MA | ZSMG_0334 | #N/A |  |  | #N/A | SMG_6150_ZTE_3457 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-20 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-SMG-8418_1 | Modernize_JAW-JT-SMG-8418 | JAW-JT-SMG-8418 | Central Java | Jawa Tengah | Kota Semarang | -7.0038 | 110.3894 | Swap | Swap Only | Modernize | Type B | MA | ZSMG_0336 | #N/A |  |  | #N/A | SMG_6150_ZTE_3459 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-20 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JI-BKL-3150_1 | Modernize_JAW-JI-BKL-3150 | JAW-JI-BKL-3150 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8285 | 110.4108 | Swap | Swap Only | Modernize | Type B | MA | ZYKT_0275 | #N/A |  |  | #N/A | YKT_6150_ZTE_3484 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-21 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-KDL-4158_1 | Modernize_JAW-JT-KDL-4158 | JAW-JT-KDL-4158 | Central Java | Jawa Tengah | Kendal | -6.9714 | 110.2333 | Swap | Swap Only | Modernize | Type B | MA | ZSMG_1205 | #N/A |  |  | #N/A | SMG_6150_ZSMG_1205 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-21 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-PTI-8533_1 | Modernize_JAW-JT-PTI-8533 | JAW-JT-PTI-8533 | Central Java | Jawa Tengah | Pati | -6.655 | 111.0918 | Swap | Swap Only | Modernize | Type B | MA | ZSMG_0119 | #N/A |  |  | #N/A | SMG_6150_ZTE_2258 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-22 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-CLP-8499_1 | Modernize_JAW-JT-CLP-8499 | JAW-JT-CLP-8499 | Central Java | Jawa Tengah | Cilacap | -7.2997 | 108.7772 | Swap | Swap Only | Modernize | Type B | MA | ZYKT_0051 | #N/A |  |  | #N/A | YKT_6150_ZTE_2274 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-22 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-CLP-8507_1 | Modernize_JAW-JT-CLP-8507 | JAW-JT-CLP-8507 | Central Java | Jawa Tengah | Cilacap | -7.7234 | 109.0104 | Swap | Swap Only | Modernize | Type B | MA | ZYKT_0101 | #N/A |  |  | #N/A | YKT_6150_ZTE_3489 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-23 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-SKT-8545_1 | Modernize_JAW-JT-SKT-8545 | JAW-JT-SKT-8545 | Central Java | Jawa Tengah | Kota Surakarta | -7.5705 | 110.8333 | Swap | Swap Only | Modernize | Type B | MA | ZSLO_0079 | #N/A |  |  | #N/A | SLO_6150_ZTE_1184 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-23 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-PWT-8363_1 | Modernize_JAW-JT-PWT-8363 | JAW-JT-PWT-8363 | Central Java | Jawa Tengah | Banyumas | -7.4134 | 109.2679 | Swap | Swap Only | Modernize | Type B | MA | ZYKT_0104 | #N/A |  |  | #N/A | YKT_6150_ZTE_3492 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-26 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-JPA-8320_1 | Modernize_JAW-JT-JPA-8320 | JAW-JT-JPA-8320 | Central Java | Jawa Tengah | Jepara | -6.5973 | 110.6697 | Swap | Swap Only | Modernize | Type B | MA | ZSMG_0175 | #N/A |  |  | #N/A | SMG_6150_ZTE_3857 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-26 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-PWD-8475_1 | Modernize_JAW-JT-PWD-8475 | JAW-JT-PWD-8475 | Central Java | Jawa Tengah | Grobogan | -7.1225 | 110.9934 | Swap | Swap Only | Modernize | Type B | MA | ZSMG_0900 | #N/A |  |  | #N/A | SMG_6150_ZSMG_0900 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Keep | 5 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-27 | 5 |  |  | 2026 | 2025-11-14 | 2025-11-17 | Reviewing | [6 empty] | Done | Done | Done | DOEID25111431 | 2025-11-17 | [9 empty] | Mingze | 2025-11-17 | 47 | [5 empty] | 2025-11-20 |  | 2025-11-20 | 47 | 2025-11-20 | 47 | TRUE | TBD | #VALUE! | 2025-11-20 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | Modernize_JAW-YO-YYK-8305_1 | Modernize_JAW-YO-YYK-8305 | JAW-YO-YYK-8305 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7816 | 110.368 | Swap | Swap Only | Modernize | Type B | MA | ZYKT_0272 | #N/A |  |  | #N/A | YKT_6150_ZTE_3481 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-27 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-PWD-8421_1 | Modernize_JAW-JT-PWD-8421 | JAW-JT-PWD-8421 | Central Java | Jawa Tengah | Grobogan | -7.1675 | 110.9011 | Swap | Swap Only | Modernize | Type B | MA | ZSMG_0169 | #N/A |  |  | #N/A | SMG_6150_ZTE_3851 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Keep | 5 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-28 | 5 |  |  | 2026 | 2025-11-14 | 2025-11-14 | Approved | 2025-11-17 | [5 empty] | Done | Done | Done | DOEID25111432 | 2025-11-20 | [9 empty] | Mingze | 2025-11-20 | 47 | [5 empty] | 2025-11-23 |  | 2025-11-23 | 47 | 2025-11-23 | 47 | TRUE | TBD | #VALUE! | 2025-11-20 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | Modernize_JAW-JT-PML-8447_1 | Modernize_JAW-JT-PML-8447 | JAW-JT-PML-8447 | Central Java | Jawa Tengah | Pemalang | -6.9063 | 109.3888 | Swap | Swap Only | Modernize | Type B | MA | ZSMG_0006 | #N/A |  |  | #N/A | SMG_6150_ZTE_0957 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-28 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-SLT-8458_1 | Modernize_JAW-JT-SLT-8458 | JAW-JT-SLT-8458 | Central Java | Jawa Tengah | Kota Salatiga | -7.345 | 110.5088 | Swap | Swap Only | Modernize | Type B | MA | ZSMG_0288 | #N/A |  |  | #N/A | SMG_6150_ZTE_1027 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-29 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-CLP-8509_1 | Modernize_JAW-JT-CLP-8509 | JAW-JT-CLP-8509 | Central Java | Jawa Tengah | Cilacap | -7.3309 | 108.654 | Swap | Swap Only | Modernize | Type B | MA | ZYKT_0120 | #N/A |  |  | #N/A | YKT_6150_ZTE_3871 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop,Double Scope |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-29 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JI-BKL-3161_1 | Modernize_JAW-JI-BKL-3161 | JAW-JI-BKL-3161 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8041 | 110.4128 | Swap | Swap Only | Modernize | Type B | MA | ZYKT_0321 | #N/A |  |  | #N/A | YKT_6150_ZTE_6654 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop,Double Scope |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-30 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-SGN-8545_1 | Modernize_JAW-JT-SGN-8545 | JAW-JT-SGN-8545 | Central Java | Jawa Tengah | Sragen | -7.5223 | 110.9985 | Swap | Swap Only | Modernize | Type A | MA | ZSLO_0723 | #N/A |  |  | #N/A | SLO_6150_ZSLO_0723 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Propose Drop, MOCN Drop |  | 0 |  |  |  | #N/A | [11 empty] | 2026-01-30 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-TMG-8502_1 | Modernize_JAW-JT-TMG-8502 | JAW-JT-TMG-8502 | Central Java | Jawa Tengah | Temanggung | -7.2391 | 110.0569 | Swap | Swap Only | Modernize | Type A | MA | ZSMG_0105 | #N/A |  |  | #N/A | SMG_6150_ZTE_2244 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Propose Drop, MOCN Drop |  | 0 |  |  |  | #N/A | [11 empty] | 2026-02-02 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-WSB-8490_1 | Modernize_JAW-JT-WSB-8490 | JAW-JT-WSB-8490 | Central Java | Jawa Tengah | Wonosobo | -7.356 | 109.9066 | Swap | Swap Only | Modernize | Type A | MA | ZYKT_0145 | #N/A |  |  | #N/A | YKT_6150_ZTE_4561 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Propose Drop, MOCN Drop |  | 0 |  |  |  | #N/A | [11 empty] | 2026-02-02 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-PBG-8443_1 | Modernize_JAW-JT-PBG-8443 | JAW-JT-PBG-8443 | Central Java | Jawa Tengah | Purbalingga | -7.3247 | 109.3502 | Swap | Swap Only | Modernize | Type A | MA | ZYKT_0077 | #N/A |  |  | #N/A | YKT_6150_ZTE_2301 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Propose Drop, MOCN Drop |  | 0 |  |  |  | #N/A | [11 empty] | 2026-02-03 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-PBG-8455_1 | Modernize_JAW-JT-PBG-8455 | JAW-JT-PBG-8455 | Central Java | Jawa Tengah | Purbalingga | -7.378 | 109.3728 | Swap | Swap Only | Modernize | Type A | MA | ZYKT_0108 | #N/A |  |  | #N/A | YKT_6150_ZTE_3833 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Propose Drop, MOCN Drop |  | 0 |  |  |  | #N/A | [11 empty] | 2026-02-03 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-BNR-8348_1 | Modernize_JAW-JT-BNR-8348 | JAW-JT-BNR-8348 | Central Java | Jawa Tengah | Banjarnegara | -7.3944 | 109.7652 | Swap | Swap Only | Modernize | Type A | MA | ZYKT_0087 | #N/A |  |  | #N/A | YKT_6150_ZTE_2311 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Keep |  | 0 |  |  |  | #N/A | [11 empty] | 2026-02-04 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-KJN-8420_1 | Modernize_JAW-JT-KJN-8420 | JAW-JT-KJN-8420 | Central Java | Jawa Tengah | Pekalongan | -6.884 | 109.6205 | Swap | Swap Only | Modernize | Type A | MA | ZSMG_0158 | #N/A |  |  | #N/A | SMG_6150_ZTE_3835 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Propose Drop, MOCN Drop |  | 0 |  |  |  | #N/A | [11 empty] | 2026-02-04 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-BLA-8321_1 | Modernize_JAW-JT-BLA-8321 | JAW-JT-BLA-8321 | Central Java | Jawa Tengah | Blora | -7.1574 | 111.5312 | Swap | Swap Only | Modernize | Type A | MA | ZSMG_0117 | #N/A |  |  | #N/A | SMG_6150_ZTE_2256 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Propose Drop,Double Scope |  | 0 |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-02-05 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-WSB-8482_1 | Modernize_JAW-JT-WSB-8482 | JAW-JT-WSB-8482 | Central Java | Jawa Tengah | Wonosobo | -7.3539 | 109.8893 | Swap | Swap Only | Modernize | Type A | MA | ZYKT_0111 | #N/A |  |  | #N/A | YKT_6150_ZTE_3842 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Keep |  | 0 |  |  |  | #N/A | [11 empty] | 2026-02-05 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-PWR-8552_1 | Modernize_JAW-JT-PWR-8552 | JAW-JT-PWR-8552 | Central Java | Jawa Tengah | Purworejo | -7.7148 | 110.0148 | Swap | Swap Only | Modernize | Type A | MA | ZYKT_0132 | #N/A |  |  | #N/A | YKT_6150_ZTE_3883 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Keep |  | 0 |  |  |  | #N/A | [11 empty] | 2026-02-06 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-KBM-8532_1 | Modernize_JAW-JT-KBM-8532 | JAW-JT-KBM-8532 | Central Java | Jawa Tengah | Kebumen | -7.7219 | 109.8055 | Swap | Swap Only | Modernize | Type A | MA | ZYKT_0064 | #N/A |  |  | #N/A | YKT_6150_ZTE_2288 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Propose Drop,Double Scope |  | 0 |  |  |  | #N/A | [11 empty] | 2026-02-06 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-KBM-8457_1 | Modernize_JAW-JT-KBM-8457 | JAW-JT-KBM-8457 | Central Java | Jawa Tengah | Kebumen | -7.6342 | 109.5743 | Swap | Swap Only | Modernize | Type A | MA | ZYKT_0065 | #N/A |  |  | #N/A | YKT_6150_ZTE_2289 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Keep |  | 0 |  |  |  | #N/A | [11 empty] | 2026-02-09 | 7 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BTG-8319_1 | New_JAW-JT-BTG-8319 | JAW-JT-BTG-8319 | Central Java | Jawa Tengah | Batang | -6.9923 | 109.9421 | Insert | New | New | Type B | MA | JAW-JT-BTG-8319 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-20 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-MGG-3528_1 | New_JAW-JT-MGG-3528 | JAW-JT-MGG-3528 | Central Java | Jawa Tengah | Kota Magelang | -7.4755 | 110.2182 | Insert | New | New | Type B | MA | JAW-JT-MGG-3528 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-20 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PTI-8507_1 | New_JAW-JT-PTI-8507 | JAW-JT-PTI-8507 | Central Java | Jawa Tengah | Pati | -6.8327 | 111.0569 | Insert | New | New | Type B | MA | JAW-JT-PTI-8507 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-20 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8363_1 | New_JAW-JT-PWT-8363 | JAW-JT-PWT-8363 | Central Java | Jawa Tengah | Banyumas | -7.4134 | 109.2679 | Insert | New | New | Type B | MA | JAW-JT-PWT-8363 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-20 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8416_1 | New_JAW-JT-PWT-8416 | JAW-JT-PWT-8416 | Central Java | Jawa Tengah | Banyumas | -7.5139 | 109.0592 | Insert | New | New | Type B | MA | JAW-JT-PWT-8416 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-20 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-TGL-8307_1 | New_JAW-JT-TGL-8307 | JAW-JT-TGL-8307 | Central Java | Jawa Tengah | Kota Tegal | -6.8535 | 109.1431 | Insert | New | New | Type B | MA | JAW-JT-TGL-8307 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-20 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-TMG-8549_1 | New_JAW-JT-TMG-8549 | JAW-JT-TMG-8549 | Central Java | Jawa Tengah | Temanggung | -7.3343 | 110.1554 | Insert | New | New | Type B | MA | JAW-JT-TMG-8549 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-20 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8563_1 | New_JAW-JT-SMG-8563 | JAW-JT-SMG-8563 | Central Java | Jawa Tengah | Kota Semarang | -7.0018 | 110.4334 | Insert | New | New | Type B | MA | JAW-JT-SMG-8563 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2025-10-20 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SGN-8512_1 | New_JAW-JT-SGN-8512 | JAW-JT-SGN-8512 | Central Java | Jawa Tengah | Sragen | -7.4188 | 110.9122 | Insert | New | New | Type B | MA | JAW-JT-SGN-8512 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-20 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SGN-8511_1 | New_JAW-JT-SGN-8511 | JAW-JT-SGN-8511 | Central Java | Jawa Tengah | Sragen | -7.3849 | 110.9114 | Insert | New | New | Type B | MA | JAW-JT-SGN-8511 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-20 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SKH-8514_1 | New_JAW-JT-SKH-8514 | JAW-JT-SKH-8514 | Central Java | Jawa Tengah | Sukoharjo | -7.7071 | 110.8326 | Insert | New | New | Type B | MA | JAW-JT-SKH-8514 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-20 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BTG-8325_1 | New_JAW-JT-BTG-8325 | JAW-JT-BTG-8325 | Central Java | Jawa Tengah | Batang | -6.971 | 109.967 | Insert | New | New | Type B | MA | JAW-JT-BTG-8325 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-20 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-WNG-8564_1 | New_JAW-JT-WNG-8564 | JAW-JT-WNG-8564 | Central Java | Jawa Tengah | Wonogiri | -7.8194 | 111.0671 | Insert | New | New | Type B | MA | JAW-JT-WNG-8564 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-20 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8297_1 | New_JAW-JT-DMK-8297 | JAW-JT-DMK-8297 | Central Java | Jawa Tengah | Demak | -7.0556 | 110.5048 | Insert | New | New | Type B | MA | JAW-JT-DMK-8297 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-21 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8501_1 | New_JAW-JT-SMG-8501 | JAW-JT-SMG-8501 | Central Java | Jawa Tengah | Kota Semarang | -6.9726 | 110.42 | Insert | New | New | Type B | MA | JAW-JT-SMG-8501 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2025-10-21 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8441_1 | New_JAW-JT-KDS-8441 | JAW-JT-KDS-8441 | Central Java | Jawa Tengah | Kudus | -6.8018 | 110.8775 | Insert | New | New | Type B | MA | JAW-JT-KDS-8441 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-21 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BYL-8265_1 | New_JAW-JT-BYL-8265 | JAW-JT-BYL-8265 | Central Java | Jawa Tengah | Boyolali | -7.536 | 110.5961 | Insert | New | New | Type B | MA | JAW-JT-BYL-8265 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-21 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SGN-8574_1 | New_JAW-JT-SGN-8574 | JAW-JT-SGN-8574 | Central Java | Jawa Tengah | Sragen | -7.3971 | 111.0689 | Insert | New | New | Type B | MA | JAW-JT-SGN-8574 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-21 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3115_1 | New_JAW-JI-BKL-3115 | JAW-JI-BKL-3115 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9211 | 110.3803 | Insert | New | New | Type B | MA | JAW-JI-BKL-3115 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-21 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-SMN-8343_1 | New_JAW-YO-SMN-8343 | JAW-YO-SMN-8343 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.677 | 110.3375 | Insert | New | New | Type B | MA | JAW-YO-SMN-8343 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-21 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-MKD-8402_1 | New_JAW-JT-MKD-8402 | JAW-JT-MKD-8402 | Central Java | Jawa Tengah | Magelang | -7.6001 | 110.2107 | Insert | New | New | Type B | MA | JAW-JT-MKD-8402 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-21 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-MKD-8439_1 | New_JAW-JT-MKD-8439 | JAW-JT-MKD-8439 | Central Java | Jawa Tengah | Magelang | -7.3895 | 110.2557 | Insert | New | New | Type B | MA | JAW-JT-MKD-8439 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-21 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BNR-8352_1 | New_JAW-JT-BNR-8352 | JAW-JT-BNR-8352 | Central Java | Jawa Tengah | Banjarnegara | -7.4166 | 109.816 | Insert | New | New | Type B | MA | JAW-JT-BNR-8352 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [6 empty] | 2025-11-02 |  |  |  |  | 2025-10-21 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3124_1 | New_JAW-JI-BKL-3124 | JAW-JI-BKL-3124 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9631 | 110.2674 | Insert | New | New | Type B | MA | JAW-JI-BKL-3124 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-21 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8332_1 | New_JAW-JT-PWT-8332 | JAW-JT-PWT-8332 | Central Java | Jawa Tengah | Banyumas | -7.4086 | 109.2347 | Insert | New | New | Type B | MA | JAW-JT-PWT-8332 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-21 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8358_1 | New_JAW-JT-PWT-8358 | JAW-JT-PWT-8358 | Central Java | Jawa Tengah | Banyumas | -7.4436 | 109.2733 | Insert | New | New | Type B | MA | JAW-JT-PWT-8358 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-21 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8315_1 | New_JAW-JT-PWT-8315 | JAW-JT-PWT-8315 | Central Java | Jawa Tengah | Banyumas | -7.4898 | 109.2306 | Insert | New | New | Type B | MA | JAW-JT-PWT-8315 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-22 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8469_1 | New_JAW-JT-PWT-8469 | JAW-JT-PWT-8469 | Central Java | Jawa Tengah | Banyumas | -7.5069 | 109.0219 | Insert | New | New | Type B | MA | JAW-JT-PWT-8469 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-22 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8447_1 | New_JAW-JT-PWT-8447 | JAW-JT-PWT-8447 | Central Java | Jawa Tengah | Banyumas | -7.3564 | 109.1099 | Insert | New | New | Type B | MA | JAW-JT-PWT-8447 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-22 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BTG-8282_1 | New_JAW-JT-BTG-8282 | JAW-JT-BTG-8282 | Central Java | Jawa Tengah | Batang | -6.9086 | 109.7434 | Insert | New | New | Type B | MA | JAW-JT-BTG-8282 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-22 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PTI-8545_1 | New_JAW-JT-PTI-8545 | JAW-JT-PTI-8545 | Central Java | Jawa Tengah | Pati | -6.7577 | 111.1238 | Insert | New | New | Type B | MA | JAW-JT-PTI-8545 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [6 empty] | 2025-11-13 |  |  |  |  | 2025-10-22 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BBS-9171_1 | New_JAW-JT-BBS-9171 | JAW-JT-BBS-9171 | Central Java | Jawa Tengah | Brebes | -6.8453 | 108.8184 | Insert | New | New | Type B | MA | JAW-JT-BBS-9171 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-22 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BBS-9172_1 | New_JAW-JT-BBS-9172 | JAW-JT-BBS-9172 | Central Java | Jawa Tengah | Brebes | -6.8688 | 108.8877 | Insert | New | New | Type B | MA | JAW-JT-BBS-9172 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-22 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8419_1 | New_JAW-JT-CLP-8419 | JAW-JT-CLP-8419 | Central Java | Jawa Tengah | Cilacap | -7.6689 | 109.2682 | Insert | New | New | Type B | MA | JAW-JT-CLP-8419 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-22 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8481_1 | New_JAW-JT-CLP-8481 | JAW-JT-CLP-8481 | Central Java | Jawa Tengah | Cilacap | -7.5917 | 109.1169 | Insert | New | New | Type B | MA | JAW-JT-CLP-8481 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-22 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8509_1 | New_JAW-JT-CLP-8509 | JAW-JT-CLP-8509 | Central Java | Jawa Tengah | Cilacap | -7.3309 | 108.654 | Insert | New | New | Type B | MA | JAW-JT-CLP-8509 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-22 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8510_1 | New_JAW-JT-CLP-8510 | JAW-JT-CLP-8510 | Central Java | Jawa Tengah | Cilacap | -7.6113 | 108.9297 | Insert | New | New | Type B | MA | JAW-JT-CLP-8510 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-22 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8525_1 | New_JAW-JT-CLP-8525 | JAW-JT-CLP-8525 | Central Java | Jawa Tengah | Cilacap | -7.2941 | 108.7361 | Insert | New | New | Type B | MA | JAW-JT-CLP-8525 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-22 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8245_1 | New_JAW-JT-BLA-8245 | JAW-JT-BLA-8245 | Central Java | Jawa Tengah | Blora | -7.0341 | 111.3811 | Insert | New | New | Type B | MA | JAW-JT-BLA-8245 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2025-10-22 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8275_1 | New_JAW-JT-BLA-8275 | JAW-JT-BLA-8275 | Central Java | Jawa Tengah | Blora | -6.9462 | 111.4286 | Insert | New | New | Type B | MA | JAW-JT-BLA-8275 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2025-10-23 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KBM-8532_1 | New_JAW-JT-KBM-8532 | JAW-JT-KBM-8532 | Central Java | Jawa Tengah | Kebumen | -7.7219 | 109.8055 | Insert | New | New | Type B | MA | JAW-JT-KBM-8532 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-23 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-RBG-8477_1 | New_JAW-JT-RBG-8477 | JAW-JT-RBG-8477 | Central Java | Jawa Tengah | Rembang | -6.6349 | 111.4864 | Insert | New | New | Type B | MA | JAW-JT-RBG-8477 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-23 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8473_1 | New_JAW-JT-KDS-8473 | JAW-JT-KDS-8473 | Central Java | Jawa Tengah | Kudus | -6.7968 | 110.9451 | Insert | New | New | Type B | MA | JAW-JT-KDS-8473 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2025-10-23 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SKT-8495_1 | New_JAW-JT-SKT-8495 | JAW-JT-SKT-8495 | Central Java | Jawa Tengah | Kota Surakarta | -7.5577 | 110.794 | Insert | New | New | Type B | MA | JAW-JT-SKT-8495 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2025-10-23 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8375_1 | New_JAW-JT-DMK-8375 | JAW-JT-DMK-8375 | Central Java | Jawa Tengah | Demak | -7.016 | 110.5956 | Insert | New | New | Type B | MA | JAW-JT-DMK-8375 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2025-10-23 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8320_1 | New_JAW-JT-PWD-8320 | JAW-JT-PWD-8320 | Central Java | Jawa Tengah | Grobogan | -7.0539 | 110.6643 | Insert | New | New | Type B | MA | JAW-JT-PWD-8320 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2025-10-23 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8438_1 | New_JAW-JT-UNR-8438 | JAW-JT-UNR-8438 | Central Java | Jawa Tengah | Semarang | -7.1967 | 110.3884 | Insert | New | New | Type B | MA | JAW-JT-UNR-8438 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | Mid Dec 25 |  | 2025-10-23 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3161_1 | New_JAW-JI-BKL-3161 | JAW-JI-BKL-3161 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8041 | 110.4128 | Insert | New | New | Type B | MA | JAW-JI-BKL-3161 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-23 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8290_1 | New_JAW-YO-YYK-8290 | JAW-YO-YYK-8290 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8222 | 110.3519 | Insert | New | New | Type B | MA | JAW-YO-YYK-8290 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2025-10-23 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3143_1 | New_JAW-JI-BKL-3143 | JAW-JI-BKL-3143 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8057 | 110.345 | Insert | New | New | Type B | MA | JAW-JI-BKL-3143 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-23 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8284_1 | New_JAW-JT-BLA-8284 | JAW-JT-BLA-8284 | Central Java | Jawa Tengah | Blora | -7.1949 | 111.4411 | Insert | New | New | Type B | MA | JAW-JT-BLA-8284 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2025-10-23 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8321_1 | New_JAW-JT-BLA-8321 | JAW-JT-BLA-8321 | Central Java | Jawa Tengah | Blora | -7.1574 | 111.5312 | Insert | New | New | Type B | MA | JAW-JT-BLA-8321 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2025-10-23 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8543_1 | New_JAW-JT-PWD-8543 | JAW-JT-PWD-8543 | Central Java | Jawa Tengah | Grobogan | -7.0796 | 111.0813 | Insert | New | New | Type B | MA | JAW-JT-PWD-8543 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2025-10-24 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8571_1 | New_JAW-JT-PWD-8571 | JAW-JT-PWD-8571 | Central Java | Jawa Tengah | Grobogan | -7.1343 | 111.1399 | Insert | New | New | Type B | MA | JAW-JT-PWD-8571 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2025-10-24 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BNR-8323_1 | New_JAW-JT-BNR-8323 | JAW-JT-BNR-8323 | Central Java | Jawa Tengah | Banjarnegara | -7.3694 | 109.6645 | Insert | New | New | Type B | MA | JAW-JT-BNR-8323 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-24 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8471_1 | New_JAW-JT-PWT-8471 | JAW-JT-PWT-8471 | Central Java | Jawa Tengah | Banyumas | -7.4187 | 109.1903 | Insert | New | New | Type B | MA | JAW-JT-PWT-8471 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-24 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-4154_1 | New_JAW-JT-SMG-4154 | JAW-JT-SMG-4154 | Central Java | Jawa Tengah | Kota Semarang | -6.9867 | 110.4236 | Insert | New | New | Type B | MA | JAW-JT-SMG-4154 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-24 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PTI-8421_1 | New_JAW-JT-PTI-8421 | JAW-JT-PTI-8421 | Central Java | Jawa Tengah | Pati | -6.9176 | 110.9102 | Insert | New | New | Type B | MA | JAW-JT-PTI-8421 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [6 empty] | 2025-10-09 |  |  |  |  | 2025-10-24 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8387_1 | New_JAW-JT-DMK-8387 | JAW-JT-DMK-8387 | Central Java | Jawa Tengah | Demak | -6.9477 | 110.6124 | Insert | New | New | Type B | MA | JAW-JT-DMK-8387 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2025-10-24 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-RBG-8479_1 | New_JAW-JT-RBG-8479 | JAW-JT-RBG-8479 | Central Java | Jawa Tengah | Rembang | -6.7591 | 111.4912 | Insert | New | New | Type B | MA | JAW-JT-RBG-8479 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-24 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-MKD-8447_1 | New_JAW-JT-MKD-8447 | JAW-JT-MKD-8447 | Central Java | Jawa Tengah | Magelang | -7.4277 | 110.2697 | Insert | New | New | Type B | MA | JAW-JT-MKD-8447 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-24 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8287_1 | New_JAW-JT-DMK-8287 | JAW-JT-DMK-8287 | Central Java | Jawa Tengah | Demak | -7.0283 | 110.4964 | Insert | New | New | Type B | MA | JAW-JT-DMK-8287 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2025-10-24 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-RBG-8499_1 | New_JAW-JT-RBG-8499 | JAW-JT-RBG-8499 | Central Java | Jawa Tengah | Rembang | -6.7684 | 111.5725 | Insert | New | New | Type B | MA | JAW-JT-RBG-8499 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-24 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8339_1 | New_JAW-JT-DMK-8339 | JAW-JT-DMK-8339 | Central Java | Jawa Tengah | Demak | -7.0566 | 110.5448 | Insert | New | New | Type B | MA | JAW-JT-DMK-8339 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2025-10-24 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8384_1 | New_JAW-JT-KDS-8384 | JAW-JT-KDS-8384 | Central Java | Jawa Tengah | Kudus | -6.8074 | 110.8235 | Insert | New | New | Type B | MA | JAW-JT-KDS-8384 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2025-10-24 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PTI-8526_1 | New_JAW-JT-PTI-8526 | JAW-JT-PTI-8526 | Central Java | Jawa Tengah | Pati | -6.5922 | 111.0679 | Insert | New | New | Type B | MA | JAW-JT-PTI-8526 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-27 | 44 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KRG-8289_1 | New_JAW-JT-KRG-8289 | JAW-JT-KRG-8289 | Central Java | Jawa Tengah | Karanganyar | -7.5407 | 110.8965 | Insert | New | New | Type B | MA | JAW-JT-KRG-8289 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-27 | 44 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BYL-8336_1 | New_JAW-JT-BYL-8336 | JAW-JT-BYL-8336 | Central Java | Jawa Tengah | Boyolali | -7.3639 | 110.7399 | Insert | New | New | Type B | MA | JAW-JT-BYL-8336 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-27 | 44 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8335_1 | New_JAW-JT-JPA-8335 | JAW-JT-JPA-8335 | Central Java | Jawa Tengah | Jepara | -6.5962 | 110.6869 | Insert | New | New | Type B | MA | JAW-JT-JPA-8335 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [6 empty] | 2025-10-05 |  |  | 2026 |  | 2025-10-27 | 44 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8561_1 | New_JAW-JT-PWD-8561 | JAW-JT-PWD-8561 | Central Java | Jawa Tengah | Grobogan | -7.1352 | 111.1119 | Insert | New | New | Type B | MA | JAW-JT-PWD-8561 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2025-10-27 | 44 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SGN-8448_1 | New_JAW-JT-SGN-8448 | JAW-JT-SGN-8448 | Central Java | Jawa Tengah | Sragen | -7.4121 | 110.7821 | Insert | New | New | Type B | MA | JAW-JT-SGN-8448 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [6 empty] | 2025-11-02 |  |  |  |  | 2025-10-27 | 44 | October |  | 2025 |  |  | #N/A | [6 empty] | Done | Done | Done | DOEID251117OI |  | 2005-11-22 | Done | Done |  |  | Done | Done | Done | Done | DCITS |  |  | 2025-11-22 | [13 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SGN-8542_1 | New_JAW-JT-SGN-8542 | JAW-JT-SGN-8542 | Central Java | Jawa Tengah | Sragen | -7.4311 | 110.9901 | Insert | New | New | Type B | MA | JAW-JT-SGN-8542 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-27 | 44 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BYL-8252_1 | New_JAW-JT-BYL-8252 | JAW-JT-BYL-8252 | Central Java | Jawa Tengah | Boyolali | -7.4655 | 110.5544 | Insert | New | New | Type B | MA | JAW-JT-BYL-8252 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2025-10-27 | 44 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SKT-8513_1 | New_JAW-JT-SKT-8513 | JAW-JT-SKT-8513 | Central Java | Jawa Tengah | Kota Surakarta | -7.5524 | 110.8136 | Insert | New | New | Type B | MA | JAW-JT-SKT-8513 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [6 empty] | 2025-11-16 |  |  | 2025-End Nov |  | 2025-10-27 | 44 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-1010_1 | New_JAW-JT-KDL-1010 | JAW-JT-KDL-1010 | Central Java | Jawa Tengah | Kendal | -6.9822 | 110.0712 | New | New | New | Type B | MA | JAW-JT-KDL-1010 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | #N/A | S000055600 | S000055601 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-10-27 | 44 | October |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4206_1 | New_JAW-JT-KDL-4206 | JAW-JT-KDL-4206 | Central Java | Jawa Tengah | Kendal | -7.0301 | 110.0483 | New | New | New | Type B | MA | JAW-JT-KDL-4206 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | #N/A | S000055601 | S000055602 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-10-27 | 44 | October |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4209_1 | New_JAW-JT-KDL-4209 | JAW-JT-KDL-4209 | Central Java | Jawa Tengah | Kendal | -7.0502 | 110.0529 | New | New | New | Type B | MA | JAW-JT-KDL-4209 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | #N/A | S000055602 | S000055603 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-10-27 | 44 | October |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-3481_1 | New_JAW-JT-KDL-3481 | JAW-JT-KDL-3481 | Central Java | Jawa Tengah | Kendal | -7.0363 | 109.9992 | New | New | New | Type B | MA | JAW-JT-KDL-3481 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | #N/A | S000055603 | S000055604 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-10-27 | 44 | October |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4025_1 | New_JAW-JT-KDL-4025 | JAW-JT-KDL-4025 | Central Java | Jawa Tengah | Kendal | -7.0662 | 109.9859 | New | New | New | Type B | MA | JAW-JT-KDL-4025 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | #N/A | S000055604 | S000055605 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-10-28 | 44 | October |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4361_1 | New_JAW-JT-KDL-4361 | JAW-JT-KDL-4361 | Central Java | Jawa Tengah | Kendal | -7.1002 | 109.9678 | New | New | New | Type B | MA | JAW-JT-KDL-4361 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | #N/A | S000055605 | S000055606 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-10-28 | 44 | October |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-3480_1 | New_JAW-JT-KDL-3480 | JAW-JT-KDL-3480 | Central Java | Jawa Tengah | Kendal | -7.1183 | 109.9627 | New | New | New | Type B | MA | JAW-JT-KDL-3480 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | #N/A | S000055606 | S000055607 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-10-28 | 44 | October |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4153_1 | New_JAW-JT-KDL-4153 | JAW-JT-KDL-4153 | Central Java | Jawa Tengah | Kendal | -7.1003 | 110.0244 | New | New | New | Type B | MA | JAW-JT-KDL-4153 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | #N/A | S000055607 | S000055595 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-10-28 | 44 | October |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4019_1 | New_JAW-JT-KDL-4019 | JAW-JT-KDL-4019 | Central Java | Jawa Tengah | Kendal | -7.1158 | 110.0158 | New | New | New | Type B | MA | JAW-JT-KDL-4019 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | #N/A | S000055595 | S000055596 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-10-28 | 44 | October |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4126_1 | New_JAW-JT-KDL-4126 | JAW-JT-KDL-4126 | Central Java | Jawa Tengah | Kendal | -7.1348 | 109.9971 | New | New | New | Type B | MA | JAW-JT-KDL-4126 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | #N/A | S000055596 | S000055597 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-10-28 | 44 | October |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0772_1 | New_JAW-JT-KDL-0772 | JAW-JT-KDL-0772 | Central Java | Jawa Tengah | Kendal | -7.1719 | 109.985 | New | New | New | Type B | MA | JAW-JT-KDL-0772 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | #N/A | S000055597 | S000055598 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-10-28 | 44 | October |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4167_1 | New_JAW-JT-KDL-4167 | JAW-JT-KDL-4167 | Central Java | Jawa Tengah | Kendal | -7.1382 | 110.0307 | New | New | New | Type B | MA | JAW-JT-KDL-4167 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | #N/A | S000055598 | S000055599 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-10-28 | 44 | October |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0776_1 | New_JAW-JT-KDL-0776 | JAW-JT-KDL-0776 | Central Java | Jawa Tengah | Kendal | -7.1203 | 110.0338 | New | New | New | Type B | MA | JAW-JT-KDL-0776 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | #N/A | S000055599 | S000055590 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-10-28 | 44 | October |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4204_1 | New_JAW-JT-KDL-4204 | JAW-JT-KDL-4204 | Central Java | Jawa Tengah | Kendal | -7.0825 | 110.0448 | New | New | New | Type B | MA | JAW-JT-KDL-4204 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | #N/A | S000055590 | S000055591 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-10-28 | 44 | October |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4211_1 | New_JAW-JT-KDL-4211 | JAW-JT-KDL-4211 | Central Java | Jawa Tengah | Kendal | -7.0628 | 110.0608 | New | New | New | Type B | MA | JAW-JT-KDL-4211 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | #N/A | S000055591 | S000055592 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-10-28 | 44 | October |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4245_1 | New_JAW-JT-KDL-4245 | JAW-JT-KDL-4245 | Central Java | Jawa Tengah | Kendal | -7.0907 | 110.1446 | New | New | New | Type B | MA | JAW-JT-KDL-4245 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | #N/A | S000055592 | S000055593 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-10-28 | 44 | October |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0712_1 | New_JAW-JT-KDL-0712 | JAW-JT-KDL-0712 | Central Java | Jawa Tengah | Kendal | -7.0829 | 110.2114 | New | New | New | Type B | MA | JAW-JT-KDL-0712 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_6 2x10G ZR + 6x10G/1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | #N/A | S000055593 | S000055594 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-10-28 | 44 | October |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4143_1 | New_JAW-JT-KDL-4143 | JAW-JT-KDL-4143 | Central Java | Jawa Tengah | Kendal | -7.0285 | 110.2003 | New | New | New | Type B | MA | JAW-JT-KDL-4143 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | #N/A | S000055594 | S000055608 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-05 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0713_1 | New_JAW-JT-KDL-0713 | JAW-JT-KDL-0713 | Central Java | Jawa Tengah | Kendal | -6.971 | 110.2635 | New | New | New | Type B | MA | JAW-JT-KDL-0713 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_3 1x25G/10G LR + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | #N/A | S000055608 | S000055609 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-05 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-3197_1 | New_JAW-JT-KDL-3197 | JAW-JT-KDL-3197 | Central Java | Jawa Tengah | Kendal | -6.9591 | 110.2551 | New | New | New | Type B | MA | JAW-JT-KDL-3197 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | #N/A | S000055610 | S000055611 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-05 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Submitted | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4164_1 | New_JAW-JT-KDL-4164 | JAW-JT-KDL-4164 | Central Java | Jawa Tengah | Kendal | -6.9668 | 110.2449 | New | New | New | Type B | MA | JAW-JT-KDL-4164 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | #N/A | S000055611 | S000055612 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-05 | 45 |  |  | 2025 |  |  | #N/A | [35 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4006_1 | New_JAW-JT-KDL-4006 | JAW-JT-KDL-4006 | Central Java | Jawa Tengah | Kendal | -6.9652 | 110.2409 | New | New | New | Type B | MA | JAW-JT-KDL-4006 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | #N/A | S000055612 | S000055613 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-05 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Submitted | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4148_1 | New_JAW-JT-KDL-4148 | JAW-JT-KDL-4148 | Central Java | Jawa Tengah | Kendal | -6.9395 | 110.2105 | New | New | New | Type B | MA | JAW-JT-KDL-4148 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | #N/A | S000055613 | S000055614 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-05 | 45 |  |  | 2025 |  |  | #N/A | [35 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-3474_1 | New_JAW-JT-KDL-3474 | JAW-JT-KDL-3474 | Central Java | Jawa Tengah | Kendal | -6.9212 | 110.1983 | New | New | New | Type B | MA | JAW-JT-KDL-3474 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | #N/A | S000055614 | S000055615 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-05 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Submitted | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4135_1 | New_JAW-JT-KDL-4135 | JAW-JT-KDL-4135 | Central Java | Jawa Tengah | Kendal | -6.9107 | 110.1792 | New | New | New | Type B | MA | JAW-JT-KDL-4135 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | #N/A | S000055615 | S000055616 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-05 | 45 |  |  | 2025 |  |  | #N/A | [35 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4029_1 | New_JAW-JT-KDL-4029 | JAW-JT-KDL-4029 | Central Java | Jawa Tengah | Kendal | -6.9407 | 110.1939 | New | New | New | Type B | MA | JAW-JT-KDL-4029 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | #N/A | S000055616 | S000055617 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-05 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Submitted | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4136_1 | New_JAW-JT-KDL-4136 | JAW-JT-KDL-4136 | Central Java | Jawa Tengah | Kendal | -6.9495 | 110.1809 | New | New | New | Type B | MA | JAW-JT-KDL-4136 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | #N/A | S000055617 | S000055618 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-05 | 45 |  |  | 2025 |  |  | #N/A | [35 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-1023_1 | New_JAW-JT-KDL-1023 | JAW-JT-KDL-1023 | Central Java | Jawa Tengah | Kendal | -6.9686 | 110.1619 | New | New | New | Type B | MA | JAW-JT-KDL-1023 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | #N/A | S000055618 | S000055619 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-05 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Submitted | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4137_1 | New_JAW-JT-KDL-4137 | JAW-JT-KDL-4137 | Central Java | Jawa Tengah | Kendal | -6.985 | 110.1872 | New | New | New | Type B | MA | JAW-JT-KDL-4137 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | #N/A | S000055619 | S000055620 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-05 | 45 |  |  | 2025 |  |  | #N/A | [35 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4238_1 | New_JAW-JT-KDL-4238 | JAW-JT-KDL-4238 | Central Java | Jawa Tengah | Kendal | -6.9667 | 110.1278 | New | New | New | Type B | MA | JAW-JT-KDL-4238 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | #N/A | S000055620 | S000055621 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-05 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Submitted | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-1025_1 | New_JAW-JT-KDL-1025 | JAW-JT-KDL-1025 | Central Java | Jawa Tengah | Kendal | -6.9654 | 110.0968 | New | New | New | Type B | MA | JAW-JT-KDL-1025 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | #N/A | S000055621 | S000055622 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-06 | 45 |  |  | 2025 |  |  | #N/A | [35 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4216_1 | New_JAW-JT-KDL-4216 | JAW-JT-KDL-4216 | Central Java | Jawa Tengah | Kendal | -6.9549 | 110.0659 | New | New | New | Type B | MA | JAW-JT-KDL-4216 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | #N/A | S000055622 | S000055623 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-06 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Submitted | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0783_1 | New_JAW-JT-KDL-0783 | JAW-JT-KDL-0783 | Central Java | Jawa Tengah | Kendal | -6.9698 | 110.0518 | New | New | New | Type B | MA | JAW-JT-KDL-0783 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | #N/A | S000055623 | S000055624 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-06 | 45 |  |  | 2025 |  |  | #N/A | [35 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4219_1 | New_JAW-JT-KDL-4219 | JAW-JT-KDL-4219 | Central Java | Jawa Tengah | Kendal | -6.9676 | 110.0737 | New | New | New | Type B | MA | JAW-JT-KDL-4219 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | #N/A | S000055624 | S000055625 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-06 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Submitted | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-3317_1 | New_JAW-JT-KDL-3317 | JAW-JT-KDL-3317 | Central Java | Jawa Tengah | Kendal | -7.0941 | 110.3461 | New | New | New | Type B | MA | JAW-JT-KDL-3317 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | #N/A | S000055626 | S000055627 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2025-624 sites |  | 2025-11-06 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0871_1 | New_JAW-JT-KDL-0871 | JAW-JT-KDL-0871 | Central Java | Jawa Tengah | Kendal | -7.0619 | 110.2861 | New | New | New | Type B | MA | JAW-JT-KDL-0871 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | #N/A | S000055627 | S000055628 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2025-624 sites |  | 2025-11-06 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4195_1 | New_JAW-JT-KDL-4195 | JAW-JT-KDL-4195 | Central Java | Jawa Tengah | Kendal | -7.0876 | 110.2851 | New | New | New | Type B | MA | JAW-JT-KDL-4195 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | #N/A | S000055628 | S000055629 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2025-624 sites |  | 2025-11-06 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4187_1 | New_JAW-JT-KDL-4187 | JAW-JT-KDL-4187 | Central Java | Jawa Tengah | Kendal | -7.0957 | 110.2883 | New | New | New | Type B | MA | JAW-JT-KDL-4187 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | #N/A | S000055629 | S000055630 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  |  |  | 2025-11-06 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4189_1 | New_JAW-JT-KDL-4189 | JAW-JT-KDL-4189 | Central Java | Jawa Tengah | Kendal | -7.1004 | 110.2931 | New | New | New | Type B | MA | JAW-JT-KDL-4189 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | #N/A | S000055630 | S000055631 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2026 | CCSI | 2025-11-06 | 45 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-24 | 48 | 2025-11-24 |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-JT-KDL-4202_1 | New_JAW-JT-KDL-4202 | JAW-JT-KDL-4202 | Central Java | Jawa Tengah | Kendal | -7.1176 | 110.3321 | New | New | New | Type B | MA | JAW-JT-KDL-4202 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | #N/A | S000055631 | S000055632 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2025-624 sites |  | 2025-11-06 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4199_1 | New_JAW-JT-KDL-4199 | JAW-JT-KDL-4199 | Central Java | Jawa Tengah | Kendal | -7.1248 | 110.3219 | New | New | New | Type B | MA | JAW-JT-KDL-4199 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | #N/A | S000055632 | S000055633 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2025-624 sites |  | 2025-11-06 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0876_1 | New_JAW-JT-KDL-0876 | JAW-JT-KDL-0876 | Central Java | Jawa Tengah | Kendal | -7.1384 | 110.3243 | New | New | New | Type B | MA | JAW-JT-KDL-0876 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | #N/A | S000055633 | S000055634 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2025-624 sites |  | 2025-11-06 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4197_1 | New_JAW-JT-KDL-4197 | JAW-JT-KDL-4197 | Central Java | Jawa Tengah | Kendal | -7.1357 | 110.301 | New | New | New | Type B | MA | JAW-JT-KDL-4197 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | #N/A | S000055634 | S000055635 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2025-624 sites |  | 2025-11-06 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4191_1 | New_JAW-JT-KDL-4191 | JAW-JT-KDL-4191 | Central Java | Jawa Tengah | Kendal | -7.1595 | 110.285 | New | New | New | Type B | MA | JAW-JT-KDL-4191 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | #N/A | S000055635 | S000055636 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2025-624 sites |  | 2025-11-07 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-3365_1 | New_JAW-JT-KDL-3365 | JAW-JT-KDL-3365 | Central Java | Jawa Tengah | Kendal | -7.1787 | 110.2805 | New | New | New | Type B | MA | JAW-JT-KDL-3365 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | #N/A | S000055636 | S000055637 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2025-624 sites |  | 2025-11-07 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0861_1 | New_JAW-JT-KDL-0861 | JAW-JT-KDL-0861 | Central Java | Jawa Tengah | Kendal | -7.1638 | 110.2536 | New | New | New | Type B | MA | JAW-JT-KDL-0861 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | #N/A | S000055637 | S000055638 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2025-624 sites |  | 2025-11-07 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0842_1 | New_JAW-JT-KDL-0842 | JAW-JT-KDL-0842 | Central Java | Jawa Tengah | Kendal | -7.1524 | 110.1983 | New | New | New | Type B | MA | JAW-JT-KDL-0842 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | #N/A | S000055638 | S000055639 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2025-624 sites |  | 2025-11-07 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0830_1 | New_JAW-JT-KDL-0830 | JAW-JT-KDL-0830 | Central Java | Jawa Tengah | Kendal | -7.1301 | 110.1684 | New | New | New | Type B | MA | JAW-JT-KDL-0830 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | #N/A | S000055639 | S000055640 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2025-624 sites |  | 2025-11-07 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0704_1 | New_JAW-JT-KDL-0704 | JAW-JT-KDL-0704 | Central Java | Jawa Tengah | Kendal | -7.1209 | 110.218 | New | New | New | Type B | MA | JAW-JT-KDL-0704 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | #N/A | S000055640 | S000055641 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2025-624 sites |  | 2025-11-07 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4173_1 | New_JAW-JT-KDL-4173 | JAW-JT-KDL-4173 | Central Java | Jawa Tengah | Kendal | -7.0551 | 110.257 | New | New | New | Type B | MA | JAW-JT-KDL-4173 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | #N/A | S000055641 | S000055642 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2025-624 sites |  | 2025-11-07 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4003_1 | New_JAW-JT-KDL-4003 | JAW-JT-KDL-4003 | Central Java | Jawa Tengah | Kendal | -6.9884 | 110.2577 | New | New | New | Type B | MA | JAW-JT-KDL-4003 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | #N/A | S000055642 | S000055643 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2025-624 sites |  | 2025-11-07 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4015_1 | New_JAW-JT-KDL-4015 | JAW-JT-KDL-4015 | Central Java | Jawa Tengah | Kendal | -6.9754 | 110.2546 | New | New | New | Type B | MA | JAW-JT-KDL-4015 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | #N/A | S000055643 | S000055644 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2025-624 sites |  | 2025-11-07 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4192_1 | New_JAW-JT-KDL-4192 | JAW-JT-KDL-4192 | Central Java | Jawa Tengah | Kendal | -6.9677 | 110.285 | New | New | New | Type B | MA | JAW-JT-KDL-4192 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | #N/A | S000055644 | S000055645 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  |  |  | 2025-11-07 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8470_1 | New_JAW-JT-DMK-8470 | JAW-JT-DMK-8470 | Central Java | Jawa Tengah | Demak | -6.8601 | 110.8076 | New | New | New | Type B | MA | JAW-JT-DMK-8470 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | #N/A | S000055677 | S000055678 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | No |  | 2026 |  | 2025-11-07 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8471_1 | New_JAW-JT-DMK-8471 | JAW-JT-DMK-8471 | Central Java | Jawa Tengah | Demak | -6.8793 | 110.8015 | New | New | New | Type B | MA | JAW-JT-DMK-8471 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | #N/A | S000055678 | S000055679 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | No |  | 2026 |  | 2025-11-07 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8468_1 | New_JAW-JT-DMK-8468 | JAW-JT-DMK-8468 | Central Java | Jawa Tengah | Demak | -6.8928 | 110.7992 | New | New | New | Type B | MA | JAW-JT-DMK-8468 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | #N/A | S000055679 | S000055680 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | No |  | 2026 |  | 2025-11-07 | 45 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8461_1 | New_JAW-JT-DMK-8461 | JAW-JT-DMK-8461 | Central Java | Jawa Tengah | Demak | -6.8916 | 110.7777 | New | New | New | Type B | MA | JAW-JT-DMK-8461 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | #N/A | S000055680 | S000055681 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | No |  | 2026 |  | 2025-11-10 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8462_1 | New_JAW-JT-DMK-8462 | JAW-JT-DMK-8462 | Central Java | Jawa Tengah | Demak | -6.9149 | 110.7792 | New | New | New | Type B | MA | JAW-JT-DMK-8462 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | #N/A | S000055681 | S000055682 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | No |  | 2026 |  | 2025-11-10 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-0844_1 | New_JAW-JT-KDS-0844 | JAW-JT-KDS-0844 | Central Java | Jawa Tengah | Kudus | -6.931 | 110.8079 | New | New | New | Type B | MA | JAW-JT-KDS-0844 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | #N/A | S000055682 | S000055683 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | No |  | 2026 |  | 2025-11-10 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-26 | 48 | 2025-11-26 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-4001_1 | New_JAW-JT-KDS-4001 | JAW-JT-KDS-4001 | Central Java | Jawa Tengah | Kudus | -6.9139 | 110.7971 | New | New | New | Type B | MA | JAW-JT-KDS-4001 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | #N/A | S000055683 | S000055684 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | No |  | 2026 |  | 2025-11-10 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-26 | 48 | 2025-11-26 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8472_1 | New_JAW-JT-DMK-8472 | JAW-JT-DMK-8472 | Central Java | Jawa Tengah | Demak | -6.8676 | 110.8227 | New | New | New | Type B | MA | JAW-JT-DMK-8472 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | #N/A | S000055684 | S000055685 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | No |  | 2026 |  | 2025-11-10 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8473_1 | New_JAW-JT-DMK-8473 | JAW-JT-DMK-8473 | Central Java | Jawa Tengah | Demak | -6.8533 | 110.832 | New | New | New | Type B | MA | JAW-JT-DMK-8473 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | #N/A | S000055685 | S000055686 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | No |  | 2026 |  | 2025-11-10 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0620_1 | New_JAW-JT-DMK-0620 | JAW-JT-DMK-0620 | Central Java | Jawa Tengah | Demak | -6.8258 | 110.7894 | New | New | New | Type B | MA | JAW-JT-DMK-0620 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | #N/A | S000055686 | S000055687 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | No |  | 2026 |  | 2025-11-10 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-4012_1 | New_JAW-JT-DMK-4012 | JAW-JT-DMK-4012 | Central Java | Jawa Tengah | Demak | -6.8066 | 110.7619 | New | New | New | Type B | MA | JAW-JT-DMK-4012 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | #N/A | S000055687 | S000055688 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | No |  | 2026 |  | 2025-11-10 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8451_1 | New_JAW-JT-DMK-8451 | JAW-JT-DMK-8451 | Central Java | Jawa Tengah | Demak | -6.8384 | 110.7494 | New | New | New | Type B | MA | JAW-JT-DMK-8451 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | #N/A | S000055688 | S000055689 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | No |  | 2026 |  | 2025-11-10 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8437_1 | New_JAW-JT-DMK-8437 | JAW-JT-DMK-8437 | Central Java | Jawa Tengah | Demak | -6.8264 | 110.7138 | New | New | New | Type B | MA | JAW-JT-DMK-8437 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | #N/A | S000055689 | S000055690 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | No |  | 2026 |  | 2025-11-10 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-4023_1 | New_JAW-JT-DMK-4023 | JAW-JT-DMK-4023 | Central Java | Jawa Tengah | Demak | -6.8382 | 110.7069 | New | New | New | Type B | MA | JAW-JT-DMK-4023 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | #N/A | S000055690 | S000055691 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | No |  | 2026 |  | 2025-11-10 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8439_1 | New_JAW-JT-DMK-8439 | JAW-JT-DMK-8439 | Central Java | Jawa Tengah | Demak | -6.8388 | 110.7207 | New | New | New | Type B | MA | JAW-JT-DMK-8439 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | #N/A | S000055691 | S000055692 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | No |  | 2026 |  | 2025-11-10 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-0874_1 | New_JAW-JT-KDS-0874 | JAW-JT-KDS-0874 | Central Java | Jawa Tengah | Kudus | -6.8191 | 110.8362 | New | New | New | Type B | MA | JAW-JT-KDS-0874 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | #N/A | S000055693 | S000055694 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | Yes |  | 2025-624 sites |  | 2025-11-10 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-26 | 48 | 2025-11-26 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8404_1 | New_JAW-JT-KDS-8404 | JAW-JT-KDS-8404 | Central Java | Jawa Tengah | Kudus | -6.8115 | 110.8342 | New | New | New | Type B | MA | JAW-JT-KDS-8404 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | #N/A | S000055694 | S000055695 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | Yes |  |  |  | 2025-11-11 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-0846_1 | New_JAW-JT-KDS-0846 | JAW-JT-KDS-0846 | Central Java | Jawa Tengah | Kudus | -6.8207 | 110.8226 | New | New | New | Type B | MA | JAW-JT-KDS-0846 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | #N/A | S000055695 | S000055696 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | Yes |  | 2026 |  | 2025-11-11 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-26 | 48 | 2025-11-26 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8386_1 | New_JAW-JT-KDS-8386 | JAW-JT-KDS-8386 | Central Java | Jawa Tengah | Kudus | -6.8136 | 110.8242 | New | New | New | Type B | MA | JAW-JT-KDS-8386 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | #N/A | S000055696 | S000055697 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | Yes |  | 2026 |  | 2025-11-11 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-26 | 48 | 2025-11-26 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8371_1 | New_JAW-JT-KDS-8371 | JAW-JT-KDS-8371 | Central Java | Jawa Tengah | Kudus | -6.8114 | 110.807 | New | New | New | Type B | MA | JAW-JT-KDS-8371 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | #N/A | S000055697 | S000055698 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | Yes |  | 2026 |  | 2025-11-11 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-26 | 48 | 2025-11-26 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8380_1 | New_JAW-JT-KDS-8380 | JAW-JT-KDS-8380 | Central Java | Jawa Tengah | Kudus | -6.802 | 110.8213 | New | New | New | Type B | MA | JAW-JT-KDS-8380 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | #N/A | S000055698 | S000055699 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | Yes |  | 2026 | YPTT | 2025-11-11 | 46 |  |  | 2025 | 2025-11-19 | 2025-11-19 | Reviewing |  |  | Submitted | Approved | [31 empty] | 2025-11-26 | 48 | 2025-11-26 |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8374_1 | New_JAW-JT-KDS-8374 | JAW-JT-KDS-8374 | Central Java | Jawa Tengah | Kudus | -6.8 | 110.8111 | New | New | New | Type B | MA | JAW-JT-KDS-8374 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | #N/A | S000055699 | S000055700 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | Yes |  |  |  | 2025-11-11 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8372_1 | New_JAW-JT-KDS-8372 | JAW-JT-KDS-8372 | Central Java | Jawa Tengah | Kudus | -6.7931 | 110.8071 | New | New | New | Type B | MA | JAW-JT-KDS-8372 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | #N/A | S000055700 | S000055701 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | Yes |  | 2026 |  | 2025-11-11 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-26 | 48 | 2025-11-26 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8367_1 | New_JAW-JT-KDS-8367 | JAW-JT-KDS-8367 | Central Java | Jawa Tengah | Kudus | -6.792 | 110.7943 | New | New | New | Type B | MA | JAW-JT-KDS-8367 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | #N/A | S000055701 | S000055702 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | Yes |  |  |  | 2025-11-11 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8361_1 | New_JAW-JT-KDS-8361 | JAW-JT-KDS-8361 | Central Java | Jawa Tengah | Kudus | -6.7815 | 110.7651 | New | New | New | Type B | MA | JAW-JT-KDS-8361 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | #N/A | S000055702 | S000055703 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | Yes |  | 2026 |  | 2025-11-11 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-26 | 48 | 2025-11-26 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8426_1 | New_JAW-JT-DMK-8426 | JAW-JT-DMK-8426 | Central Java | Jawa Tengah | Demak | -6.7701 | 110.692 | New | New | New | Type B | MA | JAW-JT-DMK-8426 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | #N/A | S000055703 | S000055704 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | Yes |  | 2026 |  | 2025-11-11 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8424_1 | New_JAW-JT-DMK-8424 | JAW-JT-DMK-8424 | Central Java | Jawa Tengah | Demak | -6.7502 | 110.669 | New | New | New | Type B | MA | JAW-JT-DMK-8424 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | #N/A | S000055704 | S000055705 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | Yes |  | 2026 |  | 2025-11-11 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0594_1 | New_JAW-JT-DMK-0594 | JAW-JT-DMK-0594 | Central Java | Jawa Tengah | Demak | -6.7689 | 110.672 | New | New | New | Type B | MA | JAW-JT-DMK-0594 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | #N/A | S000055705 | S000055706 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | Yes |  | 2026 |  | 2025-11-11 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0622_1 | New_JAW-JT-DMK-0622 | JAW-JT-DMK-0622 | Central Java | Jawa Tengah | Demak | -6.7822 | 110.6562 | New | New | New | Type B | MA | JAW-JT-DMK-0622 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | #N/A | S000055706 | S000055707 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | Yes |  | 2026 |  | 2025-11-11 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8440_1 | New_JAW-JT-DMK-8440 | JAW-JT-DMK-8440 | Central Java | Jawa Tengah | Demak | -6.8216 | 110.7276 | New | New | New | Type B | MA | JAW-JT-DMK-8440 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | #N/A | S000055707 | S000055708 | 12. NY TERMINATION | 2025-12-20 | 51 |  |  | Yes |  | 2026 |  | 2025-11-11 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8430_1 | New_JAW-JT-DMK-8430 | JAW-JT-DMK-8430 | Central Java | Jawa Tengah | Demak | -6.8951 | 110.7002 | New | New | New | Type B | MA | JAW-JT-DMK-8430 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | #N/A | S000055709 | S000055710 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  |  |  | 2025-11-12 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8433_1 | New_JAW-JT-DMK-8433 | JAW-JT-DMK-8433 | Central Java | Jawa Tengah | Demak | -6.9036 | 110.7098 | New | New | New | Type B | MA | JAW-JT-DMK-8433 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | #N/A | S000055710 | S000055711 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-11-12 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8435_1 | New_JAW-JT-DMK-8435 | JAW-JT-DMK-8435 | Central Java | Jawa Tengah | Demak | -6.9165 | 110.7115 | New | New | New | Type B | MA | JAW-JT-DMK-8435 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | #N/A | S000055711 | S000055712 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-11-12 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8429_1 | New_JAW-JT-DMK-8429 | JAW-JT-DMK-8429 | Central Java | Jawa Tengah | Demak | -6.9475 | 110.6988 | New | New | New | Type B | MA | JAW-JT-DMK-8429 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | #N/A | S000055712 | S000055713 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-11-12 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0621_1 | New_JAW-JT-DMK-0621 | JAW-JT-DMK-0621 | Central Java | Jawa Tengah | Demak | -6.9406 | 110.6814 | New | New | New | Type B | MA | JAW-JT-DMK-0621 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | #N/A | S000055713 | S000055714 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-11-12 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8421_1 | New_JAW-JT-DMK-8421 | JAW-JT-DMK-8421 | Central Java | Jawa Tengah | Demak | -6.9626 | 110.6781 | New | New | New | Type B | MA | JAW-JT-DMK-8421 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | #N/A | S000055714 | S000055715 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-11-12 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8419_1 | New_JAW-JT-DMK-8419 | JAW-JT-DMK-8419 | Central Java | Jawa Tengah | Demak | -6.9708 | 110.6737 | New | New | New | Type B | MA | JAW-JT-DMK-8419 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | #N/A | S000055715 | S000055716 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-11-12 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8443_1 | New_JAW-JT-DMK-8443 | JAW-JT-DMK-8443 | Central Java | Jawa Tengah | Demak | -6.9847 | 110.7188 | New | New | New | Type B | MA | JAW-JT-DMK-8443 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | #N/A | S000055716 | S000055717 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 | YPTT | 2025-11-12 | 46 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8438_1 | New_JAW-JT-DMK-8438 | JAW-JT-DMK-8438 | Central Java | Jawa Tengah | Demak | -6.9981 | 110.7165 | New | New | New | Type B | MA | JAW-JT-DMK-8438 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | #N/A | S000055717 | S000055718 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-11-12 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8448_1 | New_JAW-JT-DMK-8448 | JAW-JT-DMK-8448 | Central Java | Jawa Tengah | Demak | -7.001 | 110.7433 | New | New | New | Type B | MA | JAW-JT-DMK-8448 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | #N/A | S000055718 | S000055719 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-11-12 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-0022_1 | New_JAW-JT-PWD-0022 | JAW-JT-PWD-0022 | Central Java | Jawa Tengah | Demak | -6.977 | 110.7584 | New | New | New | Type B | MA | JAW-JT-PWD-0022 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | #N/A | S000055719 | S000055720 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-11-12 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8450_1 | New_JAW-JT-DMK-8450 | JAW-JT-DMK-8450 | Central Java | Jawa Tengah | Demak | -6.9593 | 110.7485 | New | New | New | Type B | MA | JAW-JT-DMK-8450 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | #N/A | S000055720 | S000055721 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-11-12 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8457_1 | New_JAW-JT-DMK-8457 | JAW-JT-DMK-8457 | Central Java | Jawa Tengah | Demak | -6.9534 | 110.7635 | New | New | New | Type B | MA | JAW-JT-DMK-8457 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | #N/A | S000055721 | S000055722 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-11-12 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8454_1 | New_JAW-JT-DMK-8454 | JAW-JT-DMK-8454 | Central Java | Jawa Tengah | Demak | -6.9325 | 110.7539 | New | New | New | Type B | MA | JAW-JT-DMK-8454 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | #N/A | S000055722 | S000055723 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-11-12 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8449_1 | New_JAW-JT-DMK-8449 | JAW-JT-DMK-8449 | Central Java | Jawa Tengah | Demak | -6.9282 | 110.7434 | New | New | New | Type B | MA | JAW-JT-DMK-8449 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | #N/A | S000055723 | S000055724 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-11-13 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8445_1 | New_JAW-JT-DMK-8445 | JAW-JT-DMK-8445 | Central Java | Jawa Tengah | Demak | -6.9136 | 110.738 | New | New | New | Type B | MA | JAW-JT-DMK-8445 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | #N/A | S000055724 | S000055725 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-11-13 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8453_1 | New_JAW-JT-DMK-8453 | JAW-JT-DMK-8453 | Central Java | Jawa Tengah | Demak | -6.8917 | 110.7503 | New | New | New | Type B | MA | JAW-JT-DMK-8453 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | #N/A | S000055725 | S000055726 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-11-13 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8441_1 | New_JAW-JT-DMK-8441 | JAW-JT-DMK-8441 | Central Java | Jawa Tengah | Demak | -6.8717 | 110.7314 | New | New | New | Type B | MA | JAW-JT-DMK-8441 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | #N/A | S000055726 | S000055727 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-11-13 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8356_1 | New_JAW-JT-DMK-8356 | JAW-JT-DMK-8356 | Central Java | Jawa Tengah | Demak | -6.9093 | 110.5661 | New | New | New | Type B | MA | JAW-JT-DMK-8356 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | #N/A | S000055728 | S000055729 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | Yes |  | 2026 | GIT | 2025-11-13 | 46 |  |  | 2025 | 2025-11-10 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8301_1 | New_JAW-JT-DMK-8301 | JAW-JT-DMK-8301 | Central Java | Jawa Tengah | Demak | -6.9106 | 110.5067 | New | New | New | Type B | MA | JAW-JT-DMK-8301 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | #N/A | S000055729 | S000055730 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | Yes |  | 2026 | GIT | 2025-11-13 | 46 |  |  | 2025 | 2025-11-10 | 2025-11-10 | Approved | 2025-11-13 |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8344_1 | New_JAW-JT-DMK-8344 | JAW-JT-DMK-8344 | Central Java | Jawa Tengah | Demak | -6.924 | 110.5348 | New | New | New | Type B | MA | JAW-JT-DMK-8344 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | #N/A | S000055730 | S000055731 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | Yes |  | 2026 | GIT | 2025-11-13 | 46 |  |  | 2025 | 2025-11-12 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8338_1 | New_JAW-JT-DMK-8338 | JAW-JT-DMK-8338 | Central Java | Jawa Tengah | Demak | -6.9128 | 110.5345 | New | New | New | Type B | MA | JAW-JT-DMK-8338 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | #N/A | S000055731 | S000055732 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | Yes |  | 2026 | GIT | 2025-11-13 | 46 |  |  | 2025 | 2025-11-10 | 2025-11-10 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8306_1 | New_JAW-JT-DMK-8306 | JAW-JT-DMK-8306 | Central Java | Jawa Tengah | Demak | -6.8958 | 110.5115 | New | New | New | Type B | MA | JAW-JT-DMK-8306 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | #N/A | S000055732 | S000055733 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | Yes |  | 2026 | GIT | 2025-11-13 | 46 |  |  | 2025 | 2025-11-08 | 2025-11-14 | Approved | 2025-11-17 |  | Submitted | Approved |  | Blok Akses, kompensasi 10jt | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8329_1 | New_JAW-JT-DMK-8329 | JAW-JT-DMK-8329 | Central Java | Jawa Tengah | Demak | -6.8824 | 110.5326 | New | New | New | Type B | MA | JAW-JT-DMK-8329 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | #N/A | S000055733 | S000055734 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | Yes |  | 2026 | GIT | 2025-11-13 | 46 |  |  | 2025 | 2025-11-10 | 2025-11-10 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8337_1 | New_JAW-JT-DMK-8337 | JAW-JT-DMK-8337 | Central Java | Jawa Tengah | Demak | -6.8692 | 110.5436 | New | New | New | Type B | MA | JAW-JT-DMK-8337 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | #N/A | S000055734 | S000055735 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | Yes |  | 2026 | GIT | 2025-11-13 | 46 |  |  | 2025 | 2025-11-10 | 2025-11-10 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-4132_1 | New_JAW-JT-DMK-4132 | JAW-JT-DMK-4132 | Central Java | Jawa Tengah | Demak | -6.8836 | 110.5523 | New | New | New | Type B | MA | JAW-JT-DMK-4132 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | #N/A | S000055735 | S000055736 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | Yes |  | 2026 | YPTT | 2025-11-13 | 46 |  |  | 2025 | 2025-11-17 | 2025-11-17 | Reviewing |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | 1 | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8353_1 | New_JAW-JT-DMK-8353 | JAW-JT-DMK-8353 | Central Java | Jawa Tengah | Demak | -6.856 | 110.5629 | New | New | New | Type B | MA | JAW-JT-DMK-8353 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | #N/A | S000055736 | S000055737 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | Yes |  | 2026 | GIT | 2025-11-13 | 46 |  |  | 2025 | 2025-11-10 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-0625_1 | New_JAW-JT-DMK-0625 | JAW-JT-DMK-0625 | Central Java | Jawa Tengah | Demak | -6.8312 | 110.5532 | New | New | New | Type B | MA | JAW-JT-DMK-0625 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | #N/A | S000055737 | S000055738 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | Yes |  | 2026 | GIT | 2025-11-13 | 46 |  |  | 2025 | 2025-11-10 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8372_1 | New_JAW-JT-DMK-8372 | JAW-JT-DMK-8372 | Central Java | Jawa Tengah | Demak | -6.8508 | 110.5924 | New | New | New | Type B | MA | JAW-JT-DMK-8372 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | #N/A | S000055738 | S000055739 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | Yes |  |  | GIT | 2025-11-14 | 46 |  |  | 2025 | 2025-11-19 | 2025-11-19 | Reviewing |  |  | Submitted | Approved |  | No BTS at site | [31 empty] | #N/A |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8368_1 | New_JAW-JT-DMK-8368 | JAW-JT-DMK-8368 | Central Java | Jawa Tengah | Demak | -6.8112 | 110.5882 | New | New | New | Type B | MA | JAW-JT-DMK-8368 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | #N/A | S000055739 | S000055740 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | Yes |  | 2026 | GIT | 2025-11-14 | 46 |  |  | 2025 | 2025-11-13 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8370_1 | New_JAW-JT-DMK-8370 | JAW-JT-DMK-8370 | Central Java | Jawa Tengah | Demak | -6.8817 | 110.5905 | New | New | New | Type B | MA | JAW-JT-DMK-8370 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | #N/A | S000055740 | S000055741 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | Yes |  |  | GIT | 2025-11-14 | 46 |  |  | 2025 | 2025-11-08 | 2025-11-19 | Reviewing |  |  | Submitted | Approved |  | No BTS at site | [31 empty] | #N/A |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-4011_1 | New_JAW-JT-DMK-4011 | JAW-JT-DMK-4011 | Central Java | Jawa Tengah | Demak | -6.8893 | 110.6479 | New | New | New | Type B | MA | JAW-JT-DMK-4011 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | #N/A | S000055741 | S000055742 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | Yes |  | 2026 | GIT | 2025-11-14 | 46 |  |  | 2025 | 2025-11-12 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8405_1 | New_JAW-JT-DMK-8405 | JAW-JT-DMK-8405 | Central Java | Jawa Tengah | Demak | -6.9062 | 110.6406 | New | New | New | Type B | MA | JAW-JT-DMK-8405 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | #N/A | S000055743 | S000055744 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2026 |  | 2025-11-14 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8417_1 | New_JAW-JT-DMK-8417 | JAW-JT-DMK-8417 | Central Java | Jawa Tengah | Demak | -6.9115 | 110.6617 | New | New | New | Type B | MA | JAW-JT-DMK-8417 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | #N/A | S000055744 | S000055745 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  |  |  | 2025-11-14 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0626_1 | New_JAW-JT-DMK-0626 | JAW-JT-DMK-0626 | Central Java | Jawa Tengah | Demak | -6.9486 | 110.6548 | New | New | New | Type B | MA | JAW-JT-DMK-0626 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | #N/A | S000055745 | S000055746 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2026 |  | 2025-11-14 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-4026_1 | New_JAW-JT-DMK-4026 | JAW-JT-DMK-4026 | Central Java | Jawa Tengah | Demak | -6.9659 | 110.6451 | New | New | New | Type B | MA | JAW-JT-DMK-4026 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | #N/A | S000055746 | S000055747 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2026 |  | 2025-11-14 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8399_1 | New_JAW-JT-DMK-8399 | JAW-JT-DMK-8399 | Central Java | Jawa Tengah | Demak | -6.9557 | 110.6326 | New | New | New | Type B | MA | JAW-JT-DMK-8399 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | #N/A | S000055747 | S000055748 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2026 |  | 2025-11-14 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8397_1 | New_JAW-JT-DMK-8397 | JAW-JT-DMK-8397 | Central Java | Jawa Tengah | Demak | -6.9425 | 110.6318 | New | New | New | Type B | MA | JAW-JT-DMK-8397 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | #N/A | S000055748 | S000055749 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2026 |  | 2025-11-14 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8386_1 | New_JAW-JT-DMK-8386 | JAW-JT-DMK-8386 | Central Java | Jawa Tengah | Demak | -6.9595 | 110.6123 | New | New | New | Type B | MA | JAW-JT-DMK-8386 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | #N/A | S000055749 | S000055750 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2026 |  | 2025-11-14 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0627_1 | New_JAW-JT-DMK-0627 | JAW-JT-DMK-0627 | Central Java | Jawa Tengah | Demak | -6.9652 | 110.5688 | New | New | New | Type B | MA | JAW-JT-DMK-0627 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | #N/A | S000055750 | S000055751 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2026 |  | 2025-11-14 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8377_1 | New_JAW-JT-DMK-8377 | JAW-JT-DMK-8377 | Central Java | Jawa Tengah | Demak | -6.9501 | 110.5848 | New | New | New | Type B | MA | JAW-JT-DMK-8377 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | #N/A | S000055751 | S000055752 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2026 |  | 2025-11-14 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8373_1 | New_JAW-JT-DMK-8373 | JAW-JT-DMK-8373 | Central Java | Jawa Tengah | Demak | -6.9332 | 110.5939 | New | New | New | Type B | MA | JAW-JT-DMK-8373 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | #N/A | S000055752 | S000055753 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2026 |  | 2025-11-14 | 46 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-4010_1 | New_JAW-JT-DMK-4010 | JAW-JT-DMK-4010 | Central Java | Jawa Tengah | Demak | -6.9227 | 110.5836 | New | New | New | Type B | MA | JAW-JT-DMK-4010 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | #N/A | S000055753 | S000055754 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2026 |  | 2025-11-17 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8378_1 | New_JAW-JT-DMK-8378 | JAW-JT-DMK-8378 | Central Java | Jawa Tengah | Demak | -6.9101 | 110.5849 | New | New | New | Type B | MA | JAW-JT-DMK-8378 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | #N/A | S000055754 | S000055755 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2026 |  | 2025-11-17 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8384_1 | New_JAW-JT-DMK-8384 | JAW-JT-DMK-8384 | Central Java | Jawa Tengah | Demak | -6.9162 | 110.6095 | New | New | New | Type B | MA | JAW-JT-DMK-8384 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | #N/A | S000055755 | S000055756 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2026 |  | 2025-11-17 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8392_1 | New_JAW-JT-DMK-8392 | JAW-JT-DMK-8392 | Central Java | Jawa Tengah | Demak | -6.9108 | 110.6176 | New | New | New | Type B | MA | JAW-JT-DMK-8392 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | #N/A | S000055756 | S000055757 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2026 |  | 2025-11-17 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8402_1 | New_JAW-JT-DMK-8402 | JAW-JT-DMK-8402 | Central Java | Jawa Tengah | Demak | -6.8891 | 110.6367 | New | New | New | Type B | MA | JAW-JT-DMK-8402 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | #N/A | S000055757 | S000055758 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2026 |  | 2025-11-17 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8400_1 | New_JAW-JT-DMK-8400 | JAW-JT-DMK-8400 | Central Java | Jawa Tengah | Demak | -6.8861 | 110.6326 | New | New | New | Type B | MA | JAW-JT-DMK-8400 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | #N/A | S000055758 | S000055759 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2026 |  | 2025-11-17 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8407_1 | New_JAW-JT-DMK-8407 | JAW-JT-DMK-8407 | Central Java | Jawa Tengah | Demak | -6.8916 | 110.6433 | New | New | New | Type B | MA | JAW-JT-DMK-8407 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | #N/A | S000055759 | S000055760 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2026 |  | 2025-11-17 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8411_1 | New_JAW-JT-DMK-8411 | JAW-JT-DMK-8411 | Central Java | Jawa Tengah | Demak | -6.9008 | 110.6491 | New | New | New | Type B | MA | JAW-JT-DMK-8411 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | #N/A | S000055760 | S000055761 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2026 | YPTT | 2025-11-17 | 47 |  |  | 2025 | 2025-11-19 | 2025-11-19 | Reviewing |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-4025_1 | New_JAW-JT-DMK-4025 | JAW-JT-DMK-4025 | Central Java | Jawa Tengah | Demak | -7.0358 | 110.5028 | New | New | New | Type B | MA | JAW-JT-DMK-4025 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | #N/A | S000055762 | S000055763 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-17 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8290_1 | New_JAW-JT-DMK-8290 | JAW-JT-DMK-8290 | Central Java | Jawa Tengah | Demak | -7.0537 | 110.4983 | New | New | New | Type B | MA | JAW-JT-DMK-8290 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | #N/A | S000055763 | S000055764 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-17 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8295_1 | New_JAW-JT-DMK-8295 | JAW-JT-DMK-8295 | Central Java | Jawa Tengah | Demak | -7.0634 | 110.5044 | New | New | New | Type B | MA | JAW-JT-DMK-8295 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | #N/A | S000055764 | S000055765 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-17 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8289_1 | New_JAW-JT-DMK-8289 | JAW-JT-DMK-8289 | Central Java | Jawa Tengah | Demak | -7.0889 | 110.4979 | New | New | New | Type B | MA | JAW-JT-DMK-8289 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | #N/A | S000055765 | S000055766 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-17 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8330_1 | New_JAW-JT-DMK-8330 | JAW-JT-DMK-8330 | Central Java | Jawa Tengah | Demak | -7.085 | 110.5327 | New | New | New | Type B | MA | JAW-JT-DMK-8330 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | #N/A | S000055766 | S000055767 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-17 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8336_1 | New_JAW-JT-DMK-8336 | JAW-JT-DMK-8336 | Central Java | Jawa Tengah | Demak | -7.0812 | 110.5427 | New | New | New | Type B | MA | JAW-JT-DMK-8336 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | #N/A | S000055767 | S000055768 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-17 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8335_1 | New_JAW-JT-DMK-8335 | JAW-JT-DMK-8335 | Central Java | Jawa Tengah | Demak | -7.0718 | 110.5393 | New | New | New | Type B | MA | JAW-JT-DMK-8335 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | #N/A | S000055768 | S000055769 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-18 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8312_1 | New_JAW-JT-DMK-8312 | JAW-JT-DMK-8312 | Central Java | Jawa Tengah | Demak | -7.0398 | 110.5165 | New | New | New | Type B | MA | JAW-JT-DMK-8312 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | #N/A | S000055769 | S000055770 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-18 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8333_1 | New_JAW-JT-DMK-8333 | JAW-JT-DMK-8333 | Central Java | Jawa Tengah | Demak | -7.0427 | 110.5386 | New | New | New | Type B | MA | JAW-JT-DMK-8333 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | #N/A | S000055771 | S000055772 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-18 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8348_1 | New_JAW-JT-DMK-8348 | JAW-JT-DMK-8348 | Central Java | Jawa Tengah | Demak | -7.0559 | 110.5547 | New | New | New | Type B | MA | JAW-JT-DMK-8348 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | #N/A | S000055772 | S000055773 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-18 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8349_1 | New_JAW-JT-DMK-8349 | JAW-JT-DMK-8349 | Central Java | Jawa Tengah | Demak | -7.0502 | 110.5576 | New | New | New | Type B | MA | JAW-JT-DMK-8349 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | #N/A | S000055773 | S000055774 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-18 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0572_1 | New_JAW-JT-DMK-0572 | JAW-JT-DMK-0572 | Central Java | Jawa Tengah | Demak | -7.0438 | 110.5767 | New | New | New | Type B | MA | JAW-JT-DMK-0572 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | #N/A | S000055774 | S000055775 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-18 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8361_1 | New_JAW-JT-DMK-8361 | JAW-JT-DMK-8361 | Central Java | Jawa Tengah | Demak | -7.0353 | 110.5736 | New | New | New | Type B | MA | JAW-JT-DMK-8361 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | #N/A | S000055775 | S000055776 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-18 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-4013_1 | New_JAW-JT-DMK-4013 | JAW-JT-DMK-4013 | Central Java | Jawa Tengah | Demak | -6.9962 | 110.5686 | New | New | New | Type B | MA | JAW-JT-DMK-4013 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | #N/A | S000055776 | S000055777 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-18 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8369_1 | New_JAW-JT-DMK-8369 | JAW-JT-DMK-8369 | Central Java | Jawa Tengah | Demak | -6.9986 | 110.5883 | New | New | New | Type B | MA | JAW-JT-DMK-8369 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | #N/A | S000055777 | S000055778 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-18 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0615_1 | New_JAW-JT-DMK-0615 | JAW-JT-DMK-0615 | Central Java | Jawa Tengah | Demak | -7.0311 | 110.5889 | New | New | New | Type B | MA | JAW-JT-DMK-0615 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | #N/A | S000055778 | S000055779 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-18 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8381_1 | New_JAW-JT-DMK-8381 | JAW-JT-DMK-8381 | Central Java | Jawa Tengah | Demak | -7.0337 | 110.6042 | New | New | New | Type B | MA | JAW-JT-DMK-8381 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | #N/A | S000055779 | S000055780 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-18 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0623_1 | New_JAW-JT-DMK-0623 | JAW-JT-DMK-0623 | Central Java | Jawa Tengah | Demak | -6.9854 | 110.6047 | New | New | New | Type B | MA | JAW-JT-DMK-0623 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | #N/A | S000055780 | S000055781 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-18 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8285_1 | New_JAW-JT-DMK-8285 | JAW-JT-DMK-8285 | Central Java | Jawa Tengah | Demak | -7.0031 | 110.4958 | New | New | New | Type B | MA | JAW-JT-DMK-8285 |  |  |  |  | - | - | - | - | New Purchase | New Ring 010 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | #N/A | S000055784 | S000055785 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | No |  |  |  | 2025-11-18 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8293_1 | New_JAW-JT-DMK-8293 | JAW-JT-DMK-8293 | Central Java | Jawa Tengah | Demak | -6.997 | 110.5029 | New | New | New | Type B | MA | JAW-JT-DMK-8293 |  |  |  |  | - | - | - | - | New Purchase | New Ring 010 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | #N/A | S000055785 | S000055786 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | No |  |  |  | 2025-11-18 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8308_1 | New_JAW-JT-DMK-8308 | JAW-JT-DMK-8308 | Central Java | Jawa Tengah | Demak | -7.0072 | 110.5119 | New | New | New | Type B | MA | JAW-JT-DMK-8308 |  |  |  |  | - | - | - | - | New Purchase | New Ring 010 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | #N/A | S000055786 | S000055787 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | No |  | 2026 |  | 2025-11-19 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-4133_1 | New_JAW-JT-DMK-4133 | JAW-JT-DMK-4133 | Central Java | Jawa Tengah | Demak | -6.9959 | 110.5419 | New | New | New | Type B | MA | JAW-JT-DMK-4133 |  |  |  |  | - | - | - | - | New Purchase | New Ring 010 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | #N/A | S000055787 | S000055788 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | No |  | 2026 |  | 2025-11-19 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8340_1 | New_JAW-JT-DMK-8340 | JAW-JT-DMK-8340 | Central Java | Jawa Tengah | Demak | -6.9766 | 110.5451 | New | New | New | Type B | MA | JAW-JT-DMK-8340 |  |  |  |  | - | - | - | - | New Purchase | New Ring 010 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | #N/A | S000055788 | S000055789 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | No |  | 2026 |  | 2025-11-19 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8320_1 | New_JAW-JT-DMK-8320 | JAW-JT-DMK-8320 | Central Java | Jawa Tengah | Demak | -6.9856 | 110.5233 | New | New | New | Type B | MA | JAW-JT-DMK-8320 |  |  |  |  | - | - | - | - | New Purchase | New Ring 010 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | #N/A | S000055789 | S000055790 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | No |  | 2026 |  | 2025-11-19 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8309_1 | New_JAW-JT-DMK-8309 | JAW-JT-DMK-8309 | Central Java | Jawa Tengah | Demak | -6.9738 | 110.5125 | New | New | New | Type B | MA | JAW-JT-DMK-8309 |  |  |  |  | - | - | - | - | New Purchase | New Ring 010 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | #N/A | S000055790 | S000055791 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | No |  | 2026 |  | 2025-11-19 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8299_1 | New_JAW-JT-DMK-8299 | JAW-JT-DMK-8299 | Central Java | Jawa Tengah | Demak | -6.9622 | 110.5056 | New | New | New | Type B | MA | JAW-JT-DMK-8299 |  |  |  |  | - | - | - | - | New Purchase | New Ring 010 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | #N/A | S000055791 | S000055792 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | No |  | 2026 |  | 2025-11-19 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8303_1 | New_JAW-JT-DMK-8303 | JAW-JT-DMK-8303 | Central Java | Jawa Tengah | Demak | -6.9532 | 110.5084 | New | New | New | Type B | MA | JAW-JT-DMK-8303 |  |  |  |  | - | - | - | - | New Purchase | New Ring 010 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | #N/A | S000055792 | S000055793 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | No |  | 2026 |  | 2025-11-19 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-4009_1 | New_JAW-JT-DMK-4009 | JAW-JT-DMK-4009 | Central Java | Jawa Tengah | Demak | -6.9451 | 110.4968 | New | New | New | Type B | MA | JAW-JT-DMK-4009 |  |  |  |  | - | - | - | - | New Purchase | New Ring 010 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | #N/A | S000055793 | S000055794 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | No |  | 2026 |  | 2025-11-19 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8425_1 | New_JAW-JT-KDS-8425 | JAW-JT-KDS-8425 | Central Java | Jawa Tengah | Kudus | -6.752 | 110.8646 | New | New | New | Type B | MA | JAW-JT-KDS-8425 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | #N/A | S000055646 | S000055647 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | Yes |  | 2026 |  | 2025-11-19 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-3501_1 | New_JAW-JT-KDS-3501 | JAW-JT-KDS-3501 | Central Java | Jawa Tengah | Kudus | -6.6906 | 110.9154 | New | New | New | Type B | MA | JAW-JT-KDS-3501 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | #N/A | S000055647 | S000055648 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | Yes |  | 2026 |  | 2025-11-19 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Submitted | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-3504_1 | New_JAW-JT-KDS-3504 | JAW-JT-KDS-3504 | Central Java | Jawa Tengah | Kudus | -6.6741 | 110.8771 | New | New | New | Type B | MA | JAW-JT-KDS-3504 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | #N/A | S000055648 | S000055649 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | Yes |  | 2026 |  | 2025-11-19 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-0852_1 | New_JAW-JT-KDS-0852 | JAW-JT-KDS-0852 | Central Java | Jawa Tengah | Kudus | -6.6979 | 110.8668 | New | New | New | Type B | MA | JAW-JT-KDS-0852 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | #N/A | S000055649 | S000055650 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | Yes |  | 2026 |  | 2025-11-19 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Submitted | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8409_1 | New_JAW-JT-KDS-8409 | JAW-JT-KDS-8409 | Central Java | Jawa Tengah | Kudus | -6.7136 | 110.8443 | New | New | New | Type B | MA | JAW-JT-KDS-8409 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | #N/A | S000055650 | S000055651 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | Yes |  | 2026 |  | 2025-11-19 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8391_1 | New_JAW-JT-KDS-8391 | JAW-JT-KDS-8391 | Central Java | Jawa Tengah | Kudus | -6.7309 | 110.8303 | New | New | New | Type B | MA | JAW-JT-KDS-8391 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | #N/A | S000055651 | S000055652 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | Yes |  | 2026 |  | 2025-11-19 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Submitted | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8408_1 | New_JAW-JT-KDS-8408 | JAW-JT-KDS-8408 | Central Java | Jawa Tengah | Kudus | -6.7293 | 110.844 | New | New | New | Type B | MA | JAW-JT-KDS-8408 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | #N/A | S000055652 | S000055653 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | Yes |  |  |  | 2025-11-20 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8417_1 | New_JAW-JT-KDS-8417 | JAW-JT-KDS-8417 | Central Java | Jawa Tengah | Kudus | -6.7295 | 110.856 | New | New | New | Type B | MA | JAW-JT-KDS-8417 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | #N/A | S000055653 | S000055654 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | Yes |  | 2026 |  | 2025-11-20 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Submitted | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8411_1 | New_JAW-JT-KDS-8411 | JAW-JT-KDS-8411 | Central Java | Jawa Tengah | Kudus | -6.7537 | 110.8453 | New | New | New | Type B | MA | JAW-JT-KDS-8411 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | #N/A | S000055654 | S000055655 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | Yes |  | 2026 |  | 2025-11-20 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8393_1 | New_JAW-JT-KDS-8393 | JAW-JT-KDS-8393 | Central Java | Jawa Tengah | Kudus | -6.773 | 110.8312 | New | New | New | Type B | MA | JAW-JT-KDS-8393 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | #N/A | S000055655 | S000055656 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | Yes |  | 2026 | YPTT | 2025-11-20 | 47 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Submitted | [33 empty] | #N/A |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-0848_1 | New_JAW-JT-KDS-0848 | JAW-JT-KDS-0848 | Central Java | Jawa Tengah | Kudus | -6.7587 | 110.8233 | New | New | New | Type B | MA | JAW-JT-KDS-0848 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | #N/A | S000055656 | S000055657 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | Yes |  | 2026 |  | 2025-11-20 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8376_1 | New_JAW-JT-KDS-8376 | JAW-JT-KDS-8376 | Central Java | Jawa Tengah | Kudus | -6.7534 | 110.8158 | New | New | New | Type B | MA | JAW-JT-KDS-8376 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | #N/A | S000055657 | S000055658 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | Yes |  | 2026 |  | 2025-11-20 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Submitted | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8366_1 | New_JAW-JT-KDS-8366 | JAW-JT-KDS-8366 | Central Java | Jawa Tengah | Kudus | -6.7781 | 110.7939 | New | New | New | Type B | MA | JAW-JT-KDS-8366 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | #N/A | S000055658 | S000055659 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | Yes |  | 2026 |  | 2025-11-20 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8405_1 | New_JAW-JT-KDS-8405 | JAW-JT-KDS-8405 | Central Java | Jawa Tengah | Kudus | -6.7867 | 110.8343 | New | New | New | Type B | MA | JAW-JT-KDS-8405 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | #N/A | S000055659 | S000055660 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | Yes |  | 2026 |  | 2025-11-20 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Submitted | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8399_1 | New_JAW-JT-KDS-8399 | JAW-JT-KDS-8399 | Central Java | Jawa Tengah | Kudus | -6.8056 | 110.837 | New | New | New | Type B | MA | JAW-JT-KDS-8399 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | #N/A | S000055660 | S000055661 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | Yes |  | 2026 | YPTT | 2025-11-20 | 47 |  |  | 2025 | 2025-11-21 | 2025-11-21 | Reviewing |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-4007_1 | New_JAW-JT-KDS-4007 | JAW-JT-KDS-4007 | Central Java | Jawa Tengah | Kudus | -6.8048 | 110.8527 | New | New | New | Type B | MA | JAW-JT-KDS-4007 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | #N/A | S000055661 | S000055662 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | Yes |  | 2026 |  | 2025-11-20 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Submitted | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8430_1 | New_JAW-JT-KDS-8430 | JAW-JT-KDS-8430 | Central Java | Jawa Tengah | Kudus | -6.8083 | 110.8517 | New | New | New | Type B | MA | JAW-JT-KDS-8430 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | #N/A | S000055662 | S000055663 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | Yes |  | 2026 |  | 2025-11-20 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-4003_1 | New_JAW-JT-KDS-4003 | JAW-JT-KDS-4003 | Central Java | Jawa Tengah | Kudus | -6.8103 | 110.8721 | New | New | New | Type B | MA | JAW-JT-KDS-4003 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | #N/A | S000055664 | S000055665 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | No |  | 2026 |  | 2025-11-20 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8448_1 | New_JAW-JT-KDS-8448 | JAW-JT-KDS-8448 | Central Java | Jawa Tengah | Kudus | -6.8115 | 110.8845 | New | New | New | Type B | MA | JAW-JT-KDS-8448 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | #N/A | S000055665 | S000055666 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | No |  | 2026 |  | 2025-11-20 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-0862_1 | New_JAW-JT-KDS-0862 | JAW-JT-KDS-0862 | Central Java | Jawa Tengah | Kudus | -6.8294 | 110.8868 | New | New | New | Type B | MA | JAW-JT-KDS-0862 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | #N/A | S000055666 | S000055667 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | No |  | 2026 |  | 2025-11-20 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-28 | 48 | 2025-11-28 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8424_1 | New_JAW-JT-KDS-8424 | JAW-JT-KDS-8424 | Central Java | Jawa Tengah | Kudus | -6.8364 | 110.8634 | New | New | New | Type B | MA | JAW-JT-KDS-8424 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | #N/A | S000055667 | S000055668 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | No |  | 2026 |  | 2025-11-21 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-28 | 48 | 2025-11-28 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8433_1 | New_JAW-JT-KDS-8433 | JAW-JT-KDS-8433 | Central Java | Jawa Tengah | Kudus | -6.867 | 110.8667 | New | New | New | Type B | MA | JAW-JT-KDS-8433 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | #N/A | S000055668 | S000055669 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | No |  | 2026 |  | 2025-11-21 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-28 | 48 | 2025-11-28 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-3505_1 | New_JAW-JT-KDS-3505 | JAW-JT-KDS-3505 | Central Java | Jawa Tengah | Kudus | -6.8458 | 110.9003 | New | New | New | Type B | MA | JAW-JT-KDS-3505 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | #N/A | S000055669 | S000055670 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | No |  | 2026 |  | 2025-11-21 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-28 | 48 | 2025-11-28 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8464_1 | New_JAW-JT-KDS-8464 | JAW-JT-KDS-8464 | Central Java | Jawa Tengah | Kudus | -6.8367 | 110.9158 | New | New | New | Type B | MA | JAW-JT-KDS-8464 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | #N/A | S000055670 | S000055671 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | No |  | 2026 |  | 2025-11-21 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-28 | 48 | 2025-11-28 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8459_1 | New_JAW-JT-KDS-8459 | JAW-JT-KDS-8459 | Central Java | Jawa Tengah | Kudus | -6.8156 | 110.9012 | New | New | New | Type B | MA | JAW-JT-KDS-8459 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | #N/A | S000055671 | S000055672 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | No |  | 2026 |  | 2025-11-21 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-28 | 48 | 2025-11-28 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8442_1 | New_JAW-JT-KDS-8442 | JAW-JT-KDS-8442 | Central Java | Jawa Tengah | Kudus | -6.7876 | 110.8813 | New | New | New | Type B | MA | JAW-JT-KDS-8442 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | #N/A | S000055672 | S000055673 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | No |  | 2026 |  | 2025-11-21 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8451_1 | New_JAW-JT-KDS-8451 | JAW-JT-KDS-8451 | Central Java | Jawa Tengah | Kudus | -6.7939 | 110.8973 | New | New | New | Type B | MA | JAW-JT-KDS-8451 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | #N/A | S000055673 | S000055674 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | No |  | 2026 | YPTT | 2025-11-21 | 47 |  |  | 2025 | 2025-11-21 | 2025-11-21 | Reviewing |  |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8457_1 | New_JAW-JT-KDS-8457 | JAW-JT-KDS-8457 | Central Java | Jawa Tengah | Kudus | -6.7923 | 110.9082 | New | New | New | Type B | MA | JAW-JT-KDS-8457 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | #N/A | S000055674 | S000055675 | 10. Ready ATP / RFS | 2025-12-14 | 50 | 2025-11-09 |  | No |  | 2026 |  | 2025-11-21 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8472_1 | New_JAW-JT-KDS-8472 | JAW-JT-KDS-8472 | Central Java | Jawa Tengah | Kudus | -6.7905 | 110.9399 | New | New | New | Type B | MA | JAW-JT-KDS-8472 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | #N/A | S000055675 | S000055676 | 10. Ready ATP / RFS | 2025-12-14 | 50 | 2025-11-09 |  | No |  | 2026 |  | 2025-11-21 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8312_1 | New_JAW-JT-PWD-8312 | JAW-JT-PWD-8312 | Central Java | Jawa Tengah | Grobogan | -6.9854 | 110.642 | New | New | New | Type B | MA | JAW-JT-PWD-8312 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | #N/A | S000054284 | S000054285 | 12. NY TERMINATION | 2025-12-07 | 49 |  |  | No |  | 2025-624 sites |  | 2025-11-21 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8325_1 | New_JAW-JT-PWD-8325 | JAW-JT-PWD-8325 | Central Java | Jawa Tengah | Grobogan | -6.9822 | 110.6672 | New | New | New | Type B | MA | JAW-JT-PWD-8325 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | #N/A | S000054285 | S000054286 | 12. NY TERMINATION | 2025-12-07 | 49 |  |  | No |  | 2026 |  | 2025-11-21 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8329_1 | New_JAW-JT-PWD-8329 | JAW-JT-PWD-8329 | Central Java | Jawa Tengah | Grobogan | -7.002 | 110.6748 | New | New | New | Type B | MA | JAW-JT-PWD-8329 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | #N/A | S000054286 | S000054287 | 12. NY TERMINATION | 2025-12-07 | 49 |  |  | No |  | 2026 |  | 2025-11-21 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-2001_1 | New_JAW-JT-PWD-2001 | JAW-JT-PWD-2001 | Central Java | Jawa Tengah | Grobogan | -7.0089 | 110.6461 | New | New | New | Type B | MA | JAW-JT-PWD-2001 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | #N/A | S000054287 | S000054288 | 12. NY TERMINATION | 2025-12-07 | 49 |  |  | No |  | 2026 |  | 2025-11-21 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-0048_1 | New_JAW-JT-PWD-0048 | JAW-JT-PWD-0048 | Central Java | Jawa Tengah | Grobogan | -7.0231 | 110.6541 | New | New | New | Type B | MA | JAW-JT-PWD-0048 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | #N/A | S000054288 | S000054289 | 12. NY TERMINATION | 2025-12-07 | 49 |  |  | No |  | 2026 |  | 2025-11-21 | 47 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8328_1 | New_JAW-JT-PWD-8328 | JAW-JT-PWD-8328 | Central Java | Jawa Tengah | Grobogan | -7.0423 | 110.6675 | New | New | New | Type B | MA | JAW-JT-PWD-8328 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | #N/A | S000054289 | S000054290 | 12. NY TERMINATION | 2025-12-07 | 49 |  |  | No |  | 2025-624 sites |  | 2025-11-24 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8324_1 | New_JAW-JT-PWD-8324 | JAW-JT-PWD-8324 | Central Java | Jawa Tengah | Grobogan | -7.0664 | 110.667 | New | New | New | Type B | MA | JAW-JT-PWD-8324 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | #N/A | S000054290 | S000054283 | 12. NY TERMINATION | 2025-12-07 | 49 |  |  | No |  | 2025-624 sites |  | 2025-11-24 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-4003_1 | New_JAW-JT-PWD-4003 | JAW-JT-PWD-4003 | Central Java | Jawa Tengah | Grobogan | -7.0664 | 110.6527 | New | New | New | Type B | MA | JAW-JT-PWD-4003 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | #N/A | S000054283 | S000054291 | 12. NY TERMINATION | 2025-12-07 | 49 |  |  | No |  | 2025-624 sites |  | 2025-11-24 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8309_1 | New_JAW-JT-PWD-8309 | JAW-JT-PWD-8309 | Central Java | Jawa Tengah | Grobogan | -7.0916 | 110.6385 | New | New | New | Type B | MA | JAW-JT-PWD-8309 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | #N/A | S000054291 | S000054292 | 12. NY TERMINATION | 2025-12-07 | 49 |  |  | No |  | 2025-624 sites |  | 2025-11-24 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8307_1 | New_JAW-JT-PWD-8307 | JAW-JT-PWD-8307 | Central Java | Jawa Tengah | Grobogan | -7.0936 | 110.6238 | New | New | New | Type B | MA | JAW-JT-PWD-8307 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | #N/A | S000054292 | S000054293 | 12. NY TERMINATION | 2025-12-07 | 49 |  |  | No |  | 2026 |  | 2025-11-24 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8302_1 | New_JAW-JT-PWD-8302 | JAW-JT-PWD-8302 | Central Java | Jawa Tengah | Grobogan | -7.0621 | 110.6092 | New | New | New | Type B | MA | JAW-JT-PWD-8302 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | #N/A | S000054293 | S000054294 | 12. NY TERMINATION | 2025-12-07 | 49 |  |  | No |  | 2025-624 sites |  | 2025-11-24 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8295_1 | New_JAW-JT-PWD-8295 | JAW-JT-PWD-8295 | Central Java | Jawa Tengah | Grobogan | -7.0664 | 110.5954 | New | New | New | Type B | MA | JAW-JT-PWD-8295 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | #N/A | S000054294 | S000054295 | 12. NY TERMINATION | 2025-12-07 | 49 |  |  | No |  | 2025-624 sites |  | 2025-11-24 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8301_1 | New_JAW-JT-PWD-8301 | JAW-JT-PWD-8301 | Central Java | Jawa Tengah | Grobogan | -7.0485 | 110.6059 | New | New | New | Type B | MA | JAW-JT-PWD-8301 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | #N/A | S000054295 | S000054296 | 12. NY TERMINATION | 2025-12-07 | 49 |  |  | No |  | 2026 |  | 2025-11-24 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8294_1 | New_JAW-JT-PWD-8294 | JAW-JT-PWD-8294 | Central Java | Jawa Tengah | Grobogan | -7.0727 | 110.5872 | New | New | New | Type B | MA | JAW-JT-PWD-8294 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | #N/A | S000054296 | S000054297 | 12. NY TERMINATION | 2025-12-07 | 49 |  |  | No |  | 2026 |  | 2025-11-24 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8297_1 | New_JAW-JT-PWD-8297 | JAW-JT-PWD-8297 | Central Java | Jawa Tengah | Grobogan | -7.0827 | 110.5979 | New | New | New | Type B | MA | JAW-JT-PWD-8297 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | #N/A | S000054297 | S000054298 | 12. NY TERMINATION | 2025-12-07 | 49 |  |  | No |  | 2026 |  | 2025-11-24 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-1534_1 | New_JAW-JT-PWD-1534 | JAW-JT-PWD-1534 | Central Java | Jawa Tengah | Grobogan | -7.0936 | 110.6037 | New | New | New | Type B | MA | JAW-JT-PWD-1534 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | #N/A | S000054298 | S000054299 | 12. NY TERMINATION | 2025-12-07 | 49 |  |  | No |  | 2026 |  | 2025-11-24 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8298_1 | New_JAW-JT-PWD-8298 | JAW-JT-PWD-8298 | Central Java | Jawa Tengah | Grobogan | -7.1156 | 110.5995 | New | New | New | Type B | MA | JAW-JT-PWD-8298 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | #N/A | S000054299 | S000054300 | 12. NY TERMINATION | 2025-12-07 | 49 |  |  | No |  | 2025-624 sites |  | 2025-11-24 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8299_1 | New_JAW-JT-PWD-8299 | JAW-JT-PWD-8299 | Central Java | Jawa Tengah | Grobogan | -7.0928 | 110.5858 | New | New | New | Type B | MA | JAW-JT-PWD-8299 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | #N/A | S000054300 | S000054301 | 12. NY TERMINATION | 2025-12-07 | 49 |  |  | No |  | 2026 |  | 2025-11-24 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8293_1 | New_JAW-JT-PWD-8293 | JAW-JT-PWD-8293 | Central Java | Jawa Tengah | Grobogan | -7.0884 | 110.5765 | New | New | New | Type B | MA | JAW-JT-PWD-8293 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | #N/A | S000054301 | S000054302 | 12. NY TERMINATION | 2025-12-07 | 49 |  |  | No |  | 2025-624 sites |  | 2025-11-25 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8676_1 | New_JAW-JT-SMG-8676 | JAW-JT-SMG-8676 | Central Java | Jawa Tengah | Kota Semarang | -7.0541 | 110.4782 | New | New | New | Type B | MA | JAW-JT-SMG-8676 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | #N/A | S000054302 | S000054303 | 12. NY TERMINATION | 2025-12-07 | 49 |  |  | No |  | 2025-End Nov |  | 2025-11-25 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8390_1 | New_JAW-JT-PWD-8390 | JAW-JT-PWD-8390 | Central Java | Jawa Tengah | Grobogan | -7.141 | 110.8576 | New | New | New | Type B | MA | JAW-JT-PWD-8390 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | #N/A | S000054304 | S000054306 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2026 |  | 2025-11-25 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8378_1 | New_JAW-JT-PWD-8378 | JAW-JT-PWD-8378 | Central Java | Jawa Tengah | Grobogan | -7.1787 | 110.8219 | New | New | New | Type B | MA | JAW-JT-PWD-8378 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | #N/A | S000054306 | S000054307 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-25 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8372_1 | New_JAW-JT-PWD-8372 | JAW-JT-PWD-8372 | Central Java | Jawa Tengah | Grobogan | -7.1653 | 110.8055 | New | New | New | Type B | MA | JAW-JT-PWD-8372 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | #N/A | S000054307 | S000054308 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-25 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8364_1 | New_JAW-JT-PWD-8364 | JAW-JT-PWD-8364 | Central Java | Jawa Tengah | Grobogan | -7.1675 | 110.7865 | New | New | New | Type B | MA | JAW-JT-PWD-8364 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | #N/A | S000054308 | S000054309 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-25 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8352_1 | New_JAW-JT-PWD-8352 | JAW-JT-PWD-8352 | Central Java | Jawa Tengah | Grobogan | -7.1738 | 110.7627 | New | New | New | Type B | MA | JAW-JT-PWD-8352 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | #N/A | S000054309 | S000054310 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2026 |  | 2025-11-25 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8354_1 | New_JAW-JT-PWD-8354 | JAW-JT-PWD-8354 | Central Java | Jawa Tengah | Grobogan | -7.148 | 110.7638 | New | New | New | Type B | MA | JAW-JT-PWD-8354 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | #N/A | S000054310 | S000054311 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2026 |  | 2025-11-25 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8370_1 | New_JAW-JT-PWD-8370 | JAW-JT-PWD-8370 | Central Java | Jawa Tengah | Grobogan | -7.1341 | 110.7992 | New | New | New | Type B | MA | JAW-JT-PWD-8370 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | #N/A | S000054311 | S000054305 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2026 |  | 2025-11-25 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8367_1 | New_JAW-JT-PWD-8367 | JAW-JT-PWD-8367 | Central Java | Jawa Tengah | Grobogan | -7.1233 | 110.7912 | New | New | New | Type B | MA | JAW-JT-PWD-8367 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | #N/A | S000054305 | S000054312 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2026 |  | 2025-11-25 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8351_1 | New_JAW-JT-PWD-8351 | JAW-JT-PWD-8351 | Central Java | Jawa Tengah | Grobogan | -7.1054 | 110.7611 | New | New | New | Type B | MA | JAW-JT-PWD-8351 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | #N/A | S000054312 | S000054313 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2026 |  | 2025-11-25 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8347_1 | New_JAW-JT-PWD-8347 | JAW-JT-PWD-8347 | Central Java | Jawa Tengah | Grobogan | -7.1061 | 110.7417 | New | New | New | Type B | MA | JAW-JT-PWD-8347 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | #N/A | S000054313 | S000054314 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2026 |  | 2025-11-25 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8339_1 | New_JAW-JT-PWD-8339 | JAW-JT-PWD-8339 | Central Java | Jawa Tengah | Grobogan | -7.1122 | 110.7163 | New | New | New | Type B | MA | JAW-JT-PWD-8339 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | #N/A | S000054314 | S000054315 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2025-11-25 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8334_1 | New_JAW-JT-PWD-8334 | JAW-JT-PWD-8334 | Central Java | Jawa Tengah | Grobogan | -7.0982 | 110.7037 | New | New | New | Type B | MA | JAW-JT-PWD-8334 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | #N/A | S000054315 | S000054316 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  |  |  | 2025-11-26 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-0038_1 | New_JAW-JT-PWD-0038 | JAW-JT-PWD-0038 | Central Java | Jawa Tengah | Grobogan | -7.1036 | 110.6891 | New | New | New | Type B | MA | JAW-JT-PWD-0038 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | #N/A | S000054316 | S000054317 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2026 |  | 2025-11-26 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-1542_1 | New_JAW-JT-PWD-1542 | JAW-JT-PWD-1542 | Central Java | Jawa Tengah | Grobogan | -7.1286 | 110.6664 | New | New | New | Type B | MA | JAW-JT-PWD-1542 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | #N/A | S000054317 | S000054318 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2026 |  | 2025-11-26 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8314_1 | New_JAW-JT-PWD-8314 | JAW-JT-PWD-8314 | Central Java | Jawa Tengah | Grobogan | -7.1543 | 110.6467 | New | New | New | Type B | MA | JAW-JT-PWD-8314 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | #N/A | S000054318 | S000054319 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2026 |  | 2025-11-26 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-1537_1 | New_JAW-JT-PWD-1537 | JAW-JT-PWD-1537 | Central Java | Jawa Tengah | Grobogan | -7.1586 | 110.6326 | New | New | New | Type B | MA | JAW-JT-PWD-1537 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | #N/A | S000054319 | S000054320 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2026 |  | 2025-11-26 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-4109_1 | New_JAW-JT-PWD-4109 | JAW-JT-PWD-4109 | Central Java | Jawa Tengah | Grobogan | -7.1708 | 110.6336 | New | New | New | Type B | MA | JAW-JT-PWD-4109 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | #N/A | S000054320 | S000054321 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2026 |  | 2025-11-26 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8311_1 | New_JAW-JT-PWD-8311 | JAW-JT-PWD-8311 | Central Java | Jawa Tengah | Grobogan | -7.2105 | 110.6406 | New | New | New | Type B | MA | JAW-JT-PWD-8311 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | #N/A | S000054321 | S000054322 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2026 |  | 2025-11-26 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-2554_1 | New_JAW-JT-UNR-2554 | JAW-JT-UNR-2554 | Central Java | Jawa Tengah | Semarang | -7.2367 | 110.6153 | New | New | New | Type B | MA | JAW-JT-UNR-2554 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | #N/A | S000054322 | S000054323 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-End Nov |  | 2025-11-26 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8558_1 | New_JAW-JT-UNR-8558 | JAW-JT-UNR-8558 | Central Java | Jawa Tengah | Semarang | -7.3155 | 110.5722 | New | New | New | Type B | MA | JAW-JT-UNR-8558 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | #N/A | S000054323 | S000054324 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-End Nov |  | 2025-11-26 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8405_1 | New_JAW-JT-PWD-8405 | JAW-JT-PWD-8405 | Central Java | Jawa Tengah | Grobogan | -7.1518 | 110.8921 | New | New | New | Type B | MA | JAW-JT-PWD-8405 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | #N/A | S000054325 | S000054326 | 12. NY TERMINATION | 2025-11-16 | 46 |  |  | No |  | 2026 | GPA | 2025-11-26 | 48 |  |  | 2025 | 2025-11-11 |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-1566_1 | New_JAW-JT-PWD-1566 | JAW-JT-PWD-1566 | Central Java | Jawa Tengah | Grobogan | -7.1689 | 110.879 | New | New | New | Type B | MA | JAW-JT-PWD-1566 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | #N/A | S000054326 | S000054327 | 12. NY TERMINATION | 2025-11-16 | 46 |  |  | No |  | 2026 | GPA | 2025-11-26 | 48 |  |  | 2025 | 2025-11-10 |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8402_1 | New_JAW-JT-PWD-8402 | JAW-JT-PWD-8402 | Central Java | Jawa Tengah | Grobogan | -7.1591 | 110.8687 | New | New | New | Type B | MA | JAW-JT-PWD-8402 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000018247 | #N/A | [9 empty] | 2026 |  | 2025-11-26 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8389_1 | New_JAW-JT-PWD-8389 | JAW-JT-PWD-8389 | Central Java | Jawa Tengah | Grobogan | -7.1655 | 110.8559 | New | New | New | Type B | MA | JAW-JT-PWD-8389 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | #N/A | S000054328 | S000054329 | 12. NY TERMINATION | 2025-11-16 | 46 |  |  | No |  | 2026 | GPA | 2025-11-26 | 48 |  |  | 2025 | 2025-11-11 |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8384_1 | New_JAW-JT-PWD-8384 | JAW-JT-PWD-8384 | Central Java | Jawa Tengah | Grobogan | -7.1912 | 110.8423 | New | New | New | Type B | MA | JAW-JT-PWD-8384 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000018247 | #N/A | [9 empty] | 2026 |  | 2025-11-27 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-0019_1 | New_JAW-JT-PWD-0019 | JAW-JT-PWD-0019 | Central Java | Jawa Tengah | Grobogan | -7.1921 | 110.8206 | New | New | New | Type B | MA | JAW-JT-PWD-0019 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | #N/A | S000054330 | S000054331 | 12. NY TERMINATION | 2025-11-16 | 46 |  |  | No |  | 2026 | GPA | 2025-11-27 | 48 |  |  | 2025 | 2025-11-11 |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8371_1 | New_JAW-JT-PWD-8371 | JAW-JT-PWD-8371 | Central Java | Jawa Tengah | Grobogan | -7.1778 | 110.8028 | New | New | New | Type B | MA | JAW-JT-PWD-8371 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | #N/A | S000054331 | S000054332 | 12. NY TERMINATION | 2025-11-16 | 46 |  |  | No |  | 2025-624 sites | GPA | 2025-11-27 | 48 |  |  | 2025 | 2025-11-11 |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8366_1 | New_JAW-JT-PWD-8366 | JAW-JT-PWD-8366 | Central Java | Jawa Tengah | Grobogan | -7.1941 | 110.7871 | New | New | New | Type B | MA | JAW-JT-PWD-8366 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | #N/A | S000054332 | S000054333 | 12. NY TERMINATION | 2025-11-16 | 46 |  |  | No |  | 2025-624 sites | GPA | 2025-11-27 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-BYL-8374_1 | New_JAW-JT-BYL-8374 | JAW-JT-BYL-8374 | Central Java | Jawa Tengah | Grobogan | -7.2022 | 110.7954 | New | New | New | Type B | MA | JAW-JT-BYL-8374 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_3 1x25G/10G LR + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | #N/A | S000054333 | S000054334 | 12. NY TERMINATION | 2025-11-16 | 46 |  |  | No |  | 2025-624 sites | GPA | 2025-11-27 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-2997_1 | New_JAW-JT-PWD-2997 | JAW-JT-PWD-2997 | Central Java | Jawa Tengah | Grobogan | -7.2456 | 110.8476 | New | New | New | Type B | MA | JAW-JT-PWD-2997 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000018247 | #N/A | [9 empty] | 2026 |  | 2025-11-27 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8412_1 | New_JAW-JT-PWD-8412 | JAW-JT-PWD-8412 | Central Java | Jawa Tengah | Grobogan | -7.2426 | 110.9033 | New | New | New | Type B | MA | JAW-JT-PWD-8412 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | #N/A | S000054335 | S000054336 | 12. NY TERMINATION | 2025-11-16 | 46 |  |  | No |  |  | GPA | 2025-11-27 | 48 |  |  | 2025 | 2025-11-10 | 2025-11-21 | Reviewing |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8442_1 | New_JAW-JT-PWD-8442 | JAW-JT-PWD-8442 | Central Java | Jawa Tengah | Grobogan | -7.2681 | 110.9323 | New | New | New | Type B | MA | JAW-JT-PWD-8442 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | #N/A | S000054336 | S000054337 | 12. NY TERMINATION | 2025-11-16 | 46 |  |  | No |  | 2026 | GPA | 2025-11-27 | 48 |  |  | 2025 | 2025-11-10 |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-0004_1 | New_JAW-JT-PWD-0004 | JAW-JT-PWD-0004 | Central Java | Jawa Tengah | Grobogan | -7.2134 | 110.9442 | New | New | New | Type B | MA | JAW-JT-PWD-0004 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | #N/A | S000054337 | S000054338 | 12. NY TERMINATION | 2025-11-16 | 46 |  |  | No |  | 2026 | GPA | 2025-11-27 | 48 |  |  | 2025 | 2025-11-10 | 2025-11-17 | Reviewing |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-1593_1 | New_JAW-JT-PWD-1593 | JAW-JT-PWD-1593 | Central Java | Jawa Tengah | Grobogan | -7.1941 | 111.0002 | New | New | New | Type B | MA | JAW-JT-PWD-1593 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | #N/A | S000054338 | S000054339 | 12. NY TERMINATION | 2025-11-16 | 46 |  |  | No |  | 2026 | GPA | 2025-11-27 | 48 |  |  | 2025 | 2025-11-10 | 2025-11-17 | Reviewing |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8481_1 | New_JAW-JT-PWD-8481 | JAW-JT-PWD-8481 | Central Java | Jawa Tengah | Grobogan | -7.1688 | 110.9991 | New | New | New | Type B | MA | JAW-JT-PWD-8481 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | #N/A | S000054339 | S000054340 | 12. NY TERMINATION | 2025-11-16 | 46 |  |  | No |  | 2025-624 sites | GPA | 2025-11-27 | 48 |  |  | 2025 | 2025-11-10 |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8474_1 | New_JAW-JT-PWD-8474 | JAW-JT-PWD-8474 | Central Java | Jawa Tengah | Grobogan | -7.1343 | 110.9903 | New | New | New | Type B | MA | JAW-JT-PWD-8474 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | #N/A | S000054340 | S000054341 | 12. NY TERMINATION | 2025-11-16 | 46 |  |  | No |  | 2026 | GPA | 2025-11-27 | 48 |  |  | 2025 | 2025-11-10 | 2025-11-19 | Reviewing |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8472_1 | New_JAW-JT-PWD-8472 | JAW-JT-PWD-8472 | Central Java | Jawa Tengah | Grobogan | -7.1036 | 110.9805 | New | New | New | Type B | MA | JAW-JT-PWD-8472 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | #N/A | S000054341 | S000054342 | 12. NY TERMINATION | 2025-11-16 | 46 |  |  | No |  | 2025-624 sites | GPA | 2025-11-27 | 48 |  |  | 2025 | 2025-11-12 |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-4001_1 | New_JAW-JT-PWD-4001 | JAW-JT-PWD-4001 | Central Java | Jawa Tengah | Grobogan | -7.1607 | 110.9029 | New | New | New | Type B | MA | JAW-JT-PWD-4001 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | #N/A | S000054343 | S000054344 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-28 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8409_1 | New_JAW-JT-PWD-8409 | JAW-JT-PWD-8409 | Central Java | Jawa Tengah | Grobogan | -7.1809 | 110.8979 | New | New | New | Type B | MA | JAW-JT-PWD-8409 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | #N/A | S000054344 | S000054345 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-28 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8392_1 | New_JAW-JT-PWD-8392 | JAW-JT-PWD-8392 | Central Java | Jawa Tengah | Grobogan | -7.2077 | 110.8633 | New | New | New | Type B | MA | JAW-JT-PWD-8392 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | #N/A | S000054345 | S000054346 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-28 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-1571_1 | New_JAW-JT-PWD-1571 | JAW-JT-PWD-1571 | Central Java | Jawa Tengah | Grobogan | -7.2179 | 110.9044 | New | New | New | Type B | MA | JAW-JT-PWD-1571 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | #N/A | S000054346 | S000054347 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-28 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8430_1 | New_JAW-JT-PWD-8430 | JAW-JT-PWD-8430 | Central Java | Jawa Tengah | Grobogan | -7.2105 | 110.9023 | New | New | New | Type B | MA | JAW-JT-PWD-8430 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | #N/A | S000054347 | S000054348 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2025-624 sites |  | 2025-11-28 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8441_1 | New_JAW-JT-PWD-8441 | JAW-JT-PWD-8441 | Central Java | Jawa Tengah | Grobogan | -7.1828 | 110.9183 | New | New | New | Type B | MA | JAW-JT-PWD-8441 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | #N/A | S000054348 | S000054349 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-28 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8423_1 | New_JAW-JT-PWD-8423 | JAW-JT-PWD-8423 | Central Java | Jawa Tengah | Grobogan | -7.1719 | 110.9125 | New | New | New | Type B | MA | JAW-JT-PWD-8423 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | #N/A | S000054349 | S000054350 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-28 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8450_1 | New_JAW-JT-PWD-8450 | JAW-JT-PWD-8450 | Central Java | Jawa Tengah | Grobogan | -7.1739 | 110.9343 | New | New | New | Type B | MA | JAW-JT-PWD-8450 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | #N/A | S000054350 | S000054351 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-28 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8453_1 | New_JAW-JT-PWD-8453 | JAW-JT-PWD-8453 | Central Java | Jawa Tengah | Grobogan | -7.1866 | 110.9459 | New | New | New | Type B | MA | JAW-JT-PWD-8453 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | #N/A | S000054351 | S000054352 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-28 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8460_1 | New_JAW-JT-PWD-8460 | JAW-JT-PWD-8460 | Central Java | Jawa Tengah | Grobogan | -7.1602 | 110.9609 | New | New | New | Type B | MA | JAW-JT-PWD-8460 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | #N/A | S000054352 | S000054353 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-28 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8468_1 | New_JAW-JT-PWD-8468 | JAW-JT-PWD-8468 | Central Java | Jawa Tengah | Grobogan | -7.1679 | 110.9743 | New | New | New | Type B | MA | JAW-JT-PWD-8468 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | #N/A | S000054353 | S000054354 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2025-624 sites |  | 2025-11-28 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8456_1 | New_JAW-JT-PWD-8456 | JAW-JT-PWD-8456 | Central Java | Jawa Tengah | Grobogan | -7.1296 | 110.9549 | New | New | New | Type B | MA | JAW-JT-PWD-8456 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | #N/A | S000054354 | S000054355 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-11-28 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8461_1 | New_JAW-JT-PWD-8461 | JAW-JT-PWD-8461 | Central Java | Jawa Tengah | Grobogan | -7.1054 | 110.9622 | New | New | New | Type B | MA | JAW-JT-PWD-8461 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | #N/A | S000054355 | S000054356 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2025-624 sites |  | 2025-11-28 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-1576_1 | New_JAW-JT-PWD-1576 | JAW-JT-PWD-1576 | Central Java | Jawa Tengah | Grobogan | -7.0951 | 110.9419 | New | New | New | Type B | MA | JAW-JT-PWD-1576 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | #N/A | S000054356 | S000054357 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2025-12-01 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8439_1 | New_JAW-JT-PWD-8439 | JAW-JT-PWD-8439 | Central Java | Jawa Tengah | Grobogan | -7.0844 | 110.9178 | New | New | New | Type B | MA | JAW-JT-PWD-8439 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | #N/A | S000054357 | S000054358 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2025-624 sites |  | 2025-12-01 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-0036_1 | New_JAW-JT-PWD-0036 | JAW-JT-PWD-0036 | Central Java | Jawa Tengah | Grobogan | -7.1602 | 111.0203 | New | New | New | Type B | MA | JAW-JT-PWD-0036 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056108 | S000056109 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-12-01 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8521_1 | New_JAW-JT-PWD-8521 | JAW-JT-PWD-8521 | Central Java | Jawa Tengah | Grobogan | -7.1592 | 111.0397 | New | New | New | Type B | MA | JAW-JT-PWD-8521 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056109 | S000056110 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-12-01 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8530_1 | New_JAW-JT-PWD-8530 | JAW-JT-PWD-8530 | Central Java | Jawa Tengah | Grobogan | -7.1822 | 111.0586 | New | New | New | Type B | MA | JAW-JT-PWD-8530 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056110 | S000056111 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-12-01 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-0027_1 | New_JAW-JT-PWD-0027 | JAW-JT-PWD-0027 | Central Java | Jawa Tengah | Grobogan | -7.1971 | 111.0699 | New | New | New | Type B | MA | JAW-JT-PWD-0027 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056111 | S000056112 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-12-01 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8555_1 | New_JAW-JT-PWD-8555 | JAW-JT-PWD-8555 | Central Java | Jawa Tengah | Grobogan | -7.2247 | 111.0861 | New | New | New | Type B | MA | JAW-JT-PWD-8555 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056112 | S000056113 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-12-01 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8538_1 | New_JAW-JT-PWD-8538 | JAW-JT-PWD-8538 | Central Java | Jawa Tengah | Grobogan | -7.1629 | 111.0768 | New | New | New | Type B | MA | JAW-JT-PWD-8538 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056113 | S000056114 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-12-01 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8548_1 | New_JAW-JT-PWD-8548 | JAW-JT-PWD-8548 | Central Java | Jawa Tengah | Grobogan | -7.1605 | 111.0898 | New | New | New | Type B | MA | JAW-JT-PWD-8548 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056114 | S000056115 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2025-624 sites |  | 2025-12-01 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8556_1 | New_JAW-JT-PWD-8556 | JAW-JT-PWD-8556 | Central Java | Jawa Tengah | Grobogan | -7.1609 | 111.1035 | New | New | New | Type B | MA | JAW-JT-PWD-8556 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056115 | S000056116 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-12-01 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8558_1 | New_JAW-JT-PWD-8558 | JAW-JT-PWD-8558 | Central Java | Jawa Tengah | Grobogan | -7.1901 | 111.1076 | New | New | New | Type B | MA | JAW-JT-PWD-8558 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056116 | S000056117 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-12-01 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8570_1 | New_JAW-JT-PWD-8570 | JAW-JT-PWD-8570 | Central Java | Jawa Tengah | Grobogan | -7.1619 | 111.138 | New | New | New | Type B | MA | JAW-JT-PWD-8570 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056117 | S000056118 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2025-624 sites | YPTT | 2025-12-01 | 49 |  |  | 2025 | 2025-11-17 | 2025-11-17 | Reviewing |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8500_1 | New_JAW-JT-PWD-8500 | JAW-JT-PWD-8500 | Central Java | Jawa Tengah | Grobogan | -7.1839 | 111.1973 | New | New | New | Type B | MA | JAW-JT-PWD-8500 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056118 | S000056119 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2025-624 sites |  | 2025-12-01 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8513_1 | New_JAW-JT-PWD-8513 | JAW-JT-PWD-8513 | Central Java | Jawa Tengah | Grobogan | -7.1899 | 111.2293 | New | New | New | Type B | MA | JAW-JT-PWD-8513 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056119 | S000056120 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2025-624 sites |  | 2025-12-02 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8511_1 | New_JAW-JT-PWD-8511 | JAW-JT-PWD-8511 | Central Java | Jawa Tengah | Grobogan | -7.1563 | 111.2218 | New | New | New | Type B | MA | JAW-JT-PWD-8511 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056120 | S000056121 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-12-02 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-1620_1 | New_JAW-JT-PWD-1620 | JAW-JT-PWD-1620 | Central Java | Jawa Tengah | Grobogan | -7.1063 | 111.2031 | New | New | New | Type B | MA | JAW-JT-PWD-1620 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056121 | S000056122 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-12-02 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8496_1 | New_JAW-JT-PWD-8496 | JAW-JT-PWD-8496 | Central Java | Jawa Tengah | Grobogan | -7.079 | 111.1935 | New | New | New | Type B | MA | JAW-JT-PWD-8496 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056122 | S000056123 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 | YPTT | 2025-12-02 | 49 |  |  | 2025 | 2025-11-17 | 2025-11-17 | Reviewing |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8493_1 | New_JAW-JT-PWD-8493 | JAW-JT-PWD-8493 | Central Java | Jawa Tengah | Grobogan | -7.0635 | 111.1681 | New | New | New | Type B | MA | JAW-JT-PWD-8493 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056123 | S000056124 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2025-624 sites |  | 2025-12-02 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8526_1 | New_JAW-JT-PWD-8526 | JAW-JT-PWD-8526 | Central Java | Jawa Tengah | Grobogan | -7.084 | 111.0531 | New | New | New | Type B | MA | JAW-JT-PWD-8526 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056124 | S000056125 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2025-624 sites |  | 2025-12-02 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8516_1 | New_JAW-JT-PWD-8516 | JAW-JT-PWD-8516 | Central Java | Jawa Tengah | Grobogan | -7.0318 | 111.0298 | New | New | New | Type B | MA | JAW-JT-PWD-8516 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056125 | S000056126 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 | YPTT | 2025-12-02 | 49 |  |  | 2025 | 2025-11-17 | 2025-11-17 | Reviewing |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8477_1 | New_JAW-JT-PWD-8477 | JAW-JT-PWD-8477 | Central Java | Jawa Tengah | Grobogan | -7.055 | 110.9968 | New | New | New | Type B | MA | JAW-JT-PWD-8477 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056126 | S000056127 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-12-02 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8459_1 | New_JAW-JT-PWD-8459 | JAW-JT-PWD-8459 | Central Java | Jawa Tengah | Grobogan | -7.0628 | 110.9597 | New | New | New | Type B | MA | JAW-JT-PWD-8459 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056127 | S000056128 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2025-624 sites |  | 2025-12-02 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8444_1 | New_JAW-JT-PWD-8444 | JAW-JT-PWD-8444 | Central Java | Jawa Tengah | Grobogan | -7.0394 | 110.9193 | New | New | New | Type B | MA | JAW-JT-PWD-8444 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | #N/A | S000056128 | S000056129 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-12-02 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8438_1 | New_JAW-JT-PWD-8438 | JAW-JT-PWD-8438 | Central Java | Jawa Tengah | Grobogan | -7.1393 | 110.9248 | New | New | New | Type B | MA | JAW-JT-PWD-8438 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | #N/A | S000054359 | S000054360 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-12-02 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8440_1 | New_JAW-JT-PWD-8440 | JAW-JT-PWD-8440 | Central Java | Jawa Tengah | Grobogan | -7.1207 | 110.9295 | New | New | New | Type B | MA | JAW-JT-PWD-8440 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | #N/A | S000054360 | S000054361 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-12-02 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8483_1 | New_JAW-JT-PWD-8483 | JAW-JT-PWD-8483 | Central Java | Jawa Tengah | Grobogan | -7.1207 | 111.0056 | New | New | New | Type B | MA | JAW-JT-PWD-8483 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | #N/A | S000054361 | S000054362 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2025-624 sites |  | 2025-12-02 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8522_1 | New_JAW-JT-PWD-8522 | JAW-JT-PWD-8522 | Central Java | Jawa Tengah | Grobogan | -7.1368 | 111.0419 | New | New | New | Type B | MA | JAW-JT-PWD-8522 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | #N/A | S000054362 | S000054363 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2025-624 sites |  | 2025-12-03 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8549_1 | New_JAW-JT-PWD-8549 | JAW-JT-PWD-8549 | Central Java | Jawa Tengah | Grobogan | -7.1326 | 111.0899 | New | New | New | Type B | MA | JAW-JT-PWD-8549 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | #N/A | S000054363 | S000054364 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  |  |  | 2025-12-03 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8490_1 | New_JAW-JT-PWD-8490 | JAW-JT-PWD-8490 | Central Java | Jawa Tengah | Grobogan | -7.1458 | 111.1725 | New | New | New | Type B | MA | JAW-JT-PWD-8490 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | #N/A | S000054364 | S000054365 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2025-624 sites |  | 2025-12-03 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-3382_1 | New_JAW-JT-PWD-3382 | JAW-JT-PWD-3382 | Central Java | Jawa Tengah | Grobogan | -7.1565 | 111.1697 | New | New | New | Type B | MA | JAW-JT-PWD-3382 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | #N/A | S000054365 | S000054366 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-12-03 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-1621_1 | New_JAW-JT-PWD-1621 | JAW-JT-PWD-1621 | Central Java | Jawa Tengah | Grobogan | -7.1805 | 111.219 | New | New | New | Type B | MA | JAW-JT-PWD-1621 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | #N/A | S000054366 | S000054367 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  |  |  | 2025-12-03 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8512_1 | New_JAW-JT-PWD-8512 | JAW-JT-PWD-8512 | Central Java | Jawa Tengah | Grobogan | -7.1677 | 111.2233 | New | New | New | Type B | MA | JAW-JT-PWD-8512 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | #N/A | S000054367 | S000054368 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2025-624 sites |  | 2025-12-03 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8507_1 | New_JAW-JT-PWD-8507 | JAW-JT-PWD-8507 | Central Java | Jawa Tengah | Grobogan | -7.1389 | 111.2105 | New | New | New | Type B | MA | JAW-JT-PWD-8507 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | #N/A | S000054368 | S000054369 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-12-03 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8492_1 | New_JAW-JT-PWD-8492 | JAW-JT-PWD-8492 | Central Java | Jawa Tengah | Grobogan | -7.1268 | 111.1803 | New | New | New | Type B | MA | JAW-JT-PWD-8492 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | #N/A | S000054369 | S000054370 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2025-624 sites |  | 2025-12-03 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8572_1 | New_JAW-JT-PWD-8572 | JAW-JT-PWD-8572 | Central Java | Jawa Tengah | Grobogan | -7.1007 | 111.1409 | New | New | New | Type B | MA | JAW-JT-PWD-8572 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | #N/A | S000054370 | S000054371 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2025-624 sites |  | 2025-12-03 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-0045_1 | New_JAW-JT-PWD-0045 | JAW-JT-PWD-0045 | Central Java | Jawa Tengah | Grobogan | -7.0827 | 111.1189 | New | New | New | Type B | MA | JAW-JT-PWD-0045 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | #N/A | S000054371 | S000054372 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-12-03 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8533_1 | New_JAW-JT-PWD-8533 | JAW-JT-PWD-8533 | Central Java | Jawa Tengah | Grobogan | -7.0976 | 111.0524 | New | New | New | Type B | MA | JAW-JT-PWD-8533 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | #N/A | S000054372 | S000054373 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2025-624 sites |  | 2025-12-03 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8503_1 | New_JAW-JT-PWD-8503 | JAW-JT-PWD-8503 | Central Java | Jawa Tengah | Grobogan | -7.0698 | 111.0217 | New | New | New | Type B | MA | JAW-JT-PWD-8503 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | #N/A | S000054373 | S000054374 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2025-624 sites |  | 2025-12-03 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8471_1 | New_JAW-JT-PWD-8471 | JAW-JT-PWD-8471 | Central Java | Jawa Tengah | Grobogan | -7.0905 | 110.9791 | New | New | New | Type B | MA | JAW-JT-PWD-8471 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | #N/A | S000054374 | S000054375 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-12-03 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8466_1 | New_JAW-JT-PWD-8466 | JAW-JT-PWD-8466 | Central Java | Jawa Tengah | Grobogan | -7.0857 | 110.9669 | New | New | New | Type B | MA | JAW-JT-PWD-8466 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | #N/A | S000054375 | S000054376 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | Yes |  | 2026 |  | 2025-12-04 | 49 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-4015_1 | New_JAW-JT-JPA-4015 | JAW-JT-JPA-4015 | Central Java | Jawa Tengah | Jepara | -6.7068 | 110.7456 | New | New | New | Type B | MA | JAW-JT-JPA-4015 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | #N/A | S000054205 | S000054206 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8441_1 | New_JAW-JT-JPA-8441 | JAW-JT-JPA-8441 | Central Java | Jawa Tengah | Jepara | -6.7303 | 110.8032 | New | New | New | Type B | MA | JAW-JT-JPA-8441 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | #N/A | S000054206 | S000054207 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-0709_1 | New_JAW-JT-JPA-0709 | JAW-JT-JPA-0709 | Central Java | Jawa Tengah | Jepara | -6.6973 | 110.8248 | New | New | New | Type B | MA | JAW-JT-JPA-0709 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | #N/A | S000054207 | S000054208 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8446_1 | New_JAW-JT-JPA-8446 | JAW-JT-JPA-8446 | Central Java | Jawa Tengah | Jepara | -6.6717 | 110.8231 | New | New | New | Type B | MA | JAW-JT-JPA-8446 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | #N/A | S000054208 | S000054209 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-0714_1 | New_JAW-JT-JPA-0714 | JAW-JT-JPA-0714 | Central Java | Jawa Tengah | Jepara | -6.6508 | 110.7552 | New | New | New | Type B | MA | JAW-JT-JPA-0714 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | #N/A | S000054209 | S000054210 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8399_1 | New_JAW-JT-JPA-8399 | JAW-JT-JPA-8399 | Central Java | Jawa Tengah | Jepara | -6.6397 | 110.7454 | New | New | New | Type B | MA | JAW-JT-JPA-8399 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | #N/A | S000054210 | S000054211 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8407_1 | New_JAW-JT-JPA-8407 | JAW-JT-JPA-8407 | Central Java | Jawa Tengah | Jepara | -6.6306 | 110.7544 | New | New | New | Type B | MA | JAW-JT-JPA-8407 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | #N/A | S000054211 | S000054212 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8388_1 | New_JAW-JT-JPA-8388 | JAW-JT-JPA-8388 | Central Java | Jawa Tengah | Jepara | -6.6073 | 110.7331 | New | New | New | Type B | MA | JAW-JT-JPA-8388 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | #N/A | S000054212 | S000054213 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8348_1 | New_JAW-JT-JPA-8348 | JAW-JT-JPA-8348 | Central Java | Jawa Tengah | Jepara | -6.5979 | 110.7053 | New | New | New | Type B | MA | JAW-JT-JPA-8348 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | #N/A | S000054213 | S000054214 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8398_1 | New_JAW-JT-JPA-8398 | JAW-JT-JPA-8398 | Central Java | Jawa Tengah | Jepara | -6.5866 | 110.7451 | New | New | New | Type B | MA | JAW-JT-JPA-8398 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | #N/A | S000054214 | S000054215 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-0609_1 | New_JAW-JT-JPA-0609 | JAW-JT-JPA-0609 | Central Java | Jawa Tengah | Jepara | -6.5991 | 110.7759 | New | New | New | Type B | MA | JAW-JT-JPA-0609 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | #N/A | S000054215 | S000054217 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-0693_1 | New_JAW-JT-JPA-0693 | JAW-JT-JPA-0693 | Central Java | Jawa Tengah | Jepara | -6.5779 | 110.7853 | New | New | New | Type B | MA | JAW-JT-JPA-0693 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | #N/A | S000054217 | S000054218 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-0702_1 | New_JAW-JT-JPA-0702 | JAW-JT-JPA-0702 | Central Java | Jawa Tengah | Jepara | -6.5641 | 110.7581 | New | New | New | Type B | MA | JAW-JT-JPA-0702 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | #N/A | S000054218 | S000054219 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8424_1 | New_JAW-JT-JPA-8424 | JAW-JT-JPA-8424 | Central Java | Jawa Tengah | Jepara | -6.542 | 110.7746 | New | New | New | Type B | MA | JAW-JT-JPA-8424 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | #N/A | S000054219 | S000054216 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8435_1 | New_JAW-JT-JPA-8435 | JAW-JT-JPA-8435 | Central Java | Jawa Tengah | Jepara | -6.558 | 110.7922 | New | New | New | Type B | MA | JAW-JT-JPA-8435 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | #N/A | S000054216 | S000054220 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8430_1 | New_JAW-JT-JPA-8430 | JAW-JT-JPA-8430 | Central Java | Jawa Tengah | Jepara | -6.5281 | 110.7832 | New | New | New | Type B | MA | JAW-JT-JPA-8430 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | #N/A | S000054220 | S000054221 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8451_1 | New_JAW-JT-JPA-8451 | JAW-JT-JPA-8451 | Central Java | Jawa Tengah | Jepara | -6.5462 | 110.8564 | New | New | New | Type B | MA | JAW-JT-JPA-8451 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | #N/A | S000054221 | S000054222 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-0708_1 | New_JAW-JT-JPA-0708 | JAW-JT-JPA-0708 | Central Java | Jawa Tengah | Jepara | -6.5154 | 110.8787 | New | New | New | Type B | MA | JAW-JT-JPA-0708 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | #N/A | S000054222 | S000054223 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8461_1 | New_JAW-JT-JPA-8461 | JAW-JT-JPA-8461 | Central Java | Jawa Tengah | Jepara | -6.5226 | 110.8932 | New | New | New | Type B | MA | JAW-JT-JPA-8461 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | #N/A | S000054223 | S000054224 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-0687_1 | New_JAW-JT-JPA-0687 | JAW-JT-JPA-0687 | Central Java | Jawa Tengah | Jepara | -6.5471 | 110.9028 | New | New | New | Type B | MA | JAW-JT-JPA-0687 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | #N/A | S000054224 | S000054225 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JI-BKL-3125_1 | New_JAW-JI-BKL-3125 | JAW-JI-BKL-3125 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8907 | 110.3356 | New | New | New | Type B | MA | JAW-JI-BKL-3125 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020469 | #N/A | [11 empty] | 2025-12-05 | 49 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3254_1 | New_JAW-JI-BKL-3254 | JAW-JI-BKL-3254 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8914 | 110.3283 | New | New | New | Type B | MA | JAW-JI-BKL-3254 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020469 | #N/A | [11 empty] | 2025-12-05 | 49 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-3001_1 | New_JAW-YO-BTL-3001 | JAW-YO-BTL-3001 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8774 | 110.3161 | New | New | New | Type B | MA | JAW-YO-BTL-3001 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020469 | #N/A | [9 empty] | 2026 |  | 2025-12-05 | 49 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3283_1 | New_JAW-JI-BKL-3283 | JAW-JI-BKL-3283 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.902 | 110.2999 | New | New | New | Type B | MA | JAW-JI-BKL-3283 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020469 | #N/A | [11 empty] | 2025-12-05 | 49 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3221_1 | New_JAW-JI-BKL-3221 | JAW-JI-BKL-3221 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8943 | 110.2963 | New | New | New | Type B | MA | JAW-JI-BKL-3221 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020469 | #N/A | [11 empty] | 2025-12-05 | 49 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3280_1 | New_JAW-JI-BKL-3280 | JAW-JI-BKL-3280 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8843 | 110.295 | New | New | New | Type B | MA | JAW-JI-BKL-3280 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020469 | #N/A | [11 empty] | 2025-12-22 | 52 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3276_1 | New_JAW-JI-BKL-3276 | JAW-JI-BKL-3276 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.863 | 110.2879 | New | New | New | Type B | MA | JAW-JI-BKL-3276 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020469 | #N/A | [11 empty] | 2025-12-22 | 52 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3184_1 | New_JAW-JI-BKL-3184 | JAW-JI-BKL-3184 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8537 | 110.2686 | New | New | New | Type B | MA | JAW-JI-BKL-3184 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020469 | #N/A | [11 empty] | 2025-12-22 | 52 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3273_1 | New_JAW-JI-BKL-3273 | JAW-JI-BKL-3273 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8518 | 110.2571 | New | New | New | Type B | MA | JAW-JI-BKL-3273 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020469 | #N/A | [11 empty] | 2025-12-22 | 52 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0150_1 | New_JAW-YO-BTL-0150 | JAW-YO-BTL-0150 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8319 | 110.2734 | New | New | New | Type B | MA | JAW-YO-BTL-0150 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020469 | #N/A | [9 empty] | 2026 |  | 2025-12-22 | 52 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-8158_1 | New_JAW-YO-BTL-8158 | JAW-YO-BTL-8158 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8132 | 110.2819 | New | New | New | Type B | MA | JAW-YO-BTL-8158 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020469 | #N/A | [9 empty] | 2026 |  | 2025-12-22 | 52 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-SMN-0004_1 | New_JAW-YO-SMN-0004 | JAW-YO-SMN-0004 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.7998 | 110.2827 | New | New | New | Type B | MA | JAW-YO-SMN-0004 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_3 1x25G/10G LR + 1x10G ZR + 6x1G LR |  |  | R0000020469 | #N/A | [9 empty] | 2026 |  | 2025-12-22 | 52 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3257_1 | New_JAW-JI-BKL-3257 | JAW-JI-BKL-3257 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8123 | 110.2503 | New | New | New | Type B | MA | JAW-JI-BKL-3257 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020469 | #N/A | [11 empty] | 2025-12-22 | 52 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0013_1 | New_JAW-YO-BTL-0013 | JAW-YO-BTL-0013 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8833 | 110.3339 | New | New | New | Type B | MA | JAW-YO-BTL-0013 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | #N/A | [9 empty] | 2026 |  | 2025-12-22 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3265_1 | New_JAW-JI-BKL-3265 | JAW-JI-BKL-3265 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8475 | 110.3392 | New | New | New | Type B | MA | JAW-JI-BKL-3265 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020470 | #N/A | [11 empty] | 2025-12-22 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0153_1 | New_JAW-YO-BTL-0153 | JAW-YO-BTL-0153 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8394 | 110.3392 | New | New | New | Type B | MA | JAW-YO-BTL-0153 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | #N/A | [9 empty] | 2026 |  | 2025-12-22 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3137_1 | New_JAW-JI-BKL-3137 | JAW-JI-BKL-3137 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.844 | 110.3325 | New | New | New | Type B | MA | JAW-JI-BKL-3137 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | #N/A | [11 empty] | 2025-12-22 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3136_1 | New_JAW-JI-BKL-3136 | JAW-JI-BKL-3136 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8355 | 110.328 | New | New | New | Type B | MA | JAW-JI-BKL-3136 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | #N/A | [11 empty] | 2025-12-22 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3191_1 | New_JAW-JI-BKL-3191 | JAW-JI-BKL-3191 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8284 | 110.3308 | New | New | New | Type B | MA | JAW-JI-BKL-3191 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | #N/A | [11 empty] | 2025-12-23 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3146_1 | New_JAW-JI-BKL-3146 | JAW-JI-BKL-3146 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8254 | 110.3353 | New | New | New | Type B | MA | JAW-JI-BKL-3146 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | #N/A | [11 empty] | 2025-12-23 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0035_1 | New_JAW-YO-BTL-0035 | JAW-YO-BTL-0035 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8232 | 110.3303 | New | New | New | Type B | MA | JAW-YO-BTL-0035 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | #N/A | [9 empty] | 2026 |  | 2025-12-23 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0132_1 | New_JAW-YO-BTL-0132 | JAW-YO-BTL-0132 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8197 | 110.3234 | New | New | New | Type B | MA | JAW-YO-BTL-0132 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | #N/A | [9 empty] | 2026 |  | 2025-12-23 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3240_1 | New_JAW-JI-BKL-3240 | JAW-JI-BKL-3240 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8113 | 110.3208 | New | New | New | Type B | MA | JAW-JI-BKL-3240 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | #N/A | [10 empty] | CCSI | 2025-12-23 | 52 |  |  | 2025 | 2025-11-11 |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-YO-BTL-0146_1 | New_JAW-YO-BTL-0146 | JAW-YO-BTL-0146 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8091 | 110.3216 | New | New | New | Type B | MA | JAW-YO-BTL-0146 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | #N/A | [9 empty] | 2026 | CCSI | 2025-12-23 | 52 |  |  | 2025 | 2025-11-11 | 2025-11-12 | Reviewing |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-JI-BKL-3156_1 | New_JAW-JI-BKL-3156 | JAW-JI-BKL-3156 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8087 | 110.3337 | New | New | New | Type B | MA | JAW-JI-BKL-3156 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | #N/A | [11 empty] | 2025-12-23 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3230_1 | New_JAW-JI-BKL-3230 | JAW-JI-BKL-3230 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8125 | 110.3374 | New | New | New | Type B | MA | JAW-JI-BKL-3230 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | #N/A | [11 empty] | 2025-12-23 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0008_1 | New_JAW-YO-BTL-0008 | JAW-YO-BTL-0008 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8174 | 110.3392 | New | New | New | Type B | MA | JAW-YO-BTL-0008 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | #N/A | [9 empty] | 2026 |  | 2025-12-23 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0136_1 | New_JAW-YO-BTL-0136 | JAW-YO-BTL-0136 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8122 | 110.3447 | New | New | New | Type B | MA | JAW-YO-BTL-0136 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | #N/A | [9 empty] | 2026 |  | 2025-12-23 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0684_1 | New_JAW-YO-YYK-0684 | JAW-YO-YYK-0684 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8011 | 110.3473 | New | New | New | Type B | MA | JAW-YO-YYK-0684 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | #N/A | [9 empty] | 2026 |  | 2025-12-23 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8289_1 | New_JAW-YO-YYK-8289 | JAW-YO-YYK-8289 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7998 | 110.3517 | New | New | New | Type B | MA | JAW-YO-YYK-8289 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | #N/A | [9 empty] | 2025-End Nov |  | 2025-12-23 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8270_1 | New_JAW-YO-YYK-8270 | JAW-YO-YYK-8270 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7975 | 110.3595 | New | New | New | Type B | MA | JAW-YO-YYK-8270 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | #N/A | [9 empty] | 2025-End Nov |  | 2025-12-23 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3268_1 | New_JAW-JI-BKL-3268 | JAW-JI-BKL-3268 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8726 | 110.4063 | New | New | New | Type B | MA | JAW-JI-BKL-3268 |  |  |  |  | - | - | - | - | New Purchase | New Ring 022 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020468 | #N/A | [11 empty] | 2025-12-24 | 52 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3255_1 | New_JAW-JI-BKL-3255 | JAW-JI-BKL-3255 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8571 | 110.4 | New | New | New | Type B | MA | JAW-JI-BKL-3255 |  |  |  |  | - | - | - | - | New Purchase | New Ring 022 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020468 | #N/A | [11 empty] | 2025-12-24 | 52 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0141_1 | New_JAW-YO-BTL-0141 | JAW-YO-BTL-0141 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8427 | 110.4003 | New | New | New | Type B | MA | JAW-YO-BTL-0141 |  |  |  |  | - | - | - | - | New Purchase | New Ring 022 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020468 | #N/A | [9 empty] | 2026 |  | 2025-12-24 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0576_1 | New_JAW-YO-YYK-0576 | JAW-YO-YYK-0576 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8317 | 110.4023 | New | New | New | Type B | MA | JAW-YO-YYK-0576 |  |  |  |  | - | - | - | - | New Purchase | New Ring 022 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020468 | #N/A | [9 empty] | 2025-End Nov |  | 2025-12-24 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8342_1 | New_JAW-YO-YYK-8342 | JAW-YO-YYK-8342 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.828 | 110.4029 | New | New | New | Type B | MA | JAW-YO-YYK-8342 |  |  |  |  | - | - | - | - | New Purchase | New Ring 022 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020468 | #N/A | [9 empty] | 2025-End Nov |  | 2025-12-24 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3234_1 | New_JAW-JI-BKL-3234 | JAW-JI-BKL-3234 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.826 | 110.4071 | New | New | New | Type B | MA | JAW-JI-BKL-3234 |  |  |  |  | - | - | - | - | New Purchase | New Ring 022 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020468 | #N/A | [11 empty] | 2025-12-24 | 52 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3217_1 | New_JAW-JI-BKL-3217 | JAW-JI-BKL-3217 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8849 | 110.3637 | New | New | New | Type B | MA | JAW-JI-BKL-3217 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020471 | #N/A | [11 empty] | 2025-12-24 | 52 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0621_1 | New_JAW-YO-BTL-0621 | JAW-YO-BTL-0621 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8725 | 110.3772 | New | New | New | Type B | MA | JAW-YO-BTL-0621 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020471 | #N/A | [9 empty] | 2026 |  | 2025-12-24 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0145_1 | New_JAW-YO-BTL-0145 | JAW-YO-BTL-0145 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8437 | 110.3911 | New | New | New | Type B | MA | JAW-YO-BTL-0145 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020471 | #N/A | [9 empty] | 2026 |  | 2025-12-24 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3155_1 | New_JAW-JI-BKL-3155 | JAW-JI-BKL-3155 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8337 | 110.3965 | New | New | New | Type B | MA | JAW-JI-BKL-3155 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020471 | #N/A | [11 empty] | 2025-12-24 | 52 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8326_1 | New_JAW-YO-YYK-8326 | JAW-YO-YYK-8326 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8357 | 110.3903 | New | New | New | Type B | MA | JAW-YO-YYK-8326 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | #N/A | [11 empty] | 2025-12-24 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3166_1 | New_JAW-JI-BKL-3166 | JAW-JI-BKL-3166 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.829 | 110.3809 | New | New | New | Type B | MA | JAW-JI-BKL-3166 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | #N/A | [11 empty] | 2025-12-24 | 52 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0536_1 | New_JAW-YO-YYK-0536 | JAW-YO-YYK-0536 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8254 | 110.3768 | New | New | New | Type B | MA | JAW-YO-YYK-0536 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | #N/A | [9 empty] | 2025-End Nov |  | 2025-12-24 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8301_1 | New_JAW-YO-YYK-8301 | JAW-YO-YYK-8301 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8205 | 110.3764 | New | New | New | Type B | MA | JAW-YO-YYK-8301 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | #N/A | [9 empty] | 2025-End Nov |  | 2025-12-25 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0079_1 | New_JAW-YO-YYK-0079 | JAW-YO-YYK-0079 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8168 | 110.3806 | New | New | New | Type B | MA | JAW-YO-YYK-0079 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | #N/A | [9 empty] | 2025-End Nov |  | 2025-12-25 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0064_1 | New_JAW-YO-YYK-0064 | JAW-YO-YYK-0064 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8157 | 110.3835 | New | New | New | Type B | MA | JAW-YO-YYK-0064 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | #N/A | [9 empty] | 2025-End Nov |  | 2025-12-25 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0553_1 | New_JAW-YO-YYK-0553 | JAW-YO-YYK-0553 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8236 | 110.3858 | New | New | New | Type B | MA | JAW-YO-YYK-0553 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | #N/A | [9 empty] | 2025-End Nov |  | 2025-12-25 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0072_1 | New_JAW-YO-YYK-0072 | JAW-YO-YYK-0072 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8266 | 110.3906 | New | New | New | Type B | MA | JAW-YO-YYK-0072 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | #N/A | [9 empty] | 2025-End Nov |  | 2025-12-25 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0562_1 | New_JAW-YO-YYK-0562 | JAW-YO-YYK-0562 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8258 | 110.3912 | New | New | New | Type B | MA | JAW-YO-YYK-0562 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | #N/A | [9 empty] | 2025-End Nov |  | 2025-12-25 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8335_1 | New_JAW-YO-YYK-8335 | JAW-YO-YYK-8335 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8244 | 110.3948 | New | New | New | Type B | MA | JAW-YO-YYK-8335 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | #N/A | [9 empty] | 2025-End Nov |  | 2025-12-25 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0646_1 | New_JAW-YO-YYK-0646 | JAW-YO-YYK-0646 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8272 | 110.3974 | New | New | New | Type B | MA | JAW-YO-YYK-0646 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | #N/A | [9 empty] | 2025-End Nov |  | 2025-12-25 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3248_1 | New_JAW-JI-BKL-3248 | JAW-JI-BKL-3248 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8155 | 110.4039 | New | New | New | Type B | MA | JAW-JI-BKL-3248 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | #N/A | [11 empty] | 2025-12-25 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3180_1 | New_JAW-JI-BKL-3180 | JAW-JI-BKL-3180 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8179 | 110.4082 | New | New | New | Type B | MA | JAW-JI-BKL-3180 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | #N/A | [11 empty] | 2025-12-25 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0089_1 | New_JAW-YO-BTL-0089 | JAW-YO-BTL-0089 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8129 | 110.4072 | New | New | New | Type B | MA | JAW-YO-BTL-0089 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | #N/A | [9 empty] | 2026 |  | 2025-12-25 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0088_1 | New_JAW-YO-BTL-0088 | JAW-YO-BTL-0088 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8063 | 110.4038 | New | New | New | Type B | MA | JAW-YO-BTL-0088 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | #N/A | [9 empty] | 2026 |  | 2025-12-25 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3178_1 | New_JAW-JI-BKL-3178 | JAW-JI-BKL-3178 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.7981 | 110.4047 | New | New | New | Type B | MA | JAW-JI-BKL-3178 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | #N/A | [11 empty] | 2025-12-25 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0087_1 | New_JAW-YO-BTL-0087 | JAW-YO-BTL-0087 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.7961 | 110.4032 | New | New | New | Type B | MA | JAW-YO-BTL-0087 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | #N/A | [9 empty] | 2026 |  | 2025-12-26 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0085_1 | New_JAW-YO-BTL-0085 | JAW-YO-BTL-0085 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.7919 | 110.4014 | New | New | New | Type B | MA | JAW-YO-BTL-0085 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | #N/A | [9 empty] | 2026 |  | 2025-12-26 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0584_1 | New_JAW-YO-BTL-0584 | JAW-YO-BTL-0584 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.7874 | 110.4098 | New | New | New | Type B | MA | JAW-YO-BTL-0584 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | #N/A | [9 empty] | 2026 |  | 2025-12-26 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3153_1 | New_JAW-JI-BKL-3153 | JAW-JI-BKL-3153 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8008 | 110.4118 | New | New | New | Type B | MA | JAW-JI-BKL-3153 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | #N/A | [11 empty] | 2025-12-26 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0650_1 | New_JAW-YO-BTL-0650 | JAW-YO-BTL-0650 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.799 | 110.4167 | New | New | New | Type B | MA | JAW-YO-BTL-0650 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | #N/A | [9 empty] | 2026 |  | 2025-12-26 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0592_1 | New_JAW-YO-BTL-0592 | JAW-YO-BTL-0592 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8107 | 110.4204 | New | New | New | Type B | MA | JAW-YO-BTL-0592 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | #N/A | [9 empty] | 2026 |  | 2025-12-26 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3245_1 | New_JAW-JI-BKL-3245 | JAW-JI-BKL-3245 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8127 | 110.4154 | New | New | New | Type B | MA | JAW-JI-BKL-3245 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | #N/A | [11 empty] | 2025-12-26 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0103_1 | New_JAW-YO-BTL-0103 | JAW-YO-BTL-0103 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8179 | 110.4172 | New | New | New | Type B | MA | JAW-YO-BTL-0103 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | #N/A | [9 empty] | 2026 |  | 2025-12-26 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3163_1 | New_JAW-JI-BKL-3163 | JAW-JI-BKL-3163 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8263 | 110.4183 | New | New | New | Type B | MA | JAW-JI-BKL-3163 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | #N/A | [11 empty] | 2025-12-26 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0148_1 | New_JAW-YO-BTL-0148 | JAW-YO-BTL-0148 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8293 | 110.4238 | New | New | New | Type B | MA | JAW-YO-BTL-0148 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020472 | #N/A | [9 empty] | 2026 |  | 2025-12-26 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3287_1 | New_JAW-JI-BKL-3287 | JAW-JI-BKL-3287 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8382 | 110.444 | New | New | New | Type B | MA | JAW-JI-BKL-3287 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | #N/A | [11 empty] | 2025-12-26 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0131_1 | New_JAW-YO-BTL-0131 | JAW-YO-BTL-0131 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8416 | 110.4501 | New | New | New | Type B | MA | JAW-YO-BTL-0131 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020472 | #N/A | [9 empty] | 2026 |  | 2025-12-26 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3267_1 | New_JAW-JI-BKL-3267 | JAW-JI-BKL-3267 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8305 | 110.4566 | New | New | New | Type B | MA | JAW-JI-BKL-3267 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | #N/A | [11 empty] | 2025-12-26 | 52 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0112_1 | New_JAW-YO-BTL-0112 | JAW-YO-BTL-0112 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8339 | 110.4634 | New | New | New | Type B | MA | JAW-YO-BTL-0112 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | #N/A | [9 empty] | 2026 |  | 2025-12-29 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3277_1 | New_JAW-JI-BKL-3277 | JAW-JI-BKL-3277 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8333 | 110.4736 | New | New | New | Type B | MA | JAW-JI-BKL-3277 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020472 | #N/A | [11 empty] | 2025-12-29 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0116_1 | New_JAW-YO-BTL-0116 | JAW-YO-BTL-0116 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8253 | 110.4808 | New | New | New | Type B | MA | JAW-YO-BTL-0116 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020472 | #N/A | [9 empty] | 2026 |  | 2025-12-29 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3262_1 | New_JAW-JI-BKL-3262 | JAW-JI-BKL-3262 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9227 | 110.3959 | New | New | New | Type B | MA | JAW-JI-BKL-3262 |  |  |  |  | - | - | - | - | New Purchase | New Ring 025 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000019967 | #N/A | [11 empty] | 2025-12-29 | 53 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-8159_1 | New_JAW-YO-BTL-8159 | JAW-YO-BTL-8159 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9188 | 110.4371 | New | New | New | Type B | MA | JAW-YO-BTL-8159 |  |  |  |  | - | - | - | - | New Purchase | New Ring 025 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000019967 | #N/A | [9 empty] | 2026 |  | 2025-12-29 | 53 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0682_1 | New_JAW-YO-BTL-0682 | JAW-YO-BTL-0682 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9097 | 110.4444 | New | New | New | Type B | MA | JAW-YO-BTL-0682 |  |  |  |  | - | - | - | - | New Purchase | New Ring 025 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019967 | #N/A | [9 empty] | 2026 |  | 2025-12-29 | 53 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3284_1 | New_JAW-JI-BKL-3284 | JAW-JI-BKL-3284 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9312 | 110.4453 | New | New | New | Type B | MA | JAW-JI-BKL-3284 |  |  |  |  | - | - | - | - | New Purchase | New Ring 025 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000019967 | #N/A | [11 empty] | 2025-12-29 | 53 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3282_1 | New_JAW-JI-BKL-3282 | JAW-JI-BKL-3282 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9242 | 110.4725 | New | New | New | Type B | MA | JAW-JI-BKL-3282 |  |  |  |  | - | - | - | - | New Purchase | New Ring 025 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019967 | #N/A | [11 empty] | 2025-12-29 | 53 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3214_1 | New_JAW-JI-BKL-3214 | JAW-JI-BKL-3214 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.898 | 110.4509 | New | New | New | Type B | MA | JAW-JI-BKL-3214 |  |  |  |  | - | - | - | - | New Purchase | New Ring 025 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019967 | #N/A | [11 empty] | 2025-12-29 | 53 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3175_1 | New_JAW-JI-BKL-3175 | JAW-JI-BKL-3175 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8823 | 110.4523 | New | New | New | Type B | MA | JAW-JI-BKL-3175 |  |  |  |  | - | - | - | - | New Purchase | New Ring 025 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000019967 | #N/A | [11 empty] | 2025-12-29 | 53 |  |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3261_1 | New_JAW-JI-BKL-3261 | JAW-JI-BKL-3261 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9316 | 110.3727 | New | New | New | Type B | MA | JAW-JI-BKL-3261 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000019968 | #N/A | [11 empty] | 2025-12-29 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0076_1 | New_JAW-YO-BTL-0076 | JAW-YO-BTL-0076 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9522 | 110.3891 | New | New | New | Type B | MA | JAW-YO-BTL-0076 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019968 | #N/A | [9 empty] | 2026 |  | 2025-12-29 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3279_1 | New_JAW-JI-BKL-3279 | JAW-JI-BKL-3279 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9731 | 110.3763 | New | New | New | Type B | MA | JAW-JI-BKL-3279 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000019968 | #N/A | [11 empty] | 2025-12-29 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3259_1 | New_JAW-JI-BKL-3259 | JAW-JI-BKL-3259 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9636 | 110.3576 | New | New | New | Type B | MA | JAW-JI-BKL-3259 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019968 | #N/A | [11 empty] | 2025-12-30 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-3004_1 | New_JAW-YO-BTL-3004 | JAW-YO-BTL-3004 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9796 | 110.3433 | New | New | New | Type B | MA | JAW-YO-BTL-3004 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000019968 | #N/A | [9 empty] | 2026 |  | 2025-12-30 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-8157_1 | New_JAW-YO-BTL-8157 | JAW-YO-BTL-8157 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9874 | 110.3236 | New | New | New | Type B | MA | JAW-YO-BTL-8157 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019968 | #N/A | [9 empty] | 2026 |  | 2025-12-30 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0134_1 | New_JAW-YO-BTL-0134 | JAW-YO-BTL-0134 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -8.0202 | 110.3263 | New | New | New | Type B | MA | JAW-YO-BTL-0134 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019968 | #N/A | [9 empty] | 2026 |  | 2025-12-30 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3225_1 | New_JAW-JI-BKL-3225 | JAW-JI-BKL-3225 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9593 | 110.3225 | New | New | New | Type B | MA | JAW-JI-BKL-3225 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019968 | #N/A | [11 empty] | 2025-12-30 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0149_1 | New_JAW-YO-BTL-0149 | JAW-YO-BTL-0149 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9434 | 110.3573 | New | New | New | Type B | MA | JAW-YO-BTL-0149 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019968 | #N/A | [9 empty] | 2026 |  | 2025-12-30 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-1584_1 | New_JAW-JT-PWD-1584 | JAW-JT-PWD-1584 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9158 | 110.3688 | New | New | New | Type B | MA | JAW-JT-PWD-1584 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019968 | #N/A | [9 empty] | 2026 |  | 2025-12-30 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0053_1 | New_JAW-YO-BTL-0053 | JAW-YO-BTL-0053 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8937 | 110.3499 | New | New | New | Type B | MA | JAW-YO-BTL-0053 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000019968 | #N/A | [9 empty] | 2026 |  | 2025-12-30 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8312_1 | New_JAW-JT-BLA-8312 | JAW-JT-BLA-8312 | Central Java | Jawa Tengah | Blora | -6.9351 | 111.4975 | New | New | New | Type B | MA | JAW-JT-BLA-8312 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019802 | #N/A | [9 empty] | 2026 |  | 2025-12-30 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-0130_1 | New_JAW-JT-BLA-0130 | JAW-JT-BLA-0130 | Central Java | Jawa Tengah | Blora | -6.9223 | 111.4698 | New | New | New | Type B | MA | JAW-JT-BLA-0130 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019802 | #N/A | [9 empty] | 2026 |  | 2025-12-30 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-0160_1 | New_JAW-JT-BLA-0160 | JAW-JT-BLA-0160 | Central Java | Jawa Tengah | Blora | -6.9228 | 111.3708 | New | New | New | Type B | MA | JAW-JT-BLA-0160 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019802 | #N/A | [9 empty] | 2026 |  | 2025-12-30 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-0154_1 | New_JAW-JT-BLA-0154 | JAW-JT-BLA-0154 | Central Java | Jawa Tengah | Blora | -6.9429 | 111.2922 | New | New | New | Type B | MA | JAW-JT-BLA-0154 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019802 | #N/A | [9 empty] | 2026 |  | 2025-12-30 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8203_1 | New_JAW-JT-BLA-8203 | JAW-JT-BLA-8203 | Central Java | Jawa Tengah | Blora | -6.9419 | 111.2624 | New | New | New | Type B | MA | JAW-JT-BLA-8203 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019802 | #N/A | [9 empty] | 2026 |  | 2025-12-30 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-0133_1 | New_JAW-JT-BLA-0133 | JAW-JT-BLA-0133 | Central Java | Jawa Tengah | Blora | -6.9562 | 111.1774 | New | New | New | Type B | MA | JAW-JT-BLA-0133 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019802 | #N/A | [9 empty] | 2026 |  | 2025-12-31 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8348_1 | New_JAW-JT-BLA-8348 | JAW-JT-BLA-8348 | Central Java | Jawa Tengah | Blora | -6.9562 | 111.1204 | New | New | New | Type B | MA | JAW-JT-BLA-8348 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019802 | #N/A | [9 empty] | 2026 |  | 2025-12-31 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8350_1 | New_JAW-JT-BLA-8350 | JAW-JT-BLA-8350 | Central Java | Jawa Tengah | Blora | -6.9758 | 111.1585 | New | New | New | Type B | MA | JAW-JT-BLA-8350 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019802 | #N/A | [9 empty] | 2026 |  | 2025-12-31 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-3168_1 | New_JAW-JT-BLA-3168 | JAW-JT-BLA-3168 | Central Java | Jawa Tengah | Blora | -6.9891 | 111.2018 | New | New | New | Type B | MA | JAW-JT-BLA-3168 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019802 | #N/A | [9 empty] | 2026 |  | 2025-12-31 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8191_1 | New_JAW-JT-BLA-8191 | JAW-JT-BLA-8191 | Central Java | Jawa Tengah | Blora | -7.0745 | 111.2208 | New | New | New | Type B | MA | JAW-JT-BLA-8191 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019802 | #N/A | [9 empty] | 2026 |  | 2025-12-31 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8197_1 | New_JAW-JT-BLA-8197 | JAW-JT-BLA-8197 | Central Java | Jawa Tengah | Blora | -7.103 | 111.2502 | New | New | New | Type B | MA | JAW-JT-BLA-8197 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019802 | #N/A | [9 empty] | 2026 |  | 2025-12-31 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8201_1 | New_JAW-JT-BLA-8201 | JAW-JT-BLA-8201 | Central Java | Jawa Tengah | Blora | -7.1744 | 111.2598 | New | New | New | Type B | MA | JAW-JT-BLA-8201 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019802 | #N/A | [9 empty] | 2026 |  | 2025-12-31 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8199_1 | New_JAW-JT-BLA-8199 | JAW-JT-BLA-8199 | Central Java | Jawa Tengah | Blora | -7.1853 | 111.2569 | New | New | New | Type B | MA | JAW-JT-BLA-8199 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019802 | #N/A | [9 empty] | 2026 |  | 2025-12-31 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8208_1 | New_JAW-JT-BLA-8208 | JAW-JT-BLA-8208 | Central Java | Jawa Tengah | Blora | -7.2003 | 111.2754 | New | New | New | Type B | MA | JAW-JT-BLA-8208 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019802 | #N/A | [9 empty] | 2026 |  | 2025-12-31 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-0136_1 | New_JAW-JT-BLA-0136 | JAW-JT-BLA-0136 | Central Java | Jawa Tengah | Blora | -7.2117 | 111.2893 | New | New | New | Type B | MA | JAW-JT-BLA-0136 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019802 | #N/A | [9 empty] | 2026 |  | 2025-12-31 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8240_1 | New_JAW-JT-BLA-8240 | JAW-JT-BLA-8240 | Central Java | Jawa Tengah | Blora | -7.2166 | 111.3718 | New | New | New | Type B | MA | JAW-JT-BLA-8240 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019802 | #N/A | [9 empty] | 2026 |  | 2025-12-31 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-0127_1 | New_JAW-JT-BLA-0127 | JAW-JT-BLA-0127 | Central Java | Jawa Tengah | Blora | -7.2368 | 111.4419 | New | New | New | Type B | MA | JAW-JT-BLA-0127 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019802 | #N/A | [9 empty] | 2026 |  | 2025-12-31 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8315_1 | New_JAW-JT-BLA-8315 | JAW-JT-BLA-8315 | Central Java | Jawa Tengah | Blora | -7.2396 | 111.5091 | New | New | New | Type B | MA | JAW-JT-BLA-8315 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK |  | R0000019802 | #N/A |  |  | 10. Ready ATP / RFS |  |  | 2025-11-09 |  |  |  | 2026 |  | 2025-12-31 | 53 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8328_1 | New_JAW-JT-BLA-8328 | JAW-JT-BLA-8328 | Central Java | Jawa Tengah | Blora | -7.1869 | 111.5561 | New | New | New | Type B | MA | JAW-JT-BLA-8328 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK |  | R0000019802 | #N/A |  |  | 10. Ready ATP / RFS |  |  | 2025-11-09 |  |  |  | 2026 |  | 2026-01-01 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-0202_1 | New_JAW-JT-BLA-0202 | JAW-JT-BLA-0202 | Central Java | Jawa Tengah | Blora | -7.1608 | 111.5857 | New | New | New | Type B | MA | JAW-JT-BLA-0202 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK |  | R0000019802 | #N/A |  |  | 10. Ready ATP / RFS |  |  | 2025-11-09 |  |  |  | 2026 |  | 2026-01-01 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8302_1 | New_JAW-JT-BLA-8302 | JAW-JT-BLA-8302 | Central Java | Jawa Tengah | Blora | -6.9737 | 111.4685 | New | New | New | Type B | MA | JAW-JT-BLA-8302 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK |  | R0000019803 | #N/A |  |  | 10. Ready ATP / RFS |  |  | 2025-11-09 |  |  |  | 2026 |  | 2026-01-01 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8293_1 | New_JAW-JT-BLA-8293 | JAW-JT-BLA-8293 | Central Java | Jawa Tengah | Blora | -6.9649 | 111.4587 | New | New | New | Type B | MA | JAW-JT-BLA-8293 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK |  | R0000019803 | #N/A |  |  | 10. Ready ATP / RFS |  |  | 2025-11-09 |  |  |  | 2026 |  | 2026-01-01 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-0149_1 | New_JAW-JT-BLA-0149 | JAW-JT-BLA-0149 | Central Java | Jawa Tengah | Blora | -6.9716 | 111.4311 | New | New | New | Type B | MA | JAW-JT-BLA-0149 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK |  | R0000019803 | #N/A |  |  | 10. Ready ATP / RFS |  |  | 2025-11-09 |  |  |  | 2026 |  | 2026-01-01 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8256_1 | New_JAW-JT-BLA-8256 | JAW-JT-BLA-8256 | Central Java | Jawa Tengah | Blora | -6.9705 | 111.3927 | New | New | New | Type B | MA | JAW-JT-BLA-8256 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK |  | R0000019803 | #N/A |  |  | 10. Ready ATP / RFS |  |  | 2025-11-09 |  |  |  | 2026 |  | 2026-01-01 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8243_1 | New_JAW-JT-BLA-8243 | JAW-JT-BLA-8243 | Central Java | Jawa Tengah | Blora | -6.9672 | 111.3774 | New | New | New | Type B | MA | JAW-JT-BLA-8243 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK |  | R0000019803 | #N/A |  |  | 10. Ready ATP / RFS |  |  | 2025-11-09 | [5 empty] | 2026-01-01 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8225_1 | New_JAW-JT-BLA-8225 | JAW-JT-BLA-8225 | Central Java | Jawa Tengah | Blora | -6.9911 | 111.3243 | New | New | New | Type B | MA | JAW-JT-BLA-8225 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK |  | R0000019803 | #N/A |  |  | 10. Ready ATP / RFS |  |  | 2025-11-09 |  |  |  | 2026 |  | 2026-01-01 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8219_1 | New_JAW-JT-BLA-8219 | JAW-JT-BLA-8219 | Central Java | Jawa Tengah | Blora | -6.9855 | 111.3013 | New | New | New | Type B | MA | JAW-JT-BLA-8219 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019803 | #N/A | [9 empty] | 2026 |  | 2026-01-01 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8194_1 | New_JAW-JT-BLA-8194 | JAW-JT-BLA-8194 | Central Java | Jawa Tengah | Blora | -7.003 | 111.2439 | New | New | New | Type B | MA | JAW-JT-BLA-8194 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019803 | #N/A | [9 empty] | 2026 |  | 2026-01-01 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8193_1 | New_JAW-JT-BLA-8193 | JAW-JT-BLA-8193 | Central Java | Jawa Tengah | Blora | -7.0543 | 111.2399 | New | New | New | Type B | MA | JAW-JT-BLA-8193 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019803 | #N/A | [9 empty] | 2026 |  | 2026-01-01 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8204_1 | New_JAW-JT-BLA-8204 | JAW-JT-BLA-8204 | Central Java | Jawa Tengah | Blora | -7.0699 | 111.2634 | New | New | New | Type B | MA | JAW-JT-BLA-8204 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019803 | #N/A | [9 empty] | 2026 |  | 2026-01-01 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8209_1 | New_JAW-JT-BLA-8209 | JAW-JT-BLA-8209 | Central Java | Jawa Tengah | Blora | -7.084 | 111.2819 | New | New | New | Type B | MA | JAW-JT-BLA-8209 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019803 | #N/A | [9 empty] | 2026 |  | 2026-01-01 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8207_1 | New_JAW-JT-BLA-8207 | JAW-JT-BLA-8207 | Central Java | Jawa Tengah | Blora | -7.1067 | 111.2737 | New | New | New | Type B | MA | JAW-JT-BLA-8207 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019803 | #N/A | [9 empty] | 2026 |  | 2026-01-02 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8217_1 | New_JAW-JT-BLA-8217 | JAW-JT-BLA-8217 | Central Java | Jawa Tengah | Blora | -7.1834 | 111.3107 | New | New | New | Type B | MA | JAW-JT-BLA-8217 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019803 | #N/A | [9 empty] | 2026 |  | 2026-01-02 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8223_1 | New_JAW-JT-BLA-8223 | JAW-JT-BLA-8223 | Central Java | Jawa Tengah | Blora | -7.191 | 111.3218 | New | New | New | Type B | MA | JAW-JT-BLA-8223 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019803 | #N/A | [9 empty] | 2026 |  | 2026-01-02 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8241_1 | New_JAW-JT-BLA-8241 | JAW-JT-BLA-8241 | Central Java | Jawa Tengah | Blora | -7.202 | 111.3725 | New | New | New | Type B | MA | JAW-JT-BLA-8241 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019803 | #N/A | [9 empty] | 2026 |  | 2026-01-02 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8271_1 | New_JAW-JT-BLA-8271 | JAW-JT-BLA-8271 | Central Java | Jawa Tengah | Blora | -7.2217 | 111.4211 | New | New | New | Type B | MA | JAW-JT-BLA-8271 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019803 | #N/A | [9 empty] | 2026 |  | 2026-01-02 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8297_1 | New_JAW-JT-BLA-8297 | JAW-JT-BLA-8297 | Central Java | Jawa Tengah | Blora | -7.2154 | 111.4524 | New | New | New | Type B | MA | JAW-JT-BLA-8297 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019803 | #N/A | [9 empty] | 2026 | CCSI | 2026-01-02 | 1 |  |  | 2026 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-JT-BLA-8308_1 | New_JAW-JT-BLA-8308 | JAW-JT-BLA-8308 | Central Java | Jawa Tengah | Blora | -7.2267 | 111.4959 | New | New | New | Type B | MA | JAW-JT-BLA-8308 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019803 | #N/A | [9 empty] | 2026 |  | 2026-01-02 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8316_1 | New_JAW-JT-BLA-8316 | JAW-JT-BLA-8316 | Central Java | Jawa Tengah | Blora | -7.2135 | 111.5127 | New | New | New | Type B | MA | JAW-JT-BLA-8316 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019803 | #N/A | [9 empty] | 2026 |  | 2026-01-02 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8326_1 | New_JAW-JT-BLA-8326 | JAW-JT-BLA-8326 | Central Java | Jawa Tengah | Blora | -7.1718 | 111.5543 | New | New | New | Type B | MA | JAW-JT-BLA-8326 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000019803 | #N/A | [9 empty] | 2026 |  | 2026-01-02 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8296_1 | New_JAW-JT-BLA-8296 | JAW-JT-BLA-8296 | Central Java | Jawa Tengah | Blora | -7.0037 | 111.4645 | New | New | New | Type B | MA | JAW-JT-BLA-8296 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | #N/A | [9 empty] | 2026 |  | 2026-01-02 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8273_1 | New_JAW-JT-BLA-8273 | JAW-JT-BLA-8273 | Central Java | Jawa Tengah | Blora | -6.9973 | 111.4175 | New | New | New | Type B | MA | JAW-JT-BLA-8273 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | #N/A | [9 empty] | 2026 |  | 2026-01-02 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8252_1 | New_JAW-JT-BLA-8252 | JAW-JT-BLA-8252 | Central Java | Jawa Tengah | Blora | -7.0048 | 111.3905 | New | New | New | Type B | MA | JAW-JT-BLA-8252 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | #N/A | [9 empty] | 2026 |  | 2026-01-02 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8237_1 | New_JAW-JT-BLA-8237 | JAW-JT-BLA-8237 | Central Java | Jawa Tengah | Blora | -7.039 | 111.3594 | New | New | New | Type B | MA | JAW-JT-BLA-8237 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | #N/A | [9 empty] | 2026 |  | 2026-01-02 | 1 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8232_1 | New_JAW-JT-BLA-8232 | JAW-JT-BLA-8232 | Central Java | Jawa Tengah | Blora | -7.0117 | 111.3504 | New | New | New | Type B | MA | JAW-JT-BLA-8232 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | #N/A | [9 empty] | 2026 |  | 2026-01-05 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8222_1 | New_JAW-JT-BLA-8222 | JAW-JT-BLA-8222 | Central Java | Jawa Tengah | Blora | -7.0393 | 111.3023 | New | New | New | Type B | MA | JAW-JT-BLA-8222 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | #N/A | [9 empty] | 2026 |  | 2026-01-05 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8212_1 | New_JAW-JT-BLA-8212 | JAW-JT-BLA-8212 | Central Java | Jawa Tengah | Blora | -7.0453 | 111.29 | New | New | New | Type B | MA | JAW-JT-BLA-8212 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | #N/A | [9 empty] | 2026 |  | 2026-01-05 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8220_1 | New_JAW-JT-BLA-8220 | JAW-JT-BLA-8220 | Central Java | Jawa Tengah | Blora | -7.0694 | 111.3141 | New | New | New | Type B | MA | JAW-JT-BLA-8220 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | #N/A | [9 empty] | 2026 |  | 2026-01-05 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8231_1 | New_JAW-JT-BLA-8231 | JAW-JT-BLA-8231 | Central Java | Jawa Tengah | Blora | -7.0451 | 111.3352 | New | New | New | Type B | MA | JAW-JT-BLA-8231 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | #N/A | [9 empty] | 2026 |  | 2026-01-05 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8233_1 | New_JAW-JT-BLA-8233 | JAW-JT-BLA-8233 | Central Java | Jawa Tengah | Blora | -7.061 | 111.3549 | New | New | New | Type B | MA | JAW-JT-BLA-8233 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | #N/A | [9 empty] | 2026 |  | 2026-01-05 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8253_1 | New_JAW-JT-BLA-8253 | JAW-JT-BLA-8253 | Central Java | Jawa Tengah | Blora | -7.0441 | 111.3914 | New | New | New | Type B | MA | JAW-JT-BLA-8253 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000020473 | #N/A | [9 empty] | 2026 |  | 2026-01-05 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8257_1 | New_JAW-JT-BLA-8257 | JAW-JT-BLA-8257 | Central Java | Jawa Tengah | Blora | -7.0944 | 111.3956 | New | New | New | Type B | MA | JAW-JT-BLA-8257 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000020473 | #N/A | [9 empty] | 2026 |  | 2026-01-05 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8279_1 | New_JAW-JT-BLA-8279 | JAW-JT-BLA-8279 | Central Java | Jawa Tengah | Blora | -7.1386 | 111.4331 | New | New | New | Type B | MA | JAW-JT-BLA-8279 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000020473 | #N/A | [9 empty] | 2026 |  | 2026-01-05 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-0166_1 | New_JAW-JT-BLA-0166 | JAW-JT-BLA-0166 | Central Java | Jawa Tengah | Blora | -7.1881 | 111.3917 | New | New | New | Type B | MA | JAW-JT-BLA-0166 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000020473 | #N/A | [9 empty] | 2026 |  | 2026-01-05 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8286_1 | New_JAW-JT-BLA-8286 | JAW-JT-BLA-8286 | Central Java | Jawa Tengah | Blora | -7.183 | 111.4497 | New | New | New | Type B | MA | JAW-JT-BLA-8286 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | #N/A | [9 empty] | 2026 |  | 2026-01-05 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8307_1 | New_JAW-JT-BLA-8307 | JAW-JT-BLA-8307 | Central Java | Jawa Tengah | Blora | -7.1669 | 111.4948 | New | New | New | Type B | MA | JAW-JT-BLA-8307 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | #N/A | [9 empty] | 2026 |  | 2026-01-05 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8309_1 | New_JAW-JT-BLA-8309 | JAW-JT-BLA-8309 | Central Java | Jawa Tengah | Blora | -7.1801 | 111.4964 | New | New | New | Type B | MA | JAW-JT-BLA-8309 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | #N/A | [9 empty] | 2026 |  | 2026-01-05 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8325_1 | New_JAW-JT-BLA-8325 | JAW-JT-BLA-8325 | Central Java | Jawa Tengah | Blora | -7.1573 | 111.5503 | New | New | New | Type B | MA | JAW-JT-BLA-8325 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | #N/A | [9 empty] | 2026 |  | 2026-01-06 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8336_1 | New_JAW-JT-BLA-8336 | JAW-JT-BLA-8336 | Central Java | Jawa Tengah | Blora | -7.1507 | 111.5783 | New | New | New | Type B | MA | JAW-JT-BLA-8336 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020473 | #N/A | [9 empty] | 2026 |  | 2026-01-06 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8339_1 | New_JAW-JT-BLA-8339 | JAW-JT-BLA-8339 | Central Java | Jawa Tengah | Blora | -7.1501 | 111.5901 | New | New | New | Type B | MA | JAW-JT-BLA-8339 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020473 | #N/A | [11 empty] | 2026-01-06 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLT-8459_1 | New_JAW-JT-SLT-8459 | JAW-JT-SLT-8459 | Central Java | Jawa Tengah | Kota Salatiga | -7.3502 | 110.51 | New | New | New | Type B | MA | JAW-JT-SLT-8459 |  |  |  |  | - | - | - | - | New Purchase | New Ring 031 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020476 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-06 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLT-8455_1 | New_JAW-JT-SLT-8455 | JAW-JT-SLT-8455 | Central Java | Jawa Tengah | Kota Salatiga | -7.3389 | 110.5063 | New | New | New | Type B | MA | JAW-JT-SLT-8455 |  |  |  |  | - | - | - | - | New Purchase | New Ring 031 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020476 | #N/A | [11 empty] | 2026-01-06 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLT-8446_1 | New_JAW-JT-SLT-8446 | JAW-JT-SLT-8446 | Central Java | Jawa Tengah | Kota Salatiga | -7.327 | 110.4994 | New | New | New | Type B | MA | JAW-JT-SLT-8446 |  |  |  |  | - | - | - | - | New Purchase | New Ring 031 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020476 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-06 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLT-8451_1 | New_JAW-JT-SLT-8451 | JAW-JT-SLT-8451 | Central Java | Jawa Tengah | Kota Salatiga | -7.3264 | 110.5052 | New | New | New | Type B | MA | JAW-JT-SLT-8451 |  |  |  |  | - | - | - | - | New Purchase | New Ring 031 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020476 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-06 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLT-2133_1 | New_JAW-JT-SLT-2133 | JAW-JT-SLT-2133 | Central Java | Jawa Tengah | Kota Salatiga | -7.3203 | 110.5108 | New | New | New | Type B | MA | JAW-JT-SLT-2133 |  |  |  |  | - | - | - | - | New Purchase | New Ring 031 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020476 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-06 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLT-8454_1 | New_JAW-JT-SLT-8454 | JAW-JT-SLT-8454 | Central Java | Jawa Tengah | Kota Salatiga | -7.3072 | 110.5061 | New | New | New | Type B | MA | JAW-JT-SLT-8454 |  |  |  |  | - | - | - | - | New Purchase | New Ring 031 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020476 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-06 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLT-2136_1 | New_JAW-JT-SLT-2136 | JAW-JT-SLT-2136 | Central Java | Jawa Tengah | Kota Salatiga | -7.3013 | 110.4908 | New | New | New | Type B | MA | JAW-JT-SLT-2136 |  |  |  |  | - | - | - | - | New Purchase | New Ring 031 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020476 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-06 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLT-8431_1 | New_JAW-JT-SLT-8431 | JAW-JT-SLT-8431 | Central Java | Jawa Tengah | Kota Salatiga | -7.2931 | 110.4769 | New | New | New | Type B | MA | JAW-JT-SLT-8431 |  |  |  |  | - | - | - | - | New Purchase | New Ring 031 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020476 | #N/A | [11 empty] | 2026-01-06 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-2350_1 | New_JAW-JT-SMG-2350 | JAW-JT-SMG-2350 | Central Java | Jawa Tengah | Kota Semarang | -6.9914 | 110.4151 | New | New | New | Type B | MA | JAW-JT-SMG-2350 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | #N/A | S000056139 | S000056140 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-06 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8510_1 | New_JAW-JT-SMG-8510 | JAW-JT-SMG-8510 | Central Java | Jawa Tengah | Kota Semarang | -6.9936 | 110.4221 | New | New | New | Type B | MA | JAW-JT-SMG-8510 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | #N/A | S000056140 | S000056141 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-06 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8506_1 | New_JAW-JT-SMG-8506 | JAW-JT-SMG-8506 | Central Java | Jawa Tengah | Kota Semarang | -6.9759 | 110.4214 | New | New | New | Type B | MA | JAW-JT-SMG-8506 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | #N/A | S000056141 | S000056142 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  |  |  | 2026-01-07 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8523_1 | New_JAW-JT-SMG-8523 | JAW-JT-SMG-8523 | Central Java | Jawa Tengah | Kota Semarang | -6.9705 | 110.4252 | New | New | New | Type B | MA | JAW-JT-SMG-8523 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | #N/A | S000056142 | S000056143 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  |  |  | 2026-01-07 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8571_1 | New_JAW-JT-SMG-8571 | JAW-JT-SMG-8571 | Central Java | Jawa Tengah | Kota Semarang | -6.9685 | 110.4341 | New | New | New | Type B | MA | JAW-JT-SMG-8571 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | #N/A | S000056143 | S000056144 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-07 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8578_1 | New_JAW-JT-SMG-8578 | JAW-JT-SMG-8578 | Central Java | Jawa Tengah | Kota Semarang | -6.9655 | 110.4405 | New | New | New | Type B | MA | JAW-JT-SMG-8578 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | #N/A | S000056144 | S000056145 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-07 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8599_1 | New_JAW-JT-SMG-8599 | JAW-JT-SMG-8599 | Central Java | Jawa Tengah | Kota Semarang | -6.9601 | 110.4474 | New | New | New | Type B | MA | JAW-JT-SMG-8599 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | #N/A | S000056145 | S000056146 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-07 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8612_1 | New_JAW-JT-SMG-8612 | JAW-JT-SMG-8612 | Central Java | Jawa Tengah | Kota Semarang | -6.9641 | 110.4535 | New | New | New | Type B | MA | JAW-JT-SMG-8612 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | #N/A | S000056146 | S000056147 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-07 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8617_1 | New_JAW-JT-SMG-8617 | JAW-JT-SMG-8617 | Central Java | Jawa Tengah | Kota Semarang | -6.9672 | 110.4567 | New | New | New | Type B | MA | JAW-JT-SMG-8617 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | #N/A | S000056147 | S000056148 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-07 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8637_1 | New_JAW-JT-SMG-8637 | JAW-JT-SMG-8637 | Central Java | Jawa Tengah | Kota Semarang | -6.9671 | 110.4612 | New | New | New | Type B | MA | JAW-JT-SMG-8637 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | #N/A | S000056148 | S000056149 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  |  |  | 2026-01-07 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8644_1 | New_JAW-JT-SMG-8644 | JAW-JT-SMG-8644 | Central Java | Jawa Tengah | Kota Semarang | -6.9712 | 110.464 | New | New | New | Type B | MA | JAW-JT-SMG-8644 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | #N/A | S000056149 | S000056150 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-07 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-2558_1 | New_JAW-JT-SMG-2558 | JAW-JT-SMG-2558 | Central Java | Jawa Tengah | Kota Semarang | -6.9727 | 110.4716 | New | New | New | Type B | MA | JAW-JT-SMG-2558 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | #N/A | S000056150 | S000056151 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-07 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8674_1 | New_JAW-JT-SMG-8674 | JAW-JT-SMG-8674 | Central Java | Jawa Tengah | Kota Semarang | -6.9766 | 110.4775 | New | New | New | Type B | MA | JAW-JT-SMG-8674 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | #N/A | S000056151 | S000056152 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-07 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-3088_1 | New_JAW-JT-SMG-3088 | JAW-JT-SMG-3088 | Central Java | Jawa Tengah | Kota Semarang | -6.9821 | 110.477 | New | New | New | Type B | MA | JAW-JT-SMG-3088 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | #N/A | S000056152 | S000056153 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-07 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-2556_1 | New_JAW-JT-SMG-2556 | JAW-JT-SMG-2556 | Central Java | Jawa Tengah | Kota Semarang | -6.9847 | 110.47 | New | New | New | Type B | MA | JAW-JT-SMG-2556 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | #N/A | S000056153 | S000056154 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-07 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-2539_1 | New_JAW-JT-SMG-2539 | JAW-JT-SMG-2539 | Central Java | Jawa Tengah | Kota Semarang | -6.9823 | 110.4599 | New | New | New | Type B | MA | JAW-JT-SMG-2539 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | #N/A | S000056154 | S000056155 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-08 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8616_1 | New_JAW-JT-SMG-8616 | JAW-JT-SMG-8616 | Central Java | Jawa Tengah | Kota Semarang | -6.9986 | 110.4567 | New | New | New | Type B | MA | JAW-JT-SMG-8616 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | #N/A | S000056155 | S000056156 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  |  |  | 2026-01-08 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8627_1 | New_JAW-JT-SMG-8627 | JAW-JT-SMG-8627 | Central Java | Jawa Tengah | Kota Semarang | -7.0108 | 110.4581 | New | New | New | Type B | MA | JAW-JT-SMG-8627 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | #N/A | S000056156 | S000056157 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-08 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8586_1 | New_JAW-JT-SMG-8586 | JAW-JT-SMG-8586 | Central Java | Jawa Tengah | Kota Semarang | -7.0079 | 110.4426 | New | New | New | Type B | MA | JAW-JT-SMG-8586 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | #N/A | S000056157 | S000056158 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-08 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8598_1 | New_JAW-JT-SMG-8598 | JAW-JT-SMG-8598 | Central Java | Jawa Tengah | Kota Semarang | -7.0065 | 110.4471 | New | New | New | Type B | MA | JAW-JT-SMG-8598 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | #N/A | S000056158 | S000056159 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-08 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-0621_1 | New_JAW-JT-SMG-0621 | JAW-JT-SMG-0621 | Central Java | Jawa Tengah | Kota Semarang | -7.0038 | 110.4387 | New | New | New | Type B | MA | JAW-JT-SMG-0621 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | #N/A | S000054812 | S000054813 | 10. Ready ATP / RFS | 2025-11-23 | 47 | 2025-11-09 |  | No |  | 2025-End Nov | YPTT | 2026-01-08 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-8566_1 | New_JAW-JT-SMG-8566 | JAW-JT-SMG-8566 | Central Java | Jawa Tengah | Kota Semarang | -7.006 | 110.4368 | New | New | New | Type B | MA | JAW-JT-SMG-8566 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | #N/A | S000054813 | S000054814 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2025-End Nov | YPTT | 2026-01-08 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-8555_1 | New_JAW-JT-SMG-8555 | JAW-JT-SMG-8555 | Central Java | Jawa Tengah | Kota Semarang | -7.006 | 110.4315 | New | New | New | Type B | MA | JAW-JT-SMG-8555 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | #N/A | S000054814 | S000054815 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2025-End Nov | YPTT | 2026-01-08 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | HOLD | New__1 | New_ |  | Central Java |  |  | #N/A | #N/A | New | New | New | Type B | MA | [5 empty] | - | - | - | - | New Purchase | New Ring 033 | Propose Drop, NO SPK | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | #N/A | #N/A | [11 empty] | 2026-01-08 | 2 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-2478_1 | New_JAW-JT-SMG-2478 | JAW-JT-SMG-2478 | Central Java | Jawa Tengah | Kota Semarang | -7.0351 | 110.4255 | New | New | New | Type B | MA | JAW-JT-SMG-2478 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | #N/A | S000054815 | S000054816 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2025-End Nov | YPTT | 2026-01-08 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-8559_1 | New_JAW-JT-SMG-8559 | JAW-JT-SMG-8559 | Central Java | Jawa Tengah | Kota Semarang | -7.0475 | 110.419 | New | New | New | Type B | MA | JAW-JT-SMG-8559 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | #N/A | S000054816 | S000054817 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2025-End Nov | YPTT | 2026-01-08 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-0625_1 | New_JAW-JT-SMG-0625 | JAW-JT-SMG-0625 | Central Java | Jawa Tengah | Kota Semarang | -7.0442 | 110.3931 | New | New | New | Type B | MA | JAW-JT-SMG-0625 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | #N/A | S000054817 | S000054818 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2025-End Nov | YPTT | 2026-01-08 | 2 |  |  | 2026 | 2025-11-13 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-8752_1 | New_JAW-JT-SMG-8752 | JAW-JT-SMG-8752 | Central Java | Jawa Tengah | Kota Semarang | -7.0484 | 110.396 | New | New | New | Type B | MA | JAW-JT-SMG-8752 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | #N/A | S000054818 | S000054819 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2025-End Nov | YPTT | 2026-01-08 | 2 |  |  | 2026 | 2025-11-12 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-8430_1 | New_JAW-JT-SMG-8430 | JAW-JT-SMG-8430 | Central Java | Jawa Tengah | Kota Semarang | -7.0575 | 110.3947 | New | New | New | Type B | MA | JAW-JT-SMG-8430 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | #N/A | S000054819 | S000054820 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2025-End Nov | YPTT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-13 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-8442_1 | New_JAW-JT-SMG-8442 | JAW-JT-SMG-8442 | Central Java | Jawa Tengah | Kota Semarang | -7.0593 | 110.3994 | New | New | New | Type B | MA | JAW-JT-SMG-8442 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | #N/A | - | S000054821 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2025-End Nov | YPTT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-11 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-2963_1 | New_JAW-JT-SMG-2963 | JAW-JT-SMG-2963 | Central Java | Jawa Tengah | Kota Semarang | -7.0848 | 110.3878 | New | New | New | Type B | MA | JAW-JT-SMG-2963 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | #N/A | S000054820 | S000054822 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2025-End Nov | YPTT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-10 | 2025-11-10 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-8415_1 | New_JAW-JT-SMG-8415 | JAW-JT-SMG-8415 | Central Java | Jawa Tengah | Kota Semarang | -7.09 | 110.3891 | New | New | New | Type B | MA | JAW-JT-SMG-8415 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | #N/A | S000054822 | S000054823 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2025-End Nov | YPTT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-13 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-0611_1 | New_JAW-JT-SMG-0611 | JAW-JT-SMG-0611 | Central Java | Jawa Tengah | Kota Semarang | -7.1037 | 110.3892 | New | New | New | Type B | MA | JAW-JT-SMG-0611 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | #N/A | S000054823 | S000054824 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2025-End Nov | YPTT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-14 | 2025-11-14 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-3064_1 | New_JAW-JT-SMG-3064 | JAW-JT-SMG-3064 | Central Java | Jawa Tengah | Kota Semarang | -7.0999 | 110.4048 | New | New | New | Type B | MA | JAW-JT-SMG-3064 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | #N/A | S000054824 | S000054825 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2025-End Nov | YPTT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-11 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-0630_1 | New_JAW-JT-SMG-0630 | JAW-JT-SMG-0630 | Central Java | Jawa Tengah | Kota Semarang | -7.0941 | 110.4071 | New | New | New | Type B | MA | JAW-JT-SMG-0630 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | #N/A | S000054825 | S000054826 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2025-End Nov | YPTT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-12 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-YO-YYK-0500_1 | New_JAW-YO-YYK-0500 | JAW-YO-YYK-0500 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7878 | 110.3642 | New | New | New | Type B | MA | JAW-YO-YYK-0500 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-09 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8283_1 | New_JAW-YO-YYK-8283 | JAW-YO-YYK-8283 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7881 | 110.3645 | New | New | New | Type B | MA | JAW-YO-YYK-8283 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-09 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0509_1 | New_JAW-YO-YYK-0509 | JAW-YO-YYK-0509 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7856 | 110.3666 | New | New | New | Type B | MA | JAW-YO-YYK-0509 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-09 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0511_1 | New_JAW-YO-YYK-0511 | JAW-YO-YYK-0511 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7827 | 110.3682 | New | New | New | Type B | MA | JAW-YO-YYK-0511 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-09 | 2 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0519_1 | New_JAW-YO-YYK-0519 | JAW-YO-YYK-0519 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7824 | 110.3696 | New | New | New | Type B | MA | JAW-YO-YYK-0519 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Propose Drop, NO SPK | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | #N/A | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-09 | 2 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0525_1 | New_JAW-YO-YYK-0525 | JAW-YO-YYK-0525 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7824 | 110.373 | New | New | New | Type B | MA | JAW-YO-YYK-0525 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | #N/A | [9 empty] | 2025-End Nov | CCSI | 2026-01-09 | 2 |  |  | 2026 |  |  | Not Started |  |  | Submitted | Approved |  | Site Already Dismantle | [31 empty] | #N/A |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-YO-YYK-0533_1 | New_JAW-YO-YYK-0533 | JAW-YO-YYK-0533 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7824 | 110.3771 | New | New | New | Type B | MA | JAW-YO-YYK-0533 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Propose Drop, NO SPK | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | #N/A | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-12 | 3 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0087_1 | New_JAW-YO-YYK-0087 | JAW-YO-YYK-0087 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7839 | 110.3772 | New | New | New | Type B | MA | JAW-YO-YYK-0087 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | #N/A | [9 empty] | 2025-End Nov | CCSI | 2026-01-12 | 3 |  |  | 2026 | 2025-11-10 | 2025-11-10 | Approved | 2025-11-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | 1 | CCSI
1 | 2 | HOLD | New__2 | New_ |  | Central Java |  |  | #N/A | #N/A | New | New | New | Type B | MA | [5 empty] | - | - | - | - | New Purchase | New Ring 034 | Propose Drop, NO SPK | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | #N/A | #N/A | [11 empty] | 2026-01-12 | 3 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8300_1 | New_JAW-YO-YYK-8300 | JAW-YO-YYK-8300 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7881 | 110.3758 | New | New | New | Type B | MA | JAW-YO-YYK-8300 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | #N/A | [9 empty] | 2025-End Nov | CCSI | 2026-01-12 | 3 |  |  | 2026 | 2025-11-21 | 2025-11-21 | Reviewing |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-YO-YYK-0077_1 | New_JAW-YO-YYK-0077 | JAW-YO-YYK-0077 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7871 | 110.3781 | New | New | New | Type B | MA | JAW-YO-YYK-0077 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-12 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8311_1 | New_JAW-YO-YYK-8311 | JAW-YO-YYK-8311 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7854 | 110.3805 | New | New | New | Type B | MA | JAW-YO-YYK-8311 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-12 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0544_1 | New_JAW-YO-YYK-0544 | JAW-YO-YYK-0544 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7825 | 110.3787 | New | New | New | Type B | MA | JAW-YO-YYK-0544 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-12 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0538_1 | New_JAW-YO-YYK-0538 | JAW-YO-YYK-0538 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7827 | 110.3802 | New | New | New | Type B | MA | JAW-YO-YYK-0538 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-12 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMN-2883_1 | New_JAW-JT-SMN-2883 | JAW-JT-SMN-2883 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7824 | 110.3817 | New | New | New | Type B | MA | JAW-JT-SMN-2883 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Propose Drop, NO SPK | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | #N/A | #N/A | [9 empty] | 2025-End Nov | CCSI | 2026-01-12 | 3 |  |  | 2026 | 2025-11-21 | 2025-11-21 | Reviewing | [37 empty] | #N/A |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-YO-YYK-8339_1 | New_JAW-YO-YYK-8339 | JAW-YO-YYK-8339 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7845 | 110.3852 | New | New | New | Type B | MA | JAW-YO-YYK-8339 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-12 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8323_1 | New_JAW-YO-YYK-8323 | JAW-YO-YYK-8323 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7868 | 110.3887 | New | New | New | Type B | MA | JAW-YO-YYK-8323 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-12 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0557_1 | New_JAW-YO-YYK-0557 | JAW-YO-YYK-0557 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7827 | 110.3871 | New | New | New | Type B | MA | JAW-YO-YYK-0557 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-12 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0537_1 | New_JAW-YO-YYK-0537 | JAW-YO-YYK-0537 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.7771 | 110.3774 | New | New | New | Type B | MA | JAW-YO-YYK-0537 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | #N/A | [9 empty] | 2026 |  | 2026-01-12 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-SMN-8387_1 | New_JAW-YO-SMN-8387 | JAW-YO-SMN-8387 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7759 | 110.3748 | New | New | New | Type B | MA | JAW-YO-SMN-8387 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-13 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-SMN-0080_1 | New_JAW-YO-SMN-0080 | JAW-YO-SMN-0080 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7782 | 110.3739 | New | New | New | Type B | MA | JAW-YO-SMN-0080 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-13 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-SMN-8378_1 | New_JAW-YO-SMN-8378 | JAW-YO-SMN-8378 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7704 | 110.366 | New | New | New | Type B | MA | JAW-YO-SMN-8378 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-13 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0085_1 | New_JAW-YO-YYK-0085 | JAW-YO-YYK-0085 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7713 | 110.3553 | New | New | New | Type B | MA | JAW-YO-YYK-0085 |  |  |  |  | - | - | - | - | New Purchase | New Ring 035 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000019970 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-13 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8273_1 | New_JAW-YO-YYK-8273 | JAW-YO-YYK-8273 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7746 | 110.3609 | New | New | New | Type B | MA | JAW-YO-YYK-8273 |  |  |  |  | - | - | - | - | New Purchase | New Ring 035 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000019970 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-13 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0489_1 | New_JAW-YO-YYK-0489 | JAW-YO-YYK-0489 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7784 | 110.3607 | New | New | New | Type B | MA | JAW-YO-YYK-0489 |  |  |  |  | - | - | - | - | New Purchase | New Ring 035 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000019970 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-13 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-SMN-0177_1 | New_JAW-YO-SMN-0177 | JAW-YO-SMN-0177 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7778 | 110.3549 | New | New | New | Type B | MA | JAW-YO-SMN-0177 |  |  |  |  | - | - | - | - | New Purchase | New Ring 035 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000019970 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-13 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8268_1 | New_JAW-YO-YYK-8268 | JAW-YO-YYK-8268 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7806 | 110.351 | New | New | New | Type B | MA | JAW-YO-YYK-8268 |  |  |  |  | - | - | - | - | New Purchase | New Ring 035 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000019970 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-13 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0481_1 | New_JAW-YO-YYK-0481 | JAW-YO-YYK-0481 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7843 | 110.3544 | New | New | New | Type B | MA | JAW-YO-YYK-0481 |  |  |  |  | - | - | - | - | New Purchase | New Ring 035 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000019970 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-13 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8281_1 | New_JAW-YO-YYK-8281 | JAW-YO-YYK-8281 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7806 | 110.3623 | New | New | New | Type B | MA | JAW-YO-YYK-8281 |  |  |  |  | - | - | - | - | New Purchase | New Ring 035 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000019970 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-13 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0147_1 | New_JAW-YO-BTL-0147 | JAW-YO-BTL-0147 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8742 | 110.3471 | New | New | New | Type B | MA | JAW-YO-BTL-0147 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020319 | #N/A | [9 empty] | 2026 |  | 2026-01-13 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3243_1 | New_JAW-JI-BKL-3243 | JAW-JI-BKL-3243 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8588 | 110.3671 | New | New | New | Type B | MA | JAW-JI-BKL-3243 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020319 | #N/A | [11 empty] | 2026-01-13 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3157_1 | New_JAW-JI-BKL-3157 | JAW-JI-BKL-3157 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8472 | 110.3589 | New | New | New | Type B | MA | JAW-JI-BKL-3157 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020319 | #N/A | [11 empty] | 2026-01-13 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3232_1 | New_JAW-JI-BKL-3232 | JAW-JI-BKL-3232 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8431 | 110.3513 | New | New | New | Type B | MA | JAW-JI-BKL-3232 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | #N/A | [11 empty] | 2026-01-14 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8264_1 | New_JAW-YO-YYK-8264 | JAW-YO-YYK-8264 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8182 | 110.3559 | New | New | New | Type B | MA | JAW-YO-YYK-8264 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-14 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8282_1 | New_JAW-YO-YYK-8282 | JAW-YO-YYK-8282 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8176 | 110.3514 | New | New | New | Type B | MA | JAW-YO-YYK-8282 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-14 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0127_1 | New_JAW-YO-YYK-0127 | JAW-YO-YYK-0127 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8053 | 110.3563 | New | New | New | Type B | MA | JAW-YO-YYK-0127 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-14 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0075_1 | New_JAW-YO-YYK-0075 | JAW-YO-YYK-0075 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8079 | 110.3607 | New | New | New | Type B | MA | JAW-YO-YYK-0075 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-14 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8298_1 | New_JAW-YO-YYK-8298 | JAW-YO-YYK-8298 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.818 | 110.3732 | New | New | New | Type B | MA | JAW-YO-YYK-8298 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-14 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8302_1 | New_JAW-YO-YYK-8302 | JAW-YO-YYK-8302 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8105 | 110.3768 | New | New | New | Type B | MA | JAW-YO-YYK-8302 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-14 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0551_1 | New_JAW-YO-YYK-0551 | JAW-YO-YYK-0551 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8093 | 110.3829 | New | New | New | Type B | MA | JAW-YO-YYK-0551 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-14 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8340_1 | New_JAW-YO-YYK-8340 | JAW-YO-YYK-8340 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8126 | 110.3858 | New | New | New | Type B | MA | JAW-YO-YYK-8340 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-14 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8327_1 | New_JAW-YO-YYK-8327 | JAW-YO-YYK-8327 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8145 | 110.3911 | New | New | New | Type B | MA | JAW-YO-YYK-8327 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | #N/A | [11 empty] | 2026-01-14 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0060_1 | New_JAW-YO-YYK-0060 | JAW-YO-YYK-0060 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8168 | 110.3966 | New | New | New | Type B | MA | JAW-YO-YYK-0060 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-14 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0501_1 | New_JAW-YO-YYK-0501 | JAW-YO-YYK-0501 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7968 | 110.3649 | New | New | New | Type B | MA | JAW-YO-YYK-0501 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-14 | 3 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8286_1 | New_JAW-YO-YYK-8286 | JAW-YO-YYK-8286 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7978 | 110.3658 | New | New | New | Type B | MA | JAW-YO-YYK-8286 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | #N/A | [9 empty] | 2025-End Nov | CCSI | 2026-01-14 | 3 |  |  | 2026 | 2025-11-21 | 2025-11-21 | Reviewing | [37 empty] | #N/A |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-YO-YYK-8315_1 | New_JAW-YO-YYK-8315 | JAW-YO-YYK-8315 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7981 | 110.3684 | New | New | New | Type B | MA | JAW-YO-YYK-8315 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-15 | 3 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0517_1 | New_JAW-YO-YYK-0517 | JAW-YO-YYK-0517 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7982 | 110.3689 | New | New | New | Type B | MA | JAW-YO-YYK-0517 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-15 | 3 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0065_1 | New_JAW-YO-YYK-0065 | JAW-YO-YYK-0065 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8017 | 110.3714 | New | New | New | Type B | MA | JAW-YO-YYK-0065 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-15 | 3 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0086_1 | New_JAW-YO-YYK-0086 | JAW-YO-YYK-0086 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7974 | 110.3724 | New | New | New | Type B | MA | JAW-YO-YYK-0086 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | #N/A | [9 empty] | 2025-End Nov | CCSI | 2026-01-15 | 3 |  |  | 2026 | 2025-11-10 | 2025-11-10 | Approved | 2025-11-17 | [36 empty] | #N/A |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-YO-YYK-8312_1 | New_JAW-YO-YYK-8312 | JAW-YO-YYK-8312 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7915 | 110.3816 | New | New | New | Type B | MA | JAW-YO-YYK-8312 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-15 | 3 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0556_1 | New_JAW-YO-YYK-0556 | JAW-YO-YYK-0556 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7899 | 110.3861 | New | New | New | Type B | MA | JAW-YO-YYK-0556 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-15 | 3 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8331_1 | New_JAW-YO-YYK-8331 | JAW-YO-YYK-8331 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7942 | 110.3926 | New | New | New | Type B | MA | JAW-YO-YYK-8331 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-15 | 3 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0558_1 | New_JAW-YO-YYK-0558 | JAW-YO-YYK-0558 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8016 | 110.3883 | New | New | New | Type B | MA | JAW-YO-YYK-0558 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-15 | 3 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8321_1 | New_JAW-YO-YYK-8321 | JAW-YO-YYK-8321 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8022 | 110.3885 | New | New | New | Type B | MA | JAW-YO-YYK-8321 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | #N/A | [11 empty] | 2026-01-15 | 3 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8330_1 | New_JAW-YO-YYK-8330 | JAW-YO-YYK-8330 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8048 | 110.392 | New | New | New | Type B | MA | JAW-YO-YYK-8330 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-15 | 3 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8334_1 | New_JAW-YO-YYK-8334 | JAW-YO-YYK-8334 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8061 | 110.3947 | New | New | New | Type B | MA | JAW-YO-YYK-8334 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-15 | 3 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0082_1 | New_JAW-YO-YYK-0082 | JAW-YO-YYK-0082 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8067 | 110.3987 | New | New | New | Type B | MA | JAW-YO-YYK-0082 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-15 | 3 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8401_1 | New_JAW-JT-DMK-8401 | JAW-JT-DMK-8401 | Central Java | Jawa Tengah | Demak | -6.9193 | 110.6338 | Insert | New | New | Type B | MA | JAW-JT-DMK-8401 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | #N/A | S000055782 | S000055783 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2026-01-15 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8390_1 | New_JAW-JT-DMK-8390 | JAW-JT-DMK-8390 | Central Java | Jawa Tengah | Demak | -6.7785 | 110.6215 | Insert | New | New | Type B | MA | JAW-JT-DMK-8390 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, NO SPK | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-01-16 | 3 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8408_1 | New_JAW-JT-DMK-8408 | JAW-JT-DMK-8408 | Central Java | Jawa Tengah | Demak | -6.8572 | 110.6438 | Insert | New | New | Type B | MA | JAW-JT-DMK-8408 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, NO SPK | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-01-16 | 3 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8314_1 | New_JAW-JT-DMK-8314 | JAW-JT-DMK-8314 | Central Java | Jawa Tengah | Demak | -7.0758 | 110.5172 | Insert | New | New | Type B | MA | JAW-JT-DMK-8314 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, NO SPK | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-01-16 | 3 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-4130_1 | New_JAW-JT-DMK-4130 | JAW-JT-DMK-4130 | Central Java | Jawa Tengah | Demak | -7.116 | 110.565 | Insert | New | New | Type B | MA | JAW-JT-DMK-4130 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, NO SPK | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-01-16 | 3 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8325_1 | New_JAW-JT-DMK-8325 | JAW-JT-DMK-8325 | Central Java | Jawa Tengah | Demak | -7.0447 | 110.5279 | Insert | New | New | Type B | MA | JAW-JT-DMK-8325 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | #N/A | S000055770 | S000055771 | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  | 2026 |  | 2026-01-16 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8326_1 | New_JAW-JT-DMK-8326 | JAW-JT-DMK-8326 | Central Java | Jawa Tengah | Demak | -7.0348 | 110.528 | Insert | New | New | Type B | MA | JAW-JT-DMK-8326 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, NO SPK | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-01-16 | 3 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8420_1 | New_JAW-JT-PWD-8420 | JAW-JT-PWD-8420 | Central Java | Jawa Tengah | Grobogan | -7.0144 | 110.9109 | Insert | New | New | Type B | MA | JAW-JT-PWD-8420 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020150 | R0000020150 | S000054773 | S000054774 | 10. Ready ATP / RFS | 2025-11-16 | 46 | 2025-11-16 |  | Yes |  | 2026 | GPA | 2026-01-16 | 3 |  |  | 2026 | 2025-11-12 |  | #N/A | [14 empty] | 2.1. Permit Letter Release | DCITS | [19 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8455_1 | New_JAW-JT-PWD-8455 | JAW-JT-PWD-8455 | Central Java | Jawa Tengah | Grobogan | -7.0834 | 110.9477 | Insert | New | New | Type B | MA | JAW-JT-PWD-8455 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020151 | R0000020151 | S000054775 | S000054776 | 10. Ready ATP / RFS | 2025-11-16 | 46 | 2025-11-23 |  | No |  | 2025-624 sites | GPA | 2026-01-16 | 3 |  |  | 2026 | 2025-11-13 |  | #N/A | [14 empty] | 2.1. Permit Letter Release | GPA | [19 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8545_1 | New_JAW-JT-PWD-8545 | JAW-JT-PWD-8545 | Central Java | Jawa Tengah | Grobogan | -7.0966 | 111.0817 | Insert | New | New | Type B | MA | JAW-JT-PWD-8545 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020152 | #N/A | S000054777 | S000054778 | 12. NY TERMINATION | 2025-11-16 | 46 | 2025-11-09 |  | Yes |  | 2025-624 sites | GPA | 2026-01-16 | 3 |  |  | 2026 | 2025-11-13 |  | #N/A | [20 empty] | DCITS | [14 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8576_1 | New_JAW-JT-PWD-8576 | JAW-JT-PWD-8576 | Central Java | Jawa Tengah | Grobogan | -7.13 | 111.1469 | Insert | New | New | Type B | MA | JAW-JT-PWD-8576 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020152 | #N/A | S000054778 | S000054779 | 12. NY TERMINATION | 2025-11-16 | 46 | 2025-11-09 |  | Yes |  | 2025-624 sites | GPA | 2026-01-16 | 3 |  |  | 2026 | 2025-11-12 |  | #N/A | [20 empty] | DCITS | [14 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8525_1 | New_JAW-JT-PWD-8525 | JAW-JT-PWD-8525 | Central Java | Jawa Tengah | Grobogan | -7.1101 | 111.0502 | Insert | New | New | Type B | MA | JAW-JT-PWD-8525 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020153 | #N/A | S000054780 | S000054781 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2025-624 sites | GPA | 2026-01-16 | 3 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8465_1 | New_JAW-JT-PWD-8465 | JAW-JT-PWD-8465 | Central Java | Jawa Tengah | Grobogan | -7.1155 | 110.9524 | Insert | New | New | Type B | MA | JAW-JT-PWD-8465 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020154 | #N/A | S000054782 | S000054783 | 12. NY TERMINATION | 2025-11-23 | 47 | 2025-11-09 |  | No |  | 2026 | GPA | 2026-01-16 | 3 |  |  | 2026 | 2025-11-10 | 2025-11-17 | Reviewing | [20 empty] | DCITS | [14 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8419_1 | New_JAW-JT-PWD-8419 | JAW-JT-PWD-8419 | Central Java | Jawa Tengah | Grobogan | -7.1205 | 110.9095 | Insert | New | New | Type B | MA | JAW-JT-PWD-8419 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020154 | #N/A | S000054783 | S000054784 | 12. NY TERMINATION | 2025-11-23 | 47 | 2025-11-09 |  | No |  | 2025-624 sites | GPA | 2026-01-16 | 3 |  |  | 2026 | 2025-11-11 | 2025-11-21 | Reviewing | [20 empty] | DCITS | [14 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8429_1 | New_JAW-JT-PWD-8429 | JAW-JT-PWD-8429 | Central Java | Jawa Tengah | Grobogan | -7.128 | 110.9165 | Insert | New | New | Type B | MA | JAW-JT-PWD-8429 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020155 | #N/A | S000054785 | S000054786 | 12. NY TERMINATION | 2026-01-12 08:00 | 3 |  |  | No |  |  |  | 2026-01-19 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8510_1 | New_JAW-JT-PWD-8510 | JAW-JT-PWD-8510 | Central Java | Jawa Tengah | Grobogan | -7.1045 | 111.0254 | Insert | New | New | Type B | MA | JAW-JT-PWD-8510 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020156 | #N/A | S000054787 | S000054788 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2026-01-19 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8527_1 | New_JAW-JT-PWD-8527 | JAW-JT-PWD-8527 | Central Java | Jawa Tengah | Grobogan | -7.1249 | 111.0559 | Insert | New | New | Type B | MA | JAW-JT-PWD-8527 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020156 | #N/A | S000054788 | S000054789 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-624 sites |  | 2026-01-19 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8559_1 | New_JAW-JT-PWD-8559 | JAW-JT-PWD-8559 | Central Java | Jawa Tengah | Grobogan | -7.1052 | 111.1078 | Insert | New | New | Type B | MA | JAW-JT-PWD-8559 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020157 | #N/A | S000054790 | S000054791 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-624 sites |  | 2026-01-19 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8534_1 | New_JAW-JT-PWD-8534 | JAW-JT-PWD-8534 | Central Java | Jawa Tengah | Grobogan | -7.0793 | 111.0705 | Insert | New | New | Type B | MA | JAW-JT-PWD-8534 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020158 | R0000020158 | S000054792 | S000054793 | 10. Ready ATP / RFS | 2025-11-30 | 48 | 2025-11-23 |  | No |  | 2025-624 sites |  | 2026-01-19 | 4 |  |  | 2026 |  |  | #N/A | [14 empty] | 0.1. NY Visit | - | [19 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8497_1 | New_JAW-JT-PWD-8497 | JAW-JT-PWD-8497 | Central Java | Jawa Tengah | Grobogan | -7.0814 | 111.0208 | Insert | New | New | Type B | MA | JAW-JT-PWD-8497 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020159 | #N/A | S000054794 | S000054795 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2026 |  | 2026-01-19 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8476_1 | New_JAW-JT-PWD-8476 | JAW-JT-PWD-8476 | Central Java | Jawa Tengah | Grobogan | -7.0815 | 110.9964 | Insert | New | New | Type B | MA | JAW-JT-PWD-8476 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-01-19 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8473_1 | New_JAW-JT-PWD-8473 | JAW-JT-PWD-8473 | Central Java | Jawa Tengah | Grobogan | -7.0653 | 110.9876 | Insert | New | New | Type B | MA | JAW-JT-PWD-8473 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-01-19 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8345_1 | New_JAW-JT-PWD-8345 | JAW-JT-PWD-8345 | Central Java | Jawa Tengah | Grobogan | -7.0356 | 110.7381 | Insert | New | New | Type B | MA | JAW-JT-PWD-8345 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020350 | #N/A | S000055190 | S000055191 | 12. NY TERMINATION | 2025-11-09 | 45 | 2025-11-09 |  | Yes |  | 2026 | GPA | 2026-01-19 | 4 |  |  | 2026 |  |  | #N/A | [20 empty] | DCITS | [14 empty] | 2025-11-14 | 46 | 2025-11-14 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8348_1 | New_JAW-JT-PWD-8348 | JAW-JT-PWD-8348 | Central Java | Jawa Tengah | Grobogan | -7.0537 | 110.7437 | Insert | New | New | Type B | MA | JAW-JT-PWD-8348 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020350 | #N/A | S000055191 | S000055192 | 12. NY TERMINATION | 2025-11-09 | 45 | 2025-11-09 |  | Yes |  | 2026 | GPA | 2026-01-19 | 4 |  |  | 2026 |  |  | #N/A | [20 empty] | DCITS | [14 empty] | 2025-11-14 | 46 | 2025-11-14 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8365_1 | New_JAW-JT-PWD-8365 | JAW-JT-PWD-8365 | Central Java | Jawa Tengah | Grobogan | -7.0897 | 110.7869 | Insert | New | New | Type B | MA | JAW-JT-PWD-8365 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020160 | R0000020160 | S000054796 | S000054797 | 10. Ready ATP / RFS | 2025-11-09 | 45 | 2025-11-09 | 2025-11-09 | No |  | 2026 | GPA | 2026-01-19 | 4 |  |  | 2026 |  |  | #N/A | [14 empty] | 2.1. Permit Letter Release | DCITS |  |  |  |  | DCITS | [14 empty] | 2025-11-14 | 46 | 2025-11-14 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8374_1 | New_JAW-JT-PWD-8374 | JAW-JT-PWD-8374 | Central Java | Jawa Tengah | Grobogan | -7.068 | 110.8082 | Insert | New | New | Type B | MA | JAW-JT-PWD-8374 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020161 | R0000020161 | S000054798 | S000054799 | 10. Ready ATP / RFS | 2025-11-09 | 45 | 2025-11-16 |  | No |  | 2026 | GPA | 2026-01-19 | 4 |  |  | 2026 | 2025-11-11 |  | #N/A | [14 empty] | 2.1. Permit Letter Release | DCITS | [19 empty] | 2025-11-14 | 46 | 2025-11-14 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8427_1 | New_JAW-JT-PWD-8427 | JAW-JT-PWD-8427 | Central Java | Jawa Tengah | Grobogan | -7.0962 | 110.9143 | Insert | New | New | Type B | MA | JAW-JT-PWD-8427 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020162 | R0000020162 | S000054800 | S000054801 | 10. Ready ATP / RFS | 2025-11-09 | 45 | 2025-11-16 |  | No |  | 2025-624 sites | GPA | 2026-01-19 | 4 |  |  | 2026 | 2025-11-12 |  | #N/A | [14 empty] | 0.1. NY Visit | GPA | [19 empty] | 2025-11-14 | 46 | 2025-11-14 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8379_1 | New_JAW-JT-PWD-8379 | JAW-JT-PWD-8379 | Central Java | Jawa Tengah | Grobogan | -7.0699 | 110.8249 | Insert | New | New | Type B | MA | JAW-JT-PWD-8379 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020163 | R0000020163 | S000054802 | S000054803 | 10. Ready ATP / RFS | 2025-11-09 | 45 | 2025-11-09 | 2025-11-09 | No |  | 2026 | GPA | 2026-01-20 | 4 |  |  | 2026 | 2025-11-12 |  | #N/A | [14 empty] | 2.1. Permit Letter Release | DCITS |  |  |  |  | DCITS | [14 empty] | 2025-11-14 | 46 | 2025-11-14 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8317_1 | New_JAW-JT-JPA-8317 | JAW-JT-JPA-8317 | Central Java | Jawa Tengah | Jepara | -6.585 | 110.6662 | Insert | New | New | Type B | MA | JAW-JT-JPA-8317 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019839 | #N/A | S000054260 | S000054261 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2026 |  | 2026-01-20 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8331_1 | New_JAW-JT-JPA-8331 | JAW-JT-JPA-8331 | Central Java | Jawa Tengah | Jepara | -6.6078 | 110.6796 | Insert | New | New | Type B | MA | JAW-JT-JPA-8331 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019840 | #N/A | S000054262 | S000054263 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2026 |  | 2026-01-20 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8464_1 | New_JAW-JT-JPA-8464 | JAW-JT-JPA-8464 | Central Java | Jawa Tengah | Jepara | -6.4933 | 110.9024 | Insert | New | New | Type B | MA | JAW-JT-JPA-8464 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019841 | #N/A | S000054264 | S000054265 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2026 |  | 2026-01-20 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8460_1 | New_JAW-JT-JPA-8460 | JAW-JT-JPA-8460 | Central Java | Jawa Tengah | Jepara | -6.5067 | 110.8922 | Insert | New | New | Type B | MA | JAW-JT-JPA-8460 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019841 | #N/A | S000054265 | S000054266 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2026 |  | 2026-01-20 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8367_1 | New_JAW-JT-JPA-8367 | JAW-JT-JPA-8367 | Central Java | Jawa Tengah | Jepara | -6.7496 | 110.714 | Insert | New | New | Type B | MA | JAW-JT-JPA-8367 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019842 | R0000019842 | S000054267 | S000054268 | 10. Ready ATP / RFS | 2025-11-30 | 48 | 2025-11-09 | 2025-11-09 | No |  | 2026 |  | 2026-01-20 | 4 |  |  | 2026 |  |  | #N/A | [14 empty] | 2.1. Permit Letter Release | DCITS |  |  |  |  | DCITS | [14 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8362_1 | New_JAW-JT-JPA-8362 | JAW-JT-JPA-8362 | Central Java | Jawa Tengah | Jepara | -6.5633 | 110.7121 | Insert | New | New | Type B | MA | JAW-JT-JPA-8362 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019843 | #N/A | S000054269 | S000054270 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2026 |  | 2026-01-20 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-3383_1 | New_JAW-JT-DMK-3383 | JAW-JT-DMK-3383 | Central Java | Jawa Tengah | Jepara | -6.7064 | 110.6223 | Insert | New | New | Type B | MA | JAW-JT-DMK-3383 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020456 | #N/A | - | S000055963 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2026 |  | 2026-01-20 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8303_1 | New_JAW-JT-JPA-8303 | JAW-JT-JPA-8303 | Central Java | Jawa Tengah | Jepara | -6.7118 | 110.6418 | Insert | New | New | Type B | MA | JAW-JT-JPA-8303 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020456 | #N/A | S000055963 | S000055964 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2026 |  | 2026-01-20 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8403_1 | New_JAW-JT-JPA-8403 | JAW-JT-JPA-8403 | Central Java | Jawa Tengah | Jepara | -6.6706 | 110.7478 | Insert | New | New | Type B | MA | JAW-JT-JPA-8403 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019844 | #N/A | S000054271 | S000054272 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2026 |  | 2026-01-20 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8354_1 | New_JAW-JT-JPA-8354 | JAW-JT-JPA-8354 | Central Java | Jawa Tengah | Jepara | -6.5711 | 110.7011 | Insert | New | New | Type B | MA | JAW-JT-JPA-8354 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019845 | #N/A | S000054273 | S000054274 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2026 |  | 2026-01-20 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8469_1 | New_JAW-JT-JPA-8469 | JAW-JT-JPA-8469 | Central Java | Jawa Tengah | Jepara | -6.4205 | 110.9727 | Insert | New | New | Type B | MA | JAW-JT-JPA-8469 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019846 | #N/A | S000054275 | S000054276 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2026 | YPTT | 2026-01-20 | 4 |  |  | 2026 | 2025-11-21 | 2025-11-21 | Reviewing | [37 empty] | #N/A |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-4117_1 | New_JAW-JT-JPA-4117 | JAW-JT-JPA-4117 | Central Java | Jawa Tengah | Jepara | -6.4932 | 110.8604 | Insert | New | New | Type B | MA | JAW-JT-JPA-4117 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020457 | #N/A | S000055965 | S000055966 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2026 |  | 2026-01-20 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8340_1 | New_JAW-JT-JPA-8340 | JAW-JT-JPA-8340 | Central Java | Jawa Tengah | Jepara | -6.6646 | 110.6916 | Insert | New | New | Type B | MA | JAW-JT-JPA-8340 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020458 | #N/A | S000055967 | S000055968 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2026 | YPTT | 2026-01-21 | 4 |  |  | 2026 | 2025-11-17 | 2025-11-17 | Reviewing | [37 empty] | #N/A |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8314_1 | New_JAW-JT-JPA-8314 | JAW-JT-JPA-8314 | Central Java | Jawa Tengah | Jepara | -6.668 | 110.6639 | Insert | New | New | Type B | MA | JAW-JT-JPA-8314 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019847 | #N/A | S000054277 | S000054278 | 12. NY TERMINATION | 2025-11-30 | 48 | 2025-11-09 |  | No |  |  |  | 2026-01-21 | 4 |  |  | 2026 |  |  | #N/A | [20 empty] | DCITS | [14 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8396_1 | New_JAW-JT-JPA-8396 | JAW-JT-JPA-8396 | Central Java | Jawa Tengah | Jepara | -6.4508 | 110.7423 | Insert | New | New | Type B | MA | JAW-JT-JPA-8396 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019848 | #N/A | S000054279 | S000054280 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2026 |  | 2026-01-21 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8333_1 | New_JAW-JT-JPA-8333 | JAW-JT-JPA-8333 | Central Java | Jawa Tengah | Jepara | -6.585 | 110.6811 | Insert | New | New | Type B | MA | JAW-JT-JPA-8333 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019849 | #N/A | S000054281 | S000054282 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  |  |  | 2026-01-21 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8265_1 | New_JAW-YO-YYK-8265 | JAW-YO-YYK-8265 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7945 | 110.3565 | Insert | New | New | Type B | MA | JAW-YO-YYK-8265 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-21 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0166_1 | New_JAW-YO-BTL-0166 | JAW-YO-BTL-0166 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.7972 | 110.3459 | Insert | New | New | Type B | MA | JAW-YO-BTL-0166 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-01-21 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-SMN-0154_1 | New_JAW-YO-SMN-0154 | JAW-YO-SMN-0154 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8002 | 110.3316 | Insert | New | New | Type B | MA | JAW-YO-SMN-0154 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_3 1x25G/10G LR + 1x10G ZR + 6x1G LR |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-01-21 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8681_1 | New_JAW-JT-SMG-8681 | JAW-JT-SMG-8681 | Central Java | Jawa Tengah | Kota Semarang | -6.969 | 110.4811 | Insert | New | New | Type B | MA | JAW-JT-SMG-8681 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020410 | #N/A | S000055800 | S000055801 | 12. NY TERMINATION | 2026-01-12 07:55 | 3 |  |  | No |  |  |  | 2026-01-21 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8498_1 | New_JAW-JT-SMG-8498 | JAW-JT-SMG-8498 | Central Java | Jawa Tengah | Kota Semarang | -6.978 | 110.4169 | Insert | New | New | Type B | MA | JAW-JT-SMG-8498 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020411 | #N/A | S000055803 | S000055802 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | No |  | 2025-End Nov |  | 2026-01-21 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-25 | 48 | 2025-11-25 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-2364_1 | New_JAW-JT-SMG-2364 | JAW-JT-SMG-2364 | Central Java | Jawa Tengah | Kota Semarang | -7.0076 | 110.3784 | Insert | New | New | Type B | MA | JAW-JT-SMG-2364 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020412 | #N/A | S000055804 | S000055805 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | Yes |  | 2025-End Nov |  | 2026-01-21 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8719_1 | New_JAW-JT-SMG-8719 | JAW-JT-SMG-8719 | Central Java | Jawa Tengah | Kota Semarang | -6.9838 | 110.357 | Insert | New | New | Type B | MA | JAW-JT-SMG-8719 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020413 | #N/A | S000055806 | S000055807 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | No |  | 2025-End Nov |  | 2026-01-21 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-25 | 48 | 2025-11-25 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8725_1 | New_JAW-JT-SMG-8725 | JAW-JT-SMG-8725 | Central Java | Jawa Tengah | Kota Semarang | -6.9863 | 110.3478 | Insert | New | New | Type B | MA | JAW-JT-SMG-8725 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020414 | #N/A | S000055808 | S000055809 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | No |  | 2025-End Nov |  | 2026-01-21 | 4 |  |  | 2026 |  |  | In Progress | [35 empty] | 2025-11-25 | 48 | 2025-11-25 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-2521_1 | New_JAW-JT-SMG-2521 | JAW-JT-SMG-2521 | Central Java | Jawa Tengah | Kota Semarang | -7.0503 | 110.4453 | Insert | New | New | Type B | MA | JAW-JT-SMG-2521 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020415 | R0000020415 | S000055810 | S000055811 | 10. Ready ATP / RFS | 2025-12-14 | 50 | 2025-11-09 | 2025-11-09 | No |  | 2025-End Nov |  | 2026-01-21 | 4 |  |  | 2026 |  |  | In Progress | [14 empty] | 2.1. Permit Letter Release | DCITS |  |  |  |  | DCITS | [14 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-3472_1 | New_JAW-JT-SMG-3472 | JAW-JT-SMG-3472 | Central Java | Jawa Tengah | Kota Semarang | -7.0204 | 110.3359 | Insert | New | New | Type B | MA | JAW-JT-SMG-3472 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020416 | R0000020416 | S000055812 | S000055813 | 10. Ready ATP / RFS | 2025-11-30 | 48 | 2025-11-23 |  | No |  | 2025-End Nov |  | 2026-01-22 | 4 |  |  | 2026 |  |  | #N/A | [14 empty] | 0.1. NY Visit | - | [19 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-2333_1 | New_JAW-JT-SMG-2333 | JAW-JT-SMG-2333 | Central Java | Jawa Tengah | Kota Semarang | -7.07 | 110.334 | Insert | New | New | Type B | MA | JAW-JT-SMG-2333 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020417 | #N/A | S000055814 | S000055815 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-22 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8726_1 | New_JAW-JT-SMG-8726 | JAW-JT-SMG-8726 | Central Java | Jawa Tengah | Kota Semarang | -7.0125 | 110.3774 | Insert | New | New | Type B | MA | JAW-JT-SMG-8726 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020418 | #N/A | S000055816 | S000055817 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-22 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8405_1 | New_JAW-JT-SMG-8405 | JAW-JT-SMG-8405 | Central Java | Jawa Tengah | Kota Semarang | -7.007 | 110.3691 | Insert | New | New | Type B | MA | JAW-JT-SMG-8405 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020418 | #N/A | S000055817 | S000055818 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-22 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8661_1 | New_JAW-JT-SMG-8661 | JAW-JT-SMG-8661 | Central Java | Jawa Tengah | Kota Semarang | -7.0196 | 110.4718 | Insert | New | New | Type B | MA | JAW-JT-SMG-8661 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020419 | #N/A | S000055819 | S000055820 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-22 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8502_1 | New_JAW-JT-SMG-8502 | JAW-JT-SMG-8502 | Central Java | Jawa Tengah | Kota Semarang | -7.0016 | 110.4202 | Insert | New | New | Type B | MA | JAW-JT-SMG-8502 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020420 | #N/A | S000055821 | S000055822 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-22 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8278_1 | New_JAW-YO-YYK-8278 | JAW-YO-YYK-8278 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7701 | 110.3616 | Insert | New | New | Type B | MA | JAW-YO-YYK-8278 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-22 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-25 | 48 | 2025-11-25 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8540_1 | New_JAW-JT-UNR-8540 | JAW-JT-UNR-8540 | Central Java | Jawa Tengah | Semarang | -7.2463 | 110.5255 | Insert | New | New | Type B | MA | JAW-JT-UNR-8540 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  |  | #N/A | [9 empty] | Mid Dec 25 |  | 2026-01-22 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8545_1 | New_JAW-JT-UNR-8545 | JAW-JT-UNR-8545 | Central Java | Jawa Tengah | Semarang | -7.2364 | 110.5374 | Insert | New | New | Type B | MA | JAW-JT-UNR-8545 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  |  | #N/A | [9 empty] | Mid Dec 25 |  | 2026-01-22 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8484_1 | New_JAW-JT-UNR-8484 | JAW-JT-UNR-8484 | Central Java | Jawa Tengah | Semarang | -7.1781 | 110.4276 | Insert | New | New | Type B | MA | JAW-JT-UNR-8484 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  |  | #N/A | [9 empty] | Mid Dec 25 |  | 2026-01-22 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-2693_1 | New_JAW-JT-UNR-2693 | JAW-JT-UNR-2693 | Central Java | Jawa Tengah | Semarang | -7.2106 | 110.4142 | Insert | New | New | Type B | MA | JAW-JT-UNR-2693 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  |  | #N/A | [9 empty] | Mid Dec 25 |  | 2026-01-22 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8518_1 | New_JAW-JT-UNR-8518 | JAW-JT-UNR-8518 | Central Java | Jawa Tengah | Semarang | -7.1853 | 110.4669 | Insert | New | New | Type B | MA | JAW-JT-UNR-8518 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  |  | #N/A | [9 empty] | Mid Dec 25 |  | 2026-01-22 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-4119_1 | New_JAW-JT-UNR-4119 | JAW-JT-UNR-4119 | Central Java | Jawa Tengah | Semarang | -7.2746 | 110.4825 | Insert | New | New | Type B | MA | JAW-JT-UNR-4119 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  |  | #N/A | [9 empty] | Mid Dec 25 |  | 2026-01-22 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-4118_1 | New_JAW-JT-UNR-4118 | JAW-JT-UNR-4118 | Central Java | Jawa Tengah | Semarang | -7.2568 | 110.5122 | Insert | New | New | Type B | MA | JAW-JT-UNR-4118 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, NO SPK | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  |  | #N/A | [9 empty] | Mid Dec 25 |  | 2026-01-23 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8546_1 | New_JAW-JT-UNR-8546 | JAW-JT-UNR-8546 | Central Java | Jawa Tengah | Semarang | -7.4045 | 110.5388 | Insert | New | New | Type B | MA | JAW-JT-UNR-8546 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-23 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8560_1 | New_JAW-JT-UNR-8560 | JAW-JT-UNR-8560 | Central Java | Jawa Tengah | Semarang | -7.4203 | 110.5865 | Insert | New | New | Type B | MA | JAW-JT-UNR-8560 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-23 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-25 | 48 | 2025-11-25 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8534_1 | New_JAW-JT-UNR-8534 | JAW-JT-UNR-8534 | Central Java | Jawa Tengah | Semarang | -7.2898 | 110.5145 | Insert | New | New | Type B | MA | JAW-JT-UNR-8534 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-23 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-25 | 48 | 2025-11-25 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-2792_1 | New_JAW-JT-UNR-2792 | JAW-JT-UNR-2792 | Central Java | Jawa Tengah | Semarang | -7.4759 | 110.6461 | Insert | New | New | Type B | MA | JAW-JT-UNR-2792 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-23 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-25 | 48 | 2025-11-25 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8535_1 | New_JAW-JT-UNR-8535 | JAW-JT-UNR-8535 | Central Java | Jawa Tengah | Semarang | -7.3945 | 110.5145 | Insert | New | New | Type B | MA | JAW-JT-UNR-8535 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, MOCN Drop | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-23 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-25 | 48 | 2025-11-25 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8573_1 | New_JAW-JT-UNR-8573 | JAW-JT-UNR-8573 | Central Java | Jawa Tengah | Semarang | -7.2352 | 110.3796 | Insert | New | New | Type B | MA | JAW-JT-UNR-8573 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  |  | #N/A | [9 empty] | Mid Dec 25 |  | 2026-01-23 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-25 | 48 | 2025-11-25 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8473_1 | New_JAW-JT-UNR-8473 | JAW-JT-UNR-8473 | Central Java | Jawa Tengah | Semarang | -7.1218 | 110.417 | Insert | New | New | Type B | MA | JAW-JT-UNR-8473 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-23 | 4 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-25 | 48 | 2025-11-25 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-2699_1 | New_JAW-JT-UNR-2699 | JAW-JT-UNR-2699 | Central Java | Jawa Tengah | Semarang | -7.1398 | 110.4181 | Insert | New | New | Type B | MA | JAW-JT-UNR-2699 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  |  | #N/A | [9 empty] | 2025-End Nov | CCSI | 2026-01-23 | 4 |  |  | 2026 |  |  | Not Started | [35 empty] | 2025-11-25 | 48 | 2025-11-25 |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-JT-PKL-1322_1 | New_JAW-JT-PKL-1322 | JAW-JT-PKL-1322 | Central Java | Jawa Tengah | Kota Pekalongan | -6.8756 | 109.6686 | Insert | New | New | Type B | MA | JAW-JT-PKL-1322 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, NO SPK | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  |  | #N/A | [11 empty] | 2026-01-23 | 4 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-3485_1 | New_JAW-JT-SMG-3485 | JAW-JT-SMG-3485 | Central Java | Jawa Tengah | Kota Semarang | -7.09636111111111 | 110.4175 | New | New | New | Type C | PAG | JAW-JT-SMG-3485 | Supernode Gombel |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000020395 | #N/A | - | S000055626 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  |  | CCSI | 2026-01-23 | 4 |  |  | 2026 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | 2025-11-24 | 48 | 2025-11-24 |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-JT-KDL-0872_1 | New_JAW-JT-KDL-0872 | JAW-JT-KDL-0872 | Central Java | Jawa Tengah | Kendal | -6.9662 | 110.287 | New | New | New | Type C | PAG | JAW-JT-KDL-0872 | Mangkang |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000020395 | #N/A | S000055645 | - | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2025-624 sites | GPA | 2026-01-23 | 4 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-24 | 48 | 2025-11-24 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0612_1 | New_JAW-JT-DMK-0612 | JAW-JT-DMK-0612 | Central Java | Jawa Tengah | Demak | -6.8503 | 110.8054 | New | New | New | Type C | PAG | JAW-JT-DMK-0612 | Karanganyar Demak |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | #N/A | S000055663 | S000055677 | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | Yes |  | 2026 | GPA | 2026-01-23 | 4 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0602_1 | New_JAW-JT-DMK-0602 | JAW-JT-DMK-0602 | Central Java | Jawa Tengah | Demak | -6.8738 | 110.7173 | New | New | New | Type C | PAG | JAW-JT-DMK-0602 | Mpls - Gajah |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000020396 | #N/A | S000055692 | - | 12. NY TERMINATION | 2025-12-14 | 50 |  |  | Yes |  | 2026 | GPA | 2026-01-26 | 5 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0613_1 | New_JAW-JT-DMK-0613 | JAW-JT-DMK-0613 | Central Java | Jawa Tengah | Demak | -6.90943055555556 | 110.633 | New | New | New | Type C | PAG | JAW-JT-DMK-0613 | Supernode Demak |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000020401 | #N/A | - | S000055728 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | Yes |  |  | YPTT | 2026-01-26 | 5 |  |  | 2026 |  |  | In Progress |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | 1 | #N/A | November
1 | 2 | CLEAR | New_JAW-JT-DMK-0602_2 | New_JAW-JT-DMK-0602 | JAW-JT-DMK-0602 | Central Java | Jawa Tengah | Demak | -6.8738 | 110.7173 | New | New | New | Type C | PAG | JAW-JT-DMK-0602 | Mpls - Gajah |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000020402 | #N/A | S000055761 | - | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | Yes |  | 2026 | GPA | 2026-01-26 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-2526_1 | New_JAW-JT-SMG-2526 | JAW-JT-SMG-2526 | Central Java | Jawa Tengah | Kota Semarang | -6.9978 | 110.4478 | New | New | New | Type C | PAG | JAW-JT-SMG-2526 | Gayamsari |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000020403 | #N/A | - | S000055762 | 10. Ready ATP / RFS | 2025-12-26 | 52 | 2025-11-09 |  | No |  | 2025-End Nov |  | 2026-01-26 | 5 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-27 | 48 | 2025-11-27 |  |  | #N/A | #N/A
1 | 2 | CLEAR | New_JAW-JT-DMK-0613_2 | New_JAW-JT-DMK-0613 | JAW-JT-DMK-0613 | Central Java | Jawa Tengah | Demak | -6.90943055555556 | 110.633 | New | New | New | Type C | PAG | JAW-JT-DMK-0613 | Supernode Demak |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000020403 | #N/A | S000055783 | - | 12. NY TERMINATION | 2025-12-26 | 52 |  |  | No |  |  | YPTT | 2026-01-26 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-1574_1 | New_JAW-JT-PWD-1574 | JAW-JT-PWD-1574 | Central Java | Jawa Tengah | Grobogan | -7.1394 | 110.9057 | New | New | New | Type C | PAG | JAW-JT-PWD-1574 | Toroh |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000019851 | #N/A | - | S000054304 | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2026 | GPA | 2026-01-26 | 5 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLT-2171_1 | New_JAW-JT-SLT-2171 | JAW-JT-SLT-2171 | Central Java | Jawa Tengah | Kota Salatiga | -7.3627 | 110.5156 | New | New | New | Type C | PAG | JAW-JT-SLT-2171 | Tingkir Salatiga |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000019851 | #N/A | S000054324 | - | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | Yes |  | 2025-End Nov |  | 2026-01-26 | 5 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 2 | CLEAR | New_JAW-JT-PWD-1574_2 | New_JAW-JT-PWD-1574 | JAW-JT-PWD-1574 | Central Java | Jawa Tengah | Grobogan | -7.1394 | 110.9057 | New | New | New | Type C | PAG | JAW-JT-PWD-1574 | Toroh |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000019852 | #N/A | - | S000054325 | 12. NY TERMINATION | 2025-11-16 | 46 |  |  | No |  | 2026 | GPA | 2026-01-26 | 5 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-1579_1 | New_JAW-JT-PWD-1579 | JAW-JT-PWD-1579 | Central Java | Jawa Tengah | Grobogan | -7.0717 | 110.917 | New | New | New | Type C | PAG | JAW-JT-PWD-1579 | Mpls - Purwodadi |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000019852 | #N/A | S000054342 | - | 12. NY TERMINATION | 2025-11-16 | 46 |  |  | No |  | 2026 | GPA | 2026-01-26 | 5 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [31 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-0641_1 | New_JAW-JT-JPA-0641 | JAW-JT-JPA-0641 | Central Java | Jawa Tengah | Jepara | -6.6431 | 110.7124 | New | New | New | Type C | PAG | JAW-JT-JPA-0641 | Ngabul |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000019804 | #N/A | - | S000054205 | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  | 2026 | Mingze | 2026-01-26 | 5 |  |  | 2026 |  |  | Not Started | [35 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PTI-1459_1 | New_JAW-JT-PTI-1459 | JAW-JT-PTI-1459 | Central Java | Jawa Tengah | Pati | -6.5355 | 110.9487 | New | New | New | Type C | PAG | JAW-JT-PTI-1459 | Cluwak Pati |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000019804 | #N/A | S000054225 | - | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  |  | Mingze | 2026-01-26 | 5 |  |  | 2026 |  |  | Not Started | [35 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-YO-BTL-0048_1 | New_JAW-YO-BTL-0048 | JAW-YO-BTL-0048 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8864 | 110.3462 | New | New | New | Type C | PAG | JAW-YO-BTL-0048 | Bantul |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020319 | #N/A | [9 empty] | 2026 |  | 2026-01-26 | 5 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-WAT-0365_1 | New_JAW-YO-WAT-0365 | JAW-YO-WAT-0365 | Central Java | Daerah Istimewa Yogyakarta | Kulon Progo | -7.8573 | 110.1609 | New | New | New | Type C | #N/A | JAW-YO-WAT-0365 | Mpls - Wates |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | #N/A | #N/A | [11 empty] | 2026-01-26 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | CLEAR | New_JAW-YO-BTL-0048_2 | New_JAW-YO-BTL-0048 | JAW-YO-BTL-0048 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8864 | 110.3462 | New | New | New | Type C | PAG | JAW-YO-BTL-0048 | Bantul |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020319 | #N/A | [9 empty] | 2026 |  | 2026-01-27 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0492_1 | New_JAW-YO-YYK-0492 | JAW-YO-YYK-0492 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7893 | 110.3595 | New | New | New | Type C | PAG | JAW-YO-YYK-0492 | Mpls - Patok Yogyakartara |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020320 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-27 | 5 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0074_1 | New_JAW-YO-BTL-0074 | JAW-YO-BTL-0074 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9223 | 110.382 | New | New | New | Type C | PAG | JAW-YO-BTL-0074 | Imogiri |  |  |  | - | - | - | - | New Purchase | New Ring 022 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000019967 | #N/A | [9 empty] | 2026 |  | 2026-01-27 | 5 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0084_1 | New_JAW-YO-YYK-0084 | JAW-YO-YYK-0084 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8209 | 110.401 | New | New | New | Type C | PAG | JAW-YO-YYK-0084 | Kota Gede |  |  |  | - | - | - | - | New Purchase | New Ring 022 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020330 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-27 | 5 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | CLEAR | New_JAW-YO-YYK-0084_2 | New_JAW-YO-YYK-0084 | JAW-YO-YYK-0084 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8209 | 110.401 | New | New | New | Type C | PAG | JAW-YO-YYK-0084 | Kota Gede |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020330 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-27 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0115_1 | New_JAW-YO-BTL-0115 | JAW-YO-BTL-0115 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8518 | 110.4749 | New | New | New | Type C | MA | JAW-YO-BTL-0115 | Patukkota |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | #N/A | #N/A | [9 empty] | 2026 |  | 2026-01-27 | 5 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | CLEAR | New_JAW-YO-BTL-0074_2 | New_JAW-YO-BTL-0074 | JAW-YO-BTL-0074 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9223 | 110.382 | New | New | New | Type C | PAG | JAW-YO-BTL-0074 | Imogiri |  |  |  | - | - | - | - | New Purchase | New Ring 025 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000019967 | #N/A | [9 empty] | 2026 |  | 2026-01-27 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | CLEAR | New_JAW-YO-BTL-0115_2 | New_JAW-YO-BTL-0115 | JAW-YO-BTL-0115 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8518 | 110.4749 | New | New | New | Type C | MA | JAW-YO-BTL-0115 | Patukkota |  |  |  | - | - | - | - | New Purchase | New Ring 025 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | #N/A | #N/A | [9 empty] | 2026 |  | 2026-01-27 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 3 | CLEAR | New_JAW-YO-BTL-0074_3 | New_JAW-YO-BTL-0074 | JAW-YO-BTL-0074 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9223 | 110.382 | New | New | New | Type C | PAG | JAW-YO-BTL-0074 | Imogiri |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000019967 | #N/A | [9 empty] | 2026 |  | 2026-01-27 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 3 | CLEAR | New_JAW-YO-BTL-0048_3 | New_JAW-YO-BTL-0048 | JAW-YO-BTL-0048 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8864 | 110.3462 | New | New | New | Type C | PAG | JAW-YO-BTL-0048 | Bantul |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020319 | #N/A | [9 empty] | 2026 |  | 2026-01-27 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-0184_1 | New_JAW-JT-BLA-0184 | JAW-JT-BLA-0184 | Central Java | Jawa Tengah | Blora | -6.9741 | 111.4834 | New | New | New | Type C | #N/A | JAW-JT-BLA-0184 | Geneng Blora |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK |  | R0000019802 | #N/A |  |  | 10. Ready ATP / RFS |  |  | 2025-11-09 |  |  |  | 2026 |  | 2026-01-27 | 5 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-3489_1 | New_JAW-JT-BLA-3489 | JAW-JT-BLA-3489 | Central Java | Jawa Tengah | Blora | -7.1473 | 111.5926 | New | New | New | Type C | #N/A | JAW-JT-BLA-3489 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | #N/A | #N/A | [9 empty] | 2026 |  | 2026-01-27 | 5 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | CLEAR | New_JAW-JT-SLT-2171_2 | New_JAW-JT-SLT-2171 | JAW-JT-SLT-2171 | Central Java | Jawa Tengah | Kota Salatiga | -7.3627 | 110.5156 | New | New | New | Type C | PAG | JAW-JT-SLT-2171 | Tingkir Salatiga |  |  |  | - | - | - | - | New Purchase | New Ring 031 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020476 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-27 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-2731_1 | New_JAW-JT-UNR-2731 | JAW-JT-UNR-2731 | Central Java | Jawa Tengah | Semarang | -7.2666 | 110.4551 | New | New | New | Type C | PAG | JAW-JT-UNR-2731 | Tuntang |  |  |  | - | - | - | - | New Purchase | New Ring 031 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | #N/A | #N/A | [9 empty] | Mid Dec 25 |  | 2026-01-28 | 5 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-2406_1 | New_JAW-JT-SMG-2406 | JAW-JT-SMG-2406 | Central Java | Jawa Tengah | Kota Semarang | -6.9856 | 110.4079 | New | New | New | Type C | PAG | JAW-JT-SMG-2406 | Simpang Lima |  |  |  | - | - | #N/A | #N/A | New Purchase | New Ring 032 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | #N/A | S000055794 | S000056139 | 12. NY TERMINATION | 2025-12-02 | 49 |  |  | No |  | 2025-End Nov |  | 2026-01-28 | 5 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 2 | CLEAR | New_JAW-JT-SMG-2526_2 | New_JAW-JT-SMG-2526 | JAW-JT-SMG-2526 | Central Java | Jawa Tengah | Kota Semarang | -6.9978 | 110.4478 | New | New | New | Type C | PAG | JAW-JT-SMG-2526 | Gayamsari |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000020477 | #N/A | S000056159 | - | 12. NY TERMINATION | 2025-11-30 | 48 |  |  | No |  | 2025-End Nov |  | 2026-01-28 | 5 |  |  | 2026 |  |  | #N/A | [35 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 3 | CLEAR | New_JAW-JT-SMG-2526_3 | New_JAW-JT-SMG-2526 | JAW-JT-SMG-2526 | Central Java | Jawa Tengah | Kota Semarang | -6.9978 | 110.4478 | New | New | New | Type C | PAG | JAW-JT-SMG-2526 | Gayamsari |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000020168 | #N/A | - | S000054812 | 10. Ready ATP / RFS | 2025-11-23 | 47 | 2025-11-09 |  | No |  | 2025-End Nov | YPTT | 2026-01-28 | 5 |  |  | 2026 |  |  | Not Started | [35 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 2 | CLEAR | New_JAW-JT-SMG-3485_2 | New_JAW-JT-SMG-3485 | JAW-JT-SMG-3485 | Central Java | Jawa Tengah | Kota Semarang | -7.09636111111111 | 110.4175 | New | New | New | Type C | PAG | JAW-JT-SMG-3485 | Supernode Gombel |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000020168 | #N/A | S000054826 | - | 12. NY TERMINATION | 2025-11-23 | 47 |  |  | No |  |  | CCSI | 2026-01-28 | 5 |  |  | 2026 |  |  | Not Started | [35 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | 1 | CCSI | November
1 | 2 | CLEAR | New_JAW-YO-YYK-0492_2 | New_JAW-YO-YYK-0492 | JAW-YO-YYK-0492 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7893 | 110.3595 | New | New | New | Type C | PAG | JAW-YO-YYK-0492 | Mpls - Patok Yogyakartara |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020320 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-28 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-SMN-0179_1 | New_JAW-YO-SMN-0179 | JAW-YO-SMN-0179 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.7666 | 110.361 | New | New | New | Type C | PAG | JAW-YO-SMN-0179 | Kricak |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000019970 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-28 | 5 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 4 | CLEAR | New_JAW-YO-BTL-0048_4 | New_JAW-YO-BTL-0048 | JAW-YO-BTL-0048 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8864 | 110.3462 | New | New | New | Type C | PAG | JAW-YO-BTL-0048 | Bantul |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020319 | #N/A | [9 empty] | 2026 |  | 2026-01-28 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 3 | CLEAR | New_JAW-YO-YYK-0084_3 | New_JAW-YO-YYK-0084 | JAW-YO-YYK-0084 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8209 | 110.401 | New | New | New | Type C | PAG | JAW-YO-YYK-0084 | Kota Gede |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020330 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-28 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 3 | CLEAR | New_JAW-YO-YYK-0492_3 | New_JAW-YO-YYK-0492 | JAW-YO-YYK-0492 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7893 | 110.3595 | New | New | New | Type C | PAG | JAW-YO-YYK-0492 | Mpls - Patok Yogyakartara |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020320 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-28 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 4 | CLEAR | New_JAW-YO-YYK-0084_4 | New_JAW-YO-YYK-0084 | JAW-YO-YYK-0084 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8209 | 110.401 | New | New | New | Type C | PAG | JAW-YO-YYK-0084 | Kota Gede |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020330 | #N/A | [9 empty] | 2025-End Nov |  | 2026-01-28 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BNR-8262_1 | New_JAW-JT-BNR-8262 | JAW-JT-BNR-8262 | Central Java | Jawa Tengah | Banjarnegara | -7.4707 | 109.4749 | Insert | New | New | Type A | MA | JAW-JT-BNR-8262 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-28 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BTG-8308_1 | New_JAW-JT-BTG-8308 | JAW-JT-BTG-8308 | Central Java | Jawa Tengah | Batang | -6.9756 | 109.8668 | Insert | New | New | Type A | MA | JAW-JT-BTG-8308 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-28 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8429_1 | New_JAW-JT-CLP-8429 | JAW-JT-CLP-8429 | Central Java | Jawa Tengah | Cilacap | -7.6905 | 109.3379 | Insert | New | New | Type A | MA | JAW-JT-CLP-8429 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-29 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KLN-8338_1 | New_JAW-JT-KLN-8338 | JAW-JT-KLN-8338 | Central Java | Jawa Tengah | Klaten | -7.7556 | 110.4954 | Insert | New | New | Type A | MA | JAW-JT-KLN-8338 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-29 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PML-8435_1 | New_JAW-JT-PML-8435 | JAW-JT-PML-8435 | Central Java | Jawa Tengah | Pemalang | -7.0689 | 109.3678 | Insert | New | New | Type A | MA | JAW-JT-PML-8435 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-29 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PML-8436_1 | New_JAW-JT-PML-8436 | JAW-JT-PML-8436 | Central Java | Jawa Tengah | Pemalang | -7.0652 | 109.3799 | Insert | New | New | Type A | MA | JAW-JT-PML-8436 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-29 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-WNO-8318_1 | New_JAW-YO-WNO-8318 | JAW-YO-WNO-8318 | Central Java | Daerah Istimewa Yogyakarta | GunungKidul | -7.9453 | 110.5506 | Insert | New | New | Type A | MA | JAW-YO-WNO-8318 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-29 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3177_1 | New_JAW-JI-BKL-3177 | JAW-JI-BKL-3177 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9306 | 110.4678 | Insert | New | New | Type A | MA | JAW-JI-BKL-3177 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-29 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-MKD-8431_1 | New_JAW-JT-MKD-8431 | JAW-JT-MKD-8431 | Central Java | Jawa Tengah | Magelang | -7.6136 | 110.2472 | Insert | New | New | Type A | MA | JAW-JT-MKD-8431 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-29 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8581_1 | New_JAW-JT-CLP-8581 | JAW-JT-CLP-8581 | Central Java | Jawa Tengah | Cilacap | -7.6675 | 109.1667 | Insert | New | New | Type A | MA | JAW-JT-CLP-8581 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-29 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8537_1 | New_JAW-JT-CLP-8537 | JAW-JT-CLP-8537 | Central Java | Jawa Tengah | Cilacap | -7.298 | 108.7871 | Insert | New | New | Type A | MA | JAW-JT-CLP-8537 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-29 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8487_1 | New_JAW-JT-CLP-8487 | JAW-JT-CLP-8487 | Central Java | Jawa Tengah | Cilacap | -7.6193 | 109.1185 | Insert | New | New | Type A | MA | JAW-JT-CLP-8487 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-29 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8371_1 | New_JAW-JT-PWT-8371 | JAW-JT-PWT-8371 | Central Java | Jawa Tengah | Banyumas | -7.4632 | 109.2684 | Insert | New | New | Type A | MA | JAW-JT-PWT-8371 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-29 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLW-8422_1 | New_JAW-JT-SLW-8422 | JAW-JT-SLW-8422 | Central Java | Jawa Tengah | Tegal | -6.8976 | 109.1902 | Insert | New | New | Type A | MA | JAW-JT-SLW-8422 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-29 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLW-8316_1 | New_JAW-JT-SLW-8316 | JAW-JT-SLW-8316 | Central Java | Jawa Tengah | Tegal | -6.9238 | 109.3256 | Insert | New | New | Type A | MA | JAW-JT-SLW-8316 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-29 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLW-8429_1 | New_JAW-JT-SLW-8429 | JAW-JT-SLW-8429 | Central Java | Jawa Tengah | Tegal | -7.1391 | 109.1752 | Insert | New | New | Type A | MA | JAW-JT-SLW-8429 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-30 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLW-8378_1 | New_JAW-JT-SLW-8378 | JAW-JT-SLW-8378 | Central Java | Jawa Tengah | Tegal | -6.9244 | 109.138 | Insert | New | New | Type A | MA | JAW-JT-SLW-8378 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-30 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-WNO-8327_1 | New_JAW-YO-WNO-8327 | JAW-YO-WNO-8327 | Central Java | Daerah Istimewa Yogyakarta | GunungKidul | -7.9878 | 110.5772 | Insert | New | New | Type A | MA | JAW-YO-WNO-8327 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-30 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BYL-8300_1 | New_JAW-JT-BYL-8300 | JAW-JT-BYL-8300 | Central Java | Jawa Tengah | Boyolali | -7.5738 | 110.6754 | Insert | New | New | Type A | MA | JAW-JT-BYL-8300 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-30 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KBM-8461_1 | New_JAW-JT-KBM-8461 | JAW-JT-KBM-8461 | Central Java | Jawa Tengah | Kebumen | -7.744 | 109.5868 | Insert | New | New | Type A | MA | JAW-JT-KBM-8461 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-30 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8634_1 | New_JAW-JT-CLP-8634 | JAW-JT-CLP-8634 | Central Java | Jawa Tengah | Cilacap | -7.4826 | 108.7949 | Insert | New | New | Type A | MA | JAW-JT-CLP-8634 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-30 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8454_1 | New_JAW-JT-PWT-8454 | JAW-JT-PWT-8454 | Central Java | Jawa Tengah | Banyumas | -7.5348 | 109.1195 | Insert | New | New | Type A | MA | JAW-JT-PWT-8454 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-30 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KBM-8491_1 | New_JAW-JT-KBM-8491 | JAW-JT-KBM-8491 | Central Java | Jawa Tengah | Kebumen | -7.6824 | 109.6605 | Insert | New | New | Type A | MA | JAW-JT-KBM-8491 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-30 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-WAT-8302_1 | New_JAW-YO-WAT-8302 | JAW-YO-WAT-8302 | Central Java | Daerah Istimewa Yogyakarta | Kulon Progo | -7.8856 | 110.1754 | Insert | New | New | Type A | MA | JAW-YO-WAT-8302 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-30 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8463_1 | New_JAW-JT-PWT-8463 | JAW-JT-PWT-8463 | Central Java | Jawa Tengah | Banyumas | -7.5382 | 109.1608 | Insert | New | New | Type A | MA | JAW-JT-PWT-8463 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-30 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8490_1 | New_JAW-JT-PWT-8490 | JAW-JT-PWT-8490 | Central Java | Jawa Tengah | Banyumas | -7.5493 | 109.2151 | Insert | New | New | Type A | MA | JAW-JT-PWT-8490 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-30 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BYL-8372_1 | New_JAW-JT-BYL-8372 | JAW-JT-BYL-8372 | Central Java | Jawa Tengah | Boyolali | -7.53 | 110.8098 | Insert | New | New | Type A | MA | JAW-JT-BYL-8372 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [6 empty] | 2025-11-05 |  |  |  |  | 2026-01-30 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-RBG-8476_1 | New_JAW-JT-RBG-8476 | JAW-JT-RBG-8476 | Central Java | Jawa Tengah | Rembang | -6.7458 | 111.4809 | Insert | New | New | Type A | MA | JAW-JT-RBG-8476 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-01-30 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BBS-9156_1 | New_JAW-JT-BBS-9156 | JAW-JT-BBS-9156 | Central Java | Jawa Tengah | Brebes | -6.9669 | 109.0634 | Insert | New | New | Type A | MA | JAW-JT-BBS-9156 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-02 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8391_1 | New_JAW-JT-CLP-8391 | JAW-JT-CLP-8391 | Central Java | Jawa Tengah | Cilacap | -7.6401 | 109.226 | Insert | New | New | Type A | MA | JAW-JT-CLP-8391 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-02 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8604_1 | New_JAW-JT-CLP-8604 | JAW-JT-CLP-8604 | Central Java | Jawa Tengah | Cilacap | -7.5634 | 108.7578 | Insert | New | New | Type A | MA | JAW-JT-CLP-8604 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-02 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8633_1 | New_JAW-JT-CLP-8633 | JAW-JT-CLP-8633 | Central Java | Jawa Tengah | Cilacap | -7.6328 | 109.2124 | Insert | New | New | Type A | MA | JAW-JT-CLP-8633 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-02 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BBS-9167_1 | New_JAW-JT-BBS-9167 | JAW-JT-BBS-9167 | Central Java | Jawa Tengah | Brebes | -7.0291 | 108.9948 | Insert | New | New | Type A | MA | JAW-JT-BBS-9167 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-02 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BBS-9185_1 | New_JAW-JT-BBS-9185 | JAW-JT-BBS-9185 | Central Java | Jawa Tengah | Brebes | -6.9807 | 108.8531 | Insert | New | New | Type A | MA | JAW-JT-BBS-9185 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-02 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8349_1 | New_JAW-JT-BLA-8349 | JAW-JT-BLA-8349 | Central Java | Jawa Tengah | Blora | -6.9512 | 111.1388 | Insert | New | New | Type A | MA | JAW-JT-BLA-8349 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-02-02 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8506_1 | New_JAW-JT-CLP-8506 | JAW-JT-CLP-8506 | Central Java | Jawa Tengah | Cilacap | -7.7337 | 109.0097 | Insert | New | New | Type A | MA | JAW-JT-CLP-8506 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-02 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8508_1 | New_JAW-JT-CLP-8508 | JAW-JT-CLP-8508 | Central Java | Jawa Tengah | Cilacap | -7.7037 | 109.02 | Insert | New | New | Type A | MA | JAW-JT-CLP-8508 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-02 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8528_1 | New_JAW-JT-CLP-8528 | JAW-JT-CLP-8528 | Central Java | Jawa Tengah | Cilacap | -7.3242 | 108.7378 | Insert | New | New | Type A | MA | JAW-JT-CLP-8528 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-02 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8542_1 | New_JAW-JT-CLP-8542 | JAW-JT-CLP-8542 | Central Java | Jawa Tengah | Cilacap | -7.4603 | 108.8015 | Insert | New | New | Type A | MA | JAW-JT-CLP-8542 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-02 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8558_1 | New_JAW-JT-CLP-8558 | JAW-JT-CLP-8558 | Central Java | Jawa Tengah | Cilacap | -7.5833 | 108.9084 | Insert | New | New | Type A | MA | JAW-JT-CLP-8558 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-02 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8575_1 | New_JAW-JT-CLP-8575 | JAW-JT-CLP-8575 | Central Java | Jawa Tengah | Cilacap | -7.296 | 108.7562 | Insert | New | New | Type A | MA | JAW-JT-CLP-8575 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-02 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8618_1 | New_JAW-JT-CLP-8618 | JAW-JT-CLP-8618 | Central Java | Jawa Tengah | Cilacap | -7.4856 | 108.841 | Insert | New | New | Type A | MA | JAW-JT-CLP-8618 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-03 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8200_1 | New_JAW-JT-BLA-8200 | JAW-JT-BLA-8200 | Central Java | Jawa Tengah | Blora | -7.0242 | 111.2572 | Insert | New | New | Type A | MA | JAW-JT-BLA-8200 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-02-03 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8299_1 | New_JAW-JT-BLA-8299 | JAW-JT-BLA-8299 | Central Java | Jawa Tengah | Blora | -6.933 | 111.4712 | Insert | New | New | Type A | MA | JAW-JT-BLA-8299 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-02-03 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-MKD-8373_1 | New_JAW-JT-MKD-8373 | JAW-JT-MKD-8373 | Central Java | Jawa Tengah | Magelang | -7.5403 | 110.1714 | Insert | New | New | Type A | MA | JAW-JT-MKD-8373 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-03 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8315_1 | New_JAW-JT-DMK-8315 | JAW-JT-DMK-8315 | Central Java | Jawa Tengah | Demak | -7.0646 | 110.5199 | Insert | New | New | Type A | MA | JAW-JT-DMK-8315 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-02-03 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8363_1 | New_JAW-JT-DMK-8363 | JAW-JT-DMK-8363 | Central Java | Jawa Tengah | Demak | -6.8472 | 110.5776 | Insert | New | New | Type A | MA | JAW-JT-DMK-8363 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [6 empty] | 2025-11-17 |  |  | 2026 |  | 2026-02-03 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8434_1 | New_JAW-JT-DMK-8434 | JAW-JT-DMK-8434 | Central Java | Jawa Tengah | Demak | -6.8683 | 110.7011 | Insert | New | New | Type A | MA | JAW-JT-DMK-8434 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [6 empty] | 2025-11-17 |  |  | 2026 |  | 2026-02-03 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-RBG-8437_1 | New_JAW-JT-RBG-8437 | JAW-JT-RBG-8437 | Central Java | Jawa Tengah | Rembang | -6.7114 | 111.3338 | Insert | New | New | Type A | MA | JAW-JT-RBG-8437 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-03 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8310_1 | New_JAW-JT-DMK-8310 | JAW-JT-DMK-8310 | Central Java | Jawa Tengah | Demak | -7.0206 | 110.5126 | Insert | New | New | Type A | MA | JAW-JT-DMK-8310 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-02-03 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWR-8510_1 | New_JAW-JT-PWR-8510 | JAW-JT-PWR-8510 | Central Java | Jawa Tengah | Purworejo | -7.7009 | 109.9036 | Insert | New | New | Type A | MA | JAW-JT-PWR-8510 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-03 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8213_1 | New_JAW-JT-BLA-8213 | JAW-JT-BLA-8213 | Central Java | Jawa Tengah | Blora | -7.0251 | 111.2929 | Insert | New | New | Type A | MA | JAW-JT-BLA-8213 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-02-03 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8269_1 | New_JAW-JT-BLA-8269 | JAW-JT-BLA-8269 | Central Java | Jawa Tengah | Blora | -7.2012 | 111.4162 | Insert | New | New | Type A | MA | JAW-JT-BLA-8269 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-02-03 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8280_1 | New_JAW-JT-BLA-8280 | JAW-JT-BLA-8280 | Central Java | Jawa Tengah | Blora | -7.1908 | 111.4184 | Insert | New | New | Type A | MA | JAW-JT-BLA-8280 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-02-03 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8552_1 | New_JAW-JT-PWD-8552 | JAW-JT-PWD-8552 | Central Java | Jawa Tengah | Grobogan | -7.0754 | 111.0954 | Insert | New | New | Type A | MA | JAW-JT-PWD-8552 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-02-04 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8476_1 | New_JAW-JT-UNR-8476 | JAW-JT-UNR-8476 | Central Java | Jawa Tengah | Semarang | -7.3772 | 110.4219 | Insert | New | New | Type A | MA | JAW-JT-UNR-8476 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [9 empty] | Mid Dec 25 |  | 2026-02-04 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8365_1 | New_JAW-JT-PWT-8365 | JAW-JT-PWT-8365 | Central Java | Jawa Tengah | Banyumas | -7.3443 | 109.2796 | Insert | New | New | Type A | MA | JAW-JT-PWT-8365 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-04 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SGN-8471_1 | New_JAW-JT-SGN-8471 | JAW-JT-SGN-8471 | Central Java | Jawa Tengah | Sragen | -7.346 | 110.8365 | Insert | New | New | Type A | MA | JAW-JT-SGN-8471 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-04 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KRG-8323_1 | New_JAW-JT-KRG-8323 | JAW-JT-KRG-8323 | Central Java | Jawa Tengah | Karanganyar | -7.5518 | 110.9846 | Insert | New | New | Type A | MA | JAW-JT-KRG-8323 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-04 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BNR-8310_1 | New_JAW-JT-BNR-8310 | JAW-JT-BNR-8310 | Central Java | Jawa Tengah | Banjarnegara | -7.373 | 109.6089 | Insert | New | New | Type A | MA | JAW-JT-BNR-8310 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-04 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BNR-8322_1 | New_JAW-JT-BNR-8322 | JAW-JT-BNR-8322 | Central Java | Jawa Tengah | Banjarnegara | -7.4219 | 109.6626 | Insert | New | New | Type A | MA | JAW-JT-BNR-8322 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-04 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BNR-8327_1 | New_JAW-JT-BNR-8327 | JAW-JT-BNR-8327 | Central Java | Jawa Tengah | Banjarnegara | -7.4749 | 109.6868 | Insert | New | New | Type A | MA | JAW-JT-BNR-8327 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-04 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BNR-8350_1 | New_JAW-JT-BNR-8350 | JAW-JT-BNR-8350 | Central Java | Jawa Tengah | Banjarnegara | -7.4086 | 109.7859 | Insert | New | New | Type A | MA | JAW-JT-BNR-8350 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-04 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8534_1 | New_JAW-JT-CLP-8534 | JAW-JT-CLP-8534 | Central Java | Jawa Tengah | Cilacap | -7.716 | 109.0158 | Insert | New | New | Type A | MA | JAW-JT-CLP-8534 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-04 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8550_1 | New_JAW-JT-CLP-8550 | JAW-JT-CLP-8550 | Central Java | Jawa Tengah | Cilacap | -7.6473 | 108.9717 | Insert | New | New | Type A | MA | JAW-JT-CLP-8550 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-04 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8361_1 | New_JAW-JT-PWT-8361 | JAW-JT-PWT-8361 | Central Java | Jawa Tengah | Banyumas | -7.3612 | 109.2757 | Insert | New | New | Type A | MA | JAW-JT-PWT-8361 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-04 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8458_1 | New_JAW-JT-PWT-8458 | JAW-JT-PWT-8458 | Central Java | Jawa Tengah | Banyumas | -7.4058 | 109.1416 | Insert | New | New | Type A | MA | JAW-JT-PWT-8458 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-04 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KJN-8440_1 | New_JAW-JT-KJN-8440 | JAW-JT-KJN-8440 | Central Java | Jawa Tengah | Pekalongan | -6.9265 | 109.6562 | Insert | New | New | Type A | MA | JAW-JT-KJN-8440 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-05 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-MKD-8467_1 | New_JAW-JT-MKD-8467 | JAW-JT-MKD-8467 | Central Java | Jawa Tengah | Magelang | -7.4299 | 110.2948 | Insert | New | New | Type A | MA | JAW-JT-MKD-8467 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-05 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8379_1 | New_JAW-JT-DMK-8379 | JAW-JT-DMK-8379 | Central Java | Jawa Tengah | Demak | -6.9175 | 110.5982 | Insert | New | New | Type A | MA | JAW-JT-DMK-8379 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-02-05 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-MKD-8416_1 | New_JAW-JT-MKD-8416 | JAW-JT-MKD-8416 | Central Java | Jawa Tengah | Magelang | -7.5439 | 110.2316 | Insert | New | New | Type A | MA | JAW-JT-MKD-8416 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-05 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-SMN-8354_1 | New_JAW-YO-SMN-8354 | JAW-YO-SMN-8354 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.6514 | 110.3476 | Insert | New | New | Type A | MA | JAW-YO-SMN-8354 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2026-02-05 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PML-8442_1 | New_JAW-JT-PML-8442 | JAW-JT-PML-8442 | Central Java | Jawa Tengah | Pemalang | -7.034 | 109.3838 | Insert | New | New | Type A | MA | JAW-JT-PML-8442 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-05 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8398_1 | New_JAW-JT-KDS-8398 | JAW-JT-KDS-8398 | Central Java | Jawa Tengah | Kudus | -6.816 | 110.8334 | Insert | New | New | Type A | MA | JAW-JT-KDS-8398 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-02-05 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SKH-8460_1 | New_JAW-JT-SKH-8460 | JAW-JT-SKH-8460 | Central Java | Jawa Tengah | Sukoharjo | -7.5678 | 110.7518 | Insert | New | New | Type A | MA | JAW-JT-SKH-8460 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-05 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8572_1 | New_JAW-JT-UNR-8572 | JAW-JT-UNR-8572 | Central Java | Jawa Tengah | Semarang | -7.3119 | 110.3624 | Insert | New | New | Type A | MA | JAW-JT-UNR-8572 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [6 empty] | 2025-10-12 |  |  | Mid Dec 25 |  | 2026-02-05 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BYL-8312_1 | New_JAW-JT-BYL-8312 | JAW-JT-BYL-8312 | Central Java | Jawa Tengah | Boyolali | -7.5306 | 110.6961 | Insert | New | New | Type A | MA | JAW-JT-BYL-8312 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [6 empty] | 2025-10-26 |  |  |  |  | 2026-02-05 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BYL-8326_1 | New_JAW-JT-BYL-8326 | JAW-JT-BYL-8326 | Central Java | Jawa Tengah | Boyolali | -7.3551 | 110.7025 | Insert | New | New | Type A | MA | JAW-JT-BYL-8326 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [6 empty] | 2025-10-19 |  |  |  |  | 2026-02-05 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BYL-8360_1 | New_JAW-JT-BYL-8360 | JAW-JT-BYL-8360 | Central Java | Jawa Tengah | Boyolali | -7.4897 | 110.7789 | Insert | New | New | Type A | MA | JAW-JT-BYL-8360 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-05 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PTI-8522_1 | New_JAW-JT-PTI-8522 | JAW-JT-PTI-8522 | Central Java | Jawa Tengah | Pati | -6.9494 | 111.0712 | Insert | New | New | Type A | MA | JAW-JT-PTI-8522 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-05 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SGN-8452_1 | New_JAW-JT-SGN-8452 | JAW-JT-SGN-8452 | Central Java | Jawa Tengah | Sragen | -7.389 | 110.8007 | Insert | New | New | Type A | MA | JAW-JT-SGN-8452 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [6 empty] | 2025-11-02 |  |  |  |  | 2026-02-06 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SGN-8515_1 | New_JAW-JT-SGN-8515 | JAW-JT-SGN-8515 | Central Java | Jawa Tengah | Sragen | -7.285 | 110.9163 | Insert | New | New | Type A | MA | JAW-JT-SGN-8515 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-06 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SKH-8449_1 | New_JAW-JT-SKH-8449 | JAW-JT-SKH-8449 | Central Java | Jawa Tengah | Sukoharjo | -7.6043 | 110.7555 | Insert | New | New | Type A | MA | JAW-JT-SKH-8449 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-06 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SKH-8535_1 | New_JAW-JT-SKH-8535 | JAW-JT-SKH-8535 | Central Java | Jawa Tengah | Sukoharjo | -7.7022 | 110.8525 | Insert | New | New | Type A | MA | JAW-JT-SKH-8535 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-06 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8563_1 | New_JAW-JT-UNR-8563 | JAW-JT-UNR-8563 | Central Java | Jawa Tengah | Semarang | -7.3687 | 110.604 | Insert | New | New | Type A | MA | JAW-JT-UNR-8563 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2026-02-06 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SKH-8477_1 | New_JAW-JT-SKH-8477 | JAW-JT-SKH-8477 | Central Java | Jawa Tengah | Sukoharjo | -7.6579 | 110.7901 | Insert | New | New | Type A | MA | JAW-JT-SKH-8477 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [6 empty] | 2025-10-19 |  |  |  |  | 2026-02-06 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KRG-8259_1 | New_JAW-JT-KRG-8259 | JAW-JT-KRG-8259 | Central Java | Jawa Tengah | Karanganyar | -7.5277 | 110.7683 | Insert | New | New | Type A | MA | JAW-JT-KRG-8259 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 |  |  |  | #N/A | [11 empty] | 2026-02-06 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | HOLD | Service Migration__1 | Service Migration_ |  | Central Java |  |  | #N/A | #N/A | Service Migration | Service Migration | Service Migration | Type A | MA | [5 empty] | - | - | - | - | Redeploy | SF Enterprise(Reuse 6120H-WA) | #N/A |  | 0 |  |  |  | #N/A | [11 empty] | 2025-10-15 | 42 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | HOLD | Service Migration__2 | Service Migration_ |  | Central Java |  |  | #N/A | #N/A | Service Migration | Service Migration | Service Migration | Type A | MA | [5 empty] | - | - | - | - | Redeploy | SF Enterprise(Reuse 6120H-WA) | #N/A |  | 0 |  |  |  | #N/A | [11 empty] | 2025-10-22 | 43 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 3 | HOLD | Service Migration__3 | Service Migration_ |  | Central Java |  |  | #N/A | #N/A | Service Migration | Service Migration | Service Migration | Type A | MA | [5 empty] | - | - | - | - | Redeploy | JAW-YO-YYK-0492(Reuse 6120H-WA) | #N/A |  | 0 |  |  |  | #N/A | [11 empty] | 2025-10-29 | 44 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0538_1 | Swap_JAW-JT-DMK-0538 | JAW-JT-DMK-0538 | Central Java | Jawa Tengah | Demak | -6.9443 | 110.4857 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0538 | Nyangkringan Genuk | TBG | IBS¦SMG_01N023 | Central Java Ring 91A | MA-JTDMK0538-01H | 10.206.27.103 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-17 | Approved | 2025-11-07 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110201 | 2025-11-02 | 2025-11-04 | done | done |  |  | done | done | done | done | YPTT | 2025-11-02 | 44 | 2025-11-04 | 2025-11-01 | 2025-11-03 | XLWO-20251103-00001154 |  | 2025-11-05 | 2025-11-09 | 2025-11-05 | 45 | 2025-11-09 | 45 | FALSE | 2025-11-09 | 45 | 2025-11-09 | 2025-11-09 | Done | #N/A | #N/A | November | 2025-11-14 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0546_1 | Swap_JAW-JT-DMK-0546 | JAW-JT-DMK-0546 | Central Java | Jawa Tengah | Demak | -7.0195 | 110.5035 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0546 | Bandungrejo Mranggen | DMT | ISAT¦14DMK034 | Central Java Ring 91A | MA-JTDMK0546-01H | 10.206.27.100 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-14 | 2025-10-15 | Approved | 2025-10-17 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110202 | 2025-11-02 | 2025-11-04 | done | done |  |  | done | done | done | done | GPA | 2025-11-02 | 44 | 2025-11-04 | 2025-11-01 | 2025-11-03 | XLWO-20251103-00001154 |  | 2025-11-05 | 2025-11-09 | 2025-11-05 | 45 | 2025-11-09 | 45 | FALSE | 2025-11-09 | 45 | 2025-11-09 | 2025-11-09 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0554_1 | Swap_JAW-JT-DMK-0554 | JAW-JT-DMK-0554 | Central Java | Jawa Tengah | Demak | -7.0472 | 110.518 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0554 | Kalitengah Mranggen Demak | DMT | DMT¦NO TP ID | Central Java Ring 91A | MA-JTDMK0554-01H | 10.206.27.99 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-14 | 2025-10-15 | Approved | 2025-10-17 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110206 | 2025-11-02 | 2025-11-04 | done | done |  |  | done | done | done | done | GPA | 2025-11-02 | 44 | 2025-11-04 | 2025-11-01 | 2025-11-03 | XLWO-20251103-00001154 |  | 2025-11-05 | 2025-11-09 | 2025-11-05 | 45 | 2025-11-09 | 45 | FALSE | 2025-11-09 | 45 | 2025-11-09 | 2025-11-09 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0561_1 | Swap_JAW-JT-DMK-0561 | JAW-JT-DMK-0561 | Central Java | Jawa Tengah | Demak | -7.0117 | 110.535 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0561 | Tegalarum Mranggen | TBG | SKP¦NO TP ID | Central Java Ring 91A | MA-JTDMK0561-01H | 10.206.27.101 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-25 | Approved | 2025-10-17 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110207 | 2025-11-02 | 2025-11-04 | done | done |  |  | done | done | done | done | GPA | 2025-11-02 | 44 | 2025-11-04 | 2025-11-01 | 2025-11-03 | XLWO-20251103-00001154 |  | 2025-11-05 | 2025-11-09 | 2025-11-05 | 45 | 2025-11-09 | 45 | FALSE | 2025-11-09 | 45 | 2025-11-09 | 2025-11-09 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0582_1 | Swap_JAW-JT-DMK-0582 | JAW-JT-DMK-0582 | Central Java | Jawa Tengah | Demak | -6.9056 | 110.6227 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0582 | Mangunjiwan Demak | Protelindo | STP¦JTDM0004 | Central Java Ring 91A | MA-JTDMK0582-01H | 10.206.27.104 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-14 | 2025-10-15 | Approved | 2025-10-17 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110209 | 2025-11-02 | 2025-11-04 | done | done |  |  | done | done | done | done | GPA | 2025-11-02 | 44 | 2025-11-04 | 2025-11-01 | 2025-11-03 | XLWO-20251103-00001154 |  | 2025-11-05 | 2025-11-07 | 2025-11-05 | 45 | 2025-11-09 | 45 | FALSE | 2025-11-09 | 45 | 2025-11-09 | 2025-11-07 | Done | #N/A | #N/A | November | 2025-11-14 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0589_1 | Swap_JAW-JT-DMK-0589 | JAW-JT-DMK-0589 | Central Java | Jawa Tengah | Demak | -6.8853 | 110.6421 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0589 | Betokan Demak | Protelindo | PRT¦JAW-CJV-0271-H-B | Central Java Ring 91A | MA-JTDMK0589-01H | 10.206.27.105 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-14 | 2025-10-15 | Approved | 2025-10-17 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110211 | 2025-11-02 | 2025-11-04 | done | done |  |  | done | done | done | done | GPA | 2025-11-02 | 44 | 2025-11-04 | 2025-11-01 | 2025-11-03 | XLWO-20251103-00001154 |  | 2025-11-05 | 2025-11-09 | 2025-11-05 | 45 | 2025-11-09 | 45 | FALSE | 2025-11-09 | 45 | 2025-11-09 | 2025-11-09 | Done | #N/A | #N/A | November | 2025-11-14 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-3210_1 | Swap_JAW-JT-DMK-3210 | JAW-JT-DMK-3210 | Central Java | Jawa Tengah | Demak | -6.9787 | 110.5061 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-3210 | MAKAM MBAH JAGO | TBG | TBG¦140014109 | Central Java Ring 91A | MA-JTDMK3210-01H | 10.206.27.102 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | Done | Access Limit due to community | Done | Done | 2025-11-02 | DOEID25110234 | 2025-11-02 | 2025-11-04 | done | done |  |  | done | done | done | done | YPTT | 2025-11-02 | 44 | 2025-11-05 | 2025-11-01 | 2025-11-03 | XLWO-20251103-00001154 |  | 2025-11-05 | 2025-11-09 | 2025-11-05 | 45 | 2025-11-09 | 45 | FALSE | 2025-11-09 | 45 | 2025-11-09 | 2025-11-09 | Done | #N/A | #N/A | November | 2025-11-14 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0537_1 | Swap_JAW-JT-DMK-0537 | JAW-JT-DMK-0537 | Central Java | Jawa Tengah | Demak | -6.8739 | 110.7881 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0537 | TUWANG DEMAK | Protelindo |  | Central Java Ring 103A | MA-JTDMK0537-01H | 10.206.29.157 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 3 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107LZ | 2025-11-13 | 2025-11-13 | done | done |  |  | done | done | done | done | GPA | 2025-11-13 | 46 | 2025-11-13 |  | 2025-11-10 | XLWO-20251110-00001853 |  | 2025-11-16 | 2025-11-13 | 2025-11-16 | 46 | 2025-11-16 | 46 | TRUE | 2025-11-13 | 46 | 2025-11-13 | 2025-11-13 | Done | #N/A | #N/A | November | 2025-11-14 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0568_1 | Swap_JAW-JT-DMK-0568 | JAW-JT-DMK-0568 | Central Java | Jawa Tengah | Demak | -6.8722 | 110.5687 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0568 | Sidorejo Karang Tengah | Protelindo |  | Central Java Ring 103A | MA-JTDMK0568-01H | 10.206.29.150 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 3 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-23 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-11 |  | Done | Done | 2025-11-08 | DOEID251107M0 | 2025-11-13 | 2025-11-12 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-13 | 46 | 2025-11-12 |  | 2025-11-10 | XLWO-20251110-00001853 |  | 2025-11-16 | 2025-11-12 | 2025-11-16 | 46 | 2025-11-16 | 46 | TRUE | 2025-11-12 | 46 | 2025-11-12 | 2025-11-12 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0569_1 | Swap_JAW-JT-DMK-0569 | JAW-JT-DMK-0569 | Central Java | Jawa Tengah | Demak | -6.8411 | 110.572 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0569 | Purworejo Bonang | TBG |  | Central Java Ring 103A | MA-JTDMK0569-01H | 10.206.29.151 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 3 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-31 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-11 |  | Done | Done | 2025-11-08 | DOEID251107M2 | 2025-11-13 | 2025-11-12 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-13 | 46 | 2025-11-12 |  | 2025-11-10 | XLWO-20251110-00001853 |  | 2025-11-16 | 2025-11-12 | 2025-11-16 | 46 | 2025-11-16 | 46 | TRUE | 2025-11-12 | 46 | 2025-11-12 | 2025-11-12 | Done | #N/A | #N/A | November | 2025-11-15 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0573_1 | Swap_JAW-JT-DMK-0573 | JAW-JT-DMK-0573 | Central Java | Jawa Tengah | Demak | -6.8846 | 110.5903 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0573 | Derekan | Centratama |  | Central Java Ring 103A | MA-JTDMK0573-01H | 10.206.29.149 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 3 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-11 |  | Done | Done | 2025-11-08 | DOEID251107M3 | 2025-11-13 | 2025-11-12 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-13 | 46 | 2025-11-12 |  | 2025-11-10 | XLWO-20251110-00001853 |  | 2025-11-16 | 2025-11-12 | 2025-11-16 | 46 | 2025-11-16 | 46 | TRUE | 2025-11-12 | 46 | 2025-11-12 | 2025-11-12 | Done | #N/A | #N/A | November | 2025-11-15 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0578_1 | Swap_JAW-JT-DMK-0578 | JAW-JT-DMK-0578 | Central Java | Jawa Tengah | Demak | -6.7975 | 110.6097 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0578 | Wedung Demak | Protelindo |  | Central Java Ring 103A | MA-JTDMK0578-01H | 10.206.29.153 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 3 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-23 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107M5 | 2025-11-13 | 2025-11-13 | done | done |  |  | done | done | done | done | GPA | 2025-11-13 | 46 | 2025-11-13 |  | 2025-11-10 | XLWO-20251110-00001853 |  | 2025-11-16 | 2025-11-13 | 2025-11-16 | 46 | 2025-11-16 | 46 | TRUE | 2025-11-13 | 46 | 2025-11-13 | 2025-11-13 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0579_1 | Swap_JAW-JT-DMK-0579 | JAW-JT-DMK-0579 | Central Java | Jawa Tengah | Demak | -6.8639 | 110.6116 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0579 | Karang Mlati Demak | DMT |  | Central Java Ring 103A | MA-JTDMK0579-01H | 10.206.29.155 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 3 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-14 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107M7 | 2025-11-14 | 2025-11-13 | done | done |  |  | done | done | done | done | GPA | 2025-11-14 | 46 | 2025-11-13 |  | 2025-11-10 | XLWO-20251110-00001853 |  | 2025-11-17 | 2025-11-13 | 2025-11-17 | 47 | 2025-11-17 | 47 | TRUE | 2025-11-13 | 46 | 2025-11-13 | 2025-11-13 | Done | #N/A | #N/A | November | 2025-11-14 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0583_1 | Swap_JAW-JT-DMK-0583 | JAW-JT-DMK-0583 | Central Java | Jawa Tengah | Demak | -6.8343 | 110.6297 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0583 | Weding Demak | TBG |  | Central Java Ring 103A | MA-JTDMK0583-01H | 10.206.29.154 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 3 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-24 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107M8 | 2025-11-14 | 2025-11-13 | done | done |  |  | done | done | done | done | GPA | 2025-11-14 | 46 | 2025-11-13 |  | 2025-11-10 | XLWO-20251110-00001853 |  | 2025-11-17 | 2025-11-13 | 2025-11-17 | 47 | 2025-11-17 | 47 | TRUE | 2025-11-13 | 46 | 2025-11-13 | 2025-11-13 | Done | #N/A | #N/A | November | 2025-11-15 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0598_1 | Swap_JAW-JT-DMK-0598 | JAW-JT-DMK-0598 | Central Java | Jawa Tengah | Demak | -6.8802 | 110.6919 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0598 | Mrisen Wonosalam | Others |  | Central Java Ring 103A | MA-JTDMK0598-01H | 10.206.29.156 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 3 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-15 | 2025-10-15 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107M9 | 2025-11-14 | 2025-11-13 | done | done |  |  | done | done | done | done | GPA | 2025-11-14 | 46 | 2025-11-13 |  | 2025-11-10 | XLWO-20251110-00001853 |  | 2025-11-17 | 2025-11-13 | 2025-11-17 | 47 | 2025-11-17 | 47 | TRUE | 2025-11-13 | 46 | 2025-11-13 | 2025-11-13 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-2971_1 | Swap_JAW-JT-DMK-2971 | JAW-JT-DMK-2971 | Central Java | Jawa Tengah | Demak | -6.826 | 110.5955 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-2971 | Poncoharjo Bonang | TBG |  | Central Java Ring 103A | MA-JTDMK2971-01H | 10.206.29.152 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 3 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-26 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-11 |  | Done | Done | 2025-11-08 | DOEID251107MB | 2025-11-14 | 2025-11-12 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-14 | 46 | 2025-11-12 |  | 2025-11-10 | XLWO-20251110-00001853 |  | 2025-11-17 | 2025-11-12 | 2025-11-17 | 47 | 2025-11-17 | 47 | TRUE | 2025-11-12 | 46 | 2025-11-12 | 2025-11-12 | Done | #N/A | #N/A | November | 2025-11-14 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0612_1 | Swap_JAW-JT-DMK-0612 | JAW-JT-DMK-0612 | Central Java | Jawa Tengah | Demak | -6.8503 | 110.8054 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-DMK-0612 | Karanganyar Demak | Centratama |  | Central Java Ring 103 | PAG-JTDMK0612-02H | 10.206.29.148 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 3 | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107LV | 2025-11-10 | 2025-11-13 | done | done |  |  | done | done | done | done | GPA | 2025-11-10 | 46 | 2025-11-13 |  | 2025-11-12 | XLWO-20251112-00001203 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 46 | 2025-11-13 | 46 | TRUE | 2025-11-13 | 46 | 2025-11-13 | 2025-11-13 | Done | #N/A | #N/A | November | 2025-11-20 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0613_1 | Swap_JAW-JT-DMK-0613 | JAW-JT-DMK-0613 | Central Java | Jawa Tengah | Demak | -6.90943055555556 | 110.633 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-DMK-0613 | Supernode Demak | 0 |  | Central Java Ring 103 | PAG-JTDMK0613-02H | 10.206.29.147 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 3 | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-11-03 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107LX | 2025-11-10 | 2025-11-13 | done | done |  |  | done | done | done | done | GPA | 2025-11-10 | 46 | 2025-11-13 |  | 2025-11-12 | XLWO-20251112-00001203 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 46 | 2025-11-13 | 46 | TRUE | 2025-11-13 | 46 | 2025-11-13 | 2025-11-13 | Done | #N/A | #N/A | November | 2025-11-20 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-SMG-2406_1 | Swap_JAW-JT-SMG-2406 | JAW-JT-SMG-2406 | Central Java | Jawa Tengah | Kota Semarang | -6.9856 | 110.4079 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-SMG-2406 | Simpang Lima | DMT |  | Central Java Ring 114 | PAG-JTSMG2406-03H | 10.219.36.1 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | GIT | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-17 | Approved | 2025-11-13 |  | Submitted | Approved | [16 empty] | GIT | [14 empty] | 2025-11-26 | 48 | 2025-11-26 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0552_1 | Swap_JAW-JT-DMK-0552 | JAW-JT-DMK-0552 | Central Java | Jawa Tengah | Demak | -7.0276 | 110.5174 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-DMK-0552 | Mranggen | TBG | IBS¦NO TP ID | Central Java Ring 25 | PAG-YG2295-01H | 10.219.208.5 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep | 2 | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-21 | 2025-10-21 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-06 |  | Done | Done | Done | DOEID25110261 | 2025-11-06 | 2025-11-05 | Done | Done |  |  | Done | Done | Done | Done | Mingze | 2025-11-06 | 45 | 2025-11-08 | 2025-11-09 | 2025-11-10 | XLWO-20251106-00001543 |  | 2025-11-09 | 2025-11-10 | 2025-11-09 | 45 | 2025-11-09 | 45 | TRUE | 2025-11-10 | 46 | 2025-11-10 | 2025-11-10 | Done | #N/A | #N/A | November | 2025-11-09 |  | 2025-11-15
1 | 2 | CLEAR | Swap_JAW-JT-DMK-0613_2 | Swap_JAW-JT-DMK-0613 | JAW-JT-DMK-0613 | Central Java | Jawa Tengah | Demak | -6.90943055555556 | 110.633 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-DMK-0613 | Supernode Demak | 0 | 0 | Central Java Ring 25 | PAG-YGSN0076-01H | 10.219.208.4 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep | 2 | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-11-03 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-06 |  | Done | Done | Done | DOEID251107QG | 2025-11-06 | 2025-11-09 | Done | Done |  |  | Done | Done | Done | Done | GCI | 2025-11-06 | 45 | 2025-11-09 | 2025-11-09 | 2025-11-10 | XLWO-20251110-00000708 |  | 2025-11-09 | 2025-11-10 | 2025-11-09 | 45 | 2025-11-09 | 45 | TRUE | 2025-11-10 | 46 | 2025-11-10 | 2025-11-10 | Done | #N/A | #N/A | November | 2025-11-14
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0571_1 | Swap_JAW-JT-DMK-0571 | JAW-JT-DMK-0571 | Central Java | Jawa Tengah | Demak | -6.9239 | 110.5726 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0571 | Batu Demak | Protelindo | PRT¦JAW-JT-DMK-0571 | Central Java Ring 25C | MA-YG2454-01H | 10.219.208.29 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-10 | 41 | October | Oct | 2025 | 2025-10-13 | 2025-10-15 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-06 |  | Done | Done | Done | DOEID25110215 | 2025-11-06 | 2025-11-05 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-06 | 45 | 2025-11-07 |  | 2025-11-08 | XLWO-20251108-00000248 |  | 2025-11-09 | 2025-11-10 | 2025-11-09 | 45 | 2025-11-10 | 46 | FALSE | 2025-11-10 | 46 | 2025-11-10 | 2025-11-10 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-SMG-0536_1 | Swap_JAW-JT-SMG-0536 | JAW-JT-SMG-0536 | Central Java | Jawa Tengah | Kota Semarang | -7.0203 | 110.4818 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SMG-0536 | Pedurungan Kidul | DMT | LJA¦NO TP ID | Central Java Ring 25C | MA-YG2531380-01H | 10.219.208.26 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | GPA | 2025-10-10 | 41 | October | Oct | 2025 | 2025-10-10 | 2025-10-30 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-06 |  | Done | Done | Done | DOEID25110218 | 2025-11-06 | 2025-11-05 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-06 | 45 | 2025-11-07 |  | 2025-11-08 | XLWO-20251108-00000248 |  | 2025-11-09 | 2025-11-10 | 2025-11-09 | 45 | 2025-11-10 | 46 | FALSE | 2025-11-10 | 46 | 2025-11-10 | 2025-11-10 | Done | #N/A | #N/A | November | 2025-11-20 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-SMG-0540_1 | Swap_JAW-JT-SMG-0540 | JAW-JT-SMG-0540 | Central Java | Jawa Tengah | Kota Semarang | -6.948 | 110.4916 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SMG-0540 | Charoen Pokhpand | Protelindo | PRT¦JAW-CJV-0563-H-P | Central Java Ring 25C | MA-YG3533581G-01H | 10.219.208.30 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | GPA | 2025-10-10 | 41 | October | Oct | 2025 | 2025-10-10 | 2025-10-12 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-06 |  | Done | Done | Done | DOEID25110265 | 2025-11-06 | 2025-11-05 | Done | Done |  |  | Done | Done | Done | Done | GCI | 2025-11-06 | 45 | 2025-11-08 |  | 2025-11-08 | XLWO-20251108-00000248 |  | 2025-11-09 | 2025-11-10 | 2025-11-09 | 45 | 2025-11-10 | 46 | FALSE | 2025-11-10 | 46 | 2025-11-10 | 2025-11-10 | Done | #N/A | #N/A | November | 2025-11-14
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0542_1 | Swap_JAW-JT-DMK-0542 | JAW-JT-DMK-0542 | Central Java | Jawa Tengah | Demak | -7.0532 | 110.4921 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0542 | Kebonbatur Mranggen | Centratama |  | Central Java Ring 25C | MA-YG3533826G-01H | 10.219.208.33 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-11 | 41 | October | Oct | 2025 | 2025-10-10 | 2025-10-12 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-09 |  | Done | Done | 2025-11-08 | DOEID251107OL | 2025-11-07 | 2025-11-10 | done | done |  |  | done | done | done | done | YPTT | 2025-11-07 | 45 | 2025-11-10 |  | 2025-11-08 | XLWO-20251108-00000248 |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | 46 | 2025-11-10 | 46 | TRUE | 2025-11-10 | 46 | 2025-11-10 | 2025-11-10 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0539_1 | Swap_JAW-JT-DMK-0539 | JAW-JT-DMK-0539 | Central Java | Jawa Tengah | Demak | -7.0366 | 110.4884 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0539 | Plamongan Pucang Gading | Centratama |  | Central Java Ring 25C | MA-YGB490-01H | 10.219.208.27 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-11 | 41 | October | Oct | 2025 | 2025-10-11 | 2025-10-15 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-09 |  | Done | Done | 2025-11-08 | DOEID251107ON | 2025-11-07 | 2025-11-10 | done | done |  |  | done | done | done | done | YPTT | 2025-11-07 | 45 | 2025-11-10 |  | 2025-11-08 | XLWO-20251108-00000248 |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | 46 | 2025-11-10 | 46 | TRUE | 2025-11-10 | 46 | 2025-11-10 | 2025-11-10 | Done | #N/A | #N/A | November | 2025-11-20
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0551_1 | Swap_JAW-JT-DMK-0551 | JAW-JT-DMK-0551 | Central Java | Jawa Tengah | Demak | -6.9443 | 110.5094 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0551 | Sayung Demak | Protelindo |  | Central Java Ring 25C | MA-YGBD45-01H | 10.219.208.24 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-10 | 41 | October | Oct | 2025 | 2025-10-11 | 2025-10-15 | Approved | 2025-10-17 |  | Submitted | Approved |  | Site Flooding | Done | Done | 2025-11-08 | DOEID251107OP | 2025-11-07 | [9 empty] | YPTT | 2025-11-07 | 45 |  |  | 2025-11-08 | XLWO-20251108-00000248 |  | 2025-11-10 |  | 2025-11-10 | 46 | 2025-11-10 | 46 | TRUE | Need Replan | #VALUE! | Need Replan |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0548_1 | Swap_JAW-JT-DMK-0548 | JAW-JT-DMK-0548 | Central Java | Jawa Tengah | Demak | -7.0411 | 110.5051 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0548 | Kalitengah Mranggen | Protelindo |  | Central Java Ring 25C | MA-YGDMK0548-01H | 10.219.208.28 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-11 | 41 | October | Oct | 2025 | 2025-10-11 | 2025-10-12 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107O6 | 2025-11-07 | 2025-11-11 | Done | Done |  |  | Done | Done | Done | Done | Mingze | 2025-11-07 | 45 | 2025-11-11 |  | 2025-11-08 | XLWO-20251108-00000248 |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 46 | 2025-11-11 | 46 | FALSE | 2025-11-11 | 46 | 2025-11-11 | 2025-11-11 | Done | #N/A | #N/A | November | 2025-11-18 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-SMG-3126_1 | Swap_JAW-JT-SMG-3126 | JAW-JT-SMG-3126 | Central Java | Jawa Tengah | Kota Semarang | -7.0247 | 110.4882 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SMG-3126 | Rusunawa Plamongan Sari | Protelindo |  | Central Java Ring 25C | MA-YGSMG3126-01H | 10.219.208.32 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | GPA | 2025-10-10 | 41 | October | Oct | 2025 | 2025-10-11 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107O8 | 2025-11-07 | 2025-11-11 | Done | Done |  |  | Done | Done | Done | Done | Mingze | 2025-11-07 | 45 | 2025-11-11 |  | 2025-11-08 | XLWO-20251108-00000248 |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 46 | 2025-11-11 | 46 | FALSE | 2025-11-11 | 46 | 2025-11-11 | 2025-11-11 | Done | #N/A | #N/A | November
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1579_1 | Swap_JAW-JT-PWD-1579 | JAW-JT-PWD-1579 | Central Java | Jawa Tengah | Grobogan | -7.0717 | 110.917 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-PWD-1579 | Mpls - Purwodadi | Others |  | Central Java Ring 28 | PAG-SM2249-01H | 10.219.208.52 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 5 | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-25 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107MG | 2025-11-20 | 2025-11-12 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-20 | 47 | 2025-11-12 |  |  |  |  | 2025-11-23 | 2025-11-21 | 2025-11-23 | 47 | 2025-11-23 | 47 | TRUE | 2025-11-20 | 47 | 2025-11-20 | 2025-11-21 | Done | #N/A | #N/A | November | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1574_1 | Swap_JAW-JT-PWD-1574 | JAW-JT-PWD-1574 | Central Java | Jawa Tengah | Grobogan | -7.1394 | 110.9057 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-PWD-1574 | Toroh | Protelindo |  | Central Java Ring 28 | PAG-SMB317-01H | 10.219.209.11 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 5 | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-20 | 2025-11-17 | Reviewing |  |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107MI | 2025-11-20 | 2025-11-12 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-20 | 47 | 2025-11-12 |  | 2025-11-10 | XLWO-20251112-00000909 |  | 2025-11-23 | 2025-11-17 | 2025-11-23 | 47 | 2025-11-23 | 47 | TRUE | 2025-11-17 | 47 | 2025-11-17 | 2025-11-17 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-PWD-0608_1 | Swap_JAW-JT-PWD-0608 | JAW-JT-PWD-0608 | Central Java | Jawa Tengah | Grobogan | -7.0213 | 110.7637 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-0608 | Godong | Protelindo |  | Central Java Ring 28C | MA-SM2298-01H | 10.219.208.51 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-18 | 2025-10-29 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107MK | 2025-11-20 | 2025-11-12 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-20 | 47 | 2025-11-12 |  | 2025-11-10 | XLWO-20251112-00000914 |  | 2025-11-23 | 2025-11-17 | 2025-11-23 | 47 | 2025-11-23 | 47 | TRUE | 2025-11-17 | 47 | 2025-11-17 | 2025-11-17 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1604_1 | Swap_JAW-JT-PWD-1604 | JAW-JT-PWD-1604 | Central Java | Jawa Tengah | Grobogan | -7.0776 | 111.0899 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1604 | Wirosari | Protelindo |  | Central Java Ring 28C | MA-SM2451-01H | 10.219.208.75 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Propose Drop, MOCN Drop | 5 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-18 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1600_1 | Swap_JAW-JT-PWD-1600 | JAW-JT-PWD-1600 | Central Java | Jawa Tengah | Grobogan | -7.0894 | 111.0489 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1600 | Tjrejowirosaric-Prtlnd | Protelindo |  | Central Java Ring 28C | MA-SM2531242-01H | 10.219.208.76 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-18 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107ML | 2025-11-20 | 2025-11-12 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-20 | 47 | 2025-11-12 |  | 2025-11-10 | XLWO-20251112-00000914 |  | 2025-11-23 | 2025-11-17 | 2025-11-23 | 47 | 2025-11-23 | 47 | TRUE | 2025-11-17 | 47 | 2025-11-17 | 2025-11-17 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1548_1 | Swap_JAW-JT-PWD-1548 | JAW-JT-PWD-1548 | Central Java | Jawa Tengah | Grobogan | -7.0646 | 110.7747 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1548 | Anggaswangi | DMT |  | Central Java Ring 28C | MA-SM2531512-01H | 10.219.208.54 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle | PT IFORTE SOLUSI INFOTEK |  |  | #N/A | [5 empty] | 2025-11-09 | 2025-11-09 |  |  | 2026 | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-18 | 2025-10-30 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-16 |  | Done | Done | Done | DOEID25111401 | 2025-11-21 | 2025-11-17 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-21 | 47 | 2025-11-17 |  | 2025-11-10 | XLWO-20251112-00000914 |  | 2025-11-24 | 2025-11-17 | 2025-11-24 | 48 | 2025-11-24 | 48 | TRUE | 2025-11-17 | 47 | 2025-11-17 | 2025-11-17 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1556_1 | Swap_JAW-JT-PWD-1556 | JAW-JT-PWD-1556 | Central Java | Jawa Tengah | Grobogan | -7.1063 | 110.8077 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1556 | Jipang Grobogan | TBG |  | Central Java Ring 28C | MA-SM2533112-01H | 10.219.208.56 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-20 | 2025-10-26 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-16 |  | Done | Done | Done | DOEID25111402 | 2025-11-21 | 2025-11-17 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-21 | 47 | 2025-11-17 |  | 2025-11-10 | XLWO-20251112-00000914 |  | 2025-11-24 | 2025-11-17 | 2025-11-24 | 48 | 2025-11-24 | 48 | TRUE | 2025-11-17 | 47 | 2025-11-17 | 2025-11-17 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1563_1 | Swap_JAW-JT-PWD-1563 | JAW-JT-PWD-1563 | Central Java | Jawa Tengah | Grobogan | -7.0567 | 110.8623 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1563 | Pulorejo | Protelindo |  | Central Java Ring 28C | MA-SM2534713-01H | 10.219.208.70 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-18 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-17 |  | Done | Done | Done | DOEID25111404 | 2025-11-21 | 2025-11-18 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-21 | 47 | 2025-11-18 |  |  |  |  | 2025-11-24 | 2025-11-18 | 2025-11-24 | 48 | 2025-11-24 | 48 | TRUE | 2025-11-18 | 47 | 2025-11-18 | 2025-11-18 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1590_1 | Swap_JAW-JT-PWD-1590 | JAW-JT-PWD-1590 | Central Java | Jawa Tengah | Grobogan | -7.1166 | 110.9681 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1590 | Nambuhan | TBG |  | Central Java Ring 28C | MA-SM2534778-01H | 10.219.208.73 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-18 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-17 |  | Done | Done | Done | DOEID25111405 | 2025-11-21 | 2025-11-18 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-21 | 47 | 2025-11-18 |  |  |  |  | 2025-11-24 | 2025-11-18 | 2025-11-24 | 48 | 2025-11-24 | 48 | TRUE | 2025-11-18 | 47 | 2025-11-18 | 2025-11-18 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1562_1 | Swap_JAW-JT-PWD-1562 | JAW-JT-PWD-1562 | Central Java | Jawa Tengah | Grobogan | -7.0852 | 110.8688 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1562 | Kluwan Penawangan | TBG |  | Central Java Ring 28C | MA-SM3533265G-01H | 10.219.208.58 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-26 | 2025-10-26 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-17 |  | Done | Done | Done | DOEID25111407 | 2025-11-21 | 2025-11-18 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-21 | 47 | 2025-11-18 |  |  |  |  | 2025-11-24 | 2025-11-18 | 2025-11-24 | 48 | 2025-11-24 | 48 | TRUE | 2025-11-18 | 47 | 2025-11-18 | 2025-11-18 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1586_1 | Swap_JAW-JT-PWD-1586 | JAW-JT-PWD-1586 | Central Java | Jawa Tengah | Grobogan | -7.1147 | 110.9371 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1586 | Kedungrejo Purwodadi | Others |  | Central Java Ring 28C | MA-SM3533386G-01H | 10.219.208.72 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-18 | 2025-11-01 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-17 |  | Done | Done | Done | DOEID25111409 | 2025-11-21 | 2025-11-18 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-21 | 47 | 2025-11-18 |  |  |  |  | 2025-11-24 | 2025-11-18 | 2025-11-24 | 48 | 2025-11-24 | 48 | TRUE | 2025-11-18 | 47 | 2025-11-18 | 2025-11-18 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1602_1 | Swap_JAW-JT-PWD-1602 | JAW-JT-PWD-1602 | Central Java | Jawa Tengah | Grobogan | -7.1297 | 111.0734 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1602 | Pulo Kulon | Protelindo |  | Central Java Ring 28C | MA-SMBD77-01H | 10.219.208.74 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-11-03 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-17 |  | Done | Done | Done | DOEID25111410 | 2025-11-21 | 2025-11-18 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-21 | 47 | 2025-11-18 |  |  |  |  | 2025-11-24 | 2025-11-18 | 2025-11-24 | 48 | 2025-11-24 | 48 | TRUE | 2025-11-18 | 47 | 2025-11-18 | 2025-11-18 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-PWD-0001_1 | Swap_JAW-JT-PWD-0001 | JAW-JT-PWD-0001 | Central Java | Jawa Tengah | Grobogan | -7.1327 | 111.0919 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-0001 | Grabagan Tuko | Centratama |  | Central Java Ring 28E | MA-JTPWD0001-01H | 10.206.30.18 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-30 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-17 |  | Done | Done | Done | DOEID25111444 | 2025-11-22 | 2025-11-18 | Done | Done |  |  | Done | Done | Done | Done | GIT | 2025-11-22 | 47 | 2025-11-18 |  |  |  |  | 2025-11-25 | 2025-11-18 | 2025-11-25 | 48 | 2025-11-25 | 48 | TRUE | 2025-11-18 | 47 | 2025-11-18 | 2025-11-18 | Done | #N/A | #N/A | November | 2025-11-19
1 | 1 | CLEAR | Swap_JAW-JT-PWD-0007_1 | Swap_JAW-JT-PWD-0007 | JAW-JT-PWD-0007 | Central Java | Jawa Tengah | Grobogan | -7.1289 | 111.0192 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-0007 | PULOKULON JETAK | Protelindo |  | Central Java Ring 28E | MA-JTPWD0007-01H | 10.206.30.17 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-17 |  | Done | Done | Done | DOEID25111445 | 2025-11-22 | 2025-11-18 | Done | Done |  |  | Done | Done | Done | Done | GIT | 2025-11-22 | 47 | 2025-11-18 |  |  |  |  | 2025-11-25 | 2025-11-18 | 2025-11-25 | 48 | 2025-11-25 | 48 | TRUE | 2025-11-18 | 47 | 2025-11-18 | 2025-11-18 | Done | #N/A | #N/A | November | 2025-11-19
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1589_1 | Swap_JAW-JT-PWD-1589 | JAW-JT-PWD-1589 | Central Java | Jawa Tengah | Grobogan | -7.0773 | 110.9656 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1589 | Mahayan Purwodadi | Others |  | Central Java Ring 28E | MA-JTPWD1589-01H | 10.206.30.23 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-21 | Not Started | 2025-10-17 |  | Submitted | Approved | 2025-11-17 |  | Done | Done | Done | DOEID25111453 | 2025-11-22 | 2025-11-18 | Done | Done |  |  | Done | Done | Done | Done | YPTT | 2025-11-22 | 47 | 2025-11-18 |  |  | XLWO-20251112-00000914 |  | 2025-11-25 | 2025-11-19 | 2025-11-25 | 48 | 2025-11-25 | 48 | TRUE | 2025-11-19 | 47 | 2025-11-19 | 2025-11-19 | Done | #N/A | #N/A | November | 2025-11-20
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1591_1 | Swap_JAW-JT-PWD-1591 | JAW-JT-PWD-1591 | Central Java | Jawa Tengah | Grobogan | -7.021 | 110.9695 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1591 | Lebak Grobogan | TBG |  | Central Java Ring 28E | MA-JTPWD1591-01H | 10.206.30.22 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-22 | Not Started | 2025-10-17 |  | Submitted | Approved | 2025-11-17 |  | Done | Done | Done | DOEID25111455 | 2025-11-22 | 2025-11-18 | Done | Done |  |  | Done | Done | Done | Done | YPTT | 2025-11-22 | 47 | 2025-11-18 |  |  | XLWO-20251112-00000914 |  | 2025-11-25 | 2025-11-19 | 2025-11-25 | 48 | 2025-11-25 | 48 | TRUE | 2025-11-19 | 47 | 2025-11-19 | 2025-11-19 | Done | #N/A | #N/A | November | 2025-11-20
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1592_1 | Swap_JAW-JT-PWD-1592 | JAW-JT-PWD-1592 | Central Java | Jawa Tengah | Grobogan | -7.1227 | 110.9932 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1592 | Sembungharjo Pulokulon | Protelindo |  | Central Java Ring 28E | MA-JTPWD1592-01H | 10.206.30.16 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Propose Drop, MOCN Drop | 5 | TypeB 6120H-SC Chassis Bundle | PT IFORTE SOLUSI INFOTEK |  |  | #N/A | [5 empty] | 2025-11-09 |  |  |  |  | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-11-17 | Reviewing |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1599_1 | Swap_JAW-JT-PWD-1599 | JAW-JT-PWD-1599 | Central Java | Jawa Tengah | Grobogan | -6.9723 | 111.0385 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1599 | Gunung Gading Kemaduhbatur | TBG |  | Central Java Ring 28E | MA-JTPWD1599-01H | 10.206.30.21 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-20 | Not Started | 2025-10-17 |  | Submitted | Approved | 2025-11-18 |  | Done | Done | Done | DOEID25111433 | 2025-11-22 | 2025-11-19 | Done | Done |  |  | Done | Done | Done | Done | Mingze | 2025-11-22 | 47 | 2025-11-19 |  |  | XLWO-20251112-00000914 |  | 2025-11-25 | 2025-11-19 | 2025-11-25 | 48 | 2025-11-25 | 48 | TRUE | 2025-11-19 | 47 | 2025-11-19 | 2025-11-19 | Done | #N/A | #N/A | November | 2025-11-20
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1608_1 | Swap_JAW-JT-PWD-1608 | JAW-JT-PWD-1608 | Central Java | Jawa Tengah | Grobogan | -6.9593 | 111.1013 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1608 | Tegalrejo Wirosari | Others |  | Central Java Ring 28E | MA-JTPWD1608-01H | 10.206.30.20 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-11-06 | Not Started | 2025-10-17 |  | Submitted | Approved | 2025-11-18 |  | Done | Done | Done | DOEID25111434 | 2025-11-22 | 2025-11-19 | Done | Done |  |  | Done | Done | Done | Done | Mingze | 2025-11-22 | 47 | 2025-11-19 |  |  | XLWO-20251112-00000914 |  | 2025-11-25 | 2025-11-19 | 2025-11-25 | 48 | 2025-11-25 | 48 | TRUE | 2025-11-19 | 47 | 2025-11-19 | 2025-11-19 | Done | #N/A | #N/A | November | 2025-11-20
1 | 1 | CLEAR | Swap_JAW-JT-PWD-3387_1 | Swap_JAW-JT-PWD-3387 | JAW-JT-PWD-3387 | Central Java | Jawa Tengah | Grobogan | -7.0094 | 111.1154 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-3387 | KARANGASEM GROBOGAN | TBG |  | Central Java Ring 28E | MA-JTPWD3387-01H | 10.206.30.19 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-24 | Not Started | 2025-10-17 |  | Submitted | Approved | 2025-11-18 |  | Done | Done | Done | DOEID251113PG | 2025-11-22 | 2025-11-19 | Done | Done |  |  | Done | Done | Done | Done | GCI | 2025-11-22 | 47 | 2025-11-19 |  |  | XLWO-20251112-00000914 |  | 2025-11-25 | 2025-11-19 | 2025-11-25 | 48 | 2025-11-25 | 48 | TRUE | 2025-11-19 | 47 | 2025-11-19 | 2025-11-19 | Done | #N/A | #N/A | November | 2025-11-20
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1993_1 | Swap_JAW-JT-SKH-1993 | JAW-JT-SKH-1993 | Central Java | Jawa Tengah | Sukoharjo | -7.7298 | 110.854 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1993 | Daleman | Protelindo |  | Central Java Ring 30E | MA-SM2534573-01H | 10.206.6.30 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-18 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1989_1 | Swap_JAW-JT-SKH-1989 | JAW-JT-SKH-1989 | Central Java | Jawa Tengah | Sukoharjo | -7.6928 | 110.8451 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1989 | Sukoharjo Selatan | Protelindo |  | Central Java Ring 30E | MA-SM253EG34-01H | 10.206.6.29 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-1068_1 | Swap_JAW-JT-KLN-1068 | JAW-JT-KLN-1068 | Central Java | Jawa Tengah | Klaten | -7.6443 | 110.7534 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-1068 | Wadung Getas Wonosari | Centratama |  | Central Java Ring 30E | MA-SM3533153G-01H | 10.206.6.34 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-18 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1958_1 | Swap_JAW-JT-SKH-1958 | JAW-JT-SKH-1958 | Central Java | Jawa Tengah | Sukoharjo | -7.6053 | 110.7889 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1958 | Sanggrahan Grogol | Others |  | Central Java Ring 30E | MA-SM3533198G-01H | 10.206.6.35 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-1057_1 | Swap_JAW-JT-KLN-1057 | JAW-JT-KLN-1057 | Central Java | Jawa Tengah | Klaten | -7.6998 | 110.7068 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-1057 | Pedan | Protelindo |  | Central Java Ring 30E | MA-SMB210-01H | 10.206.6.33 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-21 | 2025-10-21 | Approved | 2025-10-17 |  | Submitted | Approved |  | Proposed Hotswap | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1982_1 | Swap_JAW-JT-SKH-1982 | JAW-JT-SKH-1982 | Central Java | Jawa Tengah | Sukoharjo | -7.7648 | 110.834 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1982 | Bulu Sukoharjo | Protelindo |  | Central Java Ring 30E | MA-SMB245-01H | 10.206.6.31 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-18 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1964_1 | Swap_JAW-JT-SKH-1964 | JAW-JT-SKH-1964 | Central Java | Jawa Tengah | Sukoharjo | -7.7562 | 110.8061 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1964 | Puron Bulu | #N/A |  | Central Java Ring 30E | MA-SMB436-01H | 10.206.9.126 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-1041_1 | Swap_JAW-JT-KLN-1041 | JAW-JT-KLN-1041 | Central Java | Jawa Tengah | Klaten | -7.7358 | 110.6628 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-1041 | Trucuk | Protelindo |  | Central Java Ring 30E | MA-SMBD73-01H | 10.206.6.32 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-14 | 42 | October | Oct | 2025 |  |  | In Progress |  |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-MGG-1158_1 | Swap_JAW-JT-MGG-1158 | JAW-JT-MGG-1158 | Central Java | Jawa Tengah | Kota Magelang | -7.4796 | 110.2269 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-MGG-1158 | Mpls - Magelang | Protelindo |  | Central Java Ring 33 | PAG-YG2238-01H | 10.206.1.232 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GIT | 2025-10-15 | 42 | October | Oct | 2025 | 2025-10-28 | 2025-10-28 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SLT-2171_1 | Swap_JAW-JT-SLT-2171 | JAW-JT-SLT-2171 | Central Java | Jawa Tengah | Kota Salatiga | -7.3627 | 110.5156 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-SLT-2171 | Tingkir Salatiga | Centratama |  | Central Java Ring 33 | PAG-YGB239-02H | 10.206.1.231 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | GIT | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-14 | 2025-10-22 | Approved | 2025-11-13 |  | Submitted | Approved | [16 empty] | GIT | [14 empty] | 2025-11-27 | 48 | 2025-11-27 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1938_1 | Swap_JAW-JT-SKH-1938 | JAW-JT-SKH-1938 | Central Java | Jawa Tengah | Sukoharjo | -7.5578 | 110.7527 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1938 | Pabelan | Protelindo |  | Central Java Ring 35E | MA-YO2533646-01H | 10.206.27.30 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1909_1 | Swap_JAW-JT-SKH-1909 | JAW-JT-SKH-1909 | Central Java | Jawa Tengah | Sukoharjo | -7.5482 | 110.7438 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1909 | PEREMPATAN KARTASURA RELOCATION | Others |  | Central Java Ring 35E | MA-YO2533654-01H | 10.206.27.31 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-3651_1 | Swap_JAW-JT-SKH-3651 | JAW-JT-SKH-3651 | Central Java | Jawa Tengah | Sukoharjo | -7.5556 | 110.7428 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-3651 | PUCANGAN KARTASURA RELOCATION | Protelindo |  | Central Java Ring 35E | MA-YO3531536G-01H | 10.206.27.33 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1937_1 | Swap_JAW-JT-SKH-1937 | JAW-JT-SKH-1937 | Central Java | Jawa Tengah | Sukoharjo | -7.5724 | 110.7473 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1937 | NGADIREJO KARTASURA | Protelindo |  | Central Java Ring 35E | MA-YO3533353G-01H | 10.206.27.34 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-16 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1931_1 | Swap_JAW-JT-SKH-1931 | JAW-JT-SKH-1931 | Central Java | Jawa Tengah | Sukoharjo | -7.5508 | 110.7374 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1931 | Kartasura | Protelindo |  | Central Java Ring 35E | MA-YOB424-01H | 10.206.27.32 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1502_1 | Swap_JAW-JT-PTI-1502 | JAW-JT-PTI-1502 | Central Java | Jawa Tengah | Pati | -6.5843 | 111.0637 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1502 | Margotuhu Kidul | Others |  | Central Java Ring 45D | MA-SM2533109-01H | 10.219.27.117 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved |  |  | Done | Done | Done | DOEID251117L9 | [10 empty] | GCI | [14 empty] | 2025-11-24 | 48 | 2025-11-24 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-4012_1 | Swap_JAW-JT-PTI-4012 | JAW-JT-PTI-4012 | Central Java | Jawa Tengah | Pati | -6.7025 | 111.1243 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-4012 | LANGGENHARJO JUWANA RELOCATION | Protelindo |  | Central Java Ring 45D | MA-SM2534237-01H | 10.219.27.118 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved |  |  | Done | Done | Done | DOEID251117LB | [10 empty] | GCI | [14 empty] | 2025-11-24 | 48 | 2025-11-24 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1499_1 | Swap_JAW-JT-PTI-1499 | JAW-JT-PTI-1499 | Central Java | Jawa Tengah | Pati | -6.7207 | 111.0571 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1499 | Bapoh Pati | Protelindo |  | Central Java Ring 45D | MA-SM2534245-01H | 10.206.26.80 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved |  |  | Done | Done | Done | DOEID251117LD | [10 empty] | GCI | [14 empty] | 2025-11-24 | 48 | 2025-11-24 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1484_1 | Swap_JAW-JT-PTI-1484 | JAW-JT-PTI-1484 | Central Java | Jawa Tengah | Pati | -6.5769 | 111.0397 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1484 | Bancaran Kedung Sari C-Prtldo | Protelindo |  | Central Java Ring 45D | MA-SM253EH80-01H | 10.219.27.116 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved |  |  | Done | Done | Done | DOEID251117K0 | [10 empty] | Mingze | [14 empty] | 2025-11-24 | 48 | 2025-11-24 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1512_1 | Swap_JAW-JT-PTI-1512 | JAW-JT-PTI-1512 | Central Java | Jawa Tengah | Pati | -6.6673 | 111.101 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1512 | Juwanatayuasmppnc-Prtldo | Protelindo |  | Central Java Ring 45D | MA-SM253EH81-01H | 10.206.26.81 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-26 | Approved | 2025-10-17 |  | Submitted | Approved |  |  | Done | Done | Done | DOEID251117K2 | [10 empty] | Mingze | [14 empty] | 2025-11-24 | 48 | 2025-11-24 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1504_1 | Swap_JAW-JT-PTI-1504 | JAW-JT-PTI-1504 | Central Java | Jawa Tengah | Pati | -6.687 | 111.0679 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1504 | Panggungroyom Wedarijaksa | DMT |  | Central Java Ring 45D | MA-SM3533138G-01H | 10.219.27.114 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Propose Drop, MOCN Drop | 10 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-26 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1478_1 | Swap_JAW-JT-PTI-1478 | JAW-JT-PTI-1478 | Central Java | Jawa Tengah | Pati | -6.7336 | 111.0158 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1478 | SIDOKERTO PATI | TBG |  | Central Java Ring 45D | MA-SM3533367G-01H | 10.219.27.112 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID251117LF |  | 2025-11-23 | Done | Done |  |  | Done | Done | Done | Done | GCI |  |  | 2025-11-21 |  | 2025-11-21 | XLWO-20251121-00000441 |  |  | 2025-11-23 | [5 empty] | 2025-11-23 | 47 | 2025-11-23 | 2025-11-23 | Done | #N/A | #N/A |  | 2025-11-24
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1490_1 | Swap_JAW-JT-PTI-1490 | JAW-JT-PTI-1490 | Central Java | Jawa Tengah | Pati | -6.7239 | 111.0501 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1490 | Mulyoharjo Pati | TBG |  | Central Java Ring 45D | MA-SM3534387G-01H | 10.219.27.113 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID251117K3 |  | 2025-11-23 | Done | Done |  |  | Done | Done | Done | Done | Mingze |  |  | 2025-11-23 |  | 2025-11-21 | XLWO-20251121-00000441 |  |  | 2025-11-23 | [5 empty] | 2025-11-23 | 47 | 2025-11-23 | 2025-11-23 | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-3318_1 | Swap_JAW-JT-PTI-3318 | JAW-JT-PTI-3318 | Central Java | Jawa Tengah | Pati | -6.6256 | 111.0505 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-3318 | Masjidd Almutaqin | TBG |  | Central Java Ring 45D | MA-SM3535362G-01H | 10.219.27.115 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-25 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID251117K5 |  | 2025-11-23 | Done | Done |  |  | Done | Done | Done | Done | Mingze |  |  | 2025-11-23 |  | 2025-11-21 | XLWO-20251121-00000441 |  |  | 2025-11-23 | [5 empty] | 2025-11-23 | 47 | 2025-11-23 | 2025-11-23 | Done | #N/A | #N/A |  | 2025-11-24
1 | 1 | CLEAR | Swap_JAW-JT-KDL-3487_1 | Swap_JAW-JT-KDL-3487 | JAW-JT-KDL-3487 | Central Java | Jawa Tengah | Kendal | -6.96536111111111 | 110.270188888889 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-KDL-3487 | Supernode Mangkang | 0 |  | Central Java Ring 66 | PAG-SM2110-02H | #N/A | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-11-07 | 2025-11-08 | Approved | 2025-11-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0098_1 | Swap_JAW-JT-BBS-0098 | JAW-JT-BBS-0098 | Central Java | Jawa Tengah | Brebes | -6.956 | 108.9988 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0098 | Kebon Agung Brebes | DMT |  | Central Java Ring 70B | MA-SM2531437-01H | 10.206.1.162 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-31 | 2025-10-31 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0063_1 | Swap_JAW-JT-BBS-0063 | JAW-JT-BBS-0063 | Central Java | Jawa Tengah | Brebes | -6.9141 | 108.8981 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0063 | Sutamaja Brebes | Others |  | Central Java Ring 70B | MA-SM2531611-01H | 10.206.1.165 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-11-06 | 2025-11-06 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0086_1 | Swap_JAW-JT-BBS-0086 | JAW-JT-BBS-0086 | Central Java | Jawa Tengah | Brebes | -6.9259 | 108.9776 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0086 | Siwungkuk Brebes | Protelindo |  | Central Java Ring 70B | MA-SM2531753-01H | 10.206.1.164 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-11-06 | 2025-11-06 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0031_1 | Swap_JAW-JT-BBS-0031 | JAW-JT-BBS-0031 | Central Java | Jawa Tengah | Brebes | -6.9637 | 108.8483 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0031 | Ciawi Banjarharjo | Protelindo |  | Central Java Ring 70B | MA-SM2531759-01H | 10.206.9.252 | ATN910C-G | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-11-03 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0111_1 | Swap_JAW-JT-BBS-0111 | JAW-JT-BBS-0111 | Central Java | Jawa Tengah | Brebes | -6.9664 | 109.0227 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0111 | Jatibarang Barat Brebes | Others |  | Central Java Ring 70B | MA-SM2531858-01H | 10.206.9.251 | ATN910C-G | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-31 | 2025-10-31 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0115_1 | Swap_JAW-JT-BBS-0115 | JAW-JT-BBS-0115 | Central Java | Jawa Tengah | Brebes | -6.944 | 109.0285 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0115 | Bojong Jatibarang | Others |  | Central Java Ring 70B | MA-SM2531874-01H | 10.206.13.110 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-22 | 2025-10-30 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0038_1 | Swap_JAW-JT-BBS-0038 | JAW-JT-BBS-0038 | Central Java | Jawa Tengah | Brebes | -6.9444 | 108.862 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0038 | Kubangpari | Others |  | Central Java Ring 70B | MA-SM2531938-01H | 10.206.1.166 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-11-03 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0106_1 | Swap_JAW-JT-BBS-0106 | JAW-JT-BBS-0106 | Central Java | Jawa Tengah | Brebes | -6.9304 | 109.0145 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0106 | Jagalempeni Brebes | Protelindo |  | Central Java Ring 70B | MA-SM2532933-01H | 10.206.1.163 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-11-07 | 2025-11-07 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0082_1 | Swap_JAW-JT-BBS-0082 | JAW-JT-BBS-0082 | Central Java | Jawa Tengah | Brebes | -7.2554 | 108.9569 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0082 | Cibentang Brebes | Others |  | Central Java Ring 70B | MA-SM253C087-01H | 10.206.1.171 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-20 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0085_1 | Swap_JAW-JT-BBS-0085 | JAW-JT-BBS-0085 | Central Java | Jawa Tengah | Brebes | -6.9663 | 108.9744 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0085 | Siandong | Others |  | Central Java Ring 70B | MA-SM3531949G-01H | 10.206.1.161 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-31 | 2025-10-31 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-3005_1 | Swap_JAW-JT-BBS-3005 | JAW-JT-BBS-3005 | Central Java | Jawa Tengah | Brebes | -6.9503 | 108.987 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-3005 | SITANGGAL LARANGAN | Protelindo |  | Central Java Ring 70B | MA-SM3535245G-01H | 10.206.13.238 | ATN910C-G | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-31 | 2025-10-31 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-3332_1 | Swap_JAW-JT-BBS-3332 | JAW-JT-BBS-3332 | Central Java | Jawa Tengah | Brebes | -6.9067 | 109.0084 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-3332 | Tanjungsari Wanasari | TBG |  | Central Java Ring 70B | MA-SM3535589G-01H | 10.206.13.152 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-20 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0069_1 | Swap_JAW-JT-BBS-0069 | JAW-JT-BBS-0069 | Central Java | Jawa Tengah | Brebes | -7.2121 | 108.9155 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0069 | Bantarkawung | TBG |  | Central Java Ring 70B | MA-SMB416-01H | 10.206.1.170 | ATN910C-G | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-20 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0009_1 | Swap_JAW-JT-BBS-0009 | JAW-JT-BBS-0009 | Central Java | Jawa Tengah | Brebes | -7.1712 | 108.7993 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0009 | Salem Brebes | Protelindo |  | Central Java Ring 70B | MA-SMB417-01H | 10.206.1.168 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-11-21 | 2025-11-21 | Reviewing |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0015_1 | Swap_JAW-JT-BBS-0015 | JAW-JT-BBS-0015 | Central Java | Jawa Tengah | Brebes | -7.077 | 108.816 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0015 | Bandungsari | Others |  | Central Java Ring 70B | MA-SMD993-01H | 10.206.1.167 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-11-03 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SLW-2239_1 | Swap_JAW-JT-SLW-2239 | JAW-JT-SLW-2239 | Central Java | Jawa Tengah | Tegal | -6.9788 | 109.1403 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-SLW-2239 | Slawi | Protelindo |  | Central Java Ring 76 | PAG-SM2312-01H | 10.206.1.109 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GIT | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-14 | 2025-10-22 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SLW-2207_1 | Swap_JAW-JT-SLW-2207 | JAW-JT-SLW-2207 | Central Java | Jawa Tengah | Tegal | -7.0484 | 109.1005 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-SLW-2207 | Balapulang | Protelindo |  | Central Java Ring 76 | PAG-SM2481-01H | 10.206.1.110 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GIT | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-14 | 2025-10-22 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-YO-YYK-0492_1 | Swap_JAW-YO-YYK-0492 | JAW-YO-YYK-0492 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7893 | 110.3595 | Swap | Swap Only | Swap | Type C | PAG | JAW-YO-YYK-0492 | Mpls - Patok Yogyakartara | Direct Lease |  | Central Java Ring 79 | PAG-SM2236-04H | 10.206.13.51 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 13 | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | YPTT | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-25 | 2025-10-25 | Approved | 2025-11-13 |  | Submitted | Approved | [16 empty] | GPA | [14 empty] | 2025-11-27 | 48 | 2025-11-27 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2150_1 | Swap_JAW-JT-SKT-2150 | JAW-JT-SKT-2150 | Central Java | Jawa Tengah | Kota Surakarta | -7.5587 | 110.8275 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKT-2150 | SOLO RELOCATION | DMT |  | Central Java Ring 79 | PAG-SMSN0070-04H | 10.206.13.57 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 13 | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | YPTT | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-15 | 2025-10-16 | Approved | 2025-11-13 |  | Submitted | Approved | [16 empty] | YPTT | [14 empty] | 2025-11-27 | 48 | 2025-11-27 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-0999_1 | Swap_JAW-JT-KLN-0999 | JAW-JT-KLN-0999 | Central Java | Jawa Tengah | Klaten | -7.7418 | 110.5526 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-0999 | Rejoso Jogonalan | DMT |  | Central Java Ring 79A | MA-JTKLN0999-01H | 10.206.29.18 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 13 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-15 | 42 | October | Oct | 2025 | 2025-11-14 | 2025-11-14 | Approved | 2025-11-17 |  | Submitted | Approved | [16 empty] | YPTT | [14 empty] | 2025-11-30 | 48 | 2025-11-30 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-YO-SMN-0336_1 | Swap_JAW-YO-SMN-0336 | JAW-YO-SMN-0336 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.7736 | 110.467 | Swap | Swap Only | Swap | Type B | MA | JAW-YO-SMN-0336 | Dogongan Tirtomartani | Protelindo |  | Central Java Ring 79A | MA-SM2533607-01H | 10.206.13.58 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 13 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | YPTT | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-20 | 2025-10-21 | Approved | 2025-10-17 |  | Submitted | Approved | [16 empty] | YPTT | [14 empty] | 2025-11-27 | 48 | 2025-11-27 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1941_1 | Swap_JAW-JT-SKH-1941 | JAW-JT-SKH-1941 | Central Java | Jawa Tengah | Sukoharjo | -7.5787 | 110.7616 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1941 | Moyang Gumpang | DMT |  | Central Java Ring 79A | MA-SM2533631-01H | 10.206.13.55 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 13 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-17 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [16 empty] | GPA | [14 empty] | 2025-11-30 | 48 | 2025-11-30 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-0997_1 | Swap_JAW-JT-KLN-0997 | JAW-JT-KLN-0997 | Central Java | Jawa Tengah | Klaten | -7.7503 | 110.5406 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-0997 | Somopuro Jogonalan | Centratama |  | Central Java Ring 79A | MA-SM3533317G-01H | 10.206.13.53 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 13 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-15 | 42 | October | Oct | 2025 | 2025-11-14 | 2025-11-14 | Approved | 2025-11-17 |  | Submitted | Approved | [16 empty] | GIT | [14 empty] | 2025-11-30 | 48 | 2025-11-30 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1926_1 | Swap_JAW-JT-SKH-1926 | JAW-JT-SKH-1926 | Central Java | Jawa Tengah | Klaten | -7.596 | 110.7215 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1926 | KAGOKAN SUKOHARJO | TBG |  | Central Java Ring 79A | MA-SM3534921G-01H | 10.206.13.54 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 13 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-15 | 42 | October | Oct | 2025 | 2025-10-20 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | [16 empty] | GIT | [14 empty] | 2025-11-30 | 48 | 2025-11-30 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-3292_1 | Swap_JAW-JT-KLN-3292 | JAW-JT-KLN-3292 | Central Java | Jawa Tengah | Klaten | -7.7313 | 110.5711 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-3292 | Sumyang Jagonalang | DMT |  | Central Java Ring 79A | MA-SM3535395G-01H | 10.206.13.59 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 13 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-15 | 42 | October | Oct | 2025 | 2025-10-21 | 2025-10-21 | Approved | 2025-10-17 |  | Submitted | Approved | [16 empty] | GCI | [14 empty] | 2025-11-30 | 48 | 2025-11-30 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-3177_1 | Swap_JAW-JT-SKH-3177 | JAW-JT-SKH-3177 | Central Java | Jawa Tengah | Sukoharjo | -7.5674 | 110.7762 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-3177 | MAKAMHAJI GATAK | TBG |  | Central Java Ring 79A | MA-SM3535497G-01H | 10.206.13.219 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Propose Drop, MOCN Drop | 13 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-20 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | [16 empty] | GCI | [14 empty] | 2025-11-30 | 48 | 2025-11-30 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2066_1 | Swap_JAW-JT-SKT-2066 | JAW-JT-SKT-2066 | Central Java | Jawa Tengah | Kota Surakarta | -7.56 | 110.8079 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKT-2066 | Manahan | Protelindo |  | Central Java Ring 79A | MA-SMB407-01H | 10.206.13.56 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 13 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | YPTT | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-19 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | [16 empty] | GCI | [14 empty] | 2025-11-30 | 48 | 2025-11-30 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PBG-1276_1 | Swap_JAW-JT-PBG-1276 | JAW-JT-PBG-1276 | Central Java | Jawa Tengah | Purbalingga | -7.3873 | 109.3623 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-PBG-1276 | Purbalngga | Protelindo |  | Central Java Ring 80 | PAG-SM2333-04H | 10.206.9.195 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GIT | 2025-10-16 | 42 | October | Oct | 2025 | 2025-11-03 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PML-1365_1 | Swap_JAW-JT-PML-1365 | JAW-JT-PML-1365 | Central Java | Jawa Tengah | Pemalang | -7.1009 | 109.3267 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-PML-1365 | Randudongkal | Protelindo |  | Central Java Ring 80 | PAG-SM2431-02H | 10.206.9.194 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GIT | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-21 | 2025-10-21 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-JPA-0619_1 | Swap_JAW-JT-JPA-0619 | JAW-JT-JPA-0619 | Central Java | Jawa Tengah | Jepara | -6.5942 | 110.6638 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-JPA-0619 | Jepara | Protelindo |  | MBH Central Java Ring 12A | MA-JTJPA0619-01H | 10.219.39.11 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 4 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-30 | 2025-10-30 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-15 |  | Done | Done | 2025-11-08 | DOEID251107NR | 2025-11-16 | 2025-11-16 | done | done |  |  | done | done | done | done | GIT | 2025-11-16 | 46 | 2025-11-16 |  | 2025-11-10 | XLWO-20251110-00001850 |  | 2025-11-19 | 2025-11-16 | 2025-11-19 | 47 | 2025-11-19 | 47 | TRUE | 2025-11-16 | 46 | 2025-11-16 | 2025-11-16 | Done | #N/A | #N/A | November | 2025-11-18 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-JPA-0651_1 | Swap_JAW-JT-JPA-0651 | JAW-JT-JPA-0651 | Central Java | Jawa Tengah | Jepara | -6.7307 | 110.723 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-JPA-0651 | Pecangaan | Protelindo |  | MBH Central Java Ring 12A | MA-JTJPA0651-01H | 10.219.37.24 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 4 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-24 | 2025-10-24 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-15 |  | Done | Done | 2025-11-08 | DOEID251107NS | 2025-11-16 | 2025-11-16 | done | done |  |  | done | done | done | done | GIT | 2025-11-16 | 46 | 2025-11-16 |  | 2025-11-10 | XLWO-20251110-00001850 |  | 2025-11-19 | 2025-11-16 | 2025-11-19 | 47 | 2025-11-19 | 47 | TRUE | 2025-11-16 | 46 | 2025-11-16 | 2025-11-16 | Done | #N/A | #N/A | November | 2025-11-18 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-JPA-0635_1 | Swap_JAW-JT-JPA-0635 | JAW-JT-JPA-0635 | Central Java | Jawa Tengah | Jepara | -6.6883 | 110.7073 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-JPA-0635 | Pecangaan Kota | Centratama |  | MBH Central Java Ring 12A | MA-JTJPA0635-01H | 10.219.37.25 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 4 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-14 | 2025-10-22 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-14 |  | Done | Done | 2025-11-08 | DOEID251107MC | 2025-11-16 | 2025-11-14 | done | done |  |  | done | done | done | done | GPA | 2025-11-16 | 46 | 2025-11-14 |  | 2025-11-10 | XLWO-20251110-00001850 |  | 2025-11-19 | 2025-11-16 | 2025-11-19 | 47 | 2025-11-19 | 47 | TRUE | 2025-11-16 | 46 | 2025-11-16 | 2025-11-16 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-JPA-0647_1 | Swap_JAW-JT-JPA-0647 | JAW-JT-JPA-0647 | Central Java | Jawa Tengah | Jepara | -6.7837 | 110.7226 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-JPA-0647 | Welahan | Centratama |  | MBH Central Java Ring 12A | MA-JTJPA0647-01H | 10.219.37.231 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 4 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2025-10-22 | 43 | October | Oct | 2025 | 2025-11-04 | 2025-11-04 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107ME | 2025-11-16 | 2025-11-13 | done | done |  |  | done | done | done | done | GPA | 2025-11-16 | 46 | 2025-11-13 |  | 2025-11-10 | XLWO-20251110-00001850 |  | 2025-11-19 | 2025-11-13 | 2025-11-19 | 47 | 2025-11-19 | 47 | TRUE | 2025-11-13 | 46 | 2025-11-13 | 2025-11-13 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1497_1 | Swap_JAW-JT-PTI-1497 | JAW-JT-PTI-1497 | Central Java | Jawa Tengah | Pati | -6.5364 | 111.0546 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1497 | Tayu | Others |  | MBH Central Java Ring 12A | MA-JTPTI1497-01H | 10.219.37.55 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 4 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-26 | 2025-10-26 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-15 |  | Done | Done | 2025-11-08 | DOEID251107NT | 2025-11-17 | 2025-11-16 | done | done |  |  | done | done | done | done | GIT | 2025-11-17 | 47 | 2025-11-16 |  | 2025-11-10 | XLWO-20251110-00001850 |  | 2025-11-20 | 2025-11-16 | 2025-11-20 | 47 | 2025-11-20 | 47 | TRUE | 2025-11-16 | 46 | 2025-11-16 | 2025-11-16 | Done | #N/A | #N/A | November | 2025-11-18 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1505_1 | Swap_JAW-JT-PTI-1505 | JAW-JT-PTI-1505 | Central Java | Jawa Tengah | Pati | -6.6661 | 111.0683 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1505 | Trangkil | Protelindo |  | MBH Central Java Ring 12A | MA-JTPTI1505-01H | 10.219.37.234 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 4 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-25 | 2025-10-25 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-15 |  | Done | Done | 2025-11-08 | DOEID251107NV | 2025-11-17 | 2025-11-16 | done | done |  |  | done | done | done | done | GIT | 2025-11-17 | 47 | 2025-11-16 |  | 2025-11-10 | XLWO-20251110-00001850 |  | 2025-11-20 | 2025-11-16 | 2025-11-20 | 47 | 2025-11-20 | 47 | TRUE | 2025-11-16 | 46 | 2025-11-16 | 2025-11-16 | Done | #N/A | #N/A | November | 2025-11-18 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-JPA-0628_1 | Swap_JAW-JT-JPA-0628 | JAW-JT-JPA-0628 | Central Java | Jawa Tengah | Jepara | -6.5686 | 110.6869 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-JPA-0628 | Mambak | Protelindo |  | MBH central Java Ring 12A | MA-JTJPA0628-01H | 10.219.37.253 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 4 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-27 | 2025-10-27 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-15 |  | Done | Done | 2025-11-08 | DOEID251107OY | 2025-11-17 | 2025-11-15 | done | done |  |  | done | done | done | done | YPTT | 2025-11-17 | 47 | 2025-11-15 |  | 2025-11-10 | XLWO-20251110-00001850 |  | 2025-11-20 | 2025-11-16 | 2025-11-20 | 47 | 2025-11-20 | 47 | TRUE | 2025-11-16 | 46 | 2025-11-16 | 2025-11-16 | Done | #N/A | #N/A | November | 2025-11-17 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-JPA-0672_1 | Swap_JAW-JT-JPA-0672 | JAW-JT-JPA-0672 | Central Java | Jawa Tengah | Jepara | -6.4821 | 110.8654 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-JPA-0672 | Keling | Protelindo |  | MBH Central Java Ring 12A | MA-JTJPA0672-01H | 10.219.37.54 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 4 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-29 | 2025-10-29 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-15 |  | Done | Done | 2025-11-08 | DOEID251107OW | 2025-11-15 | 2025-11-15 | done | done |  |  | done | done | done | done | YPTT | 2025-11-15 | 46 | 2025-11-15 |  | 2025-11-10 | XLWO-20251110-00001850 |  | 2025-11-18 | 2025-11-16 | 2025-11-18 | 47 | 2025-11-18 | 47 | TRUE | 2025-11-16 | 46 | 2025-11-16 | 2025-11-16 | Done | #N/A | #N/A | November | 2025-11-20
1 | 1 | CLEAR | Swap_JAW-JT-JPA-0638_1 | Swap_JAW-JT-JPA-0638 | JAW-JT-JPA-0638 | Central Java | Jawa Tengah | Jepara | -6.5274 | 110.7113 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-JPA-0638 | Mlonggo | Protelindo |  | MBH Central Java Ring 12A | MA-JTJPA0638-01H | 10.219.37.53 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 4 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-14 | 2025-10-22 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-15 |  | Done | Done | 2025-11-08 | DOEID251107NP | 2025-11-15 | 2025-11-16 | done | done |  |  | done | done | done | done | GIT | 2025-11-15 | 46 | 2025-11-16 |  | 2025-11-10 | XLWO-20251110-00001850 |  | 2025-11-18 | 2025-11-16 | 2025-11-18 | 47 | 2025-11-18 | 47 | TRUE | 2025-11-16 | 46 | 2025-11-16 | 2025-11-16 | Done | #N/A | #N/A | November | 2025-11-18 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-JPA-0629_1 | Swap_JAW-JT-JPA-0629 | JAW-JT-JPA-0629 | Central Java | Jawa Tengah | Jepara | -6.6204 | 110.6881 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-JPA-0629 | Tahunan | Centratama |  | MBH Central Java Ring 12A | MA-JTJPA0629-01H | 10.219.37.26 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 4 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-27 | 2025-10-27 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-15 |  | Done | Done | 2025-11-08 | DOEID251107NQ | 2025-11-15 | 2025-11-16 | done | done |  |  | done | done | done | done | GIT | 2025-11-15 | 46 | 2025-11-16 |  | 2025-11-10 | XLWO-20251110-00001850 |  | 2025-11-18 | 2025-11-16 | 2025-11-18 | 47 | 2025-11-18 | 47 | TRUE | 2025-11-16 | 46 | 2025-11-16 | 2025-11-16 | Done | #N/A | #N/A | November | 2025-11-18 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-MKD-1216_1 | Swap_JAW-JT-MKD-1216 | JAW-JT-MKD-1216 | Central Java | Jawa Tengah | Magelang | -7.3834 | 110.2549 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-MKD-1216 | Secang | Others |  | MBH Central Java Ring 13E | MA-JTMKD1216-01H | 10.219.37.13 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GIT | 2025-10-15 | 42 | October | Oct | 2025 | 2025-10-25 | 2025-10-25 | Approved | 2025-10-17 |  | Submitted | Approved | [16 empty] | GIT | [14 empty] | 2025-11-27 | 48 | 2025-11-27 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-2662_1 | Swap_JAW-JT-UNR-2662 | JAW-JT-UNR-2662 | Central Java | Jawa Tengah | Semarang | -7.2183 | 110.3467 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-2662 | Candi Ambarawa | TBG |  | MBH Central Java Ring 13E | MA-JTUNR2662-01H | 10.219.37.129 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | Mid Dec 25 | GIT | 2025-10-28 | 44 | October | Oct | 2025 | 2025-10-25 | 2025-10-25 | Approved | 2025-10-17 |  | Submitted | Approved | [16 empty] | GIT | [14 empty] | 2025-11-25 | 48 | 2025-11-25 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-2663_1 | Swap_JAW-JT-UNR-2663 | JAW-JT-UNR-2663 | Central Java | Jawa Tengah | Semarang | -7.3046 | 110.3562 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-2663 | Bedono | Protelindo |  | MBH Central Java Ring 13E | MA-JTUNR2663-01H | 10.219.37.12 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | Mid Dec 25 | GIT | 2025-10-28 | 44 | October | Oct | 2025 | 2025-10-23 | 2025-10-23 | Approved | 2025-10-17 |  | Submitted | Approved | [16 empty] | GIT | [14 empty] | 2025-11-25 | 48 | 2025-11-25 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-2665_1 | Swap_JAW-JT-UNR-2665 | JAW-JT-UNR-2665 | Central Java | Jawa Tengah | Semarang | -7.2234 | 110.3672 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-2665 | Bandungan | Protelindo |  | MBH Central Java Ring 13E | MA-JTUNR2665-01H | 10.219.37.224 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | Mid Dec 25 | GIT | 2025-10-28 | 44 | October | Oct | 2025 | 2025-10-25 | 2025-10-25 | Approved | 2025-10-17 |  | Submitted | Approved | [16 empty] | GPA | [14 empty] | 2025-11-25 | 48 | 2025-11-25 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-2666_1 | Swap_JAW-JT-UNR-2666 | JAW-JT-UNR-2666 | Central Java | Jawa Tengah | Semarang | -7.2744 | 110.3695 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-2666 | Jambu | TBG |  | MBH Central Java Ring 13E | MA-JTUNR2666-01H | 10.219.37.245 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | Mid Dec 25 | GIT | 2025-10-27 | 44 | October | Oct | 2025 | 2025-10-20 | 2025-10-24 | Approved | 2025-10-17 |  | Submitted | Approved | [16 empty] | GIT | [14 empty] | 2025-11-25 | 48 | 2025-11-25 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-2682_1 | Swap_JAW-JT-UNR-2682 | JAW-JT-UNR-2682 | Central Java | Jawa Tengah | Semarang | -7.2518 | 110.4013 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-2682 | Kota Ambarawa Reloc | TBG |  | MBH Central Java Ring 13E | MA-JTUNR2682-01H | 10.219.37.241 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | Mid Dec 25 | GIT | 2025-10-27 | 44 | October | Oct | 2025 | 2025-10-20 | 2025-10-21 | Approved | 2025-10-17 |  | Submitted | Approved | [16 empty] | GIT | [14 empty] | 2025-11-25 | 48 | 2025-11-25 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-2690_1 | Swap_JAW-JT-UNR-2690 | JAW-JT-UNR-2690 | Central Java | Jawa Tengah | Semarang | -7.2737 | 110.412 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-2690 | Pojoksari Ambarawa | Protelindo |  | MBH Central Java Ring 13E | MA-JTUNR2690-01H | 10.219.37.243 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | Mid Dec 25 | GIT | 2025-10-27 | 44 | October | Oct | 2025 | 2025-10-17 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | [16 empty] | YPTT | [14 empty] | 2025-11-25 | 48 | 2025-11-25 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-3316_1 | Swap_JAW-JT-UNR-3316 | JAW-JT-UNR-3316 | Central Java | Jawa Tengah | Semarang | -7.2571 | 110.4237 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-3316 | Tambakboyo Ambarawa | TBG |  | MBH Central Java Ring 13E | MA-JTUNR3316-01H | 10.219.37.244 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | Mid Dec 25 | GIT | 2025-10-27 | 44 | October | Oct | 2025 | 2025-10-17 | 2025-10-22 | Approved | 2025-10-17 |  | Submitted | Approved | [16 empty] | GIT | [14 empty] | 2025-11-26 | 48 | 2025-11-26 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-3338_1 | Swap_JAW-JT-UNR-3338 | JAW-JT-UNR-3338 | Central Java | Jawa Tengah | Semarang | -7.2717 | 110.4 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-3338 | Merpati Ambarawa | Others |  | MBH Central Java Ring 13E | MA-JTUNR3338-01H | 10.219.37.242 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | Mid Dec 25 | GIT | 2025-10-28 | 44 | October | Oct | 2025 | 2025-10-23 | 2025-10-23 | Approved | 2025-10-17 |  | Submitted | Approved | [16 empty] | GIT | [14 empty] | 2025-11-26 | 48 | 2025-11-26 |  | Done | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-KDL-3487_2 | Swap_JAW-JT-KDL-3487 | JAW-JT-KDL-3487 | Central Java | Jawa Tengah | Kendal | -6.96536111111111 | 110.270188888889 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-KDL-3487 | Supernode Mangkang | 0 |  | Central Java Ring 05 | PAG-JTSMG2526-03H | 10.219.36.2 | ATN910C | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-20 | 43 | October |  | 2025 | 2025-11-08 | 2025-11-08 | Approved | 2025-11-17 | [36 empty] | #N/A |  | NY | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BNR-0237_1 | Swap_JAW-JT-BNR-0237 | JAW-JT-BNR-0237 | Central Java | Jawa Tengah | Banjarnegara | -7.396 | 109.697 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-BNR-0237 | Banjarnegara | Protelindo |  | Central Java Ring 101 | PAG-JTBNR0237-05H | 10.206.54.34 | ATN910C | Huawei | New Purchase | Linknet NNI,PAG1 | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | CCSI | 2025-11-26 | 48 |  |  | 2025 | 2025-10-29 | 2025-10-29 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PWT-1716_1 | Swap_JAW-JT-PWT-1716 | JAW-JT-PWT-1716 | Central Java | Jawa Tengah | Banyumas | -7.4218 | 109.2214 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-PWT-1716 | Mpls - Purwokerto | Direct Lease |  | Central Java Ring 101 | PAG-JTPWT1716-07H | 10.206.54.33 | ATN910C | Huawei | New Purchase | Linknet NNI,PAG2 | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | NY | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1923_1 | Swap_JAW-JT-SKH-1923 | JAW-JT-SKH-1923 | Central Java | Jawa Tengah | Sukoharjo | -7.68366944444444 | 110.8363 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKH-1923 | Supernode Solo | 0 |  | Central Java Ring 11 | PAG-YGSN0070-06H | 10.219.36.22 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [11 empty] | 2025-11-26 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PBG-1263_1 | Swap_JAW-JT-PBG-1263 | JAW-JT-PBG-1263 | Central Java | Jawa Tengah | Purbalingga | -7.2267 | 109.3257 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-PBG-1263 | Karang Reja Purbalingga | Protelindo |  | Central Java Ring 119 | PAG-JTPBG1263-02H | 10.206.30.179 | ATN910C | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | CCSI | 2025-11-26 | 48 |  |  | 2025 | 2025-11-07 | 2025-11-10 | Approved | 2025-11-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PML-1427_1 | Swap_JAW-JT-PML-1427 | JAW-JT-PML-1427 | Central Java | Jawa Tengah | Pemalang | -7.0136 | 109.4904 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-PML-1427 | Bodeh Pemalang | Centratama |  | Central Java Ring 119 | PAG-JTPML1427-02H | 10.206.30.180 | ATN910C | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | CCSI | 2025-11-26 | 48 |  |  | 2025 | 2025-10-25 | 2025-10-30 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-TGL-2576_1 | Swap_JAW-JT-TGL-2576 | JAW-JT-TGL-2576 | Central Java | Jawa Tengah | Kota Tegal | -6.877 | 109.1045 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-TGL-2576 | Sumur Panggang | Protelindo |  | Central Java Ring 13A | PAG-SM2483-01H | 10.219.217.72 | NE40E(V8) | Huawei | New Purchase | Linknet NNI,PAG1 | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-17 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-TGL-2600_1 | Swap_JAW-JT-TGL-2600 | JAW-JT-TGL-2600 | Central Java | Jawa Tengah | Kota Tegal | -6.8618 | 109.143 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-TGL-2600 | HUT Tegal | Direct Lease |  | Central Java Ring 14 | PAG-SM2309-01H | 10.219.217.73 | NE40E(V8) | Huawei | New Purchase | Linknet NNI,PAG2 | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-17 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-YO-SMN-0067_1 | Swap_JAW-YO-SMN-0067 | JAW-YO-SMN-0067 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.6449 | 110.4231 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-YO-SMN-0067 | Kaliurang | Protelindo |  | Central Java Ring 16 | PAG-YG2265-01H | 10.219.217.16 | ATN910C-B | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | PT IFORTE SOLUSI INFOTEK |  |  | #N/A | [5 empty] | 2025-11-09 |  |  |  | 2025-End Nov |  | 2025-11-27 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [16 empty] | YPTT | [14 empty] | 2025-11-27 | 48 | 2025-11-27 |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-YO-SMN-0292_1 | Swap_JAW-YO-SMN-0292 | JAW-YO-SMN-0292 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.7645 | 110.4236 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-YO-SMN-0292 | Kalasan | Others |  | Central Java Ring 16 | PAG-YG2271-01H | 10.219.217.17 | ATN910C-B | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2025-11-27 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [16 empty] | GPA | [14 empty] | 2025-11-27 | 48 | 2025-11-27 |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-YO-BTL-0074_1 | Swap_JAW-YO-BTL-0074 | JAW-YO-BTL-0074 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9223 | 110.382 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-YO-BTL-0074 | Imogiri | Centratama |  | Central Java Ring 21 | PAG-YG2276-01H | 10.219.217.157 | ATN910C-B | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2025-11-27 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-YO-WNO-0012_1 | Swap_JAW-YO-WNO-0012 | JAW-YO-WNO-0012 | Central Java | Daerah Istimewa Yogyakarta | Gunungkidul | -7.9688 | 110.5969 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-YO-WNO-0012 | WONOSARI RELOCATION | Protelindo |  | Central Java Ring 21 | PAG-YG2278-02H | 10.219.217.158 | ATN910C-B | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [11 empty] | 2025-11-27 | 48 |  |  | 2025 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-SKT-2150_2 | Swap_JAW-JT-SKT-2150 | JAW-JT-SKT-2150 | Central Java | Jawa Tengah | Kota Surakarta | -7.5587 | 110.8275 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKT-2150 | SOLO RELOCATION | DMT |  | Central Java Ring 24 | PAG-YG2225-01H | 10.219.221.225 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 12 | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | YPTT | 2025-10-20 | 43 | October | Oct | 2025 |  |  | Not Started |  |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2125_1 | Swap_JAW-JT-SKT-2125 | JAW-JT-SKT-2125 | Central Java | Jawa Tengah | Kota Surakarta | -7.5558 | 110.8441 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKT-2125 | Tentara Pelajar | Centratama |  | Central Java Ring 24 | PAG-YG2370-01H | 10.219.221.226 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 12 | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | YPTT | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-19 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2081_1 | Swap_JAW-JT-SKT-2081 | JAW-JT-SKT-2081 | Central Java | Jawa Tengah | Kota Surakarta | -7.5677 | 110.8173 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKT-2081 | Gajahmada Solo | Protelindo |  | Central Java Ring 24B | MA-YG2371-01H | 10.219.221.37 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch | Keep | 12 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | YPTT | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-17 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-2141_1 | Swap_JAW-JT-KRG-2141 | JAW-JT-KRG-2141 | Central Java | Jawa Tengah | Karanganyar | -7.5551 | 110.8749 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-2141 | Ngringo Palur | Protelindo |  | Central Java Ring 24B | MA-YG2533616-01H | 10.219.221.241 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch | Keep | 12 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-18 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2074_1 | Swap_JAW-JT-SKT-2074 | JAW-JT-SKT-2074 | Central Java | Jawa Tengah | Kota Surakarta | -7.5586 | 110.8141 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKT-2074 | Mt Haryono Solo | TBG |  | Central Java Ring 24B | MA-YG2533622-01H | 10.219.221.236 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch | Keep | 12 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | YPTT | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-17 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2071_1 | Swap_JAW-JT-SKT-2071 | JAW-JT-SKT-2071 | Central Java | Jawa Tengah | Kota Surakarta | -7.536 | 110.8109 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKT-2071 | #N/A | Direct Lease |  | Central Java Ring 24B | MA-YG2533636-01H | 10.219.221.240 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch | Keep | 12 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | YPTT | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-17 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-2060_1 | Swap_JAW-JT-KRG-2060 | JAW-JT-KRG-2060 | Central Java | Jawa Tengah | Karanganyar | -7.5358 | 110.8001 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-2060 | Banyuanyar2 | Protelindo |  | Central Java Ring 24B | MA-YG2533644-01H | 10.219.221.239 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch | Keep | 12 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-14 | 2025-10-15 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-2139_1 | Swap_JAW-JT-KRG-2139 | JAW-JT-KRG-2139 | Central Java | Jawa Tengah | Karanganyar | -7.5647 | 110.8683 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-2139 | Puncang Sawit | TBG |  | Central Java Ring 24B | MA-YG2533661-01H | 10.219.221.242 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch | Keep | 12 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-15 | 2025-10-16 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-2140_1 | Swap_JAW-JT-KRG-2140 | JAW-JT-KRG-2140 | Central Java | Jawa Tengah | Karanganyar | -7.5669 | 110.8737 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-2140 | Palur Mall | Centratama |  | Central Java Ring 24B | MA-YG253PX299-01H | 10.206.13.6 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 12 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-14 | 2025-10-15 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2075_1 | Swap_JAW-JT-SKT-2075 | JAW-JT-SKT-2075 | Central Java | Jawa Tengah | Kota Surakarta | -7.5498 | 110.8153 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKT-2075 | Tirtonadi | Protelindo |  | Central Java Ring 24B | MA-YG3533625G-01H | 10.219.221.235 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch | Keep | 12 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | YPTT | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-16 | 2025-10-16 | Approved | 2025-10-17 |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-2052_1 | Swap_JAW-JT-KRG-2052 | JAW-JT-KRG-2052 | Central Java | Jawa Tengah | Karanganyar | -7.5368 | 110.7925 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-2052 | Sumber Surakarta | Centratama |  | Central Java Ring 24B | MA-YGB408-01H | 10.219.221.238 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch | Keep | 12 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-14 | 2025-10-15 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0540_1 | Swap_JAW-JT-DMK-0540 | JAW-JT-DMK-0540 | Central Java | Jawa Tengah | Demak | -6.9871 | 110.6834 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0540 | SARIMULYO DEMAK | Protelindo |  | Central Java Ring 25D | MA-JTDMK0540-01H | 10.206.29.160 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-24 | 2025-10-31 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107O8 | 2025-11-08 | 2025-11-11 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-08 | 45 | 2025-11-11 |  | 2025-11-10 | XLWO-20251110-00001844 |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | 46 | 2025-11-11 | 46 | TRUE | 2025-11-11 | 46 | 2025-11-11 | 2025-11-11 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0562_1 | Swap_JAW-JT-DMK-0562 | JAW-JT-DMK-0562 | Central Java | Jawa Tengah | Demak | -6.9586 | 110.5453 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0562 | Perampelan Sayung | DMT |  | Central Java Ring 25D | MA-JTDMK0562-01H | 10.206.29.162 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-25 | 2025-10-25 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-09 |  | Done | Done | 2025-11-08 | DOEID251107LN | 2025-11-08 | 2025-11-10 | done | done |  |  | done | done | done | done | GPA | 2025-11-08 | 45 | 2025-11-10 |  | 2025-11-10 | XLWO-20251110-00001844 |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | 46 | 2025-11-11 | 46 | TRUE | 2025-11-11 | 46 | 2025-11-11 | 2025-11-11 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0565_1 | Swap_JAW-JT-DMK-0565 | JAW-JT-DMK-0565 | Central Java | Jawa Tengah | Demak | -7.0929 | 110.5591 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0565 | Jragung Karangawen Demak | TBG |  | Central Java Ring 25D | MA-JTDMK0565-01H | 10.206.29.164 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-24 | 2025-10-31 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-09 |  | Done | Done | 2025-11-08 | DOEID251107LO | 2025-11-08 | 2025-11-10 | done | done |  |  | done | done | done | done | GPA | 2025-11-08 | 45 | 2025-11-10 |  | 2025-11-10 | XLWO-20251110-00001844 |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | 46 | 2025-11-11 | 46 | TRUE | 2025-11-11 | 46 | 2025-11-11 | 2025-11-11 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0575_1 | Swap_JAW-JT-DMK-0575 | JAW-JT-DMK-0575 | Central Java | Jawa Tengah | Demak | -7.0521 | 110.5961 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0575 | Rejosari Karangawen | TBG |  | Central Java Ring 25D | MA-JTDMK0575-01H | 10.206.29.163 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-24 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107LP | 2025-11-09 | 2025-11-11 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-09 | 45 | 2025-11-11 |  | 2025-11-10 | XLWO-20251110-00001844 |  | 2025-11-12 | 2025-11-11 | 2025-11-12 | 46 | 2025-11-12 | 46 | TRUE | 2025-11-11 | 46 | 2025-11-11 | 2025-11-11 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0584_1 | Swap_JAW-JT-DMK-0584 | JAW-JT-DMK-0584 | Central Java | Jawa Tengah | Demak | -6.9283 | 110.6297 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0584 | Ploso Demak | DMT |  | Central Java Ring 25D | MA-JTDMK0584-01H | 10.206.29.159 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-25 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107LR | 2025-11-09 | 2025-11-11 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-09 | 45 | 2025-11-11 |  | 2025-11-10 | XLWO-20251110-00001844 |  | 2025-11-12 | 2025-11-11 | 2025-11-12 | 46 | 2025-11-12 | 46 | TRUE | 2025-11-11 | 46 | 2025-11-11 | 2025-11-11 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0593_1 | Swap_JAW-JT-DMK-0593 | JAW-JT-DMK-0593 | Central Java | Jawa Tengah | Demak | -6.912 | 110.658 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0593 | Mojodemak Wonosalam | Centratama |  | Central Java Ring 25D | MA-JTDMK0593-01H | 10.206.29.158 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-25 | 2025-10-25 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107LS | 2025-11-09 | 2025-11-11 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-09 | 45 | 2025-11-11 |  | 2025-11-10 | XLWO-20251110-00001844 |  | 2025-11-12 | 2025-11-11 | 2025-11-12 | 46 | 2025-11-12 | 46 | TRUE | 2025-11-11 | 46 | 2025-11-11 | 2025-11-11 | Done | #N/A | #N/A | November | 2025-11-20 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-1543_1 | Swap_JAW-JT-DMK-1543 | JAW-JT-DMK-1543 | Central Java | Jawa Tengah | Demak | -7.0185 | 110.6963 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-1543 | Kebonagung (Colocated Hcpt) | Protelindo |  | Central Java Ring 25D | MA-JTDMK1543-01H | 10.206.29.161 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-25 | 2025-11-10 | Approved | 2025-11-13 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107LT | 2025-11-09 | 2025-11-11 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-09 | 45 | 2025-11-11 |  | 2025-11-10 | XLWO-20251110-00001844 |  | 2025-11-12 | 2025-11-11 | 2025-11-12 | 46 | 2025-11-12 | 46 | TRUE | 2025-11-11 | 46 | 2025-11-11 | 2025-11-11 | Done | #N/A | #N/A | November | 2025-11-20 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0564_1 | Swap_JAW-JT-DMK-0564 | JAW-JT-DMK-0564 | Central Java | Jawa Tengah | Demak | -7.12 | 110.5526 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0564 | Jragung Karangawen | TBG |  | Central Java Ring 25E | MA-JTDMK0564-01H | 10.206.29.172 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-11-03 | 45 |  |  | 2025 | 2025-10-24 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107OQ | 2025-11-09 | 2025-11-11 | Done | Done |  |  | Done | Done | Done | Done | YPTT | 2025-11-09 | 45 | 2025-11-11 |  | 2025-11-11 | XLWO-20251111-00000513 |  | 2025-11-12 | 2025-11-12 | 2025-11-12 | 46 | 2025-11-12 | 46 | TRUE | 2025-11-12 | 46 | 2025-11-12 | 2025-11-12 | Done | #N/A | #N/A | November | 2025-11-17 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0567_1 | Swap_JAW-JT-DMK-0567 | JAW-JT-DMK-0567 | Central Java | Jawa Tengah | Demak | -7.0651 | 110.567 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0567 | Tlogorejo Karangawen | Others |  | Central Java Ring 25E | MA-JTDMK0567-01H | 10.206.29.171 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-11-03 | 45 |  |  | 2025 | 2025-10-24 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107OR | 2025-11-09 | 2025-11-11 | Done | Done |  |  | Done | Done | Done | Done | YPTT | 2025-11-09 | 45 | 2025-11-11 |  | 2025-11-11 | XLWO-20251111-00000513 |  | 2025-11-12 | 2025-11-12 | 2025-11-12 | 46 | 2025-11-12 | 46 | TRUE | 2025-11-12 | 46 | 2025-11-12 | 2025-11-12 | Done | #N/A | #N/A | November | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0577_1 | Swap_JAW-JT-DMK-0577 | JAW-JT-DMK-0577 | Central Java | Jawa Tengah | Demak | -7.0048 | 110.5959 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0577 | Pundenarum Karangawen | Protelindo |  | Central Java Ring 25E | MA-JTDMK0577-01H | 10.206.29.169 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-11-03 | 45 |  |  | 2025 | 2025-10-26 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107OS | 2025-11-10 | 2025-11-11 | Done | Done |  |  | Done | Done | Done | Done | YPTT | 2025-11-10 | 46 | 2025-11-11 |  | 2025-11-11 | XLWO-20251111-00000513 |  | 2025-11-13 | 2025-11-12 | 2025-11-13 | 46 | 2025-11-13 | 46 | TRUE | 2025-11-12 | 46 | 2025-11-12 | 2025-11-12 | Done | #N/A | #N/A | November | 2025-11-18 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0580_1 | Swap_JAW-JT-DMK-0580 | JAW-JT-DMK-0580 | Central Java | Jawa Tengah | Demak | -6.9468 | 110.6122 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0580 | Beberan Panggang | Centratama |  | Central Java Ring 25E | MA-JTDMK0580-01H | 10.206.29.167 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Propose Drop, MOCN Drop | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-11-03 | 45 |  |  | 2025 | 2025-10-22 | 2025-10-22 | Approved | 2025-11-07 |  | Submitted | Approved | [21 empty] | 2025-11-11 | XLWO-20251111-00000513 | [10 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0595_1 | Swap_JAW-JT-DMK-0595 | JAW-JT-DMK-0595 | Central Java | Jawa Tengah | Demak | -6.9278 | 110.6729 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0595 | Wonosalam | Protelindo |  | Central Java Ring 25E | MA-JTDMK0595-01H | 10.206.29.166 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-11-03 | 45 |  |  | 2025 | 2025-10-25 | 2025-10-25 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-11 |  | Done | Done | 2025-11-08 | DOEID251107OU | 2025-11-10 | 2025-11-11 | Done | Done |  |  | Done | Done | Done | Done | YPTT | 2025-11-10 | 46 | 2025-11-11 |  | 2025-11-11 | XLWO-20251111-00000513 |  | 2025-11-13 | 2025-11-12 | 2025-11-13 | 46 | 2025-11-13 | 46 | TRUE | 2025-11-12 | 46 | 2025-11-12 | 2025-11-12 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-2970_1 | Swap_JAW-JT-DMK-2970 | JAW-JT-DMK-2970 | Central Java | Jawa Tengah | Demak | -7.0236 | 110.7356 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-2970 | Werdoyo Kebonagung | TBG |  | Central Java Ring 25E | MA-JTDMK2970-01H | 10.206.29.168 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-11-03 | 45 |  |  | 2025 | 2025-10-25 | 2025-11-03 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107OA | 2025-11-10 | 2025-11-11 | Done | Done |  |  | Done | Done | Done | Done | Mingze | 2025-11-10 | 46 | 2025-11-11 |  | 2025-11-11 | XLWO-20251111-00000513 |  | 2025-11-13 | 2025-11-12 | 2025-11-13 | 46 | 2025-11-13 | 46 | TRUE | 2025-11-12 | 46 | 2025-11-12 | 2025-11-12 | Done | #N/A | #N/A | November | 2025-11-14 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-2972_1 | Swap_JAW-JT-DMK-2972 | JAW-JT-DMK-2972 | Central Java | Jawa Tengah | Demak | -7.0091 | 110.5567 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-2972 | Candisari Mranggen | TBG |  | Central Java Ring 25E | MA-JTDMK2972-01H | 10.206.29.170 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-11-03 | 45 |  |  | 2025 | 2025-10-26 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107OB | 2025-11-10 | 2025-11-11 | Done | Done |  |  | Done | Done | Done | Done | Mingze | 2025-11-10 | 46 | 2025-11-11 |  | 2025-11-11 | XLWO-20251111-00000513 |  | 2025-11-13 | 2025-11-12 | 2025-11-13 | 46 | 2025-11-13 | 46 | TRUE | 2025-11-12 | 46 | 2025-11-12 | 2025-11-12 | Done | #N/A | #N/A | November | 2025-11-14 |  | 2025-11-21
1 | 2 | CLEAR | Swap_JAW-JT-PBG-1276_2 | Swap_JAW-JT-PBG-1276 | JAW-JT-PBG-1276 | Central Java | Jawa Tengah | Purbalingga | -7.3873 | 109.3623 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-PBG-1276 | Purbalngga | Protelindo |  | Central Java Ring 27 | PAG-SM2333-02H | 10.219.208.124 | NE40E(V8) | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GIT | 2025-10-16 | 42 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  | NY | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-BNR-0237_2 | Swap_JAW-JT-BNR-0237 | JAW-JT-BNR-0237 | Central Java | Jawa Tengah | Banjarnegara | -7.396 | 109.697 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-BNR-0237 | Banjarnegara | Protelindo |  | Central Java Ring 27 | PAG-SM2342-02H | 10.219.208.123 | NE40E(V8) | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | CCSI | 2025-12-04 | 49 |  |  | 2025 | 2025-10-29 | 2025-10-29 | Approved | 2025-11-07 | [36 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1984_1 | Swap_JAW-JT-SKH-1984 | JAW-JT-SKH-1984 | Central Java | Jawa Tengah | Sukoharjo | -7.6784 | 110.8379 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKH-1984 | HUT Sukoharjo | Others |  | Central Java Ring 30 | PAG-SM2263-01H | 10.206.1.244 | NE40E(V8) | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 14 | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 3 | CLEAR | Swap_JAW-JT-SKT-2150_3 | Swap_JAW-JT-SKT-2150 | JAW-JT-SKT-2150 | Central Java | Jawa Tengah | Kota Surakarta | -7.5587 | 110.8275 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKT-2150 | SOLO RELOCATION | DMT |  | Central Java Ring 30 | PAG-SMSN0070-07H | 10.206.1.245 | NE40E(V8) | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 14 | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | YPTT | 2025-10-20 | 43 | October |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [33 empty] | 0 |  | NY | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1969_1 | Swap_JAW-JT-SKH-1969 | JAW-JT-SKH-1969 | Central Java | Jawa Tengah | Sukoharjo | -7.6907 | 110.8105 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1969 | Combongan Sukoharjo | DMT |  | Central Java Ring 30B | MA-SM2319-01H | 10.206.6.0 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | Mingze | 2025-12-04 | 49 |  |  | 2025 | 2025-11-12 | 2025-11-18 | Reviewing |  |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1968_1 | Swap_JAW-JT-SKH-1968 | JAW-JT-SKH-1968 | Central Java | Jawa Tengah | Sukoharjo | -7.7139 | 110.8113 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1968 | Banmati Sukoharjo (C-Indosat) | DMT |  | Central Java Ring 30B | MA-SM2531501-01H | 10.206.6.1 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | Mingze | 2025-12-05 | 49 |  |  | 2025 | 2025-11-12 | 2025-11-18 | Reviewing |  |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-YO-WNO-0473_1 | Swap_JAW-YO-WNO-0473 | JAW-YO-WNO-0473 | Central Java | Jawa Tengah | Sukoharjo | -7.6189 | 110.7681 | Swap | Swap Only | Swap | Type B | MA | JAW-YO-WNO-0473 | Teloyo Wonosari Klaten | Protelindo |  | Central Java Ring 30B | MA-SM2533081-01H | 10.206.6.3 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1980_1 | Swap_JAW-JT-SKH-1980 | JAW-JT-SKH-1980 | Central Java | Jawa Tengah | Sukoharjo | -7.6816 | 110.8318 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1980 | Jetis Sukoharjo | Others |  | Central Java Ring 30B | MA-SM3533197G-01H | 10.206.1.255 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1939_1 | Swap_JAW-JT-SKH-1939 | JAW-JT-SKH-1939 | Central Java | Jawa Tengah | Sukoharjo | -7.7333 | 110.7585 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1939 | SISWODIPURAN | TBG |  | Central Java Ring 30B | MA-SM3534708G-01H | 10.206.6.2 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | Mingze | 2025-12-05 | 49 |  |  | 2025 | 2025-11-12 | 2025-11-18 | Reviewing |  |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1985_1 | Swap_JAW-JT-SKH-1985 | JAW-JT-SKH-1985 | Central Java | Jawa Tengah | Sukoharjo | -7.743 | 110.84 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1985 | Lawu Nguter | DMT |  | Central Java Ring 30D | MA-SM3533158G-01H | 10.206.6.13 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1965_1 | Swap_JAW-JT-SKH-1965 | JAW-JT-SKH-1965 | Central Java | Jawa Tengah | Sukoharjo | -7.6008 | 110.8064 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1965 | Kwarasan Grogol | TBG |  | Central Java Ring 30D | MA-SM3533199G-01H | 10.206.6.18 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | Mingze | 2025-12-05 | 49 |  |  | 2025 | 2025-11-18 | 2025-11-18 | Reviewing |  |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-1067_1 | Swap_JAW-JT-KLN-1067 | JAW-JT-KLN-1067 | Central Java | Jawa Tengah | Klaten | -7.7332 | 110.7378 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-1067 | Soka Karangdowo | Protelindo |  | Central Java Ring 30D | MA-SM3533228G-01H | 10.206.6.14 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | Mingze | 2025-12-22 | 52 |  |  | 2025 | 2025-11-01 | 2025-11-04 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-1058_1 | Swap_JAW-JT-KLN-1058 | JAW-JT-KLN-1058 | Central Java | Jawa Tengah | Klaten | -7.7127 | 110.7059 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-1058 | Beji Pedan | Protelindo |  | Central Java Ring 30D | MA-SM3533230G-01H | 10.206.6.15 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | Mingze | 2025-12-22 | 52 |  |  | 2025 | 2025-11-18 | 2025-11-18 | Reviewing |  |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1987_1 | Swap_JAW-JT-SKH-1987 | JAW-JT-SKH-1987 | Central Java | Jawa Tengah | Sukoharjo | -7.6856 | 110.8416 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1987 | Gayam Sukoharjo | DMT |  | Central Java Ring 30D | MA-SM3533355G-01H | 10.206.6.11 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | Mingze | 2025-12-22 | 52 |  |  | 2025 | 2025-11-12 | 2025-11-18 | Reviewing |  |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1943_1 | Swap_JAW-JT-SKH-1943 | JAW-JT-SKH-1943 | Central Java | Jawa Tengah | Sukoharjo | -7.6056 | 110.7656 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1943 | DUWET KLATEN | TBG |  | Central Java Ring 30D | MA-SM3534925G-01H | 10.206.6.17 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | Mingze | 2025-12-22 | 52 |  |  | 2025 | 2025-11-18 | 2025-11-18 | Reviewing |  |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1995_1 | Swap_JAW-JT-SKH-1995 | JAW-JT-SKH-1995 | Central Java | Jawa Tengah | Sukoharjo | -7.7086 | 110.8553 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1995 | Kepuh Sukoharjo | Protelindo |  | Central Java Ring 30D | MA-SMB254-01H | 10.206.6.12 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | Mingze | 2025-12-22 | 52 |  |  | 2025 | 2025-11-18 | 2025-11-18 | Reviewing |  |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-1066_1 | Swap_JAW-JT-KLN-1066 | JAW-JT-KLN-1066 | Central Java | Jawa Tengah | Klaten | -7.6759 | 110.7349 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-1066 | Ketitang Juwiring | Protelindo |  | Central Java Ring 30D | MA-SMBD85-01H | 10.206.6.16 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | Mingze | 2025-12-22 | 52 |  |  | 2025 | 2025-11-01 | 2025-11-04 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | 0 |  | Done | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-UNR-2663_2 | Swap_JAW-JT-UNR-2663 | JAW-JT-UNR-2663 | Central Java | Jawa Tengah | Semarang | -7.3046 | 110.3562 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-UNR-2663 | Bedono | Protelindo |  | Central Java Ring 31 | PAG-SM2384-01H | 10.219.214.223 | NE40E(V8) | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | Mid Dec 25 | GIT | 2025-10-28 | 44 | October |  | 2025 |  |  | #N/A | [37 empty] | #N/A |  | NY | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-2694_1 | Swap_JAW-JT-UNR-2694 | JAW-JT-UNR-2694 | Central Java | Jawa Tengah | Semarang | -7.2513 | 110.4144 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-UNR-2694 | Doplang | Others |  | Central Java Ring 31 | PAG-SM2531825-01H | 10.219.214.222 | NE40E(V8) | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | Mid Dec 25 | Mingze | 2025-12-23 | 52 |  |  | 2025 | 2025-11-03 | 2025-11-03 | Approved | 2025-11-07 |  | Submitted | Approved | [16 empty] | Mingze | [14 empty] | 2025-11-27 | 48 | 2025-11-27 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2035_1 | Swap_JAW-JT-SKT-2035 | JAW-JT-SKT-2035 | Central Java | Jawa Tengah | Kota Surakarta | -7.546 | 110.78 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKT-2035 | Baturan Reloc | Protelindo |  | Central Java Ring 34 | PAG-SM2369-01H | 10.219.209.196 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | CCSI | 2025-12-23 | 52 |  |  | 2025 | 2025-10-29 | 2025-11-01 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-SLT-2171_2 | Swap_JAW-JT-SLT-2171 | JAW-JT-SLT-2171 | Central Java | Jawa Tengah | Kota Salatiga | -7.3627 | 110.5156 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SLT-2171 | Tingkir Salatiga | Centratama |  | Central Java Ring 34 | PAG-SMB239-02H | 10.219.209.197 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | GIT | 2025-10-14 | 42 | October |  | 2025 | 2025-10-14 |  | Not Started |  |  | Submitted | Approved | [33 empty] | #N/A |  | NY | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-1082_1 | Swap_JAW-JT-BYL-1082 | JAW-JT-BYL-1082 | Central Java | Jawa Tengah | Boyolali | -7.4624 | 110.8029 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-1082 | Kalioso | Protelindo |  | Central Java Ring 34A | MA-JTBYL1082-01H | 10.206.27.43 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-06 | 45 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved |  | Site Will Be Reloc | [14 empty] | GPA | [14 empty] | 2025-11-28 | 48 | 2025-11-28 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0351_1 | Swap_JAW-JT-BYL-0351 | JAW-JT-BYL-0351 | Central Java | Jawa Tengah | Boyolali | -7.3566 | 110.733 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0351 | Sumberagung Klego | DMT |  | Central Java Ring 34A | MA-SM2531902-01H | 10.219.209.201 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-11-12 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [16 empty] | YPTT | [14 empty] | 2025-11-28 | 48 | 2025-11-28 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0331_1 | Swap_JAW-JT-BYL-0331 | JAW-JT-BYL-0331 | Central Java | Jawa Tengah | Boyolali | -7.3511 | 110.6586 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0331 | Klimas Karanggede | TBG |  | Central Java Ring 34A | MA-SM2533750-01H | 10.219.209.202 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-10-31 | 2025-10-31 | Approved | 2025-11-07 |  | Submitted | Approved | [16 empty] | YPTT | [14 empty] | 2025-11-28 | 48 | 2025-11-28 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0339_1 | Swap_JAW-JT-BYL-0339 | JAW-JT-BYL-0339 | Central Java | Jawa Tengah | Boyolali | -7.3569 | 110.6902 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0339 | Klego Boyolali | Protelindo |  | Central Java Ring 34A | MA-SM3531903G-01H | 10.219.209.208 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-10-31 | 2025-10-31 | Approved | 2025-11-07 |  | Submitted | Approved | [16 empty] | GPA | [14 empty] | 2025-11-28 | 48 | 2025-11-28 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0332_1 | Swap_JAW-JT-BYL-0332 | JAW-JT-BYL-0332 | Central Java | Jawa Tengah | Boyolali | -7.3112 | 110.66 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0332 | Wonosegoro | DMT |  | Central Java Ring 34A | MA-SM3531904G-01H | 10.219.209.209 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-11-04 | 2025-11-04 | Approved | 2025-11-07 |  | Submitted | Approved | [16 empty] | Mingze | [14 empty] | 2025-11-28 | 48 | 2025-11-28 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-1912_1 | Swap_JAW-JT-BYL-1912 | JAW-JT-BYL-1912 | Central Java | Jawa Tengah | Boyolali | -7.4282 | 110.7599 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-1912 | Galeh Tangen | Protelindo |  | Central Java Ring 34A | MA-SM3533174G-01H | 10.219.209.199 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-11-06 | 2025-11-06 | Approved | 2025-11-07 |  | Submitted | Approved | [16 empty] | Mingze | [14 empty] | 2025-11-28 | 48 | 2025-11-28 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0324_1 | Swap_JAW-JT-BYL-0324 | JAW-JT-BYL-0324 | Central Java | Jawa Tengah | Boyolali | -7.4058 | 110.7456 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0324 | Repaking Wonosegoro | DMT |  | Central Java Ring 34A | MA-SM3534046G-01H | 10.219.209.206 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-11-07 | 2025-11-10 | Approved | 2025-11-13 |  | Submitted | Approved | [16 empty] | GPA | [14 empty] | 2025-11-28 | 48 | 2025-11-28 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-2977_1 | Swap_JAW-JT-BYL-2977 | JAW-JT-BYL-2977 | Central Java | Jawa Tengah | Boyolali | -7.3789 | 110.7494 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-2977 | Beji Andong | TBG |  | Central Java Ring 34A | MA-SM3535223G-01H | 10.219.209.207 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-11-10 | 2025-11-10 | Approved | 2025-11-13 |  | Submitted | Approved | [16 empty] | GPA | [14 empty] | 2025-11-28 | 48 | 2025-11-28 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-3357_1 | Swap_JAW-JT-UNR-3357 | JAW-JT-UNR-3357 | Central Java | Jawa Tengah | Semarang | -7.3631 | 110.5348 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-3357 | Barukan Tengaran | Protelindo |  | Central Java Ring 34A | MA-SM3535594G-01H | 10.219.209.204 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | Mingze | 2025-12-25 | 52 |  |  | 2025 | 2025-11-03 | 2025-11-03 | Approved | 2025-11-07 |  | Submitted | Approved | [16 empty] | Mingze | [14 empty] | 2025-11-26 | 48 | 2025-11-26 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0360_1 | Swap_JAW-JT-BYL-0360 | JAW-JT-BYL-0360 | Central Java | Jawa Tengah | Boyolali | -7.3747 | 110.7688 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0360 | Andong Boyolali | Protelindo |  | Central Java Ring 34A | MA-SMB372-01H | 10.219.209.200 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-10-31 | 2025-10-31 | Approved | 2025-11-07 |  | Submitted | Approved | [16 empty] | GIT | [14 empty] | 2025-11-28 | 48 | 2025-11-28 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-2785_1 | Swap_JAW-JT-UNR-2785 | JAW-JT-UNR-2785 | Central Java | Jawa Tengah | Semarang | -7.3671 | 110.5949 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-2785 | Medayu Suruh | TBG |  | Central Java Ring 34A | MA-SMBD40-01H | 10.219.209.210 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | Mingze | 2025-12-25 | 52 |  |  | 2025 | 2025-11-21 | 2025-11-21 | Reviewing |  |  | Submitted | Approved | [16 empty] | GCI | [14 empty] | 2025-11-26 | 48 | 2025-11-26 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0355_1 | Swap_JAW-JT-BYL-0355 | JAW-JT-BYL-0355 | Central Java | Jawa Tengah | Boyolali | -7.3067 | 110.7517 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0355 | Kemusu Boyolali | Protelindo |  | Central Java Ring 34A | MA-JTBYL0355-01H | 10.206.27.44 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-06 | 45 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [16 empty] | GIT | [14 empty] | 2025-11-28 | 48 | 2025-11-28 |  | Done | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-SKT-2035_2 | Swap_JAW-JT-SKT-2035 | JAW-JT-SKT-2035 | Central Java | Jawa Tengah | Kota Surakarta | -7.546 | 110.78 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKT-2035 | Baturan Reloc | Protelindo |  | Central Java Ring 35 | PAG-BD2369-02H | 10.219.209.211 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | CCSI | 2025-12-25 | 52 |  |  | 2025 | 2025-10-29 | 2025-11-01 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-1055_1 | Swap_JAW-JT-KLN-1055 | JAW-JT-KLN-1055 | Central Java | Jawa Tengah | Klaten | -7.6166 | 110.7014 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-KLN-1055 | Kota Delanggu | Centratama |  | Central Java Ring 35 | PAG-BD2401-01H | 10.219.209.212 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | Mingze | 2025-12-25 | 52 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0346_1 | Swap_JAW-JT-BYL-0346 | JAW-JT-BYL-0346 | Central Java | Jawa Tengah | Boyolali | -7.5554 | 110.7137 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0346 | Delanggu | Protelindo |  | Central Java Ring 35B | MA-BD2230-01H | 10.219.209.226 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-10-29 | 2025-10-29 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0306_1 | Swap_JAW-JT-BYL-0306 | JAW-JT-BYL-0306 | Central Java | Jawa Tengah | Boyolali | -7.5772 | 110.5868 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0306 | Tambak Tulung | TBG |  | Central Java Ring 35B | MA-BD2533753-01H | 10.219.209.230 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-11-01 | 2025-11-01 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0311_1 | Swap_JAW-JT-BYL-0311 | JAW-JT-BYL-0311 | Central Java | Jawa Tengah | Boyolali | -7.5464 | 110.607 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0311 | Siswodipuran Boyolali Boyolali | Protelindo |  | Central Java Ring 35B | MA-BD3533157G-01H | 10.219.209.229 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-11-01 | 2025-11-01 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-0350_1 | Swap_JAW-JT-KRG-0350 | JAW-JT-KRG-0350 | Central Java | Jawa Tengah | Karanganyar | -7.5299 | 110.7286 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-0350 | Ngesrep Ngemplak | Protelindo |  | Central Java Ring 35B | MA-BD3533466G-01H | 10.219.209.225 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | Mingze | 2025-12-26 | 52 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0341_1 | Swap_JAW-JT-BYL-0341 | JAW-JT-BYL-0341 | Central Java | Jawa Tengah | Boyolali | -7.5245 | 110.6941 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0341 | Trayu Banyudono | DMT |  | Central Java Ring 35B | MA-BD3533869G-01H | 10.219.209.227 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-10-30 | 2025-10-30 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-3428_1 | Swap_JAW-JT-KRG-3428 | JAW-JT-KRG-3428 | Central Java | Jawa Tengah | Karanganyar | -7.5439 | 110.7538 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-3428 | Puri Permata AdiSucipto | DMT |  | Central Java Ring 35B | MA-BD3535643G-01H | 10.219.209.224 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | Mingze | 2025-12-26 | 52 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0335_1 | Swap_JAW-JT-BYL-0335 | JAW-JT-BYL-0335 | Central Java | Jawa Tengah | Boyolali | -7.5696 | 110.6759 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0335 | Sawit Boyolali | Centratama |  | Central Java Ring 35B | MA-SMD920-01H | 10.206.26.174 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-06 | 45 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-1078_1 | Swap_JAW-JT-KRG-1078 | JAW-JT-KRG-1078 | Central Java | Jawa Tengah | Karanganyar | -7.5308 | 110.7773 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-1078 | Gdgncolomaduc-Prtldo | Protelindo |  | Central Java Ring 35C | MA-BD253EH83-01H | 10.219.209.231 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | Mingze | 2025-12-29 | 53 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0348_1 | Swap_JAW-JT-BYL-0348 | JAW-JT-BYL-0348 | Central Java | Jawa Tengah | Boyolali | -7.4291 | 110.7201 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0348 | Pojok Nogosari | DMT |  | Central Java Ring 35C | MA-BD3531901G-01H | 10.219.209.233 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-10-30 | 2025-10-30 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0305_1 | Swap_JAW-JT-BYL-0305 | JAW-JT-BYL-0305 | Central Java | Jawa Tengah | Boyolali | -7.5401 | 110.5837 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0305 | Pusporenggo Musuk | Protelindo |  | Central Java Ring 35C | MA-BD3533237G-01H | 10.219.209.242 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-10 | 46 |  |  | 2025 | 2025-10-30 | 2025-10-30 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0329_1 | Swap_JAW-JT-BYL-0329 | JAW-JT-BYL-0329 | Central Java | Jawa Tengah | Boyolali | -7.5149 | 110.6568 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0329 | Krasak Teras | DMT |  | Central Java Ring 35C | MA-BD3533339G-01H | 10.219.209.235 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-10 | 46 |  |  | 2025 | 2025-11-07 | 2025-11-07 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0328_1 | Swap_JAW-JT-BYL-0328 | JAW-JT-BYL-0328 | Central Java | Jawa Tengah | Boyolali | -7.5375 | 110.6547 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0328 | Banyudono2 | DMT |  | Central Java Ring 35C | MA-BD3533649G-01H | 10.219.209.239 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-10 | 46 |  |  | 2025 | 2025-11-01 | 2025-11-01 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0347_1 | Swap_JAW-JT-BYL-0347 | JAW-JT-BYL-0347 | Central Java | Jawa Tengah | Boyolali | -7.5163 | 110.7167 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0347 | Ngargorejo Ngemplak | DMT |  | Central Java Ring 35C | MA-BD3533861G-01H | 10.219.209.234 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-10 | 46 |  |  | 2025 | 2025-11-03 | 2025-11-03 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0317_1 | Swap_JAW-JT-BYL-0317 | JAW-JT-BYL-0317 | Central Java | Jawa Tengah | Boyolali | -7.5522 | 110.6251 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0317 | BUTUH MOJOSONGO | Others |  | Central Java Ring 35C | MA-BD3534095G-01H | 10.219.209.241 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-10 | 46 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0326_1 | Swap_JAW-JT-BYL-0326 | JAW-JT-BYL-0326 | Central Java | Jawa Tengah | Boyolali | -7.5799 | 110.6503 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0326 | KADIRESO TERAS | TBG |  | Central Java Ring 35C | MA-BD3534374G-01H | 10.219.209.243 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-10 | 46 |  |  | 2025 | 2025-10-30 | 2025-10-31 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0357_1 | Swap_JAW-JT-BYL-0357 | JAW-JT-BYL-0357 | Central Java | Jawa Tengah | Boyolali | -7.4454 | 110.7564 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0357 | NOGOSARI BOYOLALI | TBG |  | Central Java Ring 35C | MA-BDBD02-01H | 10.219.209.232 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-10 | 46 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0215_1 | Swap_JAW-JT-BYL-0215 | JAW-JT-BYL-0215 | Central Java | Jawa Tengah | Boyolali | -7.5489 | 110.6613 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0215 | Teras Salakan | DMT |  | Central Java Ring 35C | MA-JTBYL0215-01H | 10.206.26.176 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-10 | 46 |  |  | 2025 | 2025-11-07 | 2025-11-07 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0224_1 | Swap_JAW-JT-BYL-0224 | JAW-JT-BYL-0224 | Central Java | Jawa Tengah | Boyolali | -7.462 | 110.6743 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0224 | BANGAK SIMO | TBG |  | Central Java Ring 35C | MA-JTBYL0224-01H | 10.206.26.175 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | YPTT | 2025-11-10 | 46 |  |  | 2025 | 2025-11-07 | 2025-11-07 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PML-1443_1 | Swap_JAW-JT-PML-1443 | JAW-JT-PML-1443 | Central Java | Jawa Tengah | Pemalang | -6.8984 | 109.5301 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-PML-1443 | Comal | Centratama |  | Central Java Ring 41 | PAG-SM2304-01H | 10.219.26.147 | NE40E(V8) | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | CCSI | 2025-12-31 | 53 |  |  | 2025 | 2025-10-24 | 2025-10-30 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PML-1393_1 | Swap_JAW-JT-PML-1393 | JAW-JT-PML-1393 | Central Java | Jawa Tengah | Pemalang | -6.8877 | 109.3893 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-PML-1393 | Mpls - Pemalang | Direct Lease |  | Central Java Ring 41 | PAG-SM2307-01H | 10.219.26.146 | NE40E(V8) | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | CCSI | 2025-12-31 | 53 |  |  | 2025 | 2025-10-24 | 2025-10-30 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2087_1 | Swap_JAW-JT-SKT-2087 | JAW-JT-SKT-2087 | Central Java | Jawa Tengah | Kota Surakarta | -7.5327 | 110.8207 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKT-2087 | Jetak | Protelindo |  | Central Java Ring 43 | PAG-YG2368-01H | 10.219.26.103 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | CCSI | 2025-12-31 | 53 |  |  | 2025 | 2025-10-30 | 2025-11-01 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2062_1 | Swap_JAW-JT-SKT-2062 | JAW-JT-SKT-2062 | Central Java | Jawa Tengah | Kota Surakarta | -7.5498 | 110.8044 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKT-2062 | Banyuanyar | Protelindo |  | Central Java Ring 43 | PAG-YG2439-03H | 10.219.26.102 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | CCSI | 2025-12-31 | 53 |  |  | 2025 | 2025-10-30 | 2025-11-01 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1892_1 | Swap_JAW-JT-SGN-1892 | JAW-JT-SGN-1892 | Central Java | Jawa Tengah | Sragen | -7.4176 | 111.0188 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1892 | Sragen Reloc | TBG |  | Central Java Ring 43A | MA-YG2267-01H | 10.219.26.105 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2025-12-31 | 53 |  |  | 2025 | 2025-11-08 | 2025-11-16 | Approved | 2025-11-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1898_1 | Swap_JAW-JT-SGN-1898 | JAW-JT-SGN-1898 | Central Java | Jawa Tengah | Sragen | -7.4186 | 111.0326 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1898 | Sragen Wetan (Collocated Protelindo) | Protelindo |  | Central Java Ring 43A | MA-YG2531109-01H | 10.219.26.106 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2025-12-31 | 53 |  |  | 2025 | 2025-11-07 |  | In Progress |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1871_1 | Swap_JAW-JT-SGN-1871 | JAW-JT-SGN-1871 | Central Java | Jawa Tengah | Sragen | -7.4091 | 110.9441 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1871 | Gawan Tanon | Protelindo |  | Central Java Ring 43A | MA-YG2531314-01H | 10.219.26.114 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-01 | 1 |  |  | 2026 | 2025-11-07 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1910_1 | Swap_JAW-JT-SGN-1910 | JAW-JT-SGN-1910 | Central Java | Jawa Tengah | Sragen | -7.3827 | 111.0862 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1910 | Toyogo Sambung Macan | Protelindo |  | Central Java Ring 43A | MA-YG2531913-01H | 10.219.26.108 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-01 | 1 |  |  | 2026 | 2025-11-07 |  | In Progress |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1885_1 | Swap_JAW-JT-SGN-1885 | JAW-JT-SGN-1885 | Central Java | Jawa Tengah | Sragen | -7.4314 | 111.0051 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1885 | Jatibatu Sragen | TBG |  | Central Java Ring 43A | MA-YG2533963-01H | 10.219.26.104 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-01 | 1 |  |  | 2026 | 2025-11-08 | 2025-11-16 | Approved | 2025-11-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-1093_1 | Swap_JAW-JT-KRG-1093 | JAW-JT-KRG-1093 | Central Java | Jawa Tengah | Karanganyar | -7.5118 | 110.911 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-1093 | Kebak Kramat Utara | Protelindo |  | Central Java Ring 43A | MA-YG2534858-01H | 10.219.26.116 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-01 | 1 |  |  | 2026 | 2025-11-07 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1862_1 | Swap_JAW-JT-SGN-1862 | JAW-JT-SGN-1862 | Central Java | Jawa Tengah | Sragen | -7.3011 | 110.9066 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1862 | Tlogotirto | TBG |  | Central Java Ring 43A | MA-YG2534872-01H | 10.219.26.113 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-01 | 1 |  |  | 2026 | 2025-11-10 | 2025-11-17 | Reviewing |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1905_1 | Swap_JAW-JT-SGN-1905 | JAW-JT-SGN-1905 | Central Java | Jawa Tengah | Sragen | -7.3607 | 111.0608 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1905 | Pasar Made | Protelindo |  | Central Java Ring 43A | MA-YG3533156G-01H | 10.219.26.110 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-01 | 1 |  |  | 2026 | 2025-11-07 |  | In Progress |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1870_1 | Swap_JAW-JT-SGN-1870 | JAW-JT-SGN-1870 | Central Java | Jawa Tengah | Sragen | -7.4384 | 110.9431 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1870 | BENTAK SIDOHARJO | DMT |  | Central Java Ring 43A | MA-YG3533243G-01H | 10.219.26.115 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-02 | 1 |  |  | 2026 | 2025-11-09 | 2025-11-17 | Reviewing |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1879_1 | Swap_JAW-JT-SGN-1879 | JAW-JT-SGN-1879 | Central Java | Jawa Tengah | Sragen | -7.3512 | 110.9851 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1879 | Pilangsari Gesi | DMT |  | Central Java Ring 43A | MA-YG3533866G-01H | 10.219.26.112 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-02 | 1 |  |  | 2026 | 2025-11-08 |  | In Progress |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-2982_1 | Swap_JAW-JT-KRG-2982 | JAW-JT-KRG-2982 | Central Java | Jawa Tengah | Karanganyar | -7.5181 | 110.87 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-2982 | KARANGTURI GONDANGREJO | Protelindo |  | Central Java Ring 43A | MA-YG3535265G-01H | 10.219.26.117 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-02 | 1 |  |  | 2026 | 2025-11-10 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-3400_1 | Swap_JAW-JT-SGN-3400 | JAW-JT-SGN-3400 | Central Java | Jawa Tengah | Sragen | -7.365 | 111.0225 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-3400 | Klandungan | Protelindo |  | Central Java Ring 43A | MA-YG3535557G9-01H | 10.219.26.111 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-02 | 1 |  |  | 2026 | 2025-11-08 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-2113_1 | Swap_JAW-JT-KRG-2113 | JAW-JT-KRG-2113 | Central Java | Jawa Tengah | Karanganyar | -7.5322 | 110.8359 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-2113 | Jayawijaya Solo | Centratama |  | Central Java Ring 43C | MA-SM3534702G-01H | 10.206.26.192 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-02 | 1 |  |  | 2026 | 2025-11-10 | 2025-11-16 | Approved | 2025-11-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1880_1 | Swap_JAW-JT-SGN-1880 | JAW-JT-SGN-1880 | Central Java | Jawa Tengah | Sragen | -7.4103 | 110.9864 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1880 | Singopadu | Protelindo |  | Central Java Ring 43C | MA-YG2531823-01H | 10.219.26.132 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-02 | 1 |  |  | 2026 | 2025-11-09 |  | In Progress |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1869_1 | Swap_JAW-JT-SGN-1869 | JAW-JT-SGN-1869 | Central Java | Jawa Tengah | Sragen | -7.3722 | 110.9424 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1869 | Suwatu Sragen | DMT |  | Central Java Ring 43C | MA-YG2531909-01H | 10.219.26.133 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-05 | 2 |  |  | 2026 | 2025-11-08 |  | In Progress |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1854_1 | Swap_JAW-JT-SGN-1854 | JAW-JT-SGN-1854 | Central Java | Jawa Tengah | Sragen | -7.3958 | 110.8589 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1854 | Peleman Sragen | DMT |  | Central Java Ring 43C | MA-YG3531912G-01H | 10.219.26.136 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-05 | 2 |  |  | 2026 | 2025-11-11 | 2025-11-17 | Reviewing |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1857_1 | Swap_JAW-JT-SGN-1857 | JAW-JT-SGN-1857 | Central Java | Jawa Tengah | Sragen | -7.4566 | 110.8917 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1857 | Gedongan Plupuh | Protelindo |  | Central Java Ring 43C | MA-YG3531989G-01H | 10.219.26.143 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-05 | 2 |  |  | 2026 | 2025-11-07 |  | In Progress |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1865_1 | Swap_JAW-JT-SGN-1865 | JAW-JT-SGN-1865 | Central Java | Jawa Tengah | Sragen | -7.4839 | 110.9129 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1865 | Sidodadi Masaran | Others |  | Central Java Ring 43C | MA-YG3533192G-01H | 10.219.26.145 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-05 | 2 |  |  | 2026 | 2025-11-09 |  | In Progress |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1858_1 | Swap_JAW-JT-SGN-1858 | JAW-JT-SGN-1858 | Central Java | Jawa Tengah | Sragen | -7.4019 | 110.8918 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1858 | Karangasem Tanon | Protelindo |  | Central Java Ring 43C | MA-YG3533239G-01H | 10.219.26.135 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-05 | 2 |  |  | 2026 | 2025-11-08 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1863_1 | Swap_JAW-JT-SGN-1863 | JAW-JT-SGN-1863 | Central Java | Jawa Tengah | Sragen | -7.4188 | 110.9122 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1863 | Sambirejo Plupuh | Centratama |  | Central Java Ring 43C | MA-YG3533325G-01H | 10.219.26.134 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-06 | 2 |  |  | 2026 | 2025-11-10 |  | In Progress |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1852_1 | Swap_JAW-JT-SGN-1852 | JAW-JT-SGN-1852 | Central Java | Jawa Tengah | Sragen | -7.4233 | 110.845 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1852 | BRANGKAL GEMOLONG | TBG |  | Central Java Ring 43C | MA-YG3534097G-01H | 10.219.26.140 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-06 | 2 |  |  | 2026 | 2025-11-08 |  | In Progress |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-3255_1 | Swap_JAW-JT-SGN-3255 | JAW-JT-SGN-3255 | Central Java | Jawa Tengah | Sragen | -7.3984 | 110.8386 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-3255 | Tegaldowo Gemolong | TBG |  | Central Java Ring 43C | MA-YG3535555G-01H | 10.219.26.137 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-06 | 2 |  |  | 2026 | 2025-11-08 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-3340_1 | Swap_JAW-JT-SGN-3340 | JAW-JT-SGN-3340 | Central Java | Jawa Tengah | Sragen | -7.4491 | 110.9195 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-3340 | PRINGANOM MASARAN | Protelindo |  | Central Java Ring 43C | MA-YG3535608G-01H | 10.219.26.142 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GCI | 2026-01-06 | 2 |  |  | 2026 | 2025-11-09 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1480_1 | Swap_JAW-JT-PTI-1480 | JAW-JT-PTI-1480 | Central Java | Jawa Tengah | Pati | -6.7527 | 111.0354 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-PTI-1480 | Pati | Others |  | Central Java Ring 45 | PAG-SM2244-01H | 10.219.27.86 | NE40E(V8) | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 10 | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-24 |  | In Progress |  |  | Submitted | Approved |  |  | Done | Done | Done | DOEID251117NN | [10 empty] | YPTT | [14 empty] | 2025-11-26 | 48 | 2025-11-26 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1520_1 | Swap_JAW-JT-PTI-1520 | JAW-JT-PTI-1520 | Central Java | Jawa Tengah | Pati | -6.7188 | 111.1446 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-PTI-1520 | Juana | Protelindo |  | Central Java Ring 45 | PAG-SM2245-01H | 10.219.27.87 | NE40E(V8) | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 10 | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-11-07 |  | In Progress |  |  | Submitted | Approved |  |  | Done | Done | Done | DOEID251117OB | [10 empty] | GPA | [14 empty] | 2025-11-26 | 48 | 2025-11-26 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1536_1 | Swap_JAW-JT-PTI-1536 | JAW-JT-PTI-1536 | Central Java | Jawa Tengah | Pati | -6.7228 | 111.128 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1536 | JUWANA BARAT RELOCATION | Protelindo |  | Central Java Ring 45F | MA-JTPTI1536-01H | 10.206.54.188 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-26 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved |  |  | Done | Done | Done | DOEID251117NP | [10 empty] | YPTT | [14 empty] | 2025-11-24 | 48 | 2025-11-24 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1405_1 | Swap_JAW-JT-PTI-1405 | JAW-JT-PTI-1405 | Central Java | Jawa Tengah | Pati | -6.825 | 111.133 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1405 | TRIGUNO PUCAKWANGI | DMT |  | Central Java Ring 45F | MA-JTPTI1405-01H | 10.206.54.185 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-30 | 2025-10-30 | Approved | 2025-11-07 |  | Submitted | Approved |  |  | Done | Done | Done | DOEID251117NR | [10 empty] | YPTT | [14 empty] | 2025-11-24 | 48 | 2025-11-24 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1406_1 | Swap_JAW-JT-PTI-1406 | JAW-JT-PTI-1406 | Central Java | Jawa Tengah | Pati | -6.7739 | 111.076 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1406 | KEDUNGMULYO JAKENAN | Protelindo |  | Central Java Ring 45F | MA-JTPTI1406-01H | 10.206.54.186 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-24 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved |  |  | Done | Done | Done | DOEID251117OD | [10 empty] | GPA | [14 empty] | 2025-11-24 | 48 | 2025-11-24 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1498_1 | Swap_JAW-JT-PTI-1498 | JAW-JT-PTI-1498 | Central Java | Jawa Tengah | Pati | -6.7836 | 111.0556 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1498 | Banjarsari Gabus Pati | Protelindo |  | Central Java Ring 45F | MA-JTPTI1498-01H | 10.206.54.182 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-24 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved |  |  | Done | Done | Done | DOEID251117O5 | [10 empty] | GIT | [14 empty] | 2025-11-24 | 48 | 2025-11-24 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1508_1 | Swap_JAW-JT-PTI-1508 | JAW-JT-PTI-1508 | Central Java | Jawa Tengah | Pati | -6.8543 | 111.0789 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1508 | Angkatan Kidul Pati | TBG |  | Central Java Ring 45F | MA-JTPTI1508-01H | 10.206.54.184 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-24 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved |  |  | Done | Done | Done | DOEID251117O7 | [10 empty] | GIT | [14 empty] | 2025-11-24 | 48 | 2025-11-24 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1514_1 | Swap_JAW-JT-PTI-1514 | JAW-JT-PTI-1514 | Central Java | Jawa Tengah | Pati | -6.7705 | 111.113 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1514 | Tambahmulyo Jakenan | DMT |  | Central Java Ring 45F | MA-JTPTI1514-01H | 10.206.54.187 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-24 | 2025-10-30 | Approved | 2025-11-07 |  | Submitted | Approved |  |  | Done | Done | Done | DOEID251117K7 | [10 empty] | Mingze | [14 empty] | 2025-11-25 | 48 | 2025-11-25 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-3325_1 | Swap_JAW-JT-PTI-3325 | JAW-JT-PTI-3325 | Central Java | Jawa Tengah | Pati | -6.854 | 111.0558 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-3325 | Angkatan Lor Tambakromo | Protelindo |  | Central Java Ring 45F | MA-JTPTI3325-01H | 10.206.54.183 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-24 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved |  |  | Done | Done | Done | DOEID251117K9 | [10 empty] | Mingze | [14 empty] | 2025-11-25 | 48 | 2025-11-25 |  | Done | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-DMK-0612_2 | Swap_JAW-JT-DMK-0612 | JAW-JT-DMK-0612 | Central Java | Jawa Tengah | Demak | -6.8503 | 110.8054 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-DMK-0612 | Karanganyar Demak | Centratama |  | Central Java Ring 46 | PAG-SM2395-03H | 10.206.7.235 | NE40E(V8) | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 6 | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-16 | 42 | October |  | 2026 |  |  | Not Started |  |  | Submitted | Approved |  |  | Done | Done | Done | DOEID25111411 | 2025-11-23 | [9 empty] | GPA | 2025-11-23 | 47 | [5 empty] | 2025-11-26 |  | 2025-11-26 | 48 | 2025-11-26 | 48 | TRUE | 2025-11-20 | 47 | 2025-11-20 |  | NY | #N/A | #N/A | November
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0925_1 | Swap_JAW-JT-KDS-0925 | JAW-JT-KDS-0925 | Central Java | Jawa Tengah | Kudus | -6.8057 | 110.8798 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-KDS-0925 | Ngembal Kulon | Centratama |  | Central Java Ring 46 | PAG-SMBC35-01H | 10.206.7.241 | NE40E(V8) | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 6 | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-08 | 2 |  |  | 2026 | 2025-11-13 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved |  |  | Done | Done | Done | DOEID25111413 | 2025-11-23 | [9 empty] | GPA | 2025-11-23 | 47 | [5 empty] | 2025-11-26 |  | 2025-11-26 | 48 | 2025-11-26 | 48 | TRUE | 2025-11-20 | 47 | 2025-11-20 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0917_1 | Swap_JAW-JT-KDS-0917 | JAW-JT-KDS-0917 | Central Java | Jawa Tengah | Kudus | -6.8079 | 110.8631 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0917 | Rendeng Kudus | Protelindo |  | Central Java Ring 46E | MA-SM2534241-01H | 10.206.7.155 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 6 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-14 | 2025-11-14 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-19 |  | Done | Done | Done | DOEID25111415 | 2025-11-23 | 2025-11-20 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-23 | 47 | 2025-11-20 |  |  | XLWO-20251112-00000910 |  | 2025-11-26 | 2025-11-20 | 2025-11-26 | 48 | 2025-11-26 | 48 | TRUE | 2025-11-20 | 47 | 2025-11-20 | 2025-11-20 | Done | #N/A | #N/A | November | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-KDS-2020_1 | Swap_JAW-JT-KDS-2020 | JAW-JT-KDS-2020 | Central Java | Jawa Tengah | Kudus | -6.7987 | 110.8136 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-2020 | KARANGAMPEL KUDUS Relocation | Others |  | Central Java Ring 46E | MA-SM2535018-01H | 10.206.7.254 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 6 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-11 | 2025-11-14 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-19 |  | Done | Done | Done | DOEID25111417 | 2025-11-23 | 2025-11-20 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-23 | 47 | 2025-11-20 |  |  | XLWO-20251112-00000910 |  | 2025-11-26 | 2025-11-20 | 2025-11-26 | 48 | 2025-11-26 | 48 | TRUE | 2025-11-20 | 47 | 2025-11-20 | 2025-11-20 | Done | #N/A | #N/A | November | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0887_1 | Swap_JAW-JT-KDS-0887 | JAW-JT-KDS-0887 | Central Java | Jawa Tengah | Kudus | -6.8034 | 110.826 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0887 | Prambatan Kudus | TBG |  | Central Java Ring 46E | MA-SM253A286-01H | 10.206.8.134 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 6 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-11 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-19 |  | Done | Done | Done | DOEID25111418 | 2025-11-23 | 2025-11-20 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-23 | 47 | 2025-11-20 |  |  | XLWO-20251112-00000910 |  | 2025-11-26 | 2025-11-20 | 2025-11-26 | 48 | 2025-11-26 | 48 | TRUE | 2025-11-20 | 47 | 2025-11-20 | 2025-11-20 | Done | #N/A | #N/A | November | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0908_1 | Swap_JAW-JT-KDS-0908 | JAW-JT-KDS-0908 | Central Java | Jawa Tengah | Kudus | -6.8039 | 110.8486 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0908 | Diponegoro Ngangguk (Collocated Protelindo) | Protelindo |  | Central Java Ring 46E | MA-SM253EH79-01H | 10.206.7.154 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 6 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-11 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-19 |  | Done | Done | Done | DOEID25111446 | 2025-11-23 | 2025-11-20 | Done | Done |  |  | Done | Done | Done | Done | GIT | 2025-11-23 | 47 | 2025-11-20 |  |  | XLWO-20251112-00000910 |  | 2025-11-26 | 2025-11-20 | 2025-11-26 | 48 | 2025-11-26 | 48 | TRUE | 2025-11-20 | 47 | 2025-11-20 | 2025-11-20 | Done | #N/A | #N/A | November | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0878_1 | Swap_JAW-JT-KDS-0878 | JAW-JT-KDS-0878 | Central Java | Jawa Tengah | Kudus | -6.7999 | 110.7867 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0878 | Kedungdowo Kaliwungu | DMT |  | Central Java Ring 46E | MA-SM3533373G-01H | 10.206.7.252 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 6 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-11 | 2025-11-19 | Reviewing |  |  | Submitted | Approved | 2025-11-19 |  | Done | Done | Done | DOEID25111448 | 2025-11-23 | 2025-11-20 | Done | Done |  |  | Done | Done | Done | Done | GIT | 2025-11-23 | 47 | 2025-11-20 |  |  | XLWO-20251112-00000910 |  | 2025-11-26 | 2025-11-20 | 2025-11-26 | 48 | 2025-11-26 | 48 | TRUE | 2025-11-20 | 47 | 2025-11-20 | 2025-11-20 | Done | #N/A | #N/A | November | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0879_1 | Swap_JAW-JT-KDS-0879 | JAW-JT-KDS-0879 | Central Java | Jawa Tengah | Kudus | -6.7892 | 110.7944 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0879 | Kaliwungu Kudus | Centratama |  | Central Java Ring 46E | MA-SMBD84-01H | 10.206.7.253 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 6 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-12 | 3 |  |  | 2026 | 2025-11-11 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-19 |  | Done | Done | Done | DOEID25111435 | 2025-11-23 | 2025-11-20 | Done | Done |  |  | Done | Done | Done | Done | Mingze | 2025-11-23 | 47 | 2025-11-20 |  |  | XLWO-20251112-00000910 |  | 2025-11-26 | 2025-11-20 | 2025-11-26 | 48 | 2025-11-26 | 48 | TRUE | 2025-11-20 | 47 | 2025-11-20 | 2025-11-20 | Done | #N/A | #N/A | November
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0902_1 | Swap_JAW-JT-KDS-0902 | JAW-JT-KDS-0902 | Central Java | Jawa Tengah | Kudus | -6.8084 | 110.8422 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0902 | Ramayana Kudus | DHOST |  | Central Java Ring 46E | MA-SMPX271-01H | 10.206.7.255 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 6 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-12 | 3 |  |  | 2026 | 2025-11-11 | 2025-11-19 | Reviewing |  |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID25111436 | 2025-11-23 | 2025-11-23 | Done | Done |  |  | Done | Done | Done | Done | Mingze | 2025-11-23 | 47 | 2025-11-21 |  | 2025-11-21 | XLWO-20251112-00001200 |  | 2025-11-26 | 2025-11-23 | 2025-11-26 | 48 | 2025-11-26 | 48 | TRUE | 2025-11-23 | 47 | 2025-11-20 | 2025-11-23 | Done | #N/A | #N/A | November
1 | 3 | CLEAR | Swap_JAW-JT-BNR-0237_3 | Swap_JAW-JT-BNR-0237 | JAW-JT-BNR-0237 | Central Java | Jawa Tengah | Banjarnegara | -7.396 | 109.697 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-BNR-0237 | Banjarnegara | Protelindo |  | Central Java Ring 52 | PAG-SM2342-04H | 10.206.1.27 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | CCSI | 2026-01-12 | 3 |  |  | 2026 | 2025-10-29 | 2025-10-29 | Approved | 2025-11-07 | [36 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KBM-0770_1 | Swap_JAW-JT-KBM-0770 | JAW-JT-KBM-0770 | Central Java | Jawa Tengah | Kebumen | -7.7234 | 109.794 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-KBM-0770 | Mpls - Prembun | Protelindo |  | Central Java Ring 52 | PAG-YG2282-03H | 10.206.1.26 | ATN910C-B | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [11 empty] | 2026-01-12 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KDL-0797_1 | Swap_JAW-JT-KDL-0797 | JAW-JT-KDL-0797 | Central Java | Jawa Tengah | Kendal | -6.9708 | 110.0789 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-KDL-0797 | Mpls - Weleri | Centratama |  | Central Java Ring 54 | PAG-SM2303-01H | 10.206.0.30 | NE40E(V8) | Huawei | New Purchase | New Ring 001 | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2025-624 sites | GPA | 2025-11-10 | 46 |  |  | 2026 | 2025-10-30 | 2025-10-30 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-1137_1 | Swap_JAW-JT-KRG-1137 | JAW-JT-KRG-1137 | Central Java | Jawa Tengah | Karanganyar | -7.6186 | 111.0751 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-KRG-1137 | Karangpandan | Protelindo |  | Central Java Ring 56 | PAG-SM2473-01H | 10.206.1.41 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [11 empty] | 2026-01-13 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-2019_1 | Swap_JAW-JT-SKH-2019 | JAW-JT-SKH-2019 | Central Java | Jawa Tengah | Sukoharjo | -7.5817 | 110.9032 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKH-2019 | Jaten Karanganyar | Protelindo |  | Central Java Ring 56 | PAG-SMCH90-03H | 10.206.1.40 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [11 empty] | 2026-01-13 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-1090_1 | Swap_JAW-JT-KRG-1090 | JAW-JT-KRG-1090 | Central Java | Jawa Tengah | Karanganyar | -7.5189 | 110.9081 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-1090 | Kebak Kramat Relocation | DMT |  | Central Java Ring 56E | MA-JTKRG1090-01H | 10.206.27.61 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-13 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-1098_1 | Swap_JAW-JT-KRG-1098 | JAW-JT-KRG-1098 | Central Java | Jawa Tengah | Karanganyar | -7.5534 | 110.9379 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-1098 | Kalijirak | Centratama |  | Central Java Ring 56E | MA-JTKRG1098-01H | 10.206.27.68 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-13 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-1126_1 | Swap_JAW-JT-KRG-1126 | JAW-JT-KRG-1126 | Central Java | Jawa Tengah | Karanganyar | -7.5731 | 111.0233 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-1126 | Kecamatan Mojogedang | Protelindo |  | Central Java Ring 56E | MA-JTKRG1126-01H | 10.206.27.64 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-13 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-2142_1 | Swap_JAW-JT-KRG-2142 | JAW-JT-KRG-2142 | Central Java | Jawa Tengah | Karanganyar | -7.5451 | 110.975 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-2142 | KALIBOTO MOJOGEDANG KARANGANYAR | DMT |  | Central Java Ring 56E | MA-JTKRG2142-01H | 10.206.27.63 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-14 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-2146_1 | Swap_JAW-JT-KRG-2146 | JAW-JT-KRG-2146 | Central Java | Jawa Tengah | Karanganyar | -7.5544 | 110.9914 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-2146 | MOJOGEDANG RELOCATION | Protelindo |  | Central Java Ring 56E | MA-JTKRG2146-01H | 10.206.27.69 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-14 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-YO-WAT-0365_1 | Swap_JAW-YO-WAT-0365 | JAW-YO-WAT-0365 | Central Java | Daerah Istimewa Yogyakarta | Kulon Progo | -7.8573 | 110.1609 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-YO-WAT-0365 | Mpls - Wates | Protelindo |  | Central Java Ring 58 | PAG-YG2280-04H | 10.206.0.161 | ATN910C-B | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [11 empty] | 2026-01-14 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-KBM-0770_2 | Swap_JAW-JT-KBM-0770 | JAW-JT-KBM-0770 | Central Java | Jawa Tengah | Kebumen | -7.7234 | 109.794 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-KBM-0770 | Mpls - Prembun | Protelindo |  | Central Java Ring 58 | PAG-YG2282-02H | 10.206.0.160 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [11 empty] | 2026-01-14 | 3 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0101_1 | Swap_JAW-JT-BBS-0101 | JAW-JT-BBS-0101 | Central Java | Jawa Tengah | Brebes | -7.2491 | 109.0068 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-BBS-0101 | Bumiayu | Centratama |  | Central Java Ring 70 | PAG-SM2340-01H | 10.206.1.99 | NE40E(V8) | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-11-10 | 46 |  |  | 2026 | 2025-10-29 | 2025-10-29 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0076_1 | Swap_JAW-JT-BBS-0076 | JAW-JT-BBS-0076 | Central Java | Jawa Tengah | Brebes | -6.9406 | 108.944 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-BBS-0076 | Slatri Brebes | Others |  | Central Java Ring 70 | PAG-SM2532932-01H | 10.206.1.98 | NE40E(V8) | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-11-10 | 46 |  |  | 2026 | 2025-11-07 | 2025-11-07 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-1037_1 | Swap_JAW-JT-KLN-1037 | JAW-JT-KLN-1037 | Central Java | Jawa Tengah | Klaten | -7.6918 | 110.6409 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-KLN-1037 | Klaten | Protelindo |  | Central Java Ring 72 | PAG-YG2231-01H | 10.219.27.149 | ATN910C-F | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [11 empty] | 2026-01-15 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-0989_1 | Swap_JAW-JT-KLN-0989 | JAW-JT-KLN-0989 | Central Java | Jawa Tengah | Klaten | -7.7508 | 110.5159 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-KLN-0989 | Prambanan | Protelindo |  | Central Java Ring 72 | PAG-YG2232-01H | 10.219.27.148 | ATN910C-B | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [11 empty] | 2026-01-15 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PWT-1773_1 | Swap_JAW-JT-PWT-1773 | JAW-JT-PWT-1773 | Central Java | Jawa Tengah | Banyumas | -7.4028 | 109.2861 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-PWT-1773 | Kembaran | Centratama |  | Central Java Ring 83 | PAG-JTPWT1773-03H | 10.206.28.210 | ATN910C | Huawei | New Purchase | Linknet NNI,PAG1 | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-17 | 42 | October | Oct | 2026 | 2025-10-18 | 2025-10-18 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-10-22 |  | 2025-10-20 | 2025-10-21 | 2025-10-21 | DOEID251021MR |  | 2025-10-22 | 2025-10-20 | 2025-10-20 |  |  | done | 2025-10-21 | 2025-10-22 | done | GPA |  |  | 2025-10-22 | 2025-10-20 | 2025-10-23 | XLWO-20251023-00000400 | RFC-20251023-00000264 | 2025-10-29 | 2025-11-05 | 2025-10-29 | [6 empty] | #N/A | 2025-11-05 | Done | #N/A | #N/A |  | 2025-11-05 |  | 2025-11-15
1 | 2 | CLEAR | Swap_JAW-JT-PWT-1716_2 | Swap_JAW-JT-PWT-1716 | JAW-JT-PWT-1716 | Central Java | Jawa Tengah | Banyumas | -7.4218 | 109.2214 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-PWT-1716 | Mpls - Purwokerto | Direct Lease |  | Central Java Ring 83 | PAG-JTPWT1716-05H | 10.206.28.211 | ATN910C | Huawei | New Purchase | Linknet NNI,PAG2 | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-17 | 42 | October | Oct | 2026 | 2025-10-17 | 2025-10-20 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-10-22 | Need 15m Power Cable | 2025-10-20 | 2025-10-21 | 2025-10-21 | DOEID251021MR |  | 2025-10-22 | 2025-10-20 | 2025-10-20 |  |  | done | 2025-10-21 | 2025-10-22 | done | GPA |  |  | 2025-10-22 | 2025-10-20 | 2025-10-23 | XLWO-20251023-00000400 | RFC-20251023-00000264 |  | 2025-10-27 | [7 empty] | #N/A | 2025-10-27 | Done | #N/A | #N/A |  | 2025-10-29 |  | 2025-11-15
1 | 3 | CLEAR | Swap_JAW-JT-DMK-0612_3 | Swap_JAW-JT-DMK-0612 | JAW-JT-DMK-0612 | Central Java | Jawa Tengah | Demak | -6.8503 | 110.8054 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-DMK-0612 | Karanganyar Demak | Centratama |  | Central Java Ring 87 | PAG-JTDMK0612-03H | 10.206.29.173 | ATN910C | Huawei | New Purchase | HRAN Upgrade | Keep | 9 | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-16 | 42 | October |  | 2026 |  |  | Not Started | [25 empty] | XLWO-20251023-00000401 | [11 empty] | #N/A |  | NY | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-PTI-1480_2 | Swap_JAW-JT-PTI-1480 | JAW-JT-PTI-1480 | Central Java | Jawa Tengah | Pati | -6.7527 | 111.0354 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-PTI-1480 | Pati | Others |  | Central Java Ring 87 | PAG-JTPTI1480-02H | 10.206.29.174 | ATN910C | Huawei | New Purchase | HRAN Upgrade | Keep | 9 | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-11-13 | 46 |  |  | 2026 |  |  | In Progress | [37 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0888_1 | Swap_JAW-JT-KDS-0888 | JAW-JT-KDS-0888 | Central Java | Jawa Tengah | Kudus | -6.9344 | 110.8272 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0888 | Kutuk Kidul Pati | Protelindo |  | Central Java Ring 87A | MA-JTKDS0888-01H | 10.206.29.177 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 9 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-01-16 | 3 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1407_1 | Swap_JAW-JT-PTI-1407 | JAW-JT-PTI-1407 | Central Java | Jawa Tengah | Pati | -6.9384 | 110.8854 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1407 | SUKOLILO BALEADI | Centratama |  | Central Java Ring 87A | MA-JTPTI1407-01H | 10.206.29.179 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 9 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-26 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-3349_1 | Swap_JAW-JT-PTI-3349 | JAW-JT-PTI-3349 | Central Java | Jawa Tengah | Pati | -6.787 | 111.0169 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-3349 | Penambuhan Martgorejo | Protelindo |  | Central Java Ring 87A | MA-JTPTI3349-01H | 10.206.29.182 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 9 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-23 | 2025-10-23 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0884_1 | Swap_JAW-JT-KDS-0884 | JAW-JT-KDS-0884 | Central Java | Jawa Tengah | Kudus | -6.8836 | 110.8171 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0884 | Undaan Lor Undaan | TBG |  | Central Java Ring 87A | MA-JTKDS0884-01H | 10.206.29.175 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 9 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-01-19 | 4 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1403_1 | Swap_JAW-JT-PTI-1403 | JAW-JT-PTI-1403 | Central Java | Jawa Tengah | Pati | -6.9646 | 110.8298 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1403 | PRAWOTO | Centratama |  | Central Java Ring 87A | MA-JTPTI1403-01H | 10.206.29.178 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 9 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-26 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1419_1 | Swap_JAW-JT-PTI-1419 | JAW-JT-PTI-1419 | Central Java | Jawa Tengah | Pati | -6.9515 | 110.9547 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1419 | NURUL SALAM | TBG |  | Central Java Ring 87A | MA-JTPTI1419-01H | 10.206.29.180 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 9 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-26 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1468_1 | Swap_JAW-JT-PTI-1468 | JAW-JT-PTI-1468 | Central Java | Jawa Tengah | Pati | -6.8361 | 111.0118 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1468 | Sundoluhur Pati | Protelindo |  | Central Java Ring 87A | MA-JTPTI1468-01H | 10.206.29.181 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 9 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-24 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KDS-3476_1 | Swap_JAW-JT-KDS-3476 | JAW-JT-KDS-3476 | Central Java | Jawa Tengah | Kudus | -6.9135 | 110.8246 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-3476 | Undaan Kudus Relocation | Protelindo |  | Central Java Ring 87A | MA-JTKDS3476-01H | 10.206.29.176 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 9 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-01-19 | 4 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-KDS-0925_2 | Swap_JAW-JT-KDS-0925 | JAW-JT-KDS-0925 | Central Java | Jawa Tengah | Kudus | -6.8057 | 110.8798 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-KDS-0925 | Ngembal Kulon | Centratama |  | Central Java Ring 88 | PAG-JTKDS0925-02H | 10.206.29.190 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 7 | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-20 | 4 |  |  | 2026 | 2025-11-13 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved |  |  | Done | Done | Done | DOEID25111420 | 2025-11-24 | [9 empty] | GPA | 2025-11-24 | 48 | [5 empty] | 2025-11-27 |  | 2025-11-27 | 48 | 2025-11-27 | 48 | TRUE | 2025-11-26 | 48 | 2025-11-26 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0942_1 | Swap_JAW-JT-KDS-0942 | JAW-JT-KDS-0942 | Central Java | Jawa Tengah | Kudus | -6.7958 | 110.9612 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-KDS-0942 | Jekulo | Protelindo |  | Central Java Ring 88 | PAG-JTKDS0942-01H | 10.206.29.191 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 7 | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-20 | 4 |  |  | 2026 | 2025-11-12 | 2025-11-14 | Approved | 2025-11-17 |  | Submitted | Approved |  |  | Done | Done | Done | DOEID25111422 | 2025-11-24 | [9 empty] | GPA | 2025-11-24 | 48 | [5 empty] | 2025-11-27 |  | 2025-11-27 | 48 | 2025-11-27 | 48 | TRUE | 2025-11-26 | 48 | 2025-11-26 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0856_1 | Swap_JAW-JT-KDS-0856 | JAW-JT-KDS-0856 | Central Java | Jawa Tengah | Kudus | -6.8163 | 110.9457 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0856 | SIDOMULYO JEKULO | DMT |  | Central Java Ring 88A | MA-JTKDS0856-01H | 10.206.29.203 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-20 | 4 |  |  | 2026 | 2025-11-13 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-21 |  | Done | Done | Done | DOEID25111456 | 2025-11-24 | 2025-11-21 | done | done |  |  | done | done | done | done | YPTT | 2025-11-24 | 48 | 2025-11-21 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-27 | 2025-11-21 | 2025-11-27 | 48 | 2025-11-27 | 48 | TRUE | 2025-11-21 | 47 | 2025-11-21 | 2025-11-21 | Done | #N/A | #N/A | November | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0861_1 | Swap_JAW-JT-KDS-0861 | JAW-JT-KDS-0861 | Central Java | Jawa Tengah | Kudus | -6.8188 | 110.9212 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0861 | BULUNGCANGKRING JEKULO | DMT |  | Central Java Ring 88A | MA-JTKDS0861-01H | 10.206.29.201 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-20 | 4 |  |  | 2026 | 2025-11-12 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-21 |  | Done | Done | Done | DOEID25111457 | 2025-11-24 | 2025-11-21 | done | done |  |  | done | done | done | done | YPTT | 2025-11-24 | 48 | 2025-11-21 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-27 | 2025-11-21 | 2025-11-27 | 48 | 2025-11-27 | 48 | TRUE | 2025-11-21 | 47 | 2025-11-21 | 2025-11-21 | Done | #N/A | #N/A | November | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0940_1 | Swap_JAW-JT-KDS-0940 | JAW-JT-KDS-0940 | Central Java | Jawa Tengah | Kudus | -6.821 | 110.933 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0940 | Bulung Kulon Jekulo | TBG |  | Central Java Ring 88A | MA-JTKDS0940-01H | 10.206.29.202 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-20 | 4 |  |  | 2026 | 2025-11-12 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-21 |  | Done | Done | Done | DOEID25111438 | 2025-11-24 | 2025-11-21 | done | done |  |  | done | done | done | done | Mingze | 2025-11-24 | 48 | 2025-11-21 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-27 | 2025-11-21 | 2025-11-27 | 48 | 2025-11-27 | 48 | TRUE | 2025-11-21 | 47 | 2025-11-21 | 2025-11-21 | Done | #N/A | #N/A | November
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0859_1 | Swap_JAW-JT-KDS-0859 | JAW-JT-KDS-0859 | Central Java | Jawa Tengah | Kudus | -6.8036 | 110.8699 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0859 | PANGLIMA BESAR DERSALAM | Protelindo |  | Central Java Ring 88A | MA-JTKDS0859-01H | 10.206.29.193 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-21 | 4 |  |  | 2026 | 2025-11-12 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID25111440 | 2025-11-24 | 2025-11-23 | Done | Done |  |  | Done | Done | Done | Done | Mingze | 2025-11-24 | 48 | 2025-11-21 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-27 | 2025-11-23 | 2025-11-27 | 48 | 2025-11-27 | 48 | TRUE | 2025-11-23 | 47 | 2025-11-23 | 2025-11-23 | Done | #N/A | #N/A | November
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0860_1 | Swap_JAW-JT-KDS-0860 | JAW-JT-KDS-0860 | Central Java | Jawa Tengah | Kudus | -6.7815 | 110.8763 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0860 | KAYUAPU WETAN BAE | Others |  | Central Java Ring 88A | MA-JTKDS0860-01H | 10.206.29.192 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-21 | 4 |  |  | 2026 | 2025-11-13 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID251113PH | 2025-11-24 | 2025-11-23 | Done | Done |  |  | Done | Done | Done | Done | GCI | 2025-11-24 | 48 | 2025-11-21 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-27 | 2025-11-23 | 2025-11-27 | 48 | 2025-11-27 | 48 | TRUE | 2025-11-23 | 47 | 2025-11-23 | 2025-11-23 | Done | #N/A | #N/A | November | 2025-11-24
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0857_1 | Swap_JAW-JT-KDS-0857 | JAW-JT-KDS-0857 | Central Java | Jawa Tengah | Kudus | -6.8285 | 110.9132 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0857 | JEKULO RAYA SADANG | DMT |  | Central Java Ring 88A | MA-JTKDS0857-01H | 10.206.29.200 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-21 | 4 |  |  | 2026 | 2025-11-12 | 2025-11-14 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-21 |  | Done | Done | Done | DOEID25111449 | 2025-11-27 | 2025-11-21 | done | done |  |  | done | done | done | done | GIT | 2025-11-27 | 48 | 2025-11-21 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-30 | 2025-11-21 | 2025-11-30 | 48 | 2025-11-30 | 48 | TRUE | 2025-11-21 | 47 | 2025-11-21 | 2025-11-21 | Done | #N/A | #N/A | November | 2025-11-24
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0863_1 | Swap_JAW-JT-KDS-0863 | JAW-JT-KDS-0863 | Central Java | Jawa Tengah | Kudus | -6.8384 | 110.8682 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0863 | GULANG KULON MEJOBO | DMT |  | Central Java Ring 88A | MA-JTKDS0863-01H | 10.206.29.199 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-21 | 4 |  |  | 2026 | 2025-11-11 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-21 |  | Done | Done | Done | DOEID25111451 | 2025-11-27 | 2025-11-21 | done | done |  |  | done | done | done | done | GIT | 2025-11-27 | 48 | 2025-11-21 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-30 | 2025-11-21 | 2025-11-30 | 48 | 2025-11-30 | 48 | TRUE | 2025-11-21 | 47 | 2025-11-21 | 2025-11-21 | Done | #N/A | #N/A | November | 2025-11-24
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0907_1 | Swap_JAW-JT-KDS-0907 | JAW-JT-KDS-0907 | Central Java | Jawa Tengah | Kudus | -6.8361 | 110.8479 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0907 | LORAM KULON JATI | TBG |  | Central Java Ring 88A | MA-JTKDS0907-01H | 10.206.29.197 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-21 | 4 |  |  | 2026 | 2025-11-11 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-21 |  | Done | Done | Done | DOEID25111458 | 2025-11-27 | 2025-11-21 | done | done |  |  | done | done | done | done | YPTT | 2025-11-27 | 48 | 2025-11-21 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-30 | 2025-11-21 | 2025-11-30 | 48 | 2025-11-30 | 48 | TRUE | 2025-11-21 | 47 | 2025-11-21 | 2025-11-21 | Done | #N/A | #N/A | November | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-KDS-3101_1 | Swap_JAW-JT-KDS-3101 | JAW-JT-KDS-3101 | Central Java | Jawa Tengah | Kudus | -6.8314 | 110.8518 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-3101 | MEJOBO KUDUS RELOCATION | TBG |  | Central Java Ring 88A | MA-JTKDS3101-01H | 10.206.29.198 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-22 | 4 |  |  | 2026 | 2025-11-11 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-24 |  | Done | Done | Done | DOEID25111460 | 2025-11-27 | 2025-11-24 | done | done |  |  | done | done | done | done | YPTT | 2025-11-27 | 48 | 2025-11-24 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-30 | 2025-11-24 | 2025-11-30 | 48 | 2025-11-30 | 48 | TRUE | 2025-11-24 | 48 | 2025-11-21 | 2025-11-24 | Done | #N/A | #N/A | November
1 | 1 | CLEAR | Swap_JAW-JT-KDS-3183_1 | Swap_JAW-JT-KDS-3183 | JAW-JT-KDS-3183 | Central Java | Jawa Tengah | Kudus | -6.8249 | 110.8381 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-3183 | GETASPEJATEN JATI | DMT |  | Central Java Ring 88A | MA-JTKDS3183-01H | 10.206.29.196 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-22 | 4 |  |  | 2026 | 2025-11-11 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID25111441 | 2025-11-27 | 2025-11-23 | Done | Done |  |  | Done | Done | Done | Done | Mingze | 2025-11-27 | 48 | 2025-11-21 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-30 | 2025-11-23 | 2025-11-30 | 48 | 2025-11-30 | 48 | TRUE | 2025-11-23 | 47 | 2025-11-23 | 2025-11-23 | Done | #N/A | #N/A | November
1 | 1 | CLEAR | Swap_JAW-JT-KDS-3449_1 | Swap_JAW-JT-KDS-3449 | JAW-JT-KDS-3449 | Central Java | Jawa Tengah | Kudus | -6.8042 | 110.8565 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-3449 | Jl Candi Prambanan Timur (Tol Manyaran) | TBG |  | Central Java Ring 88A | MA-JTKDS3449-01H | 10.206.29.194 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GIT | 2026-01-22 | 4 |  |  | 2026 | 2025-11-19 | 2025-11-19 | Reviewing |  |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID25111442 | 2025-11-27 | 2025-11-23 | Done | Done |  |  | Done | Done | Done | Done | Mingze | 2025-11-27 | 48 | 2025-11-21 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-30 | 2025-11-23 | 2025-11-30 | 48 | 2025-11-30 | 48 | TRUE | 2025-11-23 | 47 | 2025-11-23 | 2025-11-23 | Done | #N/A | #N/A | November
1 | 2 | CLEAR | Swap_JAW-JT-DMK-0552_2 | Swap_JAW-JT-DMK-0552 | JAW-JT-DMK-0552 | Central Java | Jawa Tengah | Demak | -7.0276 | 110.5174 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-DMK-0552 | Mranggen | TBG | IBS¦NO TP ID | Central Java Ring 91 | PAG-JTDMK0552-02H | 10.206.27.97 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 1 | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-24 | 43 | October |  | 2026 | 2025-10-31 | 2025-10-31 | Approved | 2025-11-07 |  |  |  | Done |  | Done | Done | 2025-11-02 | DOEID25110259 | 2025-11-02 | 2025-11-04 | done | done |  |  | done | done | done | done | Mingze | 2025-11-02 | 44 | 2025-11-04 | 2025-11-01 | 2025-11-03 | XLWO-20251103-00002369 |  | 2025-11-05 | 2025-11-06 | 2025-11-05 | 45 | 2025-11-06 | 45 | FALSE | 2025-11-06 | 45 | 2025-11-06 | 2025-11-06 | Done | #N/A | #N/A | November | 2025-11-08 |  | 2025-11-15
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0602_1 | Swap_JAW-JT-DMK-0602 | JAW-JT-DMK-0602 | Central Java | Jawa Tengah | Demak | -6.8738 | 110.7173 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-DMK-0602 | Mpls - Gajah | Protelindo | PRT¦JAW-JT-DMK-0602 | Central Java Ring 91 | PAG-SM2395-02H | 10.206.27.98 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 1 | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-11-03 | 45 |  |  | 2026 | 2025-10-12 | 2025-10-13 | Approved | 2025-11-07 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110263 | 2025-11-02 | 2025-11-04 | done | done |  |  | done | done | done | done | GPA | 2025-11-02 | 44 | 2025-11-04 | 2025-11-01 | 2025-11-03 | XLWO-20251103-00002369 |  | 2025-11-05 | 2025-11-06 | 2025-11-05 | 45 | 2025-11-06 | 45 | FALSE | 2025-11-06 | 45 | 2025-11-06 | 2025-11-06 | Done | #N/A | #N/A | November | 2025-11-20 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0547_1 | Swap_JAW-JT-DMK-0547 | JAW-JT-DMK-0547 | Central Java | Jawa Tengah | Demak | -6.9916 | 110.5118 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0547 | BRUMBUNG MRANGGEN | DMT | DMT¦M00-JT-65441 | Central Java Ring 91B | MA-JTDMK0547-01H | 10.206.27.108 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-11-03 | 45 |  |  | 2026 | 2025-10-24 | 2025-10-25 | Approved | 2025-11-07 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110219 | 2025-11-03 | 2025-11-06 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-03 | 45 | 2025-11-06 | 2025-11-03 | 2025-11-05 | XLWO-20251105-00000156 |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | 45 | 2025-11-06 | 45 | TRUE | 2025-11-06 | 45 | 2025-11-06 | 2025-11-06 | Done | #N/A | #N/A | November | 2025-11-15 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0549_1 | Swap_JAW-JT-DMK-0549 | JAW-JT-DMK-0549 | Central Java | Jawa Tengah | Demak | -7.0532 | 110.5066 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0549 | Kebonrojo | Centratama | ISAT¦14SMG112 | Central Java Ring 91B | MA-JTDMK0549-01H | 10.206.27.106 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-11-03 | 45 |  |  | 2026 | 2025-10-23 | 2025-10-29 | Approved | 2025-11-07 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110221 | 2025-11-03 | 2025-11-06 | Done | Done |  |  | Done | Done | Done | Done | GPA | 2025-11-03 | 45 | 2025-11-06 | 2025-11-03 | 2025-11-05 | XLWO-20251105-00000156 |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | 45 | 2025-11-06 | 45 | TRUE | 2025-11-06 | 45 | 2025-11-06 | 2025-11-06 | Done | #N/A | #N/A | November | 2025-11-15 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0558_1 | Swap_JAW-JT-DMK-0558 | JAW-JT-DMK-0558 | Central Java | Jawa Tengah | Demak | -7.0289 | 110.5322 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0558 | Kembang Arum Mranggen C-Prtd | Protelindo | PRT¦JAW-CJV-0273-H-P | Central Java Ring 91B | MA-JTDMK0558-01H | 10.206.27.107 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-11-03 | 45 |  |  | 2026 | 2025-10-26 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110238 | 2025-11-03 | 2025-11-05 | done | done |  |  | done | Done | done | done | Mingze | 2025-11-03 | 45 | 2025-11-05 | 2025-11-03 | 2025-11-05 | XLWO-20251105-00000156 |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | 45 | 2025-11-06 | 45 | TRUE | 2025-11-06 | 45 | 2025-11-06 | 2025-11-06 | Done | #N/A | #N/A | November | 2025-11-09 |  | 2025-11-15
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0559_1 | Swap_JAW-JT-DMK-0559 | JAW-JT-DMK-0559 | Central Java | Jawa Tengah | Demak | -6.9324 | 110.534 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0559 | Gemulak Sayung | Protelindo | PRT¦JAW-CJV-0459-H-P | Central Java Ring 91B | MA-JTDMK0559-01H | 10.206.27.110 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-11-03 | 45 |  |  | 2026 | 2025-10-25 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110239 | 2025-11-03 | 2025-11-05 | done | done |  |  | done | Done | done | done | Mingze | 2025-11-03 | 45 | 2025-11-05 | 2025-11-03 | 2025-11-05 | XLWO-20251105-00000156 |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | 45 | 2025-11-06 | 45 | TRUE | 2025-11-06 | 45 | 2025-11-06 | 2025-11-06 | Done | #N/A | #N/A | November | 2025-11-09 |  | 2025-11-15
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0585_1 | Swap_JAW-JT-DMK-0585 | JAW-JT-DMK-0585 | Central Java | Jawa Tengah | Demak | -6.8914 | 110.6309 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0585 | Mangunjiwan Demak | TBG | IBS¦SMG_01N039 | Central Java Ring 91B | MA-JTDMK0585-01H | 10.206.27.111 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-11-03 | 45 |  |  | 2026 | 2025-10-22 | 2025-10-22 | Approved | 2025-11-07 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110235 | 2025-11-03 | 2025-11-05 | done | done |  |  | done | Done | done | done | YPTT | 2025-11-03 | 45 | 2025-11-05 | 2025-11-03 | 2025-11-05 | XLWO-20251105-00000156 |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | 45 | 2025-11-06 | 45 | TRUE | 2025-11-06 | 45 | 2025-11-06 | 2025-11-06 | Done | #N/A | #N/A | November | 2025-11-09 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0596_1 | Swap_JAW-JT-DMK-0596 | JAW-JT-DMK-0596 | Central Java | Jawa Tengah | Demak | -6.8827 | 110.6766 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0596 | Bolo Demak | Protelindo | ISAT¦14DMK031 | Central Java Ring 91B | MA-SM2531529-01H | 10.206.27.112 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-11-03 | 45 |  |  | 2026 | 2025-10-25 | 2025-10-25 | Approved | 2025-11-07 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110237 | 2025-11-03 | 2025-11-05 | done | done |  |  | done | Done | done | done | YPTT | 2025-11-03 | 45 | 2025-11-05 | 2025-11-03 | 2025-11-05 | XLWO-20251105-00000156 |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | 45 | 2025-11-06 | 45 | TRUE | 2025-11-06 | 45 | 2025-11-06 | 2025-11-06 | Done | #N/A | #N/A | November | 2025-11-09 |  | 2025-11-21
1 | 2 | CLEAR | Swap_JAW-JT-KDL-0797_2 | Swap_JAW-JT-KDL-0797 | JAW-JT-KDL-0797 | Central Java | Jawa Tengah | Kendal | -6.9708 | 110.0789 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-KDL-0797 | Mpls - Weleri | Centratama |  | Central Java Ring 92 | PAG-JTKDL0797-02H | 10.206.29.229 | ATN910C | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2025-624 sites | GPA | 2025-11-10 | 46 |  |  | 2026 | 2025-10-30 | 2025-10-30 | Approved | 2025-11-07 | [36 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KDL-0872_1 | Swap_JAW-JT-KDL-0872 | JAW-JT-KDL-0872 | Central Java | Jawa Tengah | Kendal | -6.9662 | 110.287 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-KDL-0872 | Mangkang | Centratama |  | Central Java Ring 92 | PAG-JTKDL0872-02H | 10.206.29.230 | ATN910C | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2025-624 sites | GPA | 2025-11-10 | 46 |  |  | 2026 |  |  | In Progress |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-2703_1 | Swap_JAW-JT-UNR-2703 | JAW-JT-UNR-2703 | Central Java | Jawa Tengah | Semarang | -7.1818 | 110.4226 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-UNR-2703 | Karangjati | Protelindo |  | Central Java Ring 93 | PAG-JTUNR2703-04H | 10.206.30.235 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | Mid Dec 25 |  | 2026-01-26 | 5 |  |  | 2026 |  |  | Not Started |  |  | Submitted | Approved | [16 empty] | GCI | [14 empty] | 2025-11-27 | 48 | 0 |  |  | #N/A | #N/A
1 | 3 | CLEAR | Swap_JAW-JT-PTI-1480_3 | Swap_JAW-JT-PTI-1480 | JAW-JT-PTI-1480 | Central Java | Jawa Tengah | Pati | -6.7527 | 111.0354 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1480 | Pati | Others |  | CENTRAL Ring 12B | MA-SM2244-01 | #N/A | ACX2200 | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-11-13 | 46 |  |  | 2026 |  |  | In Progress | [37 empty] | #N/A |  | Done | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-KDS-0942_2 | Swap_JAW-JT-KDS-0942 | JAW-JT-KDS-0942 | Central Java | Jawa Tengah | Kudus | -6.7958 | 110.9612 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0942 | Jekulo | Protelindo |  | CENTRAL Ring 12B | MA-SM2289-01 | #N/A | ACX2200 | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-01-27 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 4 | CLEAR | Swap_JAW-JT-DMK-0612_4 | Swap_JAW-JT-DMK-0612 | JAW-JT-DMK-0612 | Central Java | Jawa Tengah | Demak | -6.8503 | 110.8054 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0612 | Karanganyar Demak | Centratama |  | CENTRAL Ring 12B | MA-SMBC26-01 | #N/A | ACX2200 | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-16 | 42 | October |  | 2026 |  |  | Not Started | [37 empty] | #N/A |  | Done | #N/A | #N/A
1 | 3 | CLEAR | Swap_JAW-JT-SLT-2171_3 | Swap_JAW-JT-SLT-2171 | JAW-JT-SLT-2171 | Central Java | Jawa Tengah | Kota Salatiga | -7.3627 | 110.5156 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SLT-2171 | Tingkir Salatiga | Centratama |  | CENTRAL Ring 13F | MA-SMB239-01 | #N/A | ACX2200 | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | GIT | 2025-10-14 | 42 | October |  | 2026 | 2025-10-14 |  | Not Started | [37 empty] | #N/A |  | NY | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-2721_1 | Swap_JAW-JT-UNR-2721 | JAW-JT-UNR-2721 | Central Java | Jawa Tengah | Semarang | -7.3741 | 110.4436 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-2721 | Getasan | Centratama |  | CENTRAL Ring 13F | MA-SMB321-01 | #N/A | ACX2200 | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | Mid Dec 25 |  | 2026-01-27 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 3 | CLEAR | Swap_JAW-JT-KDL-3487_3 | Swap_JAW-JT-KDL-3487 | JAW-JT-KDL-3487 | Central Java | Jawa Tengah | Kendal | -6.96536111111111 | 110.270188888889 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDL-3487 | Supernode Mangkang | 0 |  | CENTRAL Ring 3A | MA-SMSN0074-01 | #N/A | ACX2200 | Juniper | New Purchase | Swap Cisco | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-20 | 43 | October |  | 2026 | 2025-11-10 | 2025-11-10 | Approved | 2025-11-17 | [36 empty] | #N/A |  | NY | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-YO-YYK-0492_2 | Swap_JAW-YO-YYK-0492 | JAW-YO-YYK-0492 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7893 | 110.3595 | Swap | Swap Only | Swap | Type C | PAG | JAW-YO-YYK-0492 | Mpls - Patok Yogyakartara | Direct Lease |  | MBH Central Java Ring 11 | PAG-YOYYK0492-01H | 10.219.36.21 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | YPTT | 2025-10-20 | 43 | October |  | 2026 |  |  | In Progress | [37 empty] | #N/A |  | NY | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SMG-2526_1 | Swap_JAW-JT-SMG-2526 | JAW-JT-SMG-2526 | Central Java | Jawa Tengah | Kota Semarang | -6.9978 | 110.4478 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-SMG-2526 | Gayamsari | Others |  | MBH Central Java Ring 114 | PAG-JTSMG2526-02H | 10.206.30.234 | ATN910C | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | PT IFORTE SOLUSI INFOTEK |  |  | #N/A | [5 empty] | 2025-11-09 |  |  |  | 2025-End Nov |  | 2026-01-28 | 5 |  |  | 2026 |  |  | Not Started |  |  | Submitted | Approved | [16 empty] | GCI | [14 empty] | 2025-11-27 | 48 | 2025-11-27 |  |  | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-KLN-1037_2 | Swap_JAW-JT-KLN-1037 | JAW-JT-KLN-1037 | Central Java | Jawa Tengah | Klaten | -7.6918 | 110.6409 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-1037 | Klaten | Protelindo |  | MBH Central Java Ring 11A | MA-JTKLN1037-01H | 10.219.37.49 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-28 | 5 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-KLN-1055_2 | Swap_JAW-JT-KLN-1055 | JAW-JT-KLN-1055 | Central Java | Jawa Tengah | Klaten | -7.6166 | 110.7014 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-1055 | Kota Delanggu | Centratama |  | MBH Central Java Ring 11A | MA-JTKLN1055-01H | 10.219.37.3 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-28 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-2031_1 | Swap_JAW-JT-SKH-2031 | JAW-JT-SKH-2031 | Central Java | Jawa Tengah | Sukoharjo | -7.5592 | 110.7637 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-2031 | Karangasem | Protelindo |  | MBH Central Java Ring 11A | MA-JTSKH2031-01H | 10.219.37.94 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-28 | 5 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 3 | CLEAR | Swap_JAW-JT-SKT-2035_3 | Swap_JAW-JT-SKT-2035 | JAW-JT-SKT-2035 | Central Java | Jawa Tengah | Kota Surakarta | -7.546 | 110.78 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKT-2035 | Baturan Reloc | Protelindo |  | MBH Central Java Ring 11A | MA-JTSKT2035-01H | 10.219.37.120 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | CCSI | 2026-01-29 | 5 |  |  | 2026 | 2025-10-29 | 2025-11-01 | Approved | 2025-11-07 | [36 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2048_1 | Swap_JAW-JT-SKT-2048 | JAW-JT-SKT-2048 | Central Java | Jawa Tengah | Kota Surakarta | -7.5619 | 110.7922 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKT-2048 | Purwosari Solo | Protelindo |  | MBH Central Java Ring 11A | MA-JTSKT2048-01H | 10.219.37.95 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | CCSI | 2026-01-29 | 5 |  |  | 2026 | 2025-10-31 | 2025-11-01 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-SKT-2062_2 | Swap_JAW-JT-SKT-2062 | JAW-JT-SKT-2062 | Central Java | Jawa Tengah | Kota Surakarta | -7.5498 | 110.8044 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKT-2062 | Banyuanyar | Protelindo |  | MBH Central Java Ring 11A | MA-JTSKT2062-01H | 10.219.37.121 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | CCSI | 2026-01-29 | 5 |  |  | 2026 | 2025-10-30 | 2025-11-01 | Approved | 2025-11-07 | [36 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-YO-SMN-0311_1 | Swap_JAW-YO-SMN-0311 | JAW-YO-SMN-0311 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.7827 | 110.4368 | Swap | Swap Only | Swap | Type B | MA | JAW-YO-SMN-0311 | Adisucipto | Centratama |  | MBH Central Java Ring 11A | MA-YOSMN0311-01H | 10.219.37.249 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-01-29 | 5 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [16 empty] | YPTT | [14 empty] | 2025-11-30 | 48 | 2025-11-30 |  |  | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-KLN-0989_2 | Swap_JAW-JT-KLN-0989 | JAW-JT-KLN-0989 | Central Java | Jawa Tengah | Klaten | -7.7508 | 110.5159 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-0989 | Prambanan | Protelindo |  | MBH Central Java Ring 11A | MA-JTKLN0989-01H | 10.219.37.20 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-01-29 | 5 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-YO-SMN-0338_1 | Swap_JAW-YO-SMN-0338 | JAW-YO-SMN-0338 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.7621 | 110.4724 | Swap | Swap Only | Swap | Type B | MA | JAW-YO-SMN-0338 | Candi Kalasan | Others |  | MBH Central Java Ring 11A | MA-YOSMN0338-01H | 10.219.37.116 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-01-30 | 5 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [16 empty] | YPTT | [14 empty] | 2025-11-30 | 48 | 2025-11-30 |  |  | #N/A | #N/A
1 | 3 | CLEAR | Swap_JAW-JT-DMK-0613_3 | Swap_JAW-JT-DMK-0613 | JAW-JT-DMK-0613 | Central Java | Jawa Tengah | Demak | -6.90943055555556 | 110.633 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-DMK-0613 | Supernode Demak | 0 |  | MBH Central Java Ring 12 | PAG-JTDMK0613-01H | 10.219.36.17 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 4 | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-16 | 42 | October |  | 2026 | 2025-11-03 | 2025-11-03 | Approved | 2025-11-07 |  |  |  | 2025-11-16 |  | Done | Done | 2025-11-08 | DOEID251107OC | 2025-11-15 | 2025-11-17 | Done | Done |  |  | Done | Done | Done | Done | Mingze | 2025-11-15 | 46 | 2025-11-16 |  | 2025-11-10 | XLWO-20251112-00001205 |  | 2025-11-18 | 2025-11-17 | 2025-11-18 | 47 | 2025-11-18 | 47 | TRUE | 2025-11-17 | 47 | 2025-11-17 | 2025-11-17 | NY | #N/A | #N/A | November | 2025-11-19
1 | 2 | CLEAR | Swap_JAW-JT-PTI-1520_2 | Swap_JAW-JT-PTI-1520 | JAW-JT-PTI-1520 | Central Java | Jawa Tengah | Pati | -6.7188 | 111.1446 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-PTI-1520 | Juana | Protelindo |  | MBH Central Java Ring 12 | PAG-JTPTI1520-01H | 10.219.36.18 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 4 | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-11-13 | 46 |  |  | 2026 |  |  | In Progress |  |  |  |  | 2025-11-16 |  | Done | Done | 2025-11-08 | DOEID251107OE | 2025-11-15 | 2025-11-17 | Done | Done |  |  | Done | Done | Done | Done | Mingze | 2025-11-15 | 46 | 2025-11-17 |  | 2025-11-10 | XLWO-20251112-00001205 |  | 2025-11-18 | 2025-11-17 | 2025-11-18 | 47 | 2025-11-18 | 47 | TRUE | 2025-11-17 | 47 | 2025-11-17 | 2025-11-17 | Done | #N/A | #N/A | November | 2025-11-19
1 | 2 | CLEAR | Swap_JAW-JT-MGG-1158_2 | Swap_JAW-JT-MGG-1158 | JAW-JT-MGG-1158 | Central Java | Jawa Tengah | Kota Magelang | -7.4796 | 110.2269 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-MGG-1158 | Mpls - Magelang | Protelindo |  | MBH Central Java Ring 13 | PAG-JTMGG1158-01H | 10.219.36.10 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GIT | 2025-10-15 | 42 | October |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  | NY | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-SMG-2406_2 | Swap_JAW-JT-SMG-2406 | JAW-JT-SMG-2406 | Central Java | Jawa Tengah | Kota Semarang | -6.9856 | 110.4079 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-SMG-2406 | Simpang Lima | DMT |  | MBH Central Java Ring 2 | PAG-JTSMG2406-01H | 10.219.36.27 | ATN910C | Huawei | New Purchase | HRAN Upgrade | Keep | 11 | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | GIT | 2025-10-14 | 42 | October |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  | NY | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-SMG-2526_2 | Swap_JAW-JT-SMG-2526 | JAW-JT-SMG-2526 | Central Java | Jawa Tengah | Kota Semarang | -6.9978 | 110.4478 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-SMG-2526 | Gayamsari | Others |  | MBH Central Java Ring 2 | PAG-JTSMG2526-01H | 10.219.36.28 | ATN910C | Huawei | New Purchase | HRAN Upgrade | Keep | 11 | TypeC 6120H-S Bundle | PT IFORTE SOLUSI INFOTEK |  |  | #N/A | [5 empty] | 2025-11-09 |  |  |  | 2025-End Nov |  | 2026-02-02 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SMG-2424_1 | Swap_JAW-JT-SMG-2424 | JAW-JT-SMG-2424 | Central Java | Jawa Tengah | Kota Semarang | -6.9839 | 110.413 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SMG-2424 | Dp Mall Semarang | Others |  | MBH Central Java Ring 2B | MA-JTSMG2424-01H | 10.206.30.175 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 11 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2026-02-02 | 6 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SMG-2432_1 | Swap_JAW-JT-SMG-2432 | JAW-JT-SMG-2432 | Central Java | Jawa Tengah | Kota Semarang | -6.9743 | 110.4142 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SMG-2432 | Imam Bonjol Poncol | DMT |  | MBH Central Java Ring 2B | MA-JTSMG2432-01H | 10.219.37.157 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 11 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2026-02-02 | 6 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SMG-2487_1 | Swap_JAW-JT-SMG-2487 | JAW-JT-SMG-2487 | Central Java | Jawa Tengah | Kota Semarang |  |  | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SMG-2487 | #N/A | #N/A |  | MBH Central Java Ring 2B | MA-JTSMG2487-01H | 10.219.37.21 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 11 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [11 empty] | 2026-02-02 | 6 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SMG-2483_1 | Swap_JAW-JT-SMG-2483 | JAW-JT-SMG-2483 | Central Java | Jawa Tengah | Kota Semarang | -6.9814 | 110.427 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SMG-2483 | Loyola Karang Saru (Colocated With Nts) | Protelindo |  | MBH Central Java Ring 2B | MA-JTSMG2483-01H | 10.219.37.161 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 11 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2026-02-02 | 6 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SMG-2528_1 | Swap_JAW-JT-SMG-2528 | JAW-JT-SMG-2528 | Central Java | Jawa Tengah | Kota Semarang | -6.9763 | 110.4491 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SMG-2528 | Muktiharjo | Centratama |  | MBH Central Java Ring 2B | MA-JTSMG2528-01H | 10.219.37.23 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 11 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2026-02-03 | 6 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SMG-2458_1 | Swap_JAW-JT-SMG-2458 | JAW-JT-SMG-2458 | Central Java | Jawa Tengah | Kota Semarang | -6.9847 | 110.425 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SMG-2458 | Bugangan Relocation | Centratama |  | MBH Central Java Ring 2B | MA-JTSMG2458-01H | 10.219.37.160 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 11 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2026-02-03 | 6 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SMG-2497_1 | Swap_JAW-JT-SMG-2497 | JAW-JT-SMG-2497 | Central Java | Jawa Tengah | Kota Semarang | -6.9841 | 110.432 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SMG-2497 | Kebon Agung | Protelindo |  | MBH Central Java Ring 2B | MA-JTSMG2497-01H | 10.219.37.22 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 11 | TypeB 6120H-SC Chassis Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov |  | 2026-02-03 | 6 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | TAKEOUT | Swap_JAW-JB-CBN-2036_1 | Swap_JAW-JB-CBN-2036 | JAW-JB-CBN-2036 | Central Java | Jawa Barat | Kota Cirebon | -6.7411 | 108.576 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JB-CBN-2036 | PEGAMBIRAN | #N/A |  | West Java Ring 14 | PAG-BD2313-01H | 10.219.221.120 | NE40E-X2-M8A | Huawei | New Purchase | Linknet NNI,PAG1 | #N/A |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [11 empty] | 2026-02-03 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | TAKEOUT | Swap_JAW-JB-CBN-2013_1 | Swap_JAW-JB-CBN-2013 | JAW-JB-CBN-2013 | Central Java | Jawa Barat | Kota Cirebon | -6.7058 | 108.554 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JB-CBN-2013 | PANCURAN CIREBON | #N/A |  | West Java Ring 14 | PAG-BD2314-03H | 10.219.221.119 | NE40E-X2-M8A | Huawei | New Purchase | Linknet NNI,PAG2 | #N/A |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [11 empty] | 2026-02-03 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-CLP-0403_1 | Swap_JAW-JT-CLP-0403 | JAW-JT-CLP-0403 | Central Java | Jawa Tengah | Cilacap | -7.4834 | 108.7923 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-CLP-0403 | Sidareja | Centratama |  | Central Java Ring 16 | PAG-BD2300-01H | 10.219.27.161 | ATN910C-B | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | CCSI | 2026-02-04 | 6 |  |  | 2026 | 2025-10-25 | 2025-10-30 | Approved | 2025-11-07 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | TAKEOUT | Swap_JAW-JB-PWK-1747_1 | Swap_JAW-JB-PWK-1747 | JAW-JB-PWK-1747 | Central Java | Jawa Barat | Purwakarta | -6.5207 | 107.4336 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JB-PWK-1747 | MARACANG PURWAKARTA | #N/A |  | West Java Ring 32 | PAG-BD2175-01H | 10.219.208.209 | NE40E-M2K-B | Huawei | New Purchase | Linknet NNI,PAG1 | #N/A |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [11 empty] | 2026-02-04 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | TAKEOUT | Swap_JAW-JB-PWK-1787_1 | Swap_JAW-JB-PWK-1787 | JAW-JB-PWK-1787 | Central Java | Jawa Barat | Purwakarta | -6.5222 | 107.458 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JB-PWK-1787 | CISEUREH | #N/A |  | West Java Ring 32 | PAG-BD1951-01H | 10.219.208.210 | NE40E-M2K-B | Huawei | New Purchase | Linknet NNI,PAG2 | #N/A |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [11 empty] | 2026-02-04 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | HOLD | Swap__1 | Swap_ |  | Central Java |  |  | #N/A | #N/A | Swap | Swap Only | Swap | Type C | PAG |  |  | #N/A |  | CENTRAL Ring 12B | CENTRAL Ring 12B-PAG1 | #N/A | #N/A | #N/A | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [11 empty] | 2026-02-04 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | HOLD | Swap__2 | Swap_ |  | Central Java |  |  | #N/A | #N/A | Swap | Swap Only | Swap | Type C | PAG |  |  | #N/A |  | CENTRAL Ring 12B | CENTRAL Ring 12B-PAG2 | #N/A | #N/A | #N/A | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [11 empty] | 2026-02-04 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 3 | HOLD | Swap__3 | Swap_ |  | Central Java |  |  | #N/A | #N/A | Swap | Swap Only | Swap | Type C | PAG |  |  | #N/A |  | CENTRAL Ring 13F | CENTRAL Ring 13F-PAG1 | #N/A | #N/A | #N/A | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [11 empty] | 2026-02-05 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 4 | HOLD | Swap__4 | Swap_ |  | Central Java |  |  | #N/A | #N/A | Swap | Swap Only | Swap | Type C | PAG |  |  | #N/A |  | CENTRAL Ring 13F | CENTRAL Ring 13F-PAG2 | #N/A | #N/A | #N/A | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [11 empty] | 2026-02-05 | 6 |  |  | 2026 |  |  | #N/A | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 4 | CLEAR | Swap_JAW-JT-KDL-3487_4 | Swap_JAW-JT-KDL-3487 | JAW-JT-KDL-3487 | Central Java | Jawa Tengah | Kendal | -6.96536111111111 | 110.270188888889 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | MA | JAW-JT-KDL-3487 | Supernode Mangkang | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | New Purchase | New Ring 001 | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [10 empty] | GPA | 2025-10-20 | 43 | October |  | 2026 | 2025-11-10 | 2025-11-10 | Approved | 2025-11-17 |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 3 | CLEAR | Swap_JAW-JT-SMG-2526_3 | Swap_JAW-JT-SMG-2526 | JAW-JT-SMG-2526 | Central Java | Jawa Tengah | Kota Semarang | -6.9978 | 110.4478 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-SMG-2526 | Gayamsari | Others |  | #N/A | #N/A | #N/A | #N/A | #N/A | New Purchase | New Ring 010 | Keep |  | TypeC 6120H-S Bundle | PT IFORTE SOLUSI INFOTEK |  |  | #N/A | [5 empty] | 2025-11-09 |  |  |  | 2025-End Nov |  | 2026-02-05 | 6 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 3 | CLEAR | Swap_JAW-JT-SMG-2406_3 | Swap_JAW-JT-SMG-2406 | JAW-JT-SMG-2406 | Central Java | Jawa Tengah | Kota Semarang | -6.9856 | 110.4079 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-SMG-2406 | Simpang Lima | DMT |  | #N/A | #N/A | #N/A | #N/A | #N/A | New Purchase | New Ring 010 | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2025-End Nov | GIT | 2025-10-14 | 42 | October |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  | NY | #N/A | #N/A
1 | 3 | CLEAR | Swap_JAW-JT-KDS-0925_3 | Swap_JAW-JT-KDS-0925 | JAW-JT-KDS-0925 | Central Java | Jawa Tengah | Kudus | -6.8057 | 110.8798 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | #N/A | JAW-JT-KDS-0925 | Ngembal Kulon | Centratama |  | #N/A | #N/A | #N/A | #N/A | #N/A | New Purchase | New Ring 011 | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-02-06 | 6 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 5 | CLEAR | Swap_JAW-JT-DMK-0612_5 | Swap_JAW-JT-DMK-0612 | JAW-JT-DMK-0612 | Central Java | Jawa Tengah | Demak | -6.8503 | 110.8054 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-DMK-0612 | Karanganyar Demak | Centratama |  | #N/A | #N/A | #N/A | #N/A | #N/A | New Purchase | New Ring 011 | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2026 | GPA | 2025-10-16 | 42 | October |  | 2026 |  |  | Not Started |  |  | Submitted | Approved | [33 empty] | #N/A |  | Done | #N/A | #N/A
1 | 4 | CLEAR | Swap_JAW-JT-KDS-0925_4 | Swap_JAW-JT-KDS-0925 | JAW-JT-KDS-0925 | Central Java | Jawa Tengah | Kudus | -6.8057 | 110.8798 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | #N/A | JAW-JT-KDS-0925 | Ngembal Kulon | Centratama |  | #N/A | #N/A | #N/A | #N/A | #N/A | New Purchase | New Ring 012 | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-02-06 | 6 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
1 | 3 | CLEAR | Swap_JAW-JT-KDS-0942_3 | Swap_JAW-JT-KDS-0942 | JAW-JT-KDS-0942 | Central Java | Jawa Tengah | Kudus | -6.7958 | 110.9612 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | #N/A | JAW-JT-KDS-0942 | Jekulo | Protelindo |  | #N/A | #N/A | #N/A | #N/A | #N/A | New Purchase | New Ring 012 | Keep |  | TypeC 6120H-S Bundle |  |  |  | #N/A | [9 empty] | 2026 |  | 2026-02-06 | 6 |  |  | 2026 |  |  | #N/A |  |  | Submitted | Approved | [33 empty] | #N/A |  |  | #N/A | #N/A
New_JAW-JT-PWD-8420_1
New_JAW-JT-PWD-8374_1
New_JAW-JT-SMG-8725_1
Formulas:
Survey Week = WEEKNUM([Survey Plan],1)
MOS Plan = [Install Plan]
Install Plan = [Integration Plan]-3
Weekly Install = WEEKNUM([Install Plan],2)
Integration Plan = [Migration Plan]
Weekly Mig = WEEKNUM([Migration Plan],2)
New Weekly Mig = WEEKNUM([New Mig Plan],2)
New Week Plan 2 = WEEKNUM([New Plan 2],2)
RFS Week Plan = WEEKNUM([RFS Plan],2)
New Plan 2 = [Y]
Note on Q759: 10333988: 与0613配对
Note on Q761: 10333988: 与2526配对

## Pivot
Province | City | SOW
Jawa Tengah | Kota Semarang | 75
Jawa Tengah | Kendal | 62
Jawa Tengah | Pati | 35
Jawa Tengah | Cilacap | 26
Jawa Tengah | Kota Surakarta | 19
Jawa Tengah | Banyumas | 19
Jawa Tengah | Jepara | 47
Jawa Tengah | Grobogan | 158
Jawa Tengah | Pemalang | 8
Jawa Tengah | Kota Salatiga | 14
Jawa Tengah | Sragen | 29
Jawa Tengah | Temanggung | 2
Jawa Tengah | Wonosobo | 2
Jawa Tengah | Purbalingga | 5
Jawa Tengah | Banjarnegara | 11
Jawa Tengah | Pekalongan | 2
Jawa Tengah | Blora | 73
Jawa Tengah | Purworejo | 2
Jawa Tengah | Kebumen | 7
Jawa Tengah | Batang | 4
Jawa Tengah | Kota Magelang | 3
Jawa Tengah | Kota Tegal | 3
Jawa Tengah | Sukoharjo | 31
Jawa Tengah | Wonogiri | 1
Jawa Tengah | Demak | 170
Jawa Tengah | Kudus | 73
Jawa Tengah | Boyolali | 33
Jawa Tengah | Magelang | 8
Jawa Tengah | Brebes | 22
Jawa Tengah | Rembang | 5
Jawa Tengah | Semarang | 36
Jawa Tengah | Karanganyar | 20
Jawa Tengah | Kota Pekalongan | 1
Jawa Tengah | Klaten | 17
Jawa Tengah | Tegal | 6

## Map Info
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Daily Plan
Uniq ID | NewXLS ID | Scope | SOW | Scope Update | Site Type | Survey Plan | Subcon | Status Team | Survey Actual Date | Remark | Uniq ID | NewXLS ID | Scope | SOW | Scope Update | Site Type | Survey Plan | Subcon | Status Team | Survey Actual Date | Remark | Uniq ID | NewXLS ID | Scope | SOW | Scope Update | Site Type | Survey Plan | Subcon | Status Team | Survey Actual Date | Remark | Uniq ID | NewXLS ID | Scope | SOW | Scope Update | Site Type | Survey Plan | Subcon | Status Team | Survey Actual Date | Remark | Uniq ID | NewXLS ID | Scope | SOW | Scope Update | Site Type | Survey Plan | Subcon | Status Team | Survey Actual Date | Remark
Swap_JAW-JT-DMK-0546_1 | JAW-JT-DMK-0546 | Swap | Swap Only | Swap | MA | 2025-10-14 | Swap impact Stitch | Onsite | 2025-10-14 | Access Issue | Swap_JAW-JT-DMK-0538_1 | JAW-JT-DMK-0538 | Swap | Swap Only | Swap | MA | 2025-10-16 | GPA | Done Survey | 2025-10-16 |  | Swap_JAW-JT-SKH-1989_1 | JAW-JT-SKH-1993 | Swap | Swap Only | Swap | MA | 2025-10-17 | YPTT | Onsite | 2025-10-17 | 90% - OG Submit | Swap_JAW-JT-DMK-0613_1 | JAW-JT-DMK-0613 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Permit not release / Carryover |  | 0 | Swap_JAW-JT-DMK-0547_1 | JAW-JT-DMK-0547 | Swap | Swap Only | Swap | MA | 2025-10-20 | GPA
Swap_JAW-JT-DMK-0554_1 | JAW-JT-DMK-0554 | Swap | Swap Only | Swap | MA | 2025-10-14 | Swap impact Stitch | Onsite | 2025-10-14 |  | Swap_JAW-JT-DMK-0561_1 | JAW-JT-DMK-0561 | Swap | Swap Only | Swap | MA | 2025-10-16 | GPA | Done Survey | 2025-10-16 |  | Swap_JAW-JT-SKH-1993_1 | JAW-JT-SKH-1989 | Swap | Swap Only | Swap | MA | 2025-10-17 | YPTT | Onsite |  | OG 80% - Rain | Swap_JAW-JT-DMK-0569_1 | JAW-JT-DMK-0569 | Swap | Swap Only | Swap | PAG | 2025-10-18 | GPA | Permit not release / Carryover |  | 0 | Swap_JAW-JT-DMK-0549_1 | JAW-JT-DMK-0549 | Swap | Swap Only | Swap | MA | 2025-10-20 | GPA
Swap_JAW-JT-DMK-0589_1 | JAW-JT-DMK-0589 | Swap | Swap Only | Swap | MA | 2025-10-14 | Swap impact Stitch | Onsite | 2025-10-14 |  | Swap_JAW-JT-DMK-3210_1 | JAW-JT-DMK-3210 | Swap | Swap Only | Swap | MA | 2025-10-16 | GPA | Done Survey | 2025-10-16 |  | Swap_JAW-JT-SKH-1982_1 | JAW-JT-SKH-1958 | Swap | Swap Only | Swap | MA | 2025-10-17 | YPTT | Onsite |  | OG 50% - Rain | Swap_JAW-JT-DMK-0552_1 | JAW-JT-DMK-0552 | Swap&Upgrade | Swap+Upgrade site | Swap | PAG | 2025-10-18 | GPA | Permit not release / Carryover |  | 0 | Swap_JAW-JT-DMK-0552_1 | JAW-JT-DMK-0552 | Swap&Upgrade | Swap+Upgrade site | Swap | PAG | 2025-10-20 | GPA
Swap_JAW-JT-DMK-0579_1 | JAW-JT-DMK-0579 | Swap | Swap Only | Swap | MA | 2025-10-14 | Swap impact Stitch | Onsite | 2025-10-14 |  | Swap_JAW-JT-DMK-0537_1 | JAW-JT-DMK-0537 | Swap | Swap Only | Swap | MA | 2025-10-16 | GPA | Done Survey | 2025-10-16 |  | Swap_JAW-JT-SKH-1958_1 | JAW-JT-SKH-1982 | Swap | Swap Only | Swap | MA | 2025-10-17 | YPTT | Onsite | 2025-10-17 | 90% - OG Submit | Swap_JAW-JT-DMK-0613_1 | JAW-JT-DMK-0613 | Swap | Swap Only | Swap | PAG | 2025-10-18 | GPA | Permit not release / Carryover |  | 0 | Swap_JAW-JT-DMK-0558_1 | JAW-JT-DMK-0558 | Swap | Swap Only | Swap | MA | 2025-10-20 | GPA
Swap_JAW-JT-UNR-2682_1 | JAW-JT-UNR-2682 | Swap | Swap Only | Swap | MA | 2025-10-27 | Swap impact Stitch |  |  |  | Swap_JAW-JT-DMK-0568_1 | JAW-JT-DMK-0568 | Swap | Swap Only | Swap | MA | 2025-10-16 | GPA | Done Survey | 2025-10-16 |  | Swap_JAW-JT-SKH-1964_1 | JAW-JT-SKH-1964 | Swap | Swap Only | Swap | MA | 2025-10-17 | YPTT | Onsite | 2025-10-17 | 90% - OG Submit | Swap_JAW-JT-DMK-0540_1 | JAW-JT-DMK-0540 | Swap | Swap Only | Swap | PAG | 2025-10-18 | GPA | Permit not release / Carryover |  | 0 | Swap_JAW-JT-DMK-0559_1 | JAW-JT-DMK-0559 | Swap | Swap Only | Swap | MA | 2025-10-20 | GPA
Swap_JAW-JT-UNR-3316_1 | JAW-JT-UNR-3316 | Swap | Swap Only | Swap | MA | 2025-10-27 | Swap impact Stitch |  |  |  | Swap_JAW-JT-DMK-0569_1 | JAW-JT-DMK-0569 | Swap | Swap Only | Swap | MA | 2025-10-16 | GPA | Rack Belting / Carryover |  |  | Swap_JAW-JT-SKT-2071_1 | JAW-JT-SKH-3651 | Swap | Swap Only | Swap | MA | 2025-10-17 | YPTT | Onsite | 2025-10-17 | 90% - OG Submit | Swap_JAW-JT-DMK-0562_1 | JAW-JT-DMK-0562 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Permit not release / Carryover |  | 0 | Swap_JAW-JT-DMK-0562_1 | JAW-JT-DMK-0562 | Swap | Swap Only | Swap | MA | 2025-10-20 | GPA
Swap_JAW-JT-UNR-3338_1 | JAW-JT-UNR-3338 | Swap | Swap Only | Swap | MA | 2025-10-28 | Swap impact Stitch |  |  |  | Swap_JAW-JT-DMK-0573_1 | JAW-JT-DMK-0573 | Swap | Swap Only | Swap | MA | 2025-10-16 | GPA | Done Survey | 2025-10-16 |  | Swap_JAW-JT-SKT-2081_1 | JAW-JT-SKT-2125 | Swap | Swap Only | Swap | PAG | 2025-10-17 | YPTT | Onsite | 2025-10-17 | 90% - OG Submit | Swap_JAW-JT-DMK-0565_1 | JAW-JT-DMK-0565 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Permit not release / Carryover |  | 0 | Swap_JAW-JT-DMK-0567_1 | JAW-JT-DMK-0567 | Swap | Swap Only | Swap | MA | 2025-10-20 | GPA
Swap_JAW-JT-KRG-2060_1 | JAW-JT-KRG-2060 | Swap | Swap Only | Swap | MA | 2025-10-24 | Swap impact Stitch | Onsite | 2025-10-14 |  | Swap_JAW-JT-DMK-0583_1 | JAW-JT-DMK-0583 | Swap | Swap Only | Swap | MA | 2025-10-16 | GPA | Done Survey | 2025-10-16 |  | Swap_JAW-JT-SKT-2074_1 | JAW-JT-SKT-2081 | Swap | Swap Only | Swap | MA | 2025-10-17 | YPTT | Onsite | 2025-10-17 | 90% - OG Submit | Swap_JAW-JT-DMK-0575_1 | JAW-JT-DMK-0575 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Permit not release / Carryover |  | 0 | Swap_JAW-JT-DMK-0575_1 | JAW-JT-DMK-0575 | Swap | Swap Only | Swap | MA | 2025-10-20 | GPA
Swap_JAW-JT-KRG-2140_1 | JAW-JT-KRG-2140 | Swap | Swap Only | Swap | MA | 2025-10-24 | Swap impact Stitch | Onsite | 2025-10-14 |  | Swap_JAW-JT-DMK-2971_1 | JAW-JT-DMK-2971 | Swap | Swap Only | Swap | MA | 2025-10-16 | GPA | Done Survey | 2025-10-16 |  | Swap_JAW-JT-SKH-3651_1 | JAW-JT-SKT-2074 | Swap | Swap Only | Swap | MA | 2025-10-17 | YPTT | Onsite | 2025-10-17 | 90% - OG Submit | Swap_JAW-JT-DMK-0584_1 | JAW-JT-DMK-0584 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Permit not release / Carryover |  | 0 | Swap_JAW-JT-PWD-1556_1 | JAW-JT-PWD-1556 | Swap | Swap Only | Swap | MA | 2025-10-20 | GPA | Onsite | 2025-10-20
Swap_JAW-JT-KRG-2052_1 | JAW-JT-KRG-2052 | Swap | Swap Only | Swap | MA | 2025-10-24 | Swap impact Stitch | Onsite | 2025-10-14 |  | Swap_JAW-JT-DMK-0612_1 | JAW-JT-DMK-0612 | Swap | Swap Only | Swap | PAG | 2025-10-16 | GPA | Done Survey | 2025-10-16 |  | Swap_JAW-JT-SKT-2125_1 | JAW-JT-SKT-2071 | Swap | Swap Only | Swap | MA | 2025-10-17 | YPTT | 2nd Site |  | Failed - Plan Tmr | Swap_JAW-JT-DMK-0593_1 | JAW-JT-DMK-0593 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Permit not release / Carryover |  | 0 | Swap_JAW-JT-PWD-1562_1 | JAW-JT-PWD-1562 | Swap | Swap Only | Swap | MA | 2025-10-20 | GPA
Swap_JAW-JT-SLW-2239_1 | JAW-JT-SLW-2239 | Swap | Swap Only | Swap | MA | 2025-10-18 | HRAN Upgrade | Onsite | 2025-10-14 |  | Swap_JAW-JT-DMK-0552_1 | JAW-JT-SMG-2406 | Swap&Upgrade | Swap+Upgrade site | Swap | PAG | 2025-10-16 | GPA | Carryover |  |  | Swap_JAW-JT-DMK-0569_1 | JAW-JT-DMK-0569 | Swap | Swap Only | Swap | MA | 2025-10-17 | GPA | 2nd Site |  | Access issue/ Key site N/y HO After MOCN / Carryover | Swap_JAW-JT-PTI-1502_1 | JAW-JT-DMK-1543 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Done Survey | 2025-10-18 | 0 | Swap_JAW-JT-PTI-1468_1 | JAW-JT-PTI-1468 | Swap | Swap Only | Swap | MA | 2025-10-20 | GPA
Swap_JAW-JT-SLW-2207_1 | JAW-JT-SLW-2207 | Swap | Swap Only | Swap | MA | 2025-10-18 | HRAN Upgrade | Onsite | 2025-10-14 |  | Swap_JAW-JT-PTI-1512_1 | JAW-JT-DMK-0552 | Swap&Upgrade | Swap+Upgrade site | Swap | PAG | 2025-10-16 | GPA | Carryover |  |  | Swap_JAW-JT-DMK-0552_1 | JAW-JT-DMK-0552 | Swap&Upgrade | Swap+Upgrade site | Swap | PAG | 2025-10-17 | GPA | 2nd Site |  | Access issue/ Key site N/y HO After MOCN / Carryover | Swap_JAW-JT-PTI-4012_1 | JAW-JT-DMK-0564 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Done Survey | 2025-10-18 | 0 | Swap_JAW-JT-PTI-1480_1 | JAW-JT-PTI-1480 | Swap | Swap Only | Swap | PAG | 2025-10-20 | GPA
Swap_JAW-JT-SLT-2171_1 | JAW-JT-SLT-2171 | Swap&Upgrade | Swap+Upgrade site | Swap | PAG | 2025-10-14 | GIT | Onsite | 2025-10-14 |  | Swap_JAW-JT-PTI-1478_1 | JAW-JT-PTI-1512 | Swap | Swap Only | Swap | MA | 2025-10-16 | GPA | Carryover |  |  | Swap_JAW-JT-PWD-0001_1 | JAW-JT-PWD-0001 | Swap | Swap Only | Swap | MA | 2025-10-17 | GPA | Onsite | 2025-10-17 | Done Survey | Swap_JAW-JT-PTI-1499_1 | JAW-JT-DMK-0567 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Done Survey | 2025-10-18 | 0 | Swap_JAW-JT-PTI-3349_1 | JAW-JT-PTI-3349 | Swap | Swap Only | Swap | MA | 2025-10-20 | GPA
Swap_JAW-JT-SLT-2171_2 | JAW-JT-SLT-2171 | Swap | Swap Only | Swap | PAG | 2025-10-14 | GIT | Onsite | 2025-10-14 |  | Swap_JAW-JT-PTI-1490_1 | JAW-JT-PTI-1478 | Swap | Swap Only | Swap | MA | 2025-10-16 | GPA | Carryover |  |  | Swap_JAW-JT-PWD-0007_1 | JAW-JT-PWD-0007 | Swap | Swap Only | Swap | MA | 2025-10-17 | GPA | Onsite | 2025-10-17 | Done Survey | Swap_JAW-JT-PTI-1484_1 | JAW-JT-DMK-0577 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Done Survey | 2025-10-18 | 0 | Swap_JAW-JT-PTI-1403_1 | JAW-JT-PTI-1403 | Swap | Swap Only | Swap | MA | 2025-10-20 | GPA
Swap_JAW-JT-SLT-2171_3 | JAW-JT-SLT-2171 | Swap | Swap Only | Swap | MA | 2025-10-14 | GIT | Onsite | 2025-10-14 |  | Swap_JAW-JT-PTI-3318_1 | JAW-JT-PTI-1490 | Swap | Swap Only | Swap | MA | 2025-10-16 | GPA | Carryover |  |  | Swap_JAW-JT-PWD-1589_1 | JAW-JT-PWD-1589 | Swap | Swap Only | Swap | MA | 2025-10-17 | GPA | Onsite | 2025-10-17 | Done Survey | Swap_JAW-JT-PTI-1512_1 | JAW-JT-DMK-0580 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Done Survey | 2025-10-18 | 0 | Swap_JAW-JT-PTI-1407_1 | JAW-JT-PTI-1407 | Swap | Swap Only | Swap | MA | 2025-10-20 | GPA
Swap_JAW-JT-DMK-0582_1 | JAW-JT-DMK-0582 | Swap | Swap Only | Swap | MA | 2025-10-14 | GPA | Onsite | 2025-10-14 |  | Swap_JAW-JT-SMG-2406_1 | JAW-JT-SLW-2207 | Swap&Upgrade | Swap+Upgrade site | Swap | PAG | 2025-10-16 | GIT | Onsite | 2025-10-16 |  | Swap_JAW-JT-PWD-1591_1 | JAW-JT-PWD-1591 | Swap | Swap Only | Swap | MA | 2025-10-17 | GPA | Onsite | 2025-10-17 | Done Survey | Swap_JAW-JT-PTI-1504_1 | JAW-JT-DMK-0595 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Done Survey | 2025-10-18 | 0 | Swap_JAW-JT-PTI-1419_1 | JAW-JT-PTI-1419 | Swap | Swap Only | Swap | MA | 2025-10-20 | GPA
Swap_JAW-JT-JPA-0635_1 | JAW-JT-JPA-0635 | Swap | Swap Only | Swap | MA | 2025-10-22 | GIT | Onsite | 2025-10-14 |  | Swap_JAW-JT-SKT-2071_1 | JAW-JT-SKH-1926 | Swap | Swap Only | Swap | MA | 2025-10-16 | YPTT | 2nd Site |  |  | Swap_JAW-JT-PWD-1592_1 | JAW-JT-PWD-1592 | Swap | Swap Only | Swap | MA | 2025-10-17 | GPA | Onsite | 2025-10-17 | Done Survey | Swap_JAW-JT-PTI-1478_1 | JAW-JT-DMK-2970 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Done Survey | 2025-10-18 | 0 | Swap_JAW-JT-DMK-0540_1 | JAW-JT-DMK-0540 | Swap | Swap Only | Swap | MA | 2025-10-20 | GPA
Swap_JAW-JT-JPA-0638_1 | JAW-JT-JPA-0638 | Swap | Swap Only | Swap | MA | 2025-10-24 | GIT | Onsite | 2025-10-14 |  | Swap_JAW-JT-SKT-2075_1 | JAW-JT-SKH-3177 | Swap | Swap Only | Swap | MA | 2025-10-16 | YPTT | Onsite | 2025-10-16 |  | Swap_JAW-JT-PWD-1599_1 | JAW-JT-PWD-1599 | Swap | Swap Only | Swap | MA | 2025-10-17 | GPA | 2nd Site | 2025-10-17 | Done Survey | Swap_JAW-JT-PTI-1490_1 | JAW-JT-DMK-2972 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Done Survey | 2025-10-18 | 0 | Swap_JAW-JT-DMK-0564_1 | JAW-JT-DMK-0564 | Swap | Swap Only | Swap | MA | 2025-10-20 | GPA
[11 empty] | Swap_JAW-JT-SKH-1926_1 | JAW-JT-SKT-2071 | Swap | Swap Only | Swap | MA | 2025-10-16 | YPTT | 2nd Site |  |  | Swap_JAW-JT-PWD-1608_1 | JAW-JT-PWD-1608 | Swap | Swap Only | Swap | MA | 2025-10-17 | GPA | 2nd Site | 2025-10-17 | Done Survey | Swap_JAW-JT-PTI-3318_1 | JAW-JT-DMK-0547 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Done Survey | 2025-10-18 | 0 | Swap_JAW-JT-DMK-0565_1 | JAW-JT-DMK-0565 | Swap | Swap Only | Swap | MA | 2025-10-20 | GPA
[11 empty] | Swap_JAW-JT-SKH-3177_1 | JAW-JT-SKT-2075 | Swap | Swap Only | Swap | MA | 2025-10-16 | YPTT | 2nd Site |  |  | Swap_JAW-JT-PWD-3387_1 | JAW-JT-PWD-3387 | Swap | Swap Only | Swap | MA | 2025-10-17 | GPA | 2nd Site | 2025-10-17 | Done Survey | Swap_JAW-JT-DMK-0549_1 | JAW-JT-DMK-0549 | Swap | Swap Only | Swap | PAG | 2025-10-18 | GPA | Permit not release / Carryover |  | 0 | Swap_JAW-JT-PWD-1574_1 | JAW-JT-PWD-1574 | Swap | Swap Only | Swap | PAG | 2025-10-20 | GPA | Onsite | 2025-10-20
[11 empty] | Swap_JAW-JT-SKH-1938_1 | JAW-JT-SKH-1938 | Swap | Swap Only | Swap | MA | 2025-10-16 | YPTT | Onsite | 2025-10-16 |  | Swap_JAW-JT-PTI-1502_1 | JAW-JT-PTI-1502 | Swap | Swap Only | Swap | MA | 2025-10-17 | GPA | 2nd Site | 2025-10-17 | Done Survey | Swap_JAW-JT-DMK-0558_1 | JAW-JT-DMK-0558 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Permit not release / Carryover |  | 0 | Swap_JAW-JT-PWD-1579_1 | JAW-JT-PWD-1579 | Swap | Swap Only | Swap | PAG | 2025-10-20 | GPA
[11 empty] | Swap_JAW-JT-SKH-1909_1 | JAW-JT-SKH-1909 | Swap | Swap Only | Swap | MA | 2025-10-16 | YPTT | Onsite | 2025-10-16 |  | Swap_JAW-JT-PTI-4012_1 | JAW-JT-PTI-4012 | Swap | Swap Only | Swap | MA | 2025-10-17 | GPA | Onsite | 2025-10-17 | Done Survey | Swap_JAW-JT-DMK-0559_1 | JAW-JT-DMK-0559 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Permit not release / Carryover |  | 0 | Swap_JAW-JT-BBS-0069_1 | JAW-JT-BBS-0069 | Swap&Upgrade | Swap+Upgrade Link | Swap | MA | 2025-10-20 | GPA | Onsite | 2025-10-20
Uniq ID | NewXLS ID | Scope | SOW | Scope Update | Site Type | Survey Plan | Subcon | Status Team | Survey Actual Date | Remark | Swap_JAW-JT-SKH-3651_1 | JAW-JT-SKH-3651 | Swap | Swap Only | Swap | MA | 2025-10-16 | YPTT | 2nd Site |  |  | Swap_JAW-JT-PTI-1499_1 | JAW-JT-PTI-1499 | Swap | Swap Only | Swap | MA | 2025-10-17 | GPA | Onsite | 2025-10-17 | Done Survey | Swap_JAW-JT-DMK-0585_1 | JAW-JT-DMK-0585 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Permit not release / Carryover |  | 0 | Swap_JAW-JT-BBS-0082_1 | JAW-JT-BBS-0082 | Swap&Upgrade | Swap+Upgrade Link | Swap | MA | 2025-10-20 | GPA
Swap_JAW-JT-JPA-0651_1 | JAW-JT-JPA-0651 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch |  |  | No One Team Onsite | Swap_JAW-JT-SKH-1937_1 | JAW-JT-SKH-1937 | Swap | Swap Only | Swap | MA | 2025-10-16 | YPTT | Onsite | 2025-10-16 |  | Swap_JAW-JT-PTI-1484_1 | JAW-JT-PTI-1484 | Swap | Swap Only | Swap | MA | 2025-10-17 | GPA | Onsite | 2025-10-17 | Done Survey | Swap_JAW-JT-DMK-0596_1 | JAW-JT-DMK-0596 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Permit not release / Carryover |  | 0 | Swap_JAW-JT-BBS-0115_1 | JAW-JT-BBS-0115 | Swap&Upgrade | Swap+Upgrade Link | Swap | MA | 2025-10-20 | GPA
Swap_JAW-JT-JPA-0647_1 | JAW-JT-JPA-0647 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch |  |  | No One Team Onsite | Swap_JAW-JT-SKH-1931_1 | JAW-JT-SKH-1931 | Swap | Swap Only | Swap | MA | 2025-10-16 | YPTT | Onsite | 2025-10-16 |  | Swap_JAW-JT-PTI-1512_1 | JAW-JT-PTI-1512 | Swap | Swap Only | Swap | MA | 2025-10-17 | GPA | Onsite | 2025-10-17 | Done Survey | Swap_JAW-JT-PWD-1590_1 | JAW-JT-PWD-1590 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Done Survey | 2025-10-18 | 0 | Swap_JAW-JT-BBS-3332_1 | JAW-JT-BBS-3332 | Swap&Upgrade | Swap+Upgrade Link | Swap | MA | 2025-10-20 | GPA | Onsite | 2025-10-20
Swap_JAW-JT-UNR-3316_1 | JAW-JT-UNR-3316 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch |  |  | No One Team Onsite | Swap_JAW-JT-SKH-1964_1 | JAW-JT-SKH-1964 | Swap | Swap Only | Swap | MA | 2025-10-16 | YPTT | 2nd Site |  |  | Swap_JAW-JT-PTI-1504_1 | JAW-JT-PTI-1504 | Swap | Swap Only | Swap | MA | 2025-10-17 | GPA | Onsite | 2025-10-17 | Done Survey | Swap_JAW-JT-PWD-1600_1 | JAW-JT-PWD-1600 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Done Survey | 2025-10-18 | 0 | Swap_JAW-JT-KLN-3292_1 | JAW-JT-KLN-3292 | Swap | Swap Only | Swap | MA | 2025-10-20 | YPTT
Swap_JAW-JT-UNR-3338_1 | JAW-JT-UNR-3338 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch |  |  | No One Team Onsite | Swap_JAW-JT-DMK-0578_1 | JAW-JT-DMK-0578 | Swap | Swap Only | Swap | MA | 2025-10-16 | GPA | Onsite | 2025-10-16 |  | Swap_JAW-JT-PTI-1478_1 | JAW-JT-PTI-1478 | Swap | Swap Only | Swap | MA | 2025-10-17 | GPA | Onsite | 2025-10-17 | Done Survey | Swap_JAW-JT-PWD-1604_1 | JAW-JT-PWD-1604 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Done Survey | 2025-10-18 | 0 | Swap_JAW-JT-SKH-1926_1 | JAW-JT-SKH-1926 | Swap | Swap Only | Swap | MA | 2025-10-20 | YPTT | Onsite | 2025-10-20
Swap_JAW-JT-UNR-2690_1 | JAW-JT-UNR-2690 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch |  |  | No One Team Onsite | Swap_JAW-JT-TGL-2576_1 | JAW-JT-TGL-2576 | Swap&Upgrade | Swap+Upgrade Link | Swap | PAG | 2025-10-16 | GPA | Onsite | 2025-10-16 |  | Swap_JAW-JT-PTI-1490_1 | JAW-JT-PTI-1490 | Swap | Swap Only | Swap | MA | 2025-10-17 | GPA | Onsite | 2025-10-17 | Done Survey | Swap_JAW-JT-PWD-1574_1 | JAW-JT-PWD-1574 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Tome is over / Carryover |  | 0 | Swap_JAW-JT-SKH-3177_1 | JAW-JT-SKH-3177 | Swap | Swap Only | Swap | MA | 2025-10-20 | YPTT | Onsite | 2025-10-20
Swap_JAW-JT-BBS-3332_1 | JAW-JT-BBS-3332 | Swap&Upgrade | Swap+Upgrade Link | Swap | MA | Keep | Ring Capacity |  |  |  | Swap_JAW-JT-TGL-2600_1 | JAW-JT-TGL-2600 | Swap&Upgrade | Swap+Upgrade Link | Swap | PAG | 2025-10-16 | GPA | Onsite | 2025-10-16 |  | Swap_JAW-JT-PTI-3318_1 | JAW-JT-PTI-3318 | Swap | Swap Only | Swap | MA | 2025-10-17 | GPA | 2nd Site | 2025-10-17 | Done Survey | Swap_JAW-JT-PWD-1579_1 | JAW-JT-PWD-1579 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Tome is over / Carryover |  | 0 | Swap_JAW-JT-KLN-0999_1 | JAW-JT-KLN-0999 | Swap | Swap Only | Swap | MA | 2025-10-20 | YPTT
Swap_JAW-JT-DMK-0612_1 | JAW-JT-DMK-0612 | Swap | Swap Only | Swap | PAG | Keep | Swap impact Stitch (PAG Part） | [14 empty] | Swap_JAW-JT-PWT-1716_1 | JAW-JT-PWT-1716 | Swap&Upgrade | Swap+Upgrade Link | Swap | PAG | 2025-10-17 | GPA | Onsite | 2025-10-17 | OnGoing Survey / Carryover | Swap_JAW-JT-PWD-0608_1 | JAW-JT-PWD-0608 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Done Survey | 2025-10-18 | 0 | Swap_JAW-JT-KLN-1057_1 | JAW-JT-KLN-1057 | Swap | Swap Only | Swap | MA | 2025-10-20 | YPTT
Swap_JAW-JT-DMK-0568_1 | JAW-JT-DMK-0568 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch | [14 empty] | Swap_JAW-JT-PWT-1716_2 | JAW-JT-TGL-2576 | Swap&Upgrade | Swap+Upgrade Link | Swap | PAG | 2025-10-17 | GPA | Onsite | 2025-10-17 | OnGoing Survey / Carryover | Swap_JAW-JT-PWD-1548_1 | JAW-JT-PWD-1548 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Done Survey | 2025-10-18 | 0 | Swap_JAW-JT-KLN-1041_1 | JAW-JT-KLN-1041 | Swap | Swap Only | Swap | MA | 2025-10-20 | YPTT
Swap_JAW-JT-DMK-0573_1 | JAW-JT-DMK-0573 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch | [14 empty] | Swap_JAW-JT-PWT-1773_1 | JAW-JT-PWT-1773 | Swap&Upgrade | Swap+Upgrade Link | Swap | PAG | 2025-10-17 | GPA | 2nd Site |  | Time is running out / Carryover | Swap_JAW-JT-PWD-1556_1 | JAW-JT-PWD-1556 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Tome is over / Carryover |  | 0 | Swap_JAW-JT-KLN-0997_1 | JAW-JT-KLN-0997 | Swap | Swap Only | Swap | MA | 2025-10-20 | YPTT
Swap_JAW-JT-DMK-2971_1 | JAW-JT-DMK-2971 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch | [14 empty] | Swap_JAW-JT-TGL-2576_2 | JAW-JT-PWT-1716 | Swap&Upgrade | Swap+Upgrade Link | Swap | PAG | 2025-10-17 | GPA | Onsite | 2025-10-17 | #N/A | Swap_JAW-JT-PWD-1562_1 | JAW-JT-PWD-1562 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Tome is over / Carryover |  | 0 | Swap_JAW-YO-YYK-0492_1 | JAW-YO-YYK-0492 | Swap | Swap Only | Swap | PAG | 2025-10-20 | YPTT
Swap_JAW-JT-DMK-0561_1 | JAW-JT-DMK-0561 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch | [14 empty] | Swap_JAW-JT-SLT-2171_1 | JAW-JT-SLT-2171 | Swap&Upgrade | Swap+Upgrade site | Swap | PAG | 2025-10-17 | GIT | OTW | 2025-10-17 | 00.Done Survey | Swap_JAW-JT-PWD-1563_1 | JAW-JT-PWD-1563 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Done Survey | 2025-10-18 | 0 | Swap_JAW-YO-SMN-0336_1 | JAW-YO-SMN-0336 | Swap | Swap Only | Swap | MA | 2025-10-20 | YPTT | Onsite | 2025-10-20
Swap_JAW-JT-DMK-3210_1 | JAW-JT-DMK-3210 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch | [14 empty] | Swap_JAW-JT-UNR-2690_1 | JAW-JT-UNR-2690 | Swap | Swap Only | Swap | MA | 2025-10-17 | GIT | OTW | 2025-10-17 | 00.Done Survey | Swap_JAW-JT-PWD-1586_1 | JAW-JT-PWD-1586 | Swap | Swap Only | Swap | MA | 2025-10-18 | GPA | Done Survey | 2025-10-18 | 0 | Swap_JAW-JT-UNR-2666_1 | JAW-JT-UNR-2666 | Swap | Swap Only | Swap | MA | 2025-10-20 | GIT | Onsite | 2025-10-20
Swap_JAW-JT-PTI-1490_1 | JAW-JT-PTI-1490 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch | [14 empty] | Swap_JAW-JT-UNR-3316_1 | JAW-JT-UNR-3316 | Swap | Swap Only | Swap | MA | 2025-10-17 | GIT | OTW | 2025-10-17 | 00.Done Survey | Swap_JAW-JT-PWT-1773_1 | JAW-JT-PWT-1773 | Swap&Upgrade | Swap+Upgrade Link | Swap | PAG | 2025-10-18 | GPA | Done Survey | 2025-10-18 | 0 | Swap_JAW-JT-UNR-2682_1 | JAW-JT-UNR-2682 | Swap | Swap Only | Swap | MA | 2025-10-20 | GIT | Onsite | 2025-10-20
Swap_JAW-JT-BBS-0069_1 | JAW-JT-BBS-0069 | Swap&Upgrade | Swap+Upgrade Link | Swap | MA | Keep | Ring Capacity | [25 empty] | Swap_JAW-JT-KRG-2141_1 | JAW-JT-KRG-2141 | Swap | Swap Only | Swap | MA | 2025-10-18 | YPTT | Onsite | 2025-10-18 | 0
Swap_JAW-JT-DMK-0537_1 | JAW-JT-DMK-0537 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch | [25 empty] | Swap_JAW-JT-SKT-2125_1 | JAW-JT-SKT-2125 | Swap | Swap Only | Swap | MA | 2025-10-18 | YPTT | #N/A |  | 0
Swap_JAW-JT-PTI-1512_1 | JAW-JT-PTI-1512 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch | [25 empty] | Swap_JAW-JT-SKH-1941_1 | JAW-JT-SKH-1941 | Swap | Swap Only | Swap | MA | 2025-10-18 | YPTT | Onsite | 2025-10-18 | 0
Swap_JAW-JT-DMK-0569_1 | JAW-JT-DMK-0569 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch | [25 empty] | Swap_JAW-JT-SKH-1993_1 | JAW-JT-SKH-1993 | Swap | Swap Only | Swap | MA | 2025-10-18 | YPTT | Onsite | 2025-10-18 | 0 |  | JAW-JT-BBS-0082
Swap_JAW-JT-DMK-0583_1 | JAW-JT-DMK-0583 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch | [25 empty] | Swap_JAW-JT-KLN-1068_1 | JAW-JT-KLN-1068 | Swap | Swap Only | Swap | MA | 2025-10-18 | YPTT | Onsite | 2025-10-18 | 0 |  | JAW-JT-BBS-0115
Swap_JAW-JT-DMK-0552_1 | JAW-JT-DMK-0552 | Swap&Upgrade | Swap+Upgrade site | Swap | PAG | Keep | HRAN Upgrade | [25 empty] | Swap_JAW-JT-SKH-1982_1 | JAW-JT-SKH-1982 | Swap | Swap Only | Swap | MA | 2025-10-18 | YPTT | Onsite | 2025-10-18 | 0 |  | JAW-JT-PWD-1562
Swap_JAW-JT-PTI-3318_1 | JAW-JT-PTI-3318 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch | [25 empty] | Swap_JAW-JT-KLN-1041_1 | JAW-JT-KLN-1041 | Swap | Swap Only | Swap | MA | 2025-10-18 | YPTT | #N/A |  | 0 |  | JAW-JT-PWD-1579
Swap_JAW-JT-DMK-0538_1 | JAW-JT-DMK-0538 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch | [37 empty] | JAW-JT-KLN-3292
Swap_JAW-JT-PTI-1478_1 | JAW-JT-PTI-1478 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch | [37 empty] | JAW-JT-KLN-0999
Swap_JAW-JT-PWT-1773_1 | JAW-JT-PWT-1773 | Swap&Upgrade | Swap+Upgrade Link | Swap | PAG | Keep | Linknet NNI,PAG1 | [37 empty] | JAW-JT-KLN-1057
Swap_JAW-JT-KRG-2060_1 | JAW-JT-KRG-2060 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch | Onsite | 2025-10-15 | [35 empty] | JAW-JT-KLN-1041
Swap_JAW-JT-KRG-2140_1 | JAW-JT-KRG-2140 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch | Onsite | 2025-10-15 | [35 empty] | JAW-JT-KLN-0997
Swap_JAW-JT-KRG-2052_1 | JAW-JT-KRG-2052 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch | Onsite | 2025-10-15 | [35 empty] | JAW-YO-YYK-0492
Swap_JAW-JT-SKT-2150_1 | JAW-JT-SKT-2150 | Swap | Swap Only | Swap | PAG | Keep | Swap impact Stitch (PAG Part） | Onsite | 2025-10-15
Swap_JAW-JT-KRG-2139_1 | JAW-JT-KRG-2139 | Swap | Swap Only | Swap | MA | Keep | Swap impact Stitch | Onsite | 2025-10-15
Formulas:
Remark = VLOOKUP([Uniq ID],IPRAN!D:AY,30,0)

## Plan Vs Actual
2025-10-16 | [8 empty] | Count of NewXLS ID | Column Labels
Subcon | Qty Team | Plan | Actual | Carry over | Subcon | Survey | TI | Area | Priority 5G | Modernize | New | Swap | Grand Total
GIT | 2 | 1 | 1 | 0 | GIT | 2 | 2 | Demak | 2025-End Nov | 2 | 142 | 39 | 183
GPA | 8 | 18 | 12 | 6 | YPTT | 4 | 3 | Semarang | Mid Dec 25 |  | 12 | 12 | 24
YPTT | 5 | 10 | 5 | 5 | GPA | 5 | 7 | Grobogan | 2026 | 3 | 388 | 107 | 498
Grand Total | 15 | 29 | 18 | 11 | CCSI | 2 |  | Belum Kelar | 2025-624 sites |  | 99 | 3 | 102
[5 empty] | Mingze | 4 |  | Jepara, Pati | Grand Total | 5 | 641 | 161 | 807
[5 empty] | Total | 17
2025-10-17
Subcon | Qty Team | Plan | Actual | Carry over
GIT | 2 | 3 | 3 | 0
GPA | 8 | 23 | 20 | 3
YPTT | 5 | 10 | 7 | 3
Grand Total | 15 | 36 | 30 | 6 |  |  |  |  | Count of NewXLS ID |  | Months | Migration Actual
[11 empty] | <27/10/2025 | Nov | Grand Total
[9 empty] | 5G Priority | Scope Update | (blank)
2025-10-18 | [8 empty] | 2025-End Nov | Modernize | 2 |  | 2
Subcon | Qty Team | Plan | Actual | Carry over | [5 empty] | New | 142 |  | 142
GIT | 2 | 0 | 0 | 0 | [5 empty] | Swap | 36 | 3 | 39
GPA | 8 | 12 | 8 | 4 |  |  |  |  | Mid Dec 25 | New | 12 |  | 12
YPTT | 5 | 6 | 4 | 2 | [5 empty] | Swap | 12 |  | 12
Grand Total | 15 | 18 | 12 | 6 |  |  |  |  | 2026 | Modernize | 3 |  | 3
[10 empty] | New | 388 |  | 388
[10 empty] | Swap | 26 | 81 | 107
2025-11-24 | [8 empty] | 2025-624 sites | New | 99 |  | 99
Subcon | Qty Team | Plan | Actual | Carry over | [5 empty] | Swap | 3 |  | 3
GIT | 2 | 2 | 2 | 0 |  |  |  |  | Grand Total |  | 723 | 84 | 807
GPA | 8 | 8 | 4 | 4
YPTT | 5 | 9 | 3 | 6
Grand Total | 15 | 19 | 9 | 10
2025-11-24
Subcon | Qty Team | SOW | Scope
GIT | 3 | Swap | IPRAN
GPA | 7 | Swap | IPRAN + IPBB
YPTT | 4 | Swap | IPRAN
CCSI | 1 | Survey | IPRAN + IPBB
Mingze | 4 | Swap | IPRAN + IPBB
GCI | 3 | Swap + FTTS | IPRAN
DCITS | 2 | Insert | IPRAN
Grand Total | 19

## Legend
Delivery Stage | Milestone
Pre-Implementation | Survey
DRM
Site Permit
MR/DN Material Delivery
MOP Preparation & Submission
FO FLP SPK
FO Own Readiness
FO FLP Readiness
Site Readiness
XL WO & RFC
Implementation | MOS & Installation
Integration
Cut Over / Migration
ATP Site Submission
ATP Site Review And Approval
Post-Implementation | Network Monitoring
Dismantle (LDM)
Inbound ZTE WH
PAC
FAC