## Dashboard IPBB
Milestone | Scope
| Swap | % | New | %
00. Migration Done | 1 | 4.167% | 0 | 0% | JAW-JT-MGG-1158 | Magelang | Plan Swap 25 Nov
01. Checklist Go no Go Migration | 1 | 4.167% | 0 | 0%
01a. Integration Done | 2 | 8.333% | 0 | 0% | JAW-JT-PWD-1579 | Purwodadi | Plan Integrate 25 Nov
02. Power On | 3 | 12.5% | 0 | 0%
02a. Installation Done | 3 | 12.5% | 0 | 0%
02a. Permit Install Release | 4 | 1.13% | 0 | 0%
02b. Permit Install Submit | 4 | 16.67% | 0 | 0%
03. Material On Delivery | 4 | 16.67% | 0 | 0%
04. Material On Region | 3 | 12.5% | 0 | 0%
05. Delivery Transfer | 3 | 12.5% | 0 | 0%
06. RFI | 4 | 16.67% | 0 | 0%
07. DRM Done | 21 | 87.5% | 0 | 0%
08. eTSS Approve XLS | 0 | 0% | 0 | 0%
08a. eTSS Approve ZTE | 4 | 16.67% | 0 | 0%
08b. eTSS Upload | 21 | 87.5% | 0 | 0%
09. Survey Done | 24 | 100% | 0 | 0%
09. Permit Survey Approve
09b. Permit Survey Submit
10. PO Batch 1 Total | 24 | 100% | 1 | 100%

## IPBB
Vendor | Region | Unique | Tower ID | Sites Name | Site Info | Long | Lat | City | TP Name | TP ID | exist info | Hostname | IP Address | Existing Device | Existing Vendor | New Info | Propose Scope | Scope Uniq | Code | BOQ Type | Final Type | Site Type | Batch | Permit Survey TP Request | Permit Survey MS Request | Permit Survey Request Status | Permit Survey TP Release | Permit Survey MS Release | Permit Survey Release Status | Subcon Survey | Survey Plan | Survey Actual | TSSR Submit by Subcon | eTSS Review Status | TSSR Approved by ZTE | TSSR Approved by XLS | DRM Date | RFI Status | Depedency | Initial LDM | RFI Date | DT Date | Material in WH Region | DO Request | DO Release | Permit Install TP Request | Permit Install MS Request | Permit Install Request Status | Permit Install TP Release | Permit Install MS Release | Permit Install Release Status | MOS Plan | Mos Actual | Subcon Install | Install Plan | Install Actual | Power On Date | MOP Submit | XLWO Release Date | XLWO Number | RFC Release Date | RFC Number | Integration Plan | Integration Actual | Checklist Go no Go | Migration Plan | Migration Actual | Final LDM | Upload to MATRA | Dismantle Date | Inbound Plan | Inbound Actual | ATP Plan | ATP Actual
ZTE | Central Java | Swap_JAW-JT-SMG-3485_01 | JAW-JT-SMG-3485 | SN Gombel |  | 110.4175 | -7.09636111111111 | Kota Semarang | NO TP NAME | NO TP ID |  | AG-SMSGB-01H | 112.215.186.119 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _01 | M6000-8S Plus | M6000-8S Plus | 2.AG | 1 | [6 empty] | GPA |  | 2025-10-28 | 2025-11-04 | Reviewing |  |  | 2025-11-05 | NY RFI | Need Modernize Rectifier & Battery
ZTE | Central Java | Swap_JAW-JT-CLP-0425_01 | JAW-JT-CLP-0425 | Gandrung Mangu |  | 108.8552 | -7.5253 | Cilacap | PT CENTRATAMA MENARA INDONESIA | JAW-JT-CLP-0425 |  | AG-SMGDM-01H | 202.152.246.146 | NE40E-M2K-B | Huawei |  | Swap | Swap_ | _01 | M6000-3S Plus | M6000-3S Plus | 2.AG | 1 | [6 empty] | CCSI | 2025-10-25 | 2025-10-25 | 2025-10-31 | Reviewing |  |  | 2025-11-04 | NY RFI | Need Modernization Battery | [8 empty] | Done |  |  | 2.0. Permit Done | 2025-11-24 | 2025-11-25
ZTE | Central Java | Swap_JAW-JT-KDL-3487_01 | JAW-JT-KDL-3487 | SN Mangkang |  | 110.270188888889 | -6.96536111111111 | Kendal | NO TP NAME | NO TP ID |  | C-SMSMK-01H | 202.152.246.86 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _01 | M6000-8SE | M6000-8SE | 3.lv C | 1 | [6 empty] | GPA | 2025-10-26 | 2025-10-28 | 2025-10-29 | Reviewing |  |  | 2025-11-04 | NY RFI | Need Upgrade PLN, Need Reloc ACPDB, Rebalancing load PLN, Need Add Battery
ZTE | Central Java | Swap_JAW-JT-KDL-3487_2 | JAW-JT-KDL-3487 | SN Mangkang |  | 110.270188888889 | -6.96536111111111 | Kendal | NO TP NAME | NO TP ID |  | C-SMSMK-02H | 202.152.247.220 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _2 | M6000-8SE | M6000-8SE | 3.lv C | 1 | [6 empty] | GPA | 2025-10-26 | 2025-10-28 | 2025-10-29 | #N/A |  |  | 2025-11-04 | NY RFI | Need Upgrade PLN, Need Reloc ACPDB, Rebalancing load PLN, Need Add Battery
ZTE | Central Java | Swap_JAW-JT-KDL-3487_3 | JAW-JT-KDL-3487 | SN Mangkang |  | 110.270188888889 | -6.96536111111111 | Kendal | NO TP NAME | NO TP ID |  | PS-SMSMK-01H | 202.152.246.117 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _3 | M6000-4SE | M6000-4SE | 4.PS | 1 | [6 empty] | GPA | 2025-10-26 | 2025-10-28 | 2025-10-29 | #N/A |  |  | 2025-11-04 | NY RFI | Need Upgrade PLN, Need Reloc ACPDB, Rebalancing load PLN, Need Add Battery
ZTE | Central Java | Swap_JAW-JT-KDL-3487_4 | JAW-JT-KDL-3487 | SN Mangkang |  | 110.270188888889 | -6.96536111111111 | Kendal | NO TP NAME | NO TP ID |  | PS-SMSMK-02H | 202.152.246.118 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _4 | M6000-4SE | M6000-4SE | 4.PS | 1 | [6 empty] | GPA | 2025-10-26 | 2025-10-28 | 2025-10-29 | #N/A |  |  | 2025-11-04 | NY RFI | Need Upgrade PLN, Need Reloc ACPDB, Rebalancing load PLN, Need Add Battery
ZTE | Central Java | Swap_JAW-YO-SMN-0149_01 | JAW-YO-SMN-0149 | Tempel |  | 110.3268 | -7.6508 | Sleman | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JAW-JGJ-0079-X-P |  | AG-YGTPL-01H | 202.152.247.168 | NE40E-M2K-B | Huawei |  | Swap | Swap_ | _01 | M6000-3S Plus | M6000-3S Plus | 2.AG | 1 | [6 empty] | GPA |  | 2025-10-21 | 2025-10-29 | Reviewing | 2025-10-21 |  | 2025-10-21 | RFI | Waiting MOCN Implementation |  | 2025-10-21 | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | 2025-11-11 | 2025-11-11 | GPA |  | 2025-11-11 | 2025-11-13 | Done | Done | Done | Done | Done | Done | 2025-11-13 | 2025-11-21 |  | 2025-11-23
ZTE | Central Java | Swap_JAW-JT-MGG-1158_01 | JAW-JT-MGG-1158 | Magelang |  | 110.2269 | -7.4796 | Kota Magelang | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JAW-CJV-0262-X-P |  | AG-SMMGL-01H | 202.152.246.18 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _01 | M6000-8S Plus | M6000-8S Plus | 2.AG | 1 | [6 empty] | GPA |  | 2025-10-23 | 2025-10-29 | Reviewing | 2025-10-21 |  | 2025-10-21 | RFI |  |  | 2025-10-21 | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | 2025-11-05 | 2025-11-08 | GPA |  | 2025-11-10 | 2025-11-23 | Done | Done | Done | Done | Done | Done | 2025-11-23 |  | 2025-11-25
ZTE | Central Java | Swap_JAW-JT-SKH-1923_01 | JAW-JT-SKH-1923 | SN Solo |  | 110.8363 | -7.68366944444444 | Sukoharjo | NO TP NAME | NO TP ID |  | AG-YGSNS-01H | 202.152.246.41 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _01 | M6000-8S Plus | M6000-8S Plus | 2.AG | 1 | [6 empty] | GPA | 2025-10-25 | 2025-10-25 | 2025-10-29 | Reviewing |  |  | 2025-11-04 | NY RFI | Need Replace Battery, Need Add Module Recti, Need Repair Genset
ZTE | Central Java | Swap_JAW-YO-YYK-0492_01 | JAW-YO-YYK-0492 | Pathuk |  | 110.3595 | -7.7893 | Kota Yogyakarta | PT XL Axiata | JAW-YO-YYK-0492 |  | C-YGPTH-01H | 112.215.186.72 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _01 | M6000-8SE | M6000-8SE | 3.lv C | 1 | [6 empty] | GPA | 2025-10-26 | 2025-10-29 | 2025-10-29 | Reviewing |  |  | 2025-11-04 | NY RFI | Need Upgrade & Modernize Rectifier, Need add Battery
ZTE | Central Java | Swap_JAW-YO-YYK-0492_2 | JAW-YO-YYK-0492 | Pathuk |  | 110.3595 | -7.7893 | Kota Yogyakarta | PT XL Axiata | JAW-YO-YYK-0492 |  | PS-YGPTH-01H | 202.152.247.207 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _2 | M6000-4SE | M6000-4SE | 4.PS | 1 | [6 empty] | GPA | 2025-10-26 | 2025-10-29 | 2025-10-29 | #N/A |  |  | 2025-11-04 | NY RFI | Need Upgrade & Modernize Rectifier, Need add Battery
ZTE | Central Java | Swap_JAW-YO-YYK-0492_3 | JAW-YO-YYK-0492 | Pathuk |  | 110.3595 | -7.7893 | Kota Yogyakarta | PT XL Axiata | JAW-YO-YYK-0492 |  | PS-YGPTH-02H | 202.152.247.208 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _3 | M6000-4SE | M6000-4SE | 4.PS | 1 | [6 empty] | GPA | 2025-10-26 | 2025-10-29 | 2025-10-29 | #N/A |  |  | 2025-11-04 | NY RFI | Need Upgrade & Modernize Rectifier, Need add Battery
ZTE | Central Java | Swap_JAW-JT-PBG-1276_01 | JAW-JT-PBG-1276 | Purbalingga |  | 109.3623 | -7.3873 | Purbalingga | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JAW-CJV-0290-X-P |  | AG-SMPBL-01H | 202.152.246.19 | NetEngine 8000 M8 | Huawei |  | Swap | Swap_ | _01 | M6000-3S Plus | M6000-3S Plus | 2.AG | 1 | [6 empty] | CCSI |  | 2025-10-24 | 2025-10-31 | Reviewing |  |  | 2025-11-04 | NY RFI | Need Upgrade PLN, Need Add Module Recti, Need Add AC, Need Modernize Battery
ZTE | Central Java | Swap_JAW-JT-PKL-1319_01 | JAW-JT-PKL-1319 | Pekalongan |  | 109.664 | -6.8909 | Kota Pekalongan | PT XL Axiata | JAW-JT-PKL-1319 |  | AG-SMPKL-01H | 112.215.48.53 | NetEngine 8000 M14 | Huawei |  | Swap | Swap_ | _01 | M6000-3S Plus | M6000-8S Plus | 2.AG | 1 | [6 empty] | GPA | 2025-10-25 | 2025-10-25 |  | #N/A |  |  | 2025-10-29 | NY RFI | Need Swap Battery
ZTE | Central Java | Swap_JAW-JT-SLT-2171_01 | JAW-JT-SLT-2171 | Tingkir Salatiga |  | 110.5156 | -7.3627 | Kota Salatiga | PT CENTRATAMA MENARA INDONESIA | JAW-JT-SLT-2171 |  | AG-SMTKR-01H | 202.152.247.182 | NE40E-M2K-B | Huawei |  | Swap | Swap_ | _01 | M6000-3S Plus | M6000-8S Plus | 2.AG | 1 | [6 empty] | CCSI |  | 2025-10-24 | 2025-10-31 | Reviewing |  |  | 2025-10-27 | NY RFI | Need Upgrade PLN Need Add AC Need Upgrade Genset
ZTE | Central Java | Swap_JAW-JT-DMK-0602_01 | JAW-JT-DMK-0602 | Gadjah Demak |  | 110.7173 | -6.8738 | Demak | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JAW-CJV-0247-X-P |  | AG-SMGJH-01H | 202.152.247.184 | NetEngine 8000 M8 | Huawei |  | Swap | Swap_ | _01 | #N/A | M6000-3S Plus | 2.AG | 1 | [6 empty] | Mingze |  | 2025-10-27 | 2025-10-31 | Reviewing | 2025-08-11 |  | 2025-11-04 | RFI
ZTE | Central Java | Swap_JAW-JT-PWD-3478_01 | JAW-JT-PWD-3478 | Purwodadi |  | 110.917 | -7.0717 | Grobogan | PT XL Axiata | JAW-JT-PWD-3478 |  | AG-SMPWD-01H | 202.152.246.40 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _01 | M6000-8S Plus | M6000-8S Plus | 2.AG | 1 | [6 empty] | Mingze |  | 2025-10-27 |  | #N/A |  |  | 2025-11-05 | NY RFI | Need Modernize Rectifier & Battery, Need Repair AC |  |  | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | 2025-11-12 | 2025-11-12 | Mingze |  | 2025-11-12 | 2025-11-23 | Done | Done | Done | Done | Done
ZTE | Central Java | Swap_JAW-YO-WNO-0012_01 | JAW-YO-WNO-0012 | Wonosari |  | 110.5969 | -7.9688 | Wonosari | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JAW-JGJ-0067-H-P |  | AG-YGWNS-01H | 202.152.247.165 | NE40E-M2K-B | Huawei |  | Swap | Swap_ | _01 | M6000-3S Plus | M6000-3S Plus | 2.AG | 1 | [6 empty] | GPA |  | 2025-10-23 | 2025-10-29 | Reviewing
ZTE | Central Java | Swap_JAW-JT-TGL-2600_01 | JAW-JT-TGL-2600 | Tegal |  | 109.143 | -6.8618 | Kota Tegal | PT XL Axiata | JAW-JT-TGL-2600 |  | AG-SMTGL-01H | 202.152.247.212 | NetEngine 8000 M14 | Huawei |  | Swap | Swap_ | _01 | M6000-8S Plus | M6000-8S Plus | 2.AG | 1 | [6 empty] | GPA | 2025-10-25 | 2025-10-25 |  | #N/A |  |  | 2025-10-29 | NY RFI | Need Swap Battery
ZTE | Central Java | Swap_JAW-JT-PTI-1520_01 | JAW-JT-PTI-1520 | Juwana |  | 111.1446 | -6.7188 | Pati | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JAW-CJV-0283-X-P |  | AG-SMJWN-01H | 202.152.247.185 | NetEngine 8000 M8 | Huawei |  | Swap | Swap_ | _01 | #N/A | M6000-3S Plus | 2.AG | 1 | [6 empty] | GPA |  | 2025-10-24 | 2025-11-04 | Reviewing |  |  | 2025-10-28 | RFI |  | 2025-10-28
ZTE | Central Java | Swap_JAW-JT-PWT-1716_01 | JAW-JT-PWT-1716 | Purwokerto |  | 109.2214 | -7.4218 | Banyumas | PT XL Axiata | XL |  | C-SMPRW-01H | 112.215.48.39 | NE40E-X8A(V8) | Huawei |  | Swap | Swap_ | _01 | M6000-8SE | M6000-8SE | 3.lv C | 1 | [6 empty] | GPA |  | 2025-10-24 | 2025-11-04 | Reviewing | 2025-08-11 |  | 2025-11-05 | NY RFI | Need Modernize Rectifier & Battery, Need AC
ZTE | Central Java | Swap_JAW-YO-WAT-0365_01 | JAW-YO-WAT-0365 | Wates |  | 110.1609 | -7.8573 | Kulon Progo | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JAW-YO-WAT-0365 |  | AG-YGWAT-01H | 112.215.48.51 | NetEngine 8000 M8 | Huawei |  | Swap | Swap_ | _01 | M6000-3S Plus | M6000-3S Plus | 2.AG | 1 | [6 empty] | Mingze |  | 2025-10-29 | 2025-11-04 | Reviewing
ZTE | Central Java | Swap_JAW-YO-BTL-0074_01 | JAW-YO-BTL-0074 | Imogiri |  | 110.382 | -7.9223 | Bantul | PT CENTRATAMA MENARA INDONESIA | JAW-YO-BTL-0074 |  | AG-YGIMG-01H | 202.152.247.166 | NetEngine 8000 M8 | Huawei |  | Swap | Swap_ | _01 | M6000-3S Plus | M6000-8S Plus | 2.AG | 1 | [6 empty] | GPA |  | 2025-10-24 | 2025-10-31 | Reviewing |  |  | 2025-10-30 | NY RFI | Need Upgrade PLN Need Upgrade & Replace Battery
ZTE | Central Java | Swap_JAW-JT-UNR-2703_01 | JAW-JT-UNR-2703 | Karangjati |  | 110.4226 | -7.1818 | Semarang | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JAW-CJV-0295-X-P |  | AG-SMKRJ-01H | 112.215.48.52 | NetEngine 8000 M14 | Huawei |  | Swap | Swap_ | _01 | M6000-3S Plus | M6000-3S Plus | 2.AG | 1 | [6 empty] | Mingze |  | 2025-10-26 | 2025-10-31 | Reviewing
ZTE | Central Java | New_JAW-YO-YYK-0492_01 | JAW-YO-YYK-0492 | Pathuk |  | 110.3595 | -7.7893 | Kota Yogyakarta | PT XL Axiata | JAW-YO-YYK-0492 |  | C-YGPTH-02H |  | NE40E-X8A(V8) | Huawei |  | New | New_ | _01 | M6000-8SE | M6000-8SE | 3.lv C | [7 empty] | GPA |  |  |  | #N/A
Formulas:
MOS Plan = [Mos Actual]-1

## Fishbone
|  |  |  | Swap Done | 110
|  | Mos + Install | 119 | NY Swap | 8 | Plan 25 November
Swap
157
|  | NY Mos + Install | 38 | Plan W48 | 38
IPRAN Nov Target
245
| New Fiber | Plan W46 | 26
| 88 | Plan W47 | 30
|  | Plan W48 | 32

## FTTS Site
RING ID LMS | TOWER ID A | Site Name A | TOWERI ID B | Site Name B | FLP PARTNER | Span ID LMS | Tower Owner Group A | Tower Owner B | Kota / Kabupaten | Termination Status A | Termination Status B | SPAN STATUS | RING Status | Ring Type | RFS Actual Date | RFS Doc | MoP Status | MMP Status | Subcon | Assignment | DO Req | DO Release | Plan Visit | Visit | Jumpering NE | Jumpering FE | RFM Status | Remark
R0000019821 | JAW-JT-JPA-0713 | KERSO_JEPARA | JAW-JT-JPA-0621 | Kedung | PT IFORTE SOLUSI INFOTEK | S000054242 | NON TBG | PT CENTRATAMA MENARA INDONESIA | JEPARA | 13b. TERMINATION ODP ACPDP | 13. TERMINATION DONE | 09. TERMINATION WORK | 10. READY ATP / RFS | Star | 2025-11-09 |  | MoP NY Prepare | Ok Proceed | GCI | Done |  |  |  | 2025-11-20 | 2025-11-20 | 2025-11-20 | RFM | RFM
R0000019823 | JAW-JT-JPA-8420 | SF-ZSMG_1948-Mindahan Batealit | JAW-JT-JPA-0660 | BATEALIT | PT IFORTE SOLUSI INFOTEK | S000054244 | TBG GROUP | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JEPARA | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | Star | 2025-11-09 |  | MoP NY Prepare | MMP Issue - Hold | GCI | Done
R0000019831 | JAW-JT-JPA-8337 | SF-ZSMG_1654-JEPARA | JAW-JT-JPA-3402 | Tahunan Tahunan | PT IFORTE SOLUSI INFOTEK | S000054252 | NON TBG | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JEPARA | 13b. TERMINATION ODP ACPDP | 13. TERMINATION DONE | 09. TERMINATION WORK | 10. READY ATP / RFS | Star | 2025-11-09 |  | MoP NY Prepare | Ok Proceed | GCI | Done |  |  |  | 2025-11-20 |  |  |  | NE Community commcase issue
R0000019833 | JAW-JT-JPA-8316 | SF-ZSMG_1747-DEMAAN JEPARA | JAW-JT-JPA-0617 | DEMAAN JEPARA | PT IFORTE SOLUSI INFOTEK | S000054254 | NON TBG | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JEPARA | 13b. TERMINATION ODP ACPDP | 13. TERMINATION DONE | 09. TERMINATION WORK | 10. READY ATP / RFS | Star | 2025-11-09 |  | MoP NY Prepare | Ok Proceed | GCI | Done |  |  |  | 2025-11-20 | 2025-11-20 | 2025-11-20 | RFM | RFM
R0000019873 | JAW-JT-PWD-8505 | SF-ZSMG2_0003-GROBOKAN GABUS | JAW-JT-PWD-1619 | 3G_GABUS_GABUS | PT IFORTE SOLUSI INFOTEK | S000054395 | TBG GROUP | PT GIHON TELEKOMUNIKASI INDONESIA | GROBOGAN | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 |  | MoP NY Prepare | MMP Issue - Hold | GCI | Done
R0000019876 | JAW-JT-PWD-8499 | SF-ZSMG_2115-Ngaringan II | JAW-JT-PWD-0150 | 3G_GAGAAN_KUNDURAN | PT IFORTE SOLUSI INFOTEK | S000054398 | NON TBG | PT TOWER BERSAMA | GROBOGAN | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 |  | MoP NY Prepare | MMP Issue - Hold | GCI | Done
R0000019879 | JAW-JT-PWD-8413 | SF-ZSMG_2690-GROBOGAN GROBOGAN 2 | JAW-JT-PWD-1582 | Grobogan | PT IFORTE SOLUSI INFOTEK | S000054401 | TBG GROUP | PT SOLUSI TUNAS PRATAMA TBK | GROBOGAN | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 |  | MOP Submitted | MMP Issue - Hold | GCI | Done
R0000019881 | JAW-JT-PWD-8523 | SF-ZSMG_1635-Plumpung Kemadoh Batur | JAW-JT-PWD-1599 | Gn.Gading Kemahduhbatur | PT IFORTE SOLUSI INFOTEK | S000054403 | TBG GROUP | PT TOWER BERSAMA | GROBOGAN | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 |  | MOP Submitted | MMP Issue - Hold | GCI | Done
R0000019884 | JAW-JT-PWD-8517 | SF-ZSMG2_0226-Grogolan Sambirejo D | JAW-JT-PWD-1600 | Tanjungrejo Wirosari (Collocation Tower) | PT IFORTE SOLUSI INFOTEK | S000054406 | NON TBG | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | GROBOGAN | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 |  | MOP Submitted | Ok Proceed | GCI | Done |  |  |  | 2025-11-21 | 2025-11-24 | 2025-11-21 |  | OG cek RSL after change SFP
R0000019975 | JAW-JT-UNR-2548 | COKROAMINOTO UNGARAN | JAW-JT-UNR-2689 | Ungaran Kota | PT IFORTE SOLUSI INFOTEK | S000054598 | NON TBG | PT DAYAMITRA TELEKOMUNIKASI | SEMARANG | 13. TERMINATION DONE | 13. TERMINATION DONE | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 |  | MoP NY Prepare | Ok Proceed | GCI | Done |  |  |  | 2025-11-21 |  | 2025-11-21 |  | SFP not detect
R0000019981 | JAW-JT-UNR-8443 | SF-ZSMG_1582-Candirejo | JAW-JT-UNR-2688 | Candirejo Ungaran | PT IFORTE SOLUSI INFOTEK | S000054604 | TBG GROUP | PT TOWER BERSAMA | SEMARANG | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 |  | MoP NY Prepare | MMP Issue - Hold | GCI | Done
R0000019991 | JAW-JT-UNR-2551 | RANDUGUNTING_RELOCATION | JAW-JT-UNR-2704 | 3G Harjosari | PT IFORTE SOLUSI INFOTEK | S000054614 | NON TBG | PT DAYAMITRA TELEKOMUNIKASI | SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 |  | MoP NY Prepare | Ok Proceed | GCI | Done |  |  |  | 2025-11-23 |  | 2025-11-23 |  | SFP not detect
R0000019997 | JAW-JT-UNR-8447 | SF-ZSMG_1591-Banaran Ambarawa | JAW-JT-UNR-2682 | Kota Ambarawa Relocation | PT IFORTE SOLUSI INFOTEK | S000054620 | TBG GROUP | PT SOLUSINDO KREASI PRATAMA | SEMARANG | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 |  | MoP NY Prepare | MMP Issue - Hold | GCI | Done
R0000020053 | JAW-JT-SMG-0617 | TUGU INDUSTRI SEMARANG | JAW-JT-SMG-2327 | Site Ngaliyan | PT IFORTE SOLUSI INFOTEK | S000054676 | NON TBG | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 |  | MOP Submitted | Ok Proceed | GCI | Done |  |  |  | 2025-11-20 | 2025-11-20 | 2025-11-19 |  | Ping UME,NDS,BSC,MME/SGW-XL RTO RTO
R0000020055 | JAW-JT-SMG-2316 | GAMBILANGU | JAW-JT-SMG-2318 | WONOSARI NGALIAN | PT IFORTE SOLUSI INFOTEK | S000054678 | TBG GROUP | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | KOTA SEMARANG | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 |  | MOP Submitted | MMP Issue - Hold | GCI | Done
R0000020062 | JAW-JT-SMG-8495 | SF-ZSMG_1006-TANGGULMAS | JAW-JT-SMG-2407 | PANGGUNG KIDUL | PT IFORTE SOLUSI INFOTEK | S000054685 | NON TBG | PT SOLUSINDO KREASI PRATAMA | KOTA SEMARANG | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 |  | MOP Submitted | MMP Issue - Hold | GCI | Done
R0000020068 | JAW-JT-SMG-2957 | MANGUNHARJOTUGU | JAW-JT-SMG-2323 | Mangkang Wetan 3G | PT IFORTE SOLUSI INFOTEK | S000054691 | NON TBG | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 |  | MOP Submitted | Ok Proceed | GCI | Done |  |  |  | 2025-11-20 | 2025-11-19 | 2025-11-19 | RFM | RFM
R0000020087 | JAW-JT-SMG-0602 | WARU PEDALANGAN BANYUMANIK | JAW-JT-SMG-2459 | Padangsari Semarang | PT IFORTE SOLUSI INFOTEK | S000054710 | NON TBG | PT TOWER BERSAMA | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 |  | MOP Submitted | Ok Proceed | GCI | Done |  |  |  | 2025-11-20 |  |  |  | NY VISIT
R0000020098 | JAW-JT-SMG-0531 | Maera Sari | JAW-JT-SMG-2509 | 3G UNDIP Tembalang | PT IFORTE SOLUSI INFOTEK | S000054721 | TBG GROUP | PT DAYAMITRA TELEKOMUNIKASI | KOTA SEMARANG | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 |  | MOP Submitted | MMP Issue - Hold | GCI | Done
R0000020102 | JAW-JT-SMG-2510 | Bulusan Tembalang | JAW-JT-SMG-3473 | LTE_TIRTO_AGUNG_RELOCATION | PT IFORTE SOLUSI INFOTEK | S000054725 | NON TBG | PT EDOTCO INFRASTRUKTUR INDONESIA | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13. TERMINATION DONE | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 |  | MOP Submitted | Ok Proceed | GCI | Done |  |  |  | 2025-11-20 |  | 2025-11-20 |  | NY VISIT
R0000020110 | JAW-JT-SMG-2317 | Wonoplumbon Kendal | JAW-JT-SMG-2322 | Mijen Semarang | PT IFORTE SOLUSI INFOTEK | S000054733 | NON TBG | PT SOLUSI TUNAS PRATAMA TBK | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 |  | MoP NY Prepare | Ok Proceed | GCI | Done |  |  |  | 2025-11-21 | 2025-11-21 | 2025-11-21 | RFM | RFM
R0000020111 | JAW-JT-SMG-2353 | SADENG GUNUNG PATI | JAW-JT-SMG-2346 | 3G_PUNGANGAN_GUNUNGPATI | PT IFORTE SOLUSI INFOTEK | S000054734 | TBG GROUP | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | KOTA SEMARANG | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-02 |  | MOP Submitted | MMP Issue - Hold | GCI | Done
R0000020133 | JAW-JT-SMG-2951 | BRINGIN NGALIYAN | JAW-JT-SMG-2336 | Kadung Pane | PT IFORTE SOLUSI INFOTEK | S000054756 | TBG GROUP | PT SOLUSI TUNAS PRATAMA TBK | KOTA SEMARANG | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 |  | MoP NY Prepare | MMP Issue - Hold | GCI | Done
R0000020137 | JAW-JT-SMG-0547 | BERINGIN NGALIYAN RELOCATION | JAW-JT-SMG-2336 | Kadung Pane | PT IFORTE SOLUSI INFOTEK | S000054760 | TBG GROUP | PT SOLUSI TUNAS PRATAMA TBK | KOTA SEMARANG | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 |  | MoP NY Prepare | MMP Issue - Hold | GCI | Done
R0000020141 | JAW-JT-SMG-2324 | Gondoriyo Ngaliyan | JAW-JT-SMG-2336 | Kadung Pane | PT IFORTE SOLUSI INFOTEK | S000054764 | TBG GROUP | PT SOLUSI TUNAS PRATAMA TBK | KOTA SEMARANG | #N/A | #N/A | 09. TERMINATION WORK | 10. READY ATP / RFS | STAR | 2025-11-09 |  | MOP Submitted | MMP Issue - Hold | GCI | Done
R0000020333 | JAW-JT-PWD-8425 | SF-ZSMG2_0621-PURWODADI UTR | JAW-JT-PWD-1572 | Kuripan Purwodadi | PT IFORTE SOLUSI INFOTEK | S000055170 | NON TBG | PT PERSADA SOKKA TAMA | GROBOGAN | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP | 09. TERMINATION WORK | 10. READY ATP / RFS | Star | 2025-11-09 |  | MoP NY Prepare | Ok Proceed | GCI | Done |  |  |  | 2025-11-24 | 2025-11-24 | 2025-11-24 |  | OK RSL//need pingtes UME,NDS,BSC,MME/SGW-XL
R0000019814 | JAW-JT-JPA-8392 | SF-ZSMG_2840-Paren Mayong B | JAW-JT-JPA-0649 | 3G KALIPUCANG WETAN | PT IFORTE SOLUSI INFOTEK | S000054235 |  |  | JEPARA | 13b. TERMINATION ODP ACPDP | 13. TERMINATION DONE |  |  | Star | 2025-11-17 |  | MoP NY Prepare | Ok Proceed | Mingze | Need Email | 1
R0000019819 | JAW-JT-JPA-8383 | SF-ZSMG_2877-Banyuputih Kalinyamatan A1 | JAW-JT-JPA-0603 | Pendosawalan | PT IFORTE SOLUSI INFOTEK | S000054240 |  |  | JEPARA | 13b. TERMINATION ODP ACPDP | 13. TERMINATION DONE |  |  | Star | 2025-11-17 |  | MoP NY Prepare | Ok Proceed | Mingze | Need Email | 2
R0000019836 | JAW-JT-JPA-8360 | SF-ZSMG2_0024-Kedungsarimulyo | JAW-JT-JPA-0601 | Kedungsarimulyo | PT IFORTE SOLUSI INFOTEK | S000054257 |  |  | JEPARA | 13b. TERMINATION ODP ACPDP | 13. TERMINATION DONE |  |  | Star | 2025-11-17 |  | MoP NY Prepare | Ok Proceed | Mingze | Need Email | 3
R0000019871 | JAW-JT-PWD-8399 | SF-ZSMG2_0099-Mangonan B@1 | JAW-JT-PWD-1565 | Brati | PT IFORTE SOLUSI INFOTEK | S000054393 |  |  | GROBOGAN | 13. TERMINATION DONE | 13. TERMINATION DONE |  |  | Star | 2025-11-17 |  | MoP NY Prepare | Ok Proceed | Mingze | Need Email | 1
R0000019875 | JAW-JT-PWD-8381 | SF-ZSMG_2952-Wolo F1 | JAW-JT-PWD-1558 | Penawangan | PT IFORTE SOLUSI INFOTEK | S000054397 |  |  | GROBOGAN | 13. TERMINATION DONE | 13. TERMINATION DONE |  |  | Star | 2025-11-17 |  | MoP NY Prepare | Ok Proceed | Mingze | Need Email | 2
R0000019885 | JAW-JT-PWD-8568 | SF-ZSMG_2947-Sukoharjo Kradenan D | JAW-JT-PWD-1613 | Kuwu | PT IFORTE SOLUSI INFOTEK | S000054407 |  |  | GROBOGAN | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP |  |  | Star | 2025-11-17 |  | MoP NY Prepare | Ok Proceed | Mingze | Need Email | 3
R0000019976 | JAW-JT-UNR-8478 | SF-ZSMG_1757-KALIREJO CITY | JAW-JT-UNR-2702 | Kutilangsari Ungaran | PT IFORTE SOLUSI INFOTEK | S000054599 |  |  | SEMARANG | 13. TERMINATION DONE | 13. TERMINATION DONE |  |  | Star | 2025-11-17 |  |  | Ok Proceed | GPA | Need Email
R0000019978 | JAW-JT-UNR-8462 | SF-ZSMG_2516-Letjend S Parman Ungaran | JAW-JT-UNR-2684 | 3G Ungaran Selatan | PT IFORTE SOLUSI INFOTEK | S000054601 |  |  | SEMARANG | 13. TERMINATION DONE | 13. TERMINATION DONE |  |  | Star | 2025-11-17 |  |  | Ok Proceed | GPA | Need Email
R0000020017 | JAW-JT-SMG-0590 | Lotte Semarang | JAW-JT-SMG-2511 | Katamso Lamper Lor (Regular) | PT IFORTE SOLUSI INFOTEK | S000054640 |  |  | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP |  |  | Star | 2025-11-17 |  |  | Ok Proceed | GPA | Need Email
R0000020082 | JAW-JT-SMG-0609 | JL. RAYASEMARANG BOJA TAMBANGAN | JAW-JT-SMG-2322 | Mijen Semarang | PT IFORTE SOLUSI INFOTEK | S000054705 |  |  | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP |  |  | Star | 2025-11-17 |  |  | Ok Proceed | GPA | Need Email
R0000020084 | JAW-JT-SMG-0603 | RASAMALA RAYA SRONDOL | JAW-JT-SMG-2459 | Padangsari Semarang | PT IFORTE SOLUSI INFOTEK | S000054707 |  |  | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP |  |  | Star | 2025-11-17 |  |  | Ok Proceed | GPA | Need Email
R0000020086 | JAW-JT-SMG-2542 | Bukit Kencana II 3G | JAW-JT-SMG-2559 | Meteseh | PT IFORTE SOLUSI INFOTEK | S000054709 |  |  | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP |  |  | Star | 2025-11-17 |  |  | Ok Proceed | GPA | Need Email
R0000020090 | JAW-JT-SMG-0544 | Transmart Setiabudi Semarang | JAW-JT-SMG-2422 | ADA_DEPT_STORE | PT IFORTE SOLUSI INFOTEK | S000054713 |  |  | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP |  |  | Star | 2025-11-17 |  |  | Ok Proceed | GPA | Need Email
R0000020093 | JAW-JT-SMG-8466 | SF-ZSMG_0643-SRONDOL | JAW-JT-SMG-2422 | ADA_DEPT_STORE | PT IFORTE SOLUSI INFOTEK | S000054716 |  |  | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP |  |  | Star | 2025-11-17 |  |  | Ok Proceed | GPA | Need Email
R0000020096 | JAW-JT-SMG-2543 | 3G_METESEH_TEMBALANG | JAW-JT-SMG-2559 | Meteseh | PT IFORTE SOLUSI INFOTEK | S000054719 |  |  | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP |  |  | Star | 2025-11-17 |  |  | Ok Proceed | GPA | Need Email
R0000020145 | JAW-JT-SMG-0622 | MANYARAN RELOCATION | JAW-JT-SMG-2368 | Kalibanteng Kidul | PT IFORTE SOLUSI INFOTEK | S000054768 |  |  | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13. TERMINATION DONE |  |  | Star | 2025-11-17 |  |  | Ok Proceed | GPA | Need Email
R0000019807 | JAW-JT-JPA-0688 | TEDUNAN | JAW-JT-JPA-0623 | 3G_BLULUKAN | PT IFORTE SOLUSI INFOTEK | S000054228 |  | PT CENTRATAMA MENARA INDONESIA | JEPARA | 13b. TERMINATION ODP ACPDP | 13. TERMINATION DONE |  |  | Star | 2025-11-23 | https://drive.google.com/drive/folders/1U1oQ2YbTZ8LNUYtVR8J7iERes1LGoNkc?usp=drive_link |  | Ok Proceed | GPA | Need Email
R0000019818 | JAW-JT-JPA-8382 | SF-ZSMG_1698-Kalinyamatan | JAW-JT-JPA-0651 | Site Pecangaan | PT IFORTE SOLUSI INFOTEK | S000054239 |  | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JEPARA | 13b. TERMINATION ODP ACPDP | 13. TERMINATION DONE |  |  | Star | 2025-11-23 | https://drive.google.com/drive/folders/1YBysRRWatrxAhR-_OGNUzFzXzylwiPpC?usp=drive_link |  | Ok Proceed | GPA | Need Email
R0000020338 | JAW-JT-UNR-8519 | SF-ZSMG_1165-Gendang UNR | JAW-JT-UNR-3201 | 3G_SRATEN_SIDOMUKTI_RELOCATION | PT IFORTE SOLUSI INFOTEK | S000055175 |  | PT XL Axiata | SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP |  |  | Star | 2025-11-23 | https://drive.google.com/drive/folders/16WiScSlS3FdKLzArfx9Ykj0Hcv1QKqr-?usp=drive_link |  | Ok Proceed | GPA | Need Email
R0000020337 | JAW-JT-JPA-8406 | SF-ZSMG_1385-Kewelahanayong GF SB | JAW-JT-JPA-0661 | Mayong | PT IFORTE SOLUSI INFOTEK | S000055174 |  | PT SOLUSI TUNAS PRATAMA TBK | JEPARA | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP |  |  | Star | 2025-11-23 | https://drive.google.com/drive/folders/1LNidHIczWnDSWr-7U8UoQ795Ul4jF2qa?usp=drive_link |  | Ok Proceed | GPA | Need Email
R0000019826 | JAW-JT-JPA-4011 | KRIYAN_JEPARA | JAW-JT-JPA-0651 | Site Pecangaan | PT IFORTE SOLUSI INFOTEK | S000054247 |  | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | JEPARA | 13b. TERMINATION ODP ACPDP | 13. TERMINATION DONE |  |  | Star | 2025-11-23 | https://drive.google.com/drive/folders/101jV-eTxzT6a6rBtBZodX50gGjv6wr4x?usp=drive_link |  | Ok Proceed | GPA | Need Email
R0000019829 | JAW-JT-JPA-8345 | SF-ZSMG2_0216-NR Mlonggo Kidul | JAW-JT-JPA-0631 | Sumawal | PT IFORTE SOLUSI INFOTEK | S000054250 |  | PT DAYAMITRA TELEKOMUNIKASI | JEPARA | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP |  |  | Star | 2025-11-23 | https://drive.google.com/drive/folders/1NaobRvBfkiUUBXIUaTCxM3Acuo40Nz2X?usp=drive_link |  | Ok Proceed | GPA | Need Email
R0000020336 | JAW-JT-JPA-8414 | SF-ZSMG2_0484-PELEMKEREP JPA | JAW-JT-JPA-0661 | Mayong | PT IFORTE SOLUSI INFOTEK | S000055173 |  | PT SOLUSI TUNAS PRATAMA TBK | JEPARA | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP |  |  | Star | 2025-11-23 | https://drive.google.com/drive/folders/1z1IPqGs9Ne4X5leHGmX3HGRhwElvABSO?usp=drive_link |  | Ok Proceed | GPA | Need Email
R0000019856 | JAW-JT-PWD-8575 | SF-ZSMG2_0323-Sendangrejo Village C 1 | JAW-JT-PWD-1613 | Kuwu | PT IFORTE SOLUSI INFOTEK | S000054378 |  | PT SOLUSI TUNAS PRATAMA TBK | GROBOGAN | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP |  |  | Star | 2025-11-23 | https://drive.google.com/drive/folders/1n-2GOGKvYMD3vk4EwW3XzvVVQijIpSl7?usp=drive_link |  | Ok Proceed | GPA | Need Email
R0000020140 | JAW-JT-SMG-8614 | SF-ZSMG_1685-Supriadi | JAW-JT-SMG-2540 | Palebon Padurungan | PT IFORTE SOLUSI INFOTEK | S000054763 |  | PT SOLUSI TUNAS PRATAMA TBK | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP |  |  | Star | 2025-11-23 | https://drive.google.com/drive/folders/1g0IUauvEMCJwV7GDUyk3HumQ4GWubgvf?usp=drive_link |  | Ok Proceed | GPA | Need Email
R0000020139 | JAW-JT-SMG-8618 | SF-ZSMG_1001-PEDURUNGAN | JAW-JT-SMG-2540 | Palebon Padurungan | PT IFORTE SOLUSI INFOTEK | S000054762 |  | PT SOLUSI TUNAS PRATAMA TBK | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP |  |  | Star | 2025-11-23 | https://drive.google.com/drive/folders/1NA6GNQcU4xgNnHpUZfxFQPotDBGqJn2H?usp=drive_link |  | Ok Proceed | GPA | Need Email
R0000020135 | JAW-JT-SMG-0607 | GAYAMSARI SELATAN SENDANGGUWO | JAW-JT-SMG-2540 | Palebon Padurungan | PT IFORTE SOLUSI INFOTEK | S000054758 |  | PT SOLUSI TUNAS PRATAMA TBK | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP |  |  | Star | 2025-11-23 | https://drive.google.com/drive/folders/1y-B8rpVRJy6wpX2V12jla2PU5aaR6cN_?usp=drive_link |  | Ok Proceed | GPA | Need Email
R0000020077 | JAW-JT-SMG-8694 | SF-ZSMG_2746-Karangroto Tambi | JAW-JT-SMG-3068 | KARANGROTOGENUK | PT IFORTE SOLUSI INFOTEK | S000054700 |  | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP |  |  | Star | 2025-11-23 | https://drive.google.com/drive/folders/13I6ZMecXzAKQ8HXAg4zIbxtf5BaQ4GZS?usp=drive_link |  | Ok Proceed | GPA | Need Email
R0000020065 | JAW-JT-SMG-8449 | SF-ZSMG_1028-Miroto Brotojoyo | JAW-JT-SMG-2409 | Tanah Mas Semarang | PT IFORTE SOLUSI INFOTEK | S000054688 |  | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP |  |  | Star | 2025-11-23 | https://drive.google.com/drive/folders/1AW4UmPBGmrnSaY0LJuen73_1wpWbhfiR?usp=drive_link |  | Ok Proceed | GPA | Need Email
R0000019984 | JAW-JT-UNR-8506 | SF-ZSMG_2748-Macan Mati Klepu | JAW-JT-UNR-2723 | Ngempon Klepu | PT IFORTE SOLUSI INFOTEK | S000054607 |  | PT DAYAMITRA TELEKOMUNIKASI | SEMARANG | 13. TERMINATION DONE | 13. TERMINATION DONE |  |  | Star | 2025-11-23 | https://drive.google.com/drive/folders/1a9_M_A_RaCqwyqXPm9kbYOlGpA5i-oPe |  | Ok Proceed | GPA | Need Email
R0000020027 | JAW-JT-SMG-3622 | NGALIYAN KOTA RELOCATION | JAW-JT-SMG-3062 | TUGUREJOTUGU | PT IFORTE SOLUSI INFOTEK | S000054650 |  | PT PROFESIONAL TELEKOMUNIKASI INDONESIA | KOTA SEMARANG | 13b. TERMINATION ODP ACPDP | 13b. TERMINATION ODP ACPDP |  |  | Star | 2025-11-23 | https://drive.google.com/drive/folders/1ME9lXFWGh2yQ_N7Itx47wXbYIdCQrufF?usp=drive_link |  | Ok Proceed | GPA | Need Email

## Dashboard
Milestone | Scope | [7 empty] | Milestone | Scope
| Swap | % | New | % | Modernize | % | Service Migration | % |  | Swap | %
00. Migration Done | 110 | 70.06% | 0 | 0% | 0 | 0% | 0 | 0% | 00. Inbound | 64 | 64.65%
01. Integration Done | 110 | 70.06% | 0 | 0% | 0 | 0% | 0 | 0% | 01. Dismantle | 105 | 106.1%
02. Installation Done | 119 | 75.8% | 1 | 1.136% | 0 | 0% | 0 | 0% | 02. Migration Done | 110 | 111.1%
02a. Permit Install Release | 119 | 75.8% | 1 | 1.136% | 0 | 0% | 0 | 0%
02b. Permit Install Submit | 119 | 75.8% | 1 | 1.136% | 0 | 0% | 0 | 0%
03. Material On Delivery | 119 | 75.8% | 1 | 1.136% | 0 | 0% | 0 | 0%
04. Material On Region | 120 | 76.43% | 1 | 1.136% | 2 | 6.452% | 0 | 0%
05. Delivery Transfer | 120 | 76.43% | 1 | 1.136% | 2 | 6.452% | 0 | 0%
06. RFI | 120 | 76.43% | 1 | 1.136% | 2 | 6.452% | 0 | 0%
07. DRM Done | 281 | 179% | 545 | 619.3% | 2 | 6.452% | 0 | 0%
08. eTSS Approve XLS | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
08a. eTSS Approve ZTE | 261 | 166.2% | 41 | 46.59% | 2 | 6.452% | 0 | 0%
08b. eTSS Upload | 262 | 166.9% | 63 | 71.59% | 2 | 6.452% | 0 | 0%
09. Survey Done | 272 | 173.2% | 81 | 92.05% | 2 | 6.452% | 0 | 0%
09. Permit Survey Approve
09b. Permit Survey Submit
10. PO Batch 1 Total | 354 | 100% | 848 | 100% | 31 | 100% | 3 | 100%

## Target Nov 25
Subcon | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | Grand Total
GCI | 2 |  |  | 3 | 5
GIT | 2 | 2 |  | 2 | 6
GPA | 2 | 4 |  | 1 | 7
Mingze | 1 | 2 |  |  | 3
YPTT | 3 | 2 | 9 | 3 | 17
Grand Total | 10 | 10 | 9 | 9 | 38
|  |  |  | Target November 2025 | SOW
|  |  |  | 27 - 30 November2025 | 38
|  |  |  | 2025-11-26 | 9
|  |  |  | Ongoing | 8
|  |  |  | Done | 110
|  |  |  | Total | 165

## IPRAN
Batch | Order | Status | Uniq ID | ScopeID | NewXLS ID | Region | Province | City | Lat | Long | Scope | SOW | Scope Update | Type | Site Type | Tower ID | SiteName | TP Name | TP ID | Ring | NE Name | IP Address | Hardware Model/Version | Exsisting HW Vendor | Material Source | Detail | Site Status | Priority | New Chasis | Leased FO Partner | SPK Status | New Ring ID Fiber | Span ID Fiber 1 | Span ID Fiber 2 | Ring ID Fiber Status | RFS Plan | RFS Week Plan | RFS Actual | XC | P1 Fiber | MMP Status | 5G Priority | Depedency | Subcon Survey | Survey Plan | Survey Week | Monthly | Monthly HQ | Survey Year | Survey Actual | TSSR Submit by Subcon | TSSR Remark | TSSR Approve ZTE | TSSR Approve XLS | DRM | DRM Status | RFI Status | Remark Survey | DT | Material in WH | DO Req | DO Release | MOS Plan | MOS Actual | Permit Install TP Submit | Permit Install MS Submit | Permit Status Submit | Permit Install TP Release | Permit Install MS Release | Permit Status Release | Subcon Install | Install Plan | Weekly Install | Install Actual | MOP Submit | XLWO Release | XLWO Number | RFC Number | Integration Plan | Integration Actual | Migration Plan | Weekly Mig | New Mig Plan | New Weekly Mig | X | New Plan 2 | New Week Plan 2 | Y | Migration Actual | Assignment | Prior Survey | Y | Monthly Target | Dismantle Date | LDM Upload | Inbound Date
1 | 1 | CLEAR | Modernize_JAW-YO-SMN-8408_1 | Modernize_JAW-YO-SMN-8408 | JAW-YO-SMN-8408 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.7416 | 110.3918 | Swap | Swap Only | Modernize | Type B | MA | ZYKT_0233 | #N/A |  |  | #N/A | YKT_6150_ZTE_1111 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-19 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-SMG-8658_1 | Modernize_JAW-JT-SMG-8658 | JAW-JT-SMG-8658 | Central Java | Jawa Tengah | Kota Semarang | -6.9638 | 110.4709 | Swap | Swap Only | Modernize | Type B | MA | ZSMG_0668 | #N/A |  |  | #N/A | SMG_6150_ZSMG_0668 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-19 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-SMG-8473_1 | Modernize_JAW-JT-SMG-8473 | JAW-JT-SMG-8473 | Central Java | Jawa Tengah | Kota Semarang | -6.9647 | 110.4119 | Swap | Swap Only | Modernize | Type B | MA | ZSMG_0334 | #N/A |  |  | #N/A | SMG_6150_ZTE_3457 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-20 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-SMG-8418_1 | Modernize_JAW-JT-SMG-8418 | JAW-JT-SMG-8418 | Central Java | Jawa Tengah | Kota Semarang | -7.0038 | 110.3894 | Swap | Swap Only | Modernize | Type B | MA | ZSMG_0336 | #N/A |  |  | #N/A | SMG_6150_ZTE_3459 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-20 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JI-BKL-3150_1 | Modernize_JAW-JI-BKL-3150 | JAW-JI-BKL-3150 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8285 | 110.4108 | Swap | Swap Only | Modernize | Type B | MA | ZYKT_0275 | #N/A |  |  | #N/A | YKT_6150_ZTE_3484 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-21 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-KDL-4158_1 | Modernize_JAW-JT-KDL-4158 | JAW-JT-KDL-4158 | Central Java | Jawa Tengah | Kendal | -6.9714 | 110.2333 | Swap | Swap Only | Modernize | Type B | MA | ZSMG_1205 | #N/A |  |  | #N/A | SMG_6150_ZSMG_1205 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-21 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-PTI-8533_1 | Modernize_JAW-JT-PTI-8533 | JAW-JT-PTI-8533 | Central Java | Jawa Tengah | Pati | -6.655 | 111.0918 | Swap | Swap Only | Modernize | Type B | MA | ZSMG_0119 | #N/A |  |  | #N/A | SMG_6150_ZTE_2258 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-22 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-CLP-8499_1 | Modernize_JAW-JT-CLP-8499 | JAW-JT-CLP-8499 | Central Java | Jawa Tengah | Cilacap | -7.2997 | 108.7772 | Swap | Swap Only | Modernize | Type B | MA | ZYKT_0051 | #N/A |  |  | #N/A | YKT_6150_ZTE_2274 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-22 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-CLP-8507_1 | Modernize_JAW-JT-CLP-8507 | JAW-JT-CLP-8507 | Central Java | Jawa Tengah | Cilacap | -7.7234 | 109.0104 | Swap | Swap Only | Modernize | Type B | MA | ZYKT_0101 | #N/A |  |  | #N/A | YKT_6150_ZTE_3489 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-23 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-SKT-8545_1 | Modernize_JAW-JT-SKT-8545 | JAW-JT-SKT-8545 | Central Java | Jawa Tengah | Kota Surakarta | -7.5705 | 110.8333 | Swap | Swap Only | Modernize | Type B | MA | ZSLO_0079 | #N/A |  |  | #N/A | SLO_6150_ZTE_1184 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-23 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-PWT-8363_1 | Modernize_JAW-JT-PWT-8363 | JAW-JT-PWT-8363 | Central Java | Jawa Tengah | Banyumas | -7.4134 | 109.2679 | Swap | Swap Only | Modernize | Type B | MA | ZYKT_0104 | #N/A |  |  | #N/A | YKT_6150_ZTE_3492 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-26 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-JPA-8320_1 | Modernize_JAW-JT-JPA-8320 | JAW-JT-JPA-8320 | Central Java | Jawa Tengah | Jepara | -6.5973 | 110.6697 | Swap | Swap Only | Modernize | Type B | MA | ZSMG_0175 | #N/A |  |  | #N/A | SMG_6150_ZTE_3857 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-26 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-PWD-8475_1 | Modernize_JAW-JT-PWD-8475 | JAW-JT-PWD-8475 | Central Java | Jawa Tengah | Grobogan | -7.1225 | 110.9934 | Swap | Swap Only | Modernize | Type B | MA | ZSMG_0900 | #N/A |  |  | #N/A | SMG_6150_ZSMG_0900 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Keep | 5 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | On Schedule Swap | GIT | 2026-01-27 | 5 |  |  | 2026 | 2025-11-14 | 2025-11-17 | Approved | 2025-11-22 |  | Submitted | Approved | Done |  | Done | Done | Done | DOEID25111431 | 2025-11-17 | [7 empty] | Mingze | 2025-11-17 | 47 | [5 empty] | 2025-11-20 |  | 2025-11-20 | 47 | 2025-11-20 | 47 | TRUE |  | 1 | 2025-11-20 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | Modernize_JAW-YO-YYK-8305_1 | Modernize_JAW-YO-YYK-8305 | JAW-YO-YYK-8305 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7816 | 110.368 | Swap | Swap Only | Modernize | Type B | MA | ZYKT_0272 | #N/A |  |  | #N/A | YKT_6150_ZTE_3481 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December |  | 2026-01-27 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-PWD-8421_1 | Modernize_JAW-JT-PWD-8421 | JAW-JT-PWD-8421 | Central Java | Jawa Tengah | Grobogan | -7.1675 | 110.9011 | Swap | Swap Only | Modernize | Type B | MA | ZSMG_0169 | #N/A |  |  | #N/A | SMG_6150_ZTE_3851 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Keep | 5 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | On Schedule Swap | GIT | 2026-01-28 | 5 |  |  | 2026 | 2025-11-14 | 2025-11-14 | Approved | 2025-11-17 |  | Submitted | Approved | Done |  | Done | Done | Done | DOEID25111432 | 2025-11-20 | [7 empty] | Mingze | 2025-11-20 | 47 | [5 empty] | 2025-11-23 |  | 2025-11-23 | 47 | 2025-11-23 | 47 | TRUE |  | 1 | 2025-11-20 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | Modernize_JAW-JT-PML-8447_1 | Modernize_JAW-JT-PML-8447 | JAW-JT-PML-8447 | Central Java | Jawa Tengah | Pemalang | -6.9063 | 109.3888 | Swap | Swap Only | Modernize | Type B | MA | ZSMG_0006 | #N/A |  |  | #N/A | SMG_6150_ZTE_0957 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-28 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-SLT-8458_1 | Modernize_JAW-JT-SLT-8458 | JAW-JT-SLT-8458 | Central Java | Jawa Tengah | Kota Salatiga | -7.345 | 110.5088 | Swap | Swap Only | Modernize | Type B | MA | ZSMG_0288 | #N/A |  |  | #N/A | SMG_6150_ZTE_1027 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December |  | 2026-01-29 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-CLP-8509_1 | Modernize_JAW-JT-CLP-8509 | JAW-JT-CLP-8509 | Central Java | Jawa Tengah | Cilacap | -7.3309 | 108.654 | Swap | Swap Only | Modernize | Type B | MA | ZYKT_0120 | #N/A |  |  | #N/A | YKT_6150_ZTE_3871 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop,Double Scope |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-29 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JI-BKL-3161_1 | Modernize_JAW-JI-BKL-3161 | JAW-JI-BKL-3161 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8041 | 110.4128 | Swap | Swap Only | Modernize | Type B | MA | ZYKT_0321 | #N/A |  |  | #N/A | YKT_6150_ZTE_6654 | #N/A | ZXCTN 6150 | ZTE | New Purchase | Modernize ZTE | Propose Drop,Double Scope |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-30 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-SGN-8545_1 | Modernize_JAW-JT-SGN-8545 | JAW-JT-SGN-8545 | Central Java | Jawa Tengah | Sragen | -7.5223 | 110.9985 | Swap | Swap Only | Modernize | Type A | MA | ZSLO_0723 | #N/A |  |  | #N/A | SLO_6150_ZSLO_0723 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Propose Drop, MOCN Drop |  | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-30 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-TMG-8502_1 | Modernize_JAW-JT-TMG-8502 | JAW-JT-TMG-8502 | Central Java | Jawa Tengah | Temanggung | -7.2391 | 110.0569 | Swap | Swap Only | Modernize | Type A | MA | ZSMG_0105 | #N/A |  |  | #N/A | SMG_6150_ZTE_2244 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Propose Drop, MOCN Drop |  | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-02 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-WSB-8490_1 | Modernize_JAW-JT-WSB-8490 | JAW-JT-WSB-8490 | Central Java | Jawa Tengah | Wonosobo | -7.356 | 109.9066 | Swap | Swap Only | Modernize | Type A | MA | ZYKT_0145 | #N/A |  |  | #N/A | YKT_6150_ZTE_4561 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Propose Drop, MOCN Drop |  | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-02 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-PBG-8443_1 | Modernize_JAW-JT-PBG-8443 | JAW-JT-PBG-8443 | Central Java | Jawa Tengah | Purbalingga | -7.3247 | 109.3502 | Swap | Swap Only | Modernize | Type A | MA | ZYKT_0077 | #N/A |  |  | #N/A | YKT_6150_ZTE_2301 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Propose Drop, MOCN Drop |  | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-03 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-PBG-8455_1 | Modernize_JAW-JT-PBG-8455 | JAW-JT-PBG-8455 | Central Java | Jawa Tengah | Purbalingga | -7.378 | 109.3728 | Swap | Swap Only | Modernize | Type A | MA | ZYKT_0108 | #N/A |  |  | #N/A | YKT_6150_ZTE_3833 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Propose Drop, MOCN Drop |  | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-03 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-BNR-8348_1 | Modernize_JAW-JT-BNR-8348 | JAW-JT-BNR-8348 | Central Java | Jawa Tengah | Banjarnegara | -7.3944 | 109.7652 | Swap | Swap Only | Modernize | Type A | MA | ZYKT_0087 | #N/A |  |  | #N/A | YKT_6150_ZTE_2311 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Keep |  | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-04 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-KJN-8420_1 | Modernize_JAW-JT-KJN-8420 | JAW-JT-KJN-8420 | Central Java | Jawa Tengah | Pekalongan | -6.884 | 109.6205 | Swap | Swap Only | Modernize | Type A | MA | ZSMG_0158 | #N/A |  |  | #N/A | SMG_6150_ZTE_3835 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Propose Drop, MOCN Drop |  | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-04 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-BLA-8321_1 | Modernize_JAW-JT-BLA-8321 | JAW-JT-BLA-8321 | Central Java | Jawa Tengah | Blora | -7.1574 | 111.5312 | Swap | Swap Only | Modernize | Type A | MA | ZSMG_0117 | #N/A |  |  | #N/A | SMG_6150_ZTE_2256 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Propose Drop,Double Scope |  | 0 | [9 empty] | #N/A |  |  | 2026 | Plan Swap December |  | 2026-02-05 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-WSB-8482_1 | Modernize_JAW-JT-WSB-8482 | JAW-JT-WSB-8482 | Central Java | Jawa Tengah | Wonosobo | -7.3539 | 109.8893 | Swap | Swap Only | Modernize | Type A | MA | ZYKT_0111 | #N/A |  |  | #N/A | YKT_6150_ZTE_3842 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Keep |  | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-05 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-PWR-8552_1 | Modernize_JAW-JT-PWR-8552 | JAW-JT-PWR-8552 | Central Java | Jawa Tengah | Purworejo | -7.7148 | 110.0148 | Swap | Swap Only | Modernize | Type A | MA | ZYKT_0132 | #N/A |  |  | #N/A | YKT_6150_ZTE_3883 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Keep |  | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-06 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-KBM-8532_1 | Modernize_JAW-JT-KBM-8532 | JAW-JT-KBM-8532 | Central Java | Jawa Tengah | Kebumen | -7.7219 | 109.8055 | Swap | Swap Only | Modernize | Type A | MA | ZYKT_0064 | #N/A |  |  | #N/A | YKT_6150_ZTE_2288 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Propose Drop,Double Scope |  | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-06 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Modernize_JAW-JT-KBM-8457_1 | Modernize_JAW-JT-KBM-8457 | JAW-JT-KBM-8457 | Central Java | Jawa Tengah | Kebumen | -7.6342 | 109.5743 | Swap | Swap Only | Modernize | Type A | MA | ZYKT_0065 | #N/A |  |  | #N/A | YKT_6150_ZTE_2289 | #N/A | ZXCTN 6150 | ZTE | Redeploy | Modernize ZTE Reuse 6120H-WA | Keep |  | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-09 | 7 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BTG-8319_1 | New_JAW-JT-BTG-8319 | JAW-JT-BTG-8319 | Central Java | Jawa Tengah | Batang | -6.9923 | 109.9421 | Insert | New | New | Type B | MA | JAW-JT-BTG-8319 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-20 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-MGG-3528_1 | New_JAW-JT-MGG-3528 | JAW-JT-MGG-3528 | Central Java | Jawa Tengah | Kota Magelang | -7.4755 | 110.2182 | Insert | New | New | Type B | MA | JAW-JT-MGG-3528 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-20 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PTI-8507_1 | New_JAW-JT-PTI-8507 | JAW-JT-PTI-8507 | Central Java | Jawa Tengah | Pati | -6.8327 | 111.0569 | Insert | New | New | Type B | MA | JAW-JT-PTI-8507 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-20 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8363_1 | New_JAW-JT-PWT-8363 | JAW-JT-PWT-8363 | Central Java | Jawa Tengah | Banyumas | -7.4134 | 109.2679 | Insert | New | New | Type B | MA | JAW-JT-PWT-8363 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-20 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8416_1 | New_JAW-JT-PWT-8416 | JAW-JT-PWT-8416 | Central Java | Jawa Tengah | Banyumas | -7.5139 | 109.0592 | Insert | New | New | Type B | MA | JAW-JT-PWT-8416 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-20 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-TGL-8307_1 | New_JAW-JT-TGL-8307 | JAW-JT-TGL-8307 | Central Java | Jawa Tengah | Kota Tegal | -6.8535 | 109.1431 | Insert | New | New | Type B | MA | JAW-JT-TGL-8307 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-20 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-TMG-8549_1 | New_JAW-JT-TMG-8549 | JAW-JT-TMG-8549 | Central Java | Jawa Tengah | Temanggung | -7.3343 | 110.1554 | Insert | New | New | Type B | MA | JAW-JT-TMG-8549 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-20 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8563_1 | New_JAW-JT-SMG-8563 | JAW-JT-SMG-8563 | Central Java | Jawa Tengah | Kota Semarang | -7.0018 | 110.4334 | Insert | New | New | Type B | MA | JAW-JT-SMG-8563 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2025-10-20 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SGN-8512_1 | New_JAW-JT-SGN-8512 | JAW-JT-SGN-8512 | Central Java | Jawa Tengah | Sragen | -7.4188 | 110.9122 | Insert | New | New | Type B | MA | JAW-JT-SGN-8512 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-20 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SGN-8511_1 | New_JAW-JT-SGN-8511 | JAW-JT-SGN-8511 | Central Java | Jawa Tengah | Sragen | -7.3849 | 110.9114 | Insert | New | New | Type B | MA | JAW-JT-SGN-8511 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-20 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SKH-8514_1 | New_JAW-JT-SKH-8514 | JAW-JT-SKH-8514 | Central Java | Jawa Tengah | Sukoharjo | -7.7071 | 110.8326 | Insert | New | New | Type B | MA | JAW-JT-SKH-8514 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-20 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BTG-8325_1 | New_JAW-JT-BTG-8325 | JAW-JT-BTG-8325 | Central Java | Jawa Tengah | Batang | -6.971 | 109.967 | Insert | New | New | Type B | MA | JAW-JT-BTG-8325 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-20 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-WNG-8564_1 | New_JAW-JT-WNG-8564 | JAW-JT-WNG-8564 | Central Java | Jawa Tengah | Wonogiri | -7.8194 | 111.0671 | Insert | New | New | Type B | MA | JAW-JT-WNG-8564 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-20 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8297_1 | New_JAW-JT-DMK-8297 | JAW-JT-DMK-8297 | Central Java | Jawa Tengah | Demak | -7.0556 | 110.5048 | Insert | New | New | Type B | MA | JAW-JT-DMK-8297 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-21 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8501_1 | New_JAW-JT-SMG-8501 | JAW-JT-SMG-8501 | Central Java | Jawa Tengah | Kota Semarang | -6.9726 | 110.42 | Insert | New | New | Type B | MA | JAW-JT-SMG-8501 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2025-10-21 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8441_1 | New_JAW-JT-KDS-8441 | JAW-JT-KDS-8441 | Central Java | Jawa Tengah | Kudus | -6.8018 | 110.8775 | Insert | New | New | Type B | MA | JAW-JT-KDS-8441 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-21 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BYL-8265_1 | New_JAW-JT-BYL-8265 | JAW-JT-BYL-8265 | Central Java | Jawa Tengah | Boyolali | -7.536 | 110.5961 | Insert | New | New | Type B | MA | JAW-JT-BYL-8265 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-21 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SGN-8574_1 | New_JAW-JT-SGN-8574 | JAW-JT-SGN-8574 | Central Java | Jawa Tengah | Sragen | -7.3971 | 111.0689 | Insert | New | New | Type B | MA | JAW-JT-SGN-8574 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-21 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3115_1 | New_JAW-JI-BKL-3115 | JAW-JI-BKL-3115 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9211 | 110.3803 | Insert | New | New | Type B | MA | JAW-JI-BKL-3115 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-21 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-SMN-8343_1 | New_JAW-YO-SMN-8343 | JAW-YO-SMN-8343 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.677 | 110.3375 | Insert | New | New | Type B | MA | JAW-YO-SMN-8343 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-21 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-MKD-8402_1 | New_JAW-JT-MKD-8402 | JAW-JT-MKD-8402 | Central Java | Jawa Tengah | Magelang | -7.6001 | 110.2107 | Insert | New | New | Type B | MA | JAW-JT-MKD-8402 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-21 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-MKD-8439_1 | New_JAW-JT-MKD-8439 | JAW-JT-MKD-8439 | Central Java | Jawa Tengah | Magelang | -7.3895 | 110.2557 | Insert | New | New | Type B | MA | JAW-JT-MKD-8439 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-21 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BNR-8352_1 | New_JAW-JT-BNR-8352 | JAW-JT-BNR-8352 | Central Java | Jawa Tengah | Banjarnegara | -7.4166 | 109.816 | Insert | New | New | Type B | MA | JAW-JT-BNR-8352 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | 2025-11-02 | [5 empty] | 2025-10-21 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3124_1 | New_JAW-JI-BKL-3124 | JAW-JI-BKL-3124 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9631 | 110.2674 | Insert | New | New | Type B | MA | JAW-JI-BKL-3124 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-21 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8332_1 | New_JAW-JT-PWT-8332 | JAW-JT-PWT-8332 | Central Java | Jawa Tengah | Banyumas | -7.4086 | 109.2347 | Insert | New | New | Type B | MA | JAW-JT-PWT-8332 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-21 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8358_1 | New_JAW-JT-PWT-8358 | JAW-JT-PWT-8358 | Central Java | Jawa Tengah | Banyumas | -7.4436 | 109.2733 | Insert | New | New | Type B | MA | JAW-JT-PWT-8358 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-21 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8315_1 | New_JAW-JT-PWT-8315 | JAW-JT-PWT-8315 | Central Java | Jawa Tengah | Banyumas | -7.4898 | 109.2306 | Insert | New | New | Type B | MA | JAW-JT-PWT-8315 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-22 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8469_1 | New_JAW-JT-PWT-8469 | JAW-JT-PWT-8469 | Central Java | Jawa Tengah | Banyumas | -7.5069 | 109.0219 | Insert | New | New | Type B | MA | JAW-JT-PWT-8469 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-22 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8447_1 | New_JAW-JT-PWT-8447 | JAW-JT-PWT-8447 | Central Java | Jawa Tengah | Banyumas | -7.3564 | 109.1099 | Insert | New | New | Type B | MA | JAW-JT-PWT-8447 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-22 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BTG-8282_1 | New_JAW-JT-BTG-8282 | JAW-JT-BTG-8282 | Central Java | Jawa Tengah | Batang | -6.9086 | 109.7434 | Insert | New | New | Type B | MA | JAW-JT-BTG-8282 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-22 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PTI-8545_1 | New_JAW-JT-PTI-8545 | JAW-JT-PTI-8545 | Central Java | Jawa Tengah | Pati | -6.7577 | 111.1238 | Insert | New | New | Type B | MA | JAW-JT-PTI-8545 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | 2025-11-13 | [5 empty] | 2025-10-22 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BBS-9171_1 | New_JAW-JT-BBS-9171 | JAW-JT-BBS-9171 | Central Java | Jawa Tengah | Brebes | -6.8453 | 108.8184 | Insert | New | New | Type B | MA | JAW-JT-BBS-9171 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-22 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BBS-9172_1 | New_JAW-JT-BBS-9172 | JAW-JT-BBS-9172 | Central Java | Jawa Tengah | Brebes | -6.8688 | 108.8877 | Insert | New | New | Type B | MA | JAW-JT-BBS-9172 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-22 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8419_1 | New_JAW-JT-CLP-8419 | JAW-JT-CLP-8419 | Central Java | Jawa Tengah | Cilacap | -7.6689 | 109.2682 | Insert | New | New | Type B | MA | JAW-JT-CLP-8419 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-22 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8481_1 | New_JAW-JT-CLP-8481 | JAW-JT-CLP-8481 | Central Java | Jawa Tengah | Cilacap | -7.5917 | 109.1169 | Insert | New | New | Type B | MA | JAW-JT-CLP-8481 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-22 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8509_1 | New_JAW-JT-CLP-8509 | JAW-JT-CLP-8509 | Central Java | Jawa Tengah | Cilacap | -7.3309 | 108.654 | Insert | New | New | Type B | MA | JAW-JT-CLP-8509 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-22 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8510_1 | New_JAW-JT-CLP-8510 | JAW-JT-CLP-8510 | Central Java | Jawa Tengah | Cilacap | -7.6113 | 108.9297 | Insert | New | New | Type B | MA | JAW-JT-CLP-8510 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-22 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8525_1 | New_JAW-JT-CLP-8525 | JAW-JT-CLP-8525 | Central Java | Jawa Tengah | Cilacap | -7.2941 | 108.7361 | Insert | New | New | Type B | MA | JAW-JT-CLP-8525 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-22 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8245_1 | New_JAW-JT-BLA-8245 | JAW-JT-BLA-8245 | Central Java | Jawa Tengah | Blora | -7.0341 | 111.3811 | Insert | New | New | Type B | MA | JAW-JT-BLA-8245 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-10-22 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8275_1 | New_JAW-JT-BLA-8275 | JAW-JT-BLA-8275 | Central Java | Jawa Tengah | Blora | -6.9462 | 111.4286 | Insert | New | New | Type B | MA | JAW-JT-BLA-8275 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-10-23 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KBM-8532_1 | New_JAW-JT-KBM-8532 | JAW-JT-KBM-8532 | Central Java | Jawa Tengah | Kebumen | -7.7219 | 109.8055 | Insert | New | New | Type B | MA | JAW-JT-KBM-8532 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-23 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-RBG-8477_1 | New_JAW-JT-RBG-8477 | JAW-JT-RBG-8477 | Central Java | Jawa Tengah | Rembang | -6.6349 | 111.4864 | Insert | New | New | Type B | MA | JAW-JT-RBG-8477 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-23 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8473_1 | New_JAW-JT-KDS-8473 | JAW-JT-KDS-8473 | Central Java | Jawa Tengah | Kudus | -6.7968 | 110.9451 | Insert | New | New | Type B | MA | JAW-JT-KDS-8473 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-10-23 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SKT-8495_1 | New_JAW-JT-SKT-8495 | JAW-JT-SKT-8495 | Central Java | Jawa Tengah | Kota Surakarta | -7.5577 | 110.794 | Insert | New | New | Type B | MA | JAW-JT-SKT-8495 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2025-10-23 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8375_1 | New_JAW-JT-DMK-8375 | JAW-JT-DMK-8375 | Central Java | Jawa Tengah | Demak | -7.016 | 110.5956 | Insert | New | New | Type B | MA | JAW-JT-DMK-8375 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-10-23 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8320_1 | New_JAW-JT-PWD-8320 | JAW-JT-PWD-8320 | Central Java | Jawa Tengah | Grobogan | -7.0539 | 110.6643 | Insert | New | New | Type B | MA | JAW-JT-PWD-8320 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-10-23 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8438_1 | New_JAW-JT-UNR-8438 | JAW-JT-UNR-8438 | Central Java | Jawa Tengah | Semarang | -7.1967 | 110.3884 | Insert | New | New | Type B | MA | JAW-JT-UNR-8438 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | Mid Dec 25 | FO NY RFS |  | 2025-10-23 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3161_1 | New_JAW-JI-BKL-3161 | JAW-JI-BKL-3161 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8041 | 110.4128 | Insert | New | New | Type B | MA | JAW-JI-BKL-3161 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-23 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8290_1 | New_JAW-YO-YYK-8290 | JAW-YO-YYK-8290 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8222 | 110.3519 | Insert | New | New | Type B | MA | JAW-YO-YYK-8290 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2025-10-23 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3143_1 | New_JAW-JI-BKL-3143 | JAW-JI-BKL-3143 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8057 | 110.345 | Insert | New | New | Type B | MA | JAW-JI-BKL-3143 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-23 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8284_1 | New_JAW-JT-BLA-8284 | JAW-JT-BLA-8284 | Central Java | Jawa Tengah | Blora | -7.1949 | 111.4411 | Insert | New | New | Type B | MA | JAW-JT-BLA-8284 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-10-23 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8321_1 | New_JAW-JT-BLA-8321 | JAW-JT-BLA-8321 | Central Java | Jawa Tengah | Blora | -7.1574 | 111.5312 | Insert | New | New | Type B | MA | JAW-JT-BLA-8321 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-10-23 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8543_1 | New_JAW-JT-PWD-8543 | JAW-JT-PWD-8543 | Central Java | Jawa Tengah | Grobogan | -7.0796 | 111.0813 | Insert | New | New | Type B | MA | JAW-JT-PWD-8543 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-10-24 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8571_1 | New_JAW-JT-PWD-8571 | JAW-JT-PWD-8571 | Central Java | Jawa Tengah | Grobogan | -7.1343 | 111.1399 | Insert | New | New | Type B | MA | JAW-JT-PWD-8571 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-10-24 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BNR-8323_1 | New_JAW-JT-BNR-8323 | JAW-JT-BNR-8323 | Central Java | Jawa Tengah | Banjarnegara | -7.3694 | 109.6645 | Insert | New | New | Type B | MA | JAW-JT-BNR-8323 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-24 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8471_1 | New_JAW-JT-PWT-8471 | JAW-JT-PWT-8471 | Central Java | Jawa Tengah | Banyumas | -7.4187 | 109.1903 | Insert | New | New | Type B | MA | JAW-JT-PWT-8471 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-24 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-4154_1 | New_JAW-JT-SMG-4154 | JAW-JT-SMG-4154 | Central Java | Jawa Tengah | Kota Semarang | -6.9867 | 110.4236 | Insert | New | New | Type B | MA | JAW-JT-SMG-4154 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, MOCN Drop | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-24 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PTI-8421_1 | New_JAW-JT-PTI-8421 | JAW-JT-PTI-8421 | Central Java | Jawa Tengah | Pati | -6.9176 | 110.9102 | Insert | New | New | Type B | MA | JAW-JT-PTI-8421 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | 2025-10-09 | [5 empty] | 2025-10-24 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8387_1 | New_JAW-JT-DMK-8387 | JAW-JT-DMK-8387 | Central Java | Jawa Tengah | Demak | -6.9477 | 110.6124 | Insert | New | New | Type B | MA | JAW-JT-DMK-8387 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-10-24 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-RBG-8479_1 | New_JAW-JT-RBG-8479 | JAW-JT-RBG-8479 | Central Java | Jawa Tengah | Rembang | -6.7591 | 111.4912 | Insert | New | New | Type B | MA | JAW-JT-RBG-8479 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-24 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-MKD-8447_1 | New_JAW-JT-MKD-8447 | JAW-JT-MKD-8447 | Central Java | Jawa Tengah | Magelang | -7.4277 | 110.2697 | Insert | New | New | Type B | MA | JAW-JT-MKD-8447 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-24 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8287_1 | New_JAW-JT-DMK-8287 | JAW-JT-DMK-8287 | Central Java | Jawa Tengah | Demak | -7.0283 | 110.4964 | Insert | New | New | Type B | MA | JAW-JT-DMK-8287 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-10-24 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-RBG-8499_1 | New_JAW-JT-RBG-8499 | JAW-JT-RBG-8499 | Central Java | Jawa Tengah | Rembang | -6.7684 | 111.5725 | Insert | New | New | Type B | MA | JAW-JT-RBG-8499 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-24 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8339_1 | New_JAW-JT-DMK-8339 | JAW-JT-DMK-8339 | Central Java | Jawa Tengah | Demak | -7.0566 | 110.5448 | Insert | New | New | Type B | MA | JAW-JT-DMK-8339 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-10-24 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8384_1 | New_JAW-JT-KDS-8384 | JAW-JT-KDS-8384 | Central Java | Jawa Tengah | Kudus | -6.8074 | 110.8235 | Insert | New | New | Type B | MA | JAW-JT-KDS-8384 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-10-24 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PTI-8526_1 | New_JAW-JT-PTI-8526 | JAW-JT-PTI-8526 | Central Java | Jawa Tengah | Pati | -6.5922 | 111.0679 | Insert | New | New | Type B | MA | JAW-JT-PTI-8526 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-27 | 44 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KRG-8289_1 | New_JAW-JT-KRG-8289 | JAW-JT-KRG-8289 | Central Java | Jawa Tengah | Karanganyar | -7.5407 | 110.8965 | Insert | New | New | Type B | MA | JAW-JT-KRG-8289 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-27 | 44 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BYL-8336_1 | New_JAW-JT-BYL-8336 | JAW-JT-BYL-8336 | Central Java | Jawa Tengah | Boyolali | -7.3639 | 110.7399 | Insert | New | New | Type B | MA | JAW-JT-BYL-8336 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-27 | 44 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8335_1 | New_JAW-JT-JPA-8335 | JAW-JT-JPA-8335 | Central Java | Jawa Tengah | Jepara | -6.5962 | 110.6869 | Insert | New | New | Type B | MA | JAW-JT-JPA-8335 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | 2025-10-05 |  |  | 2026 | FO NY RFS |  | 2025-10-27 | 44 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8561_1 | New_JAW-JT-PWD-8561 | JAW-JT-PWD-8561 | Central Java | Jawa Tengah | Grobogan | -7.1352 | 111.1119 | Insert | New | New | Type B | MA | JAW-JT-PWD-8561 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Propose Drop, NO SPK | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-10-27 | 44 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SGN-8448_1 | New_JAW-JT-SGN-8448 | JAW-JT-SGN-8448 | Central Java | Jawa Tengah | Sragen | -7.4121 | 110.7821 | Insert | New | New | Type B | MA | JAW-JT-SGN-8448 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | 2025-11-02 |  |  |  |  | DCITS | 2025-10-27 | 44 | October |  | 2025 | 2025-11-22 |  |  |  |  | Submitted | Approved | Done |  | Done | Done | Done | DOEID251117OI |  | 2005-11-22 | Done | Done | Done | Done | Done | Done | DCITS | 2025-11-21 | 47 | 2025-11-22 | [13 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SGN-8542_1 | New_JAW-JT-SGN-8542 | JAW-JT-SGN-8542 | Central Java | Jawa Tengah | Sragen | -7.4311 | 110.9901 | Insert | New | New | Type B | MA | JAW-JT-SGN-8542 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-27 | 44 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BYL-8252_1 | New_JAW-JT-BYL-8252 | JAW-JT-BYL-8252 | Central Java | Jawa Tengah | Boyolali | -7.4655 | 110.5544 | Insert | New | New | Type B | MA | JAW-JT-BYL-8252 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2025-10-27 | 44 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SKT-8513_1 | New_JAW-JT-SKT-8513 | JAW-JT-SKT-8513 | Central Java | Jawa Tengah | Kota Surakarta | -7.5524 | 110.8136 | Insert | New | New | Type B | MA | JAW-JT-SKT-8513 |  |  |  |  | - | - | - | - | New Purchase | Modernize ZTE | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | 2025-11-16 |  |  | 2025-End Nov | FO NY RFS |  | 2025-10-27 | 44 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-1010_1 | New_JAW-JT-KDL-1010 | JAW-JT-KDL-1010 | Central Java | Jawa Tengah | Kendal | -6.9822 | 110.0712 | New | New | New | Type B | MA | JAW-JT-KDL-1010 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | S000055600 | S000055601 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-10-27 | 44 | October |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4206_1 | New_JAW-JT-KDL-4206 | JAW-JT-KDL-4206 | Central Java | Jawa Tengah | Kendal | -7.0301 | 110.0483 | New | New | New | Type B | MA | JAW-JT-KDL-4206 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | S000055601 | S000055602 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-10-27 | 44 | October |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4209_1 | New_JAW-JT-KDL-4209 | JAW-JT-KDL-4209 | Central Java | Jawa Tengah | Kendal | -7.0502 | 110.0529 | New | New | New | Type B | MA | JAW-JT-KDL-4209 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | S000055602 | S000055603 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-10-27 | 44 | October |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-3481_1 | New_JAW-JT-KDL-3481 | JAW-JT-KDL-3481 | Central Java | Jawa Tengah | Kendal | -7.0363 | 109.9992 | New | New | New | Type B | MA | JAW-JT-KDL-3481 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | S000055603 | S000055604 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-10-27 | 44 | October |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4025_1 | New_JAW-JT-KDL-4025 | JAW-JT-KDL-4025 | Central Java | Jawa Tengah | Kendal | -7.0662 | 109.9859 | New | New | New | Type B | MA | JAW-JT-KDL-4025 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | S000055604 | S000055605 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-10-28 | 44 | October |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4361_1 | New_JAW-JT-KDL-4361 | JAW-JT-KDL-4361 | Central Java | Jawa Tengah | Kendal | -7.1002 | 109.9678 | New | New | New | Type B | MA | JAW-JT-KDL-4361 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | S000055605 | S000055606 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-10-28 | 44 | October |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-3480_1 | New_JAW-JT-KDL-3480 | JAW-JT-KDL-3480 | Central Java | Jawa Tengah | Kendal | -7.1183 | 109.9627 | New | New | New | Type B | MA | JAW-JT-KDL-3480 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | S000055606 | S000055607 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-10-28 | 44 | October |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4153_1 | New_JAW-JT-KDL-4153 | JAW-JT-KDL-4153 | Central Java | Jawa Tengah | Kendal | -7.1003 | 110.0244 | New | New | New | Type B | MA | JAW-JT-KDL-4153 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | S000055607 | S000055595 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-10-28 | 44 | October |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4019_1 | New_JAW-JT-KDL-4019 | JAW-JT-KDL-4019 | Central Java | Jawa Tengah | Kendal | -7.1158 | 110.0158 | New | New | New | Type B | MA | JAW-JT-KDL-4019 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | S000055595 | S000055596 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-10-28 | 44 | October |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4126_1 | New_JAW-JT-KDL-4126 | JAW-JT-KDL-4126 | Central Java | Jawa Tengah | Kendal | -7.1348 | 109.9971 | New | New | New | Type B | MA | JAW-JT-KDL-4126 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | S000055596 | S000055597 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-10-28 | 44 | October |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0772_1 | New_JAW-JT-KDL-0772 | JAW-JT-KDL-0772 | Central Java | Jawa Tengah | Kendal | -7.1719 | 109.985 | New | New | New | Type B | MA | JAW-JT-KDL-0772 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | S000055597 | S000055598 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-10-28 | 44 | October |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4167_1 | New_JAW-JT-KDL-4167 | JAW-JT-KDL-4167 | Central Java | Jawa Tengah | Kendal | -7.1382 | 110.0307 | New | New | New | Type B | MA | JAW-JT-KDL-4167 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | S000055598 | S000055599 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-10-28 | 44 | October |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0776_1 | New_JAW-JT-KDL-0776 | JAW-JT-KDL-0776 | Central Java | Jawa Tengah | Kendal | -7.1203 | 110.0338 | New | New | New | Type B | MA | JAW-JT-KDL-0776 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | S000055599 | S000055590 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-10-28 | 44 | October |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4204_1 | New_JAW-JT-KDL-4204 | JAW-JT-KDL-4204 | Central Java | Jawa Tengah | Kendal | -7.0825 | 110.0448 | New | New | New | Type B | MA | JAW-JT-KDL-4204 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | S000055590 | S000055591 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-10-28 | 44 | October |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4211_1 | New_JAW-JT-KDL-4211 | JAW-JT-KDL-4211 | Central Java | Jawa Tengah | Kendal | -7.0628 | 110.0608 | New | New | New | Type B | MA | JAW-JT-KDL-4211 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | S000055591 | S000055592 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-10-28 | 44 | October |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4245_1 | New_JAW-JT-KDL-4245 | JAW-JT-KDL-4245 | Central Java | Jawa Tengah | Kendal | -7.0907 | 110.1446 | New | New | New | Type B | MA | JAW-JT-KDL-4245 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | S000055592 | S000055593 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-10-28 | 44 | October |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0712_1 | New_JAW-JT-KDL-0712 | JAW-JT-KDL-0712 | Central Java | Jawa Tengah | Kendal | -7.0829 | 110.2114 | New | New | New | Type B | MA | JAW-JT-KDL-0712 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_6 2x10G ZR + 6x10G/1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | S000055593 | S000055594 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-10-28 | 44 | October |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4143_1 | New_JAW-JT-KDL-4143 | JAW-JT-KDL-4143 | Central Java | Jawa Tengah | Kendal | -7.0285 | 110.2003 | New | New | New | Type B | MA | JAW-JT-KDL-4143 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | S000055594 | S000055608 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-05 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0713_1 | New_JAW-JT-KDL-0713 | JAW-JT-KDL-0713 | Central Java | Jawa Tengah | Kendal | -6.971 | 110.2635 | New | New | New | Type B | MA | JAW-JT-KDL-0713 |  |  |  |  | - | - | - | - | New Purchase | New Ring 001 | Keep | 1 | Bundle_Type B_3 1x25G/10G LR + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020393 | S000055608 | S000055609 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-05 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-3197_1 | New_JAW-JT-KDL-3197 | JAW-JT-KDL-3197 | Central Java | Jawa Tengah | Kendal | -6.9591 | 110.2551 | New | New | New | Type B | MA | JAW-JT-KDL-3197 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | S000055610 | S000055611 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-05 | 45 |  |  | 2025 | [5 empty] | Submitted | Submitted | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4164_1 | New_JAW-JT-KDL-4164 | JAW-JT-KDL-4164 | Central Java | Jawa Tengah | Kendal | -6.9668 | 110.2449 | New | New | New | Type B | MA | JAW-JT-KDL-4164 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | S000055611 | S000055612 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-05 | 45 |  |  | 2025 | [36 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4006_1 | New_JAW-JT-KDL-4006 | JAW-JT-KDL-4006 | Central Java | Jawa Tengah | Kendal | -6.9652 | 110.2409 | New | New | New | Type B | MA | JAW-JT-KDL-4006 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | S000055612 | S000055613 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-05 | 45 |  |  | 2025 | [5 empty] | Submitted | Submitted | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4148_1 | New_JAW-JT-KDL-4148 | JAW-JT-KDL-4148 | Central Java | Jawa Tengah | Kendal | -6.9395 | 110.2105 | New | New | New | Type B | MA | JAW-JT-KDL-4148 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | S000055613 | S000055614 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-05 | 45 |  |  | 2025 | [36 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-3474_1 | New_JAW-JT-KDL-3474 | JAW-JT-KDL-3474 | Central Java | Jawa Tengah | Kendal | -6.9212 | 110.1983 | New | New | New | Type B | MA | JAW-JT-KDL-3474 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | S000055614 | S000055615 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-05 | 45 |  |  | 2025 | [5 empty] | Submitted | Submitted | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4135_1 | New_JAW-JT-KDL-4135 | JAW-JT-KDL-4135 | Central Java | Jawa Tengah | Kendal | -6.9107 | 110.1792 | New | New | New | Type B | MA | JAW-JT-KDL-4135 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | S000055615 | S000055616 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-05 | 45 |  |  | 2025 | [36 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4029_1 | New_JAW-JT-KDL-4029 | JAW-JT-KDL-4029 | Central Java | Jawa Tengah | Kendal | -6.9407 | 110.1939 | New | New | New | Type B | MA | JAW-JT-KDL-4029 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | S000055616 | S000055617 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-05 | 45 |  |  | 2025 | [5 empty] | Submitted | Submitted | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4136_1 | New_JAW-JT-KDL-4136 | JAW-JT-KDL-4136 | Central Java | Jawa Tengah | Kendal | -6.9495 | 110.1809 | New | New | New | Type B | MA | JAW-JT-KDL-4136 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | S000055617 | S000055618 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-05 | 45 |  |  | 2025 | [36 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-1023_1 | New_JAW-JT-KDL-1023 | JAW-JT-KDL-1023 | Central Java | Jawa Tengah | Kendal | -6.9686 | 110.1619 | New | New | New | Type B | MA | JAW-JT-KDL-1023 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | S000055618 | S000055619 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-05 | 45 |  |  | 2025 | [5 empty] | Submitted | Submitted | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4137_1 | New_JAW-JT-KDL-4137 | JAW-JT-KDL-4137 | Central Java | Jawa Tengah | Kendal | -6.985 | 110.1872 | New | New | New | Type B | MA | JAW-JT-KDL-4137 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | S000055619 | S000055620 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-05 | 45 |  |  | 2025 | [36 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4238_1 | New_JAW-JT-KDL-4238 | JAW-JT-KDL-4238 | Central Java | Jawa Tengah | Kendal | -6.9667 | 110.1278 | New | New | New | Type B | MA | JAW-JT-KDL-4238 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | S000055620 | S000055621 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-05 | 45 |  |  | 2025 | [5 empty] | Submitted | Submitted | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-1025_1 | New_JAW-JT-KDL-1025 | JAW-JT-KDL-1025 | Central Java | Jawa Tengah | Kendal | -6.9654 | 110.0968 | New | New | New | Type B | MA | JAW-JT-KDL-1025 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | S000055621 | S000055622 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-06 | 45 |  |  | 2025 | [36 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4216_1 | New_JAW-JT-KDL-4216 | JAW-JT-KDL-4216 | Central Java | Jawa Tengah | Kendal | -6.9549 | 110.0659 | New | New | New | Type B | MA | JAW-JT-KDL-4216 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | S000055622 | S000055623 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-06 | 45 |  |  | 2025 | [5 empty] | Submitted | Submitted | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0783_1 | New_JAW-JT-KDL-0783 | JAW-JT-KDL-0783 | Central Java | Jawa Tengah | Kendal | -6.9698 | 110.0518 | New | New | New | Type B | MA | JAW-JT-KDL-0783 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | S000055623 | S000055624 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-06 | 45 |  |  | 2025 | [36 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4219_1 | New_JAW-JT-KDL-4219 | JAW-JT-KDL-4219 | Central Java | Jawa Tengah | Kendal | -6.9676 | 110.0737 | New | New | New | Type B | MA | JAW-JT-KDL-4219 |  |  |  |  | - | - | - | - | New Purchase | New Ring 002 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020394 | S000055624 | S000055625 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-06 | 45 |  |  | 2025 | [5 empty] | Submitted | Submitted | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-3317_1 | New_JAW-JT-KDL-3317 | JAW-JT-KDL-3317 | Central Java | Jawa Tengah | Kendal | -7.0941 | 110.3461 | New | New | New | Type B | MA | JAW-JT-KDL-3317 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | S000055626 | S000055627 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-06 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0871_1 | New_JAW-JT-KDL-0871 | JAW-JT-KDL-0871 | Central Java | Jawa Tengah | Kendal | -7.0619 | 110.2861 | New | New | New | Type B | MA | JAW-JT-KDL-0871 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | S000055627 | S000055628 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-06 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4195_1 | New_JAW-JT-KDL-4195 | JAW-JT-KDL-4195 | Central Java | Jawa Tengah | Kendal | -7.0876 | 110.2851 | New | New | New | Type B | MA | JAW-JT-KDL-4195 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | S000055628 | S000055629 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-06 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4187_1 | New_JAW-JT-KDL-4187 | JAW-JT-KDL-4187 | Central Java | Jawa Tengah | Kendal | -7.0957 | 110.2883 | New | New | New | Type B | MA | JAW-JT-KDL-4187 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | S000055629 | S000055630 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  |  |  |  | 2025-11-06 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4189_1 | New_JAW-JT-KDL-4189 | JAW-JT-KDL-4189 | Central Java | Jawa Tengah | Kendal | -7.1004 | 110.2931 | New | New | New | Type B | MA | JAW-JT-KDL-4189 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | S000055630 | S000055631 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2026 | FO NY RFS | CCSI | 2025-11-06 | 45 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-24 | 48 | 2025-11-24 |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-JT-KDL-4202_1 | New_JAW-JT-KDL-4202 | JAW-JT-KDL-4202 | Central Java | Jawa Tengah | Kendal | -7.1176 | 110.3321 | New | New | New | Type B | MA | JAW-JT-KDL-4202 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | S000055631 | S000055632 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-06 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4199_1 | New_JAW-JT-KDL-4199 | JAW-JT-KDL-4199 | Central Java | Jawa Tengah | Kendal | -7.1248 | 110.3219 | New | New | New | Type B | MA | JAW-JT-KDL-4199 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | S000055632 | S000055633 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-06 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0876_1 | New_JAW-JT-KDL-0876 | JAW-JT-KDL-0876 | Central Java | Jawa Tengah | Kendal | -7.1384 | 110.3243 | New | New | New | Type B | MA | JAW-JT-KDL-0876 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | S000055633 | S000055634 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-06 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4197_1 | New_JAW-JT-KDL-4197 | JAW-JT-KDL-4197 | Central Java | Jawa Tengah | Kendal | -7.1357 | 110.301 | New | New | New | Type B | MA | JAW-JT-KDL-4197 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | S000055634 | S000055635 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-06 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4191_1 | New_JAW-JT-KDL-4191 | JAW-JT-KDL-4191 | Central Java | Jawa Tengah | Kendal | -7.1595 | 110.285 | New | New | New | Type B | MA | JAW-JT-KDL-4191 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | S000055635 | S000055636 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-07 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-3365_1 | New_JAW-JT-KDL-3365 | JAW-JT-KDL-3365 | Central Java | Jawa Tengah | Kendal | -7.1787 | 110.2805 | New | New | New | Type B | MA | JAW-JT-KDL-3365 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | S000055636 | S000055637 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-07 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0861_1 | New_JAW-JT-KDL-0861 | JAW-JT-KDL-0861 | Central Java | Jawa Tengah | Kendal | -7.1638 | 110.2536 | New | New | New | Type B | MA | JAW-JT-KDL-0861 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | S000055637 | S000055638 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-07 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0842_1 | New_JAW-JT-KDL-0842 | JAW-JT-KDL-0842 | Central Java | Jawa Tengah | Kendal | -7.1524 | 110.1983 | New | New | New | Type B | MA | JAW-JT-KDL-0842 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | S000055638 | S000055639 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-07 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0830_1 | New_JAW-JT-KDL-0830 | JAW-JT-KDL-0830 | Central Java | Jawa Tengah | Kendal | -7.1301 | 110.1684 | New | New | New | Type B | MA | JAW-JT-KDL-0830 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | S000055639 | S000055640 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-07 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-0704_1 | New_JAW-JT-KDL-0704 | JAW-JT-KDL-0704 | Central Java | Jawa Tengah | Kendal | -7.1209 | 110.218 | New | New | New | Type B | MA | JAW-JT-KDL-0704 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | S000055640 | S000055641 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-07 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4173_1 | New_JAW-JT-KDL-4173 | JAW-JT-KDL-4173 | Central Java | Jawa Tengah | Kendal | -7.0551 | 110.257 | New | New | New | Type B | MA | JAW-JT-KDL-4173 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | S000055641 | S000055642 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-07 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4003_1 | New_JAW-JT-KDL-4003 | JAW-JT-KDL-4003 | Central Java | Jawa Tengah | Kendal | -6.9884 | 110.2577 | New | New | New | Type B | MA | JAW-JT-KDL-4003 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | S000055642 | S000055643 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-07 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4015_1 | New_JAW-JT-KDL-4015 | JAW-JT-KDL-4015 | Central Java | Jawa Tengah | Kendal | -6.9754 | 110.2546 | New | New | New | Type B | MA | JAW-JT-KDL-4015 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | S000055643 | S000055644 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-07 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDL-4192_1 | New_JAW-JT-KDL-4192 | JAW-JT-KDL-4192 | Central Java | Jawa Tengah | Kendal | -6.9677 | 110.285 | New | New | New | Type B | MA | JAW-JT-KDL-4192 |  |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020395 | S000055644 | S000055645 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  |  |  |  | 2025-11-07 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8470_1 | New_JAW-JT-DMK-8470 | JAW-JT-DMK-8470 | Central Java | Jawa Tengah | Demak | -6.8601 | 110.8076 | New | New | New | Type B | MA | JAW-JT-DMK-8470 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | S000055677 | S000055678 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-07 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8471_1 | New_JAW-JT-DMK-8471 | JAW-JT-DMK-8471 | Central Java | Jawa Tengah | Demak | -6.8793 | 110.8015 | New | New | New | Type B | MA | JAW-JT-DMK-8471 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | S000055678 | S000055679 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-07 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8468_1 | New_JAW-JT-DMK-8468 | JAW-JT-DMK-8468 | Central Java | Jawa Tengah | Demak | -6.8928 | 110.7992 | New | New | New | Type B | MA | JAW-JT-DMK-8468 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | S000055679 | S000055680 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-07 | 45 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8461_1 | New_JAW-JT-DMK-8461 | JAW-JT-DMK-8461 | Central Java | Jawa Tengah | Demak | -6.8916 | 110.7777 | New | New | New | Type B | MA | JAW-JT-DMK-8461 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | S000055680 | S000055681 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-10 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8462_1 | New_JAW-JT-DMK-8462 | JAW-JT-DMK-8462 | Central Java | Jawa Tengah | Demak | -6.9149 | 110.7792 | New | New | New | Type B | MA | JAW-JT-DMK-8462 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | S000055681 | S000055682 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-10 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-0844_1 | New_JAW-JT-KDS-0844 | JAW-JT-KDS-0844 | Central Java | Jawa Tengah | Kudus | -6.931 | 110.8079 | New | New | New | Type B | MA | JAW-JT-KDS-0844 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | S000055682 | S000055683 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-10 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-26 | 48 | 2025-11-26 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-4001_1 | New_JAW-JT-KDS-4001 | JAW-JT-KDS-4001 | Central Java | Jawa Tengah | Kudus | -6.9139 | 110.7971 | New | New | New | Type B | MA | JAW-JT-KDS-4001 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | S000055683 | S000055684 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-10 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-26 | 48 | 2025-11-26 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8472_1 | New_JAW-JT-DMK-8472 | JAW-JT-DMK-8472 | Central Java | Jawa Tengah | Demak | -6.8676 | 110.8227 | New | New | New | Type B | MA | JAW-JT-DMK-8472 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | S000055684 | S000055685 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-10 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8473_1 | New_JAW-JT-DMK-8473 | JAW-JT-DMK-8473 | Central Java | Jawa Tengah | Demak | -6.8533 | 110.832 | New | New | New | Type B | MA | JAW-JT-DMK-8473 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | S000055685 | S000055686 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-10 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0620_1 | New_JAW-JT-DMK-0620 | JAW-JT-DMK-0620 | Central Java | Jawa Tengah | Demak | -6.8258 | 110.7894 | New | New | New | Type B | MA | JAW-JT-DMK-0620 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | S000055686 | S000055687 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-10 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-4012_1 | New_JAW-JT-DMK-4012 | JAW-JT-DMK-4012 | Central Java | Jawa Tengah | Demak | -6.8066 | 110.7619 | New | New | New | Type B | MA | JAW-JT-DMK-4012 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | S000055687 | S000055688 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-10 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8451_1 | New_JAW-JT-DMK-8451 | JAW-JT-DMK-8451 | Central Java | Jawa Tengah | Demak | -6.8384 | 110.7494 | New | New | New | Type B | MA | JAW-JT-DMK-8451 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | S000055688 | S000055689 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-10 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8437_1 | New_JAW-JT-DMK-8437 | JAW-JT-DMK-8437 | Central Java | Jawa Tengah | Demak | -6.8264 | 110.7138 | New | New | New | Type B | MA | JAW-JT-DMK-8437 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | S000055689 | S000055690 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-10 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-4023_1 | New_JAW-JT-DMK-4023 | JAW-JT-DMK-4023 | Central Java | Jawa Tengah | Demak | -6.8382 | 110.7069 | New | New | New | Type B | MA | JAW-JT-DMK-4023 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | S000055690 | S000055691 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-10 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8439_1 | New_JAW-JT-DMK-8439 | JAW-JT-DMK-8439 | Central Java | Jawa Tengah | Demak | -6.8388 | 110.7207 | New | New | New | Type B | MA | JAW-JT-DMK-8439 |  |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020398 | S000055691 | S000055692 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-10 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-0874_1 | New_JAW-JT-KDS-0874 | JAW-JT-KDS-0874 | Central Java | Jawa Tengah | Kudus | -6.8191 | 110.8362 | New | New | New | Type B | MA | JAW-JT-KDS-0874 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | S000055693 | S000055694 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-10 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-26 | 48 | 2025-11-26 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8404_1 | New_JAW-JT-KDS-8404 | JAW-JT-KDS-8404 | Central Java | Jawa Tengah | Kudus | -6.8115 | 110.8342 | New | New | New | Type B | MA | JAW-JT-KDS-8404 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | S000055694 | S000055695 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | Yes |  |  |  |  | 2025-11-11 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-0846_1 | New_JAW-JT-KDS-0846 | JAW-JT-KDS-0846 | Central Java | Jawa Tengah | Kudus | -6.8207 | 110.8226 | New | New | New | Type B | MA | JAW-JT-KDS-0846 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | S000055695 | S000055696 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-11 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-26 | 48 | 2025-11-26 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8386_1 | New_JAW-JT-KDS-8386 | JAW-JT-KDS-8386 | Central Java | Jawa Tengah | Kudus | -6.8136 | 110.8242 | New | New | New | Type B | MA | JAW-JT-KDS-8386 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | S000055696 | S000055697 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-11 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-26 | 48 | 2025-11-26 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8371_1 | New_JAW-JT-KDS-8371 | JAW-JT-KDS-8371 | Central Java | Jawa Tengah | Kudus | -6.8114 | 110.807 | New | New | New | Type B | MA | JAW-JT-KDS-8371 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | S000055697 | S000055698 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-11 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-26 | 48 | 2025-11-26 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8380_1 | New_JAW-JT-KDS-8380 | JAW-JT-KDS-8380 | Central Java | Jawa Tengah | Kudus | -6.802 | 110.8213 | New | New | New | Type B | MA | JAW-JT-KDS-8380 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | S000055698 | S000055699 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | Yes |  | 2026 | FO NY RFS | YPTT | 2025-11-11 | 46 |  |  | 2025 | 2025-11-19 | 2025-11-19 | Approved | 2025-11-22 |  | Submitted | Approved | [29 empty] | 2025-11-26 | 48 | 2025-11-26 |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8374_1 | New_JAW-JT-KDS-8374 | JAW-JT-KDS-8374 | Central Java | Jawa Tengah | Kudus | -6.8 | 110.8111 | New | New | New | Type B | MA | JAW-JT-KDS-8374 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | S000055699 | S000055700 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | Yes |  |  |  |  | 2025-11-11 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8372_1 | New_JAW-JT-KDS-8372 | JAW-JT-KDS-8372 | Central Java | Jawa Tengah | Kudus | -6.7931 | 110.8071 | New | New | New | Type B | MA | JAW-JT-KDS-8372 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | S000055700 | S000055701 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-11 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-26 | 48 | 2025-11-26 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8367_1 | New_JAW-JT-KDS-8367 | JAW-JT-KDS-8367 | Central Java | Jawa Tengah | Kudus | -6.792 | 110.7943 | New | New | New | Type B | MA | JAW-JT-KDS-8367 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | S000055701 | S000055702 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | Yes |  |  |  |  | 2025-11-11 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8361_1 | New_JAW-JT-KDS-8361 | JAW-JT-KDS-8361 | Central Java | Jawa Tengah | Kudus | -6.7815 | 110.7651 | New | New | New | Type B | MA | JAW-JT-KDS-8361 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | S000055702 | S000055703 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-11 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-26 | 48 | 2025-11-26 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8426_1 | New_JAW-JT-DMK-8426 | JAW-JT-DMK-8426 | Central Java | Jawa Tengah | Demak | -6.7701 | 110.692 | New | New | New | Type B | MA | JAW-JT-DMK-8426 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | S000055703 | S000055704 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-11 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8424_1 | New_JAW-JT-DMK-8424 | JAW-JT-DMK-8424 | Central Java | Jawa Tengah | Demak | -6.7502 | 110.669 | New | New | New | Type B | MA | JAW-JT-DMK-8424 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | S000055704 | S000055705 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-11 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0594_1 | New_JAW-JT-DMK-0594 | JAW-JT-DMK-0594 | Central Java | Jawa Tengah | Demak | -6.7689 | 110.672 | New | New | New | Type B | MA | JAW-JT-DMK-0594 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | S000055705 | S000055706 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-11 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0622_1 | New_JAW-JT-DMK-0622 | JAW-JT-DMK-0622 | Central Java | Jawa Tengah | Demak | -6.7822 | 110.6562 | New | New | New | Type B | MA | JAW-JT-DMK-0622 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | S000055706 | S000055707 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-11 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8440_1 | New_JAW-JT-DMK-8440 | JAW-JT-DMK-8440 | Central Java | Jawa Tengah | Demak | -6.8216 | 110.7276 | New | New | New | Type B | MA | JAW-JT-DMK-8440 |  |  |  |  | - | - | - | - | New Purchase | New Ring 005 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020399 | S000055707 | S000055708 | 12. NY TERMINATION | 2025-12-20 | 51 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-11 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8430_1 | New_JAW-JT-DMK-8430 | JAW-JT-DMK-8430 | Central Java | Jawa Tengah | Demak | -6.8951 | 110.7002 | New | New | New | Type B | MA | JAW-JT-DMK-8430 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | S000055709 | S000055710 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  |  |  |  | 2025-11-12 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8433_1 | New_JAW-JT-DMK-8433 | JAW-JT-DMK-8433 | Central Java | Jawa Tengah | Demak | -6.9036 | 110.7098 | New | New | New | Type B | MA | JAW-JT-DMK-8433 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | S000055710 | S000055711 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-12 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8435_1 | New_JAW-JT-DMK-8435 | JAW-JT-DMK-8435 | Central Java | Jawa Tengah | Demak | -6.9165 | 110.7115 | New | New | New | Type B | MA | JAW-JT-DMK-8435 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | S000055711 | S000055712 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-12 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8429_1 | New_JAW-JT-DMK-8429 | JAW-JT-DMK-8429 | Central Java | Jawa Tengah | Demak | -6.9475 | 110.6988 | New | New | New | Type B | MA | JAW-JT-DMK-8429 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | S000055712 | S000055713 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-12 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0621_1 | New_JAW-JT-DMK-0621 | JAW-JT-DMK-0621 | Central Java | Jawa Tengah | Demak | -6.9406 | 110.6814 | New | New | New | Type B | MA | JAW-JT-DMK-0621 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | S000055713 | S000055714 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-12 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8421_1 | New_JAW-JT-DMK-8421 | JAW-JT-DMK-8421 | Central Java | Jawa Tengah | Demak | -6.9626 | 110.6781 | New | New | New | Type B | MA | JAW-JT-DMK-8421 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | S000055714 | S000055715 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-12 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8419_1 | New_JAW-JT-DMK-8419 | JAW-JT-DMK-8419 | Central Java | Jawa Tengah | Demak | -6.9708 | 110.6737 | New | New | New | Type B | MA | JAW-JT-DMK-8419 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | S000055715 | S000055716 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-12 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8443_1 | New_JAW-JT-DMK-8443 | JAW-JT-DMK-8443 | Central Java | Jawa Tengah | Demak | -6.9847 | 110.7188 | New | New | New | Type B | MA | JAW-JT-DMK-8443 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | S000055716 | S000055717 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS | YPTT | 2025-11-12 | 46 |  |  | 2025 | 2025-11-22 | 2025-11-21 11:03:08 | Reviewing |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8438_1 | New_JAW-JT-DMK-8438 | JAW-JT-DMK-8438 | Central Java | Jawa Tengah | Demak | -6.9981 | 110.7165 | New | New | New | Type B | MA | JAW-JT-DMK-8438 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | S000055717 | S000055718 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-12 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8448_1 | New_JAW-JT-DMK-8448 | JAW-JT-DMK-8448 | Central Java | Jawa Tengah | Demak | -7.001 | 110.7433 | New | New | New | Type B | MA | JAW-JT-DMK-8448 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | S000055718 | S000055719 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-12 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-0022_1 | New_JAW-JT-PWD-0022 | JAW-JT-PWD-0022 | Central Java | Jawa Tengah | Demak | -6.977 | 110.7584 | New | New | New | Type B | MA | JAW-JT-PWD-0022 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | S000055719 | S000055720 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-12 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8450_1 | New_JAW-JT-DMK-8450 | JAW-JT-DMK-8450 | Central Java | Jawa Tengah | Demak | -6.9593 | 110.7485 | New | New | New | Type B | MA | JAW-JT-DMK-8450 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | S000055720 | S000055721 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-12 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8457_1 | New_JAW-JT-DMK-8457 | JAW-JT-DMK-8457 | Central Java | Jawa Tengah | Demak | -6.9534 | 110.7635 | New | New | New | Type B | MA | JAW-JT-DMK-8457 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | S000055721 | S000055722 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-12 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8454_1 | New_JAW-JT-DMK-8454 | JAW-JT-DMK-8454 | Central Java | Jawa Tengah | Demak | -6.9325 | 110.7539 | New | New | New | Type B | MA | JAW-JT-DMK-8454 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | S000055722 | S000055723 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-12 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8449_1 | New_JAW-JT-DMK-8449 | JAW-JT-DMK-8449 | Central Java | Jawa Tengah | Demak | -6.9282 | 110.7434 | New | New | New | Type B | MA | JAW-JT-DMK-8449 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | S000055723 | S000055724 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-13 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8445_1 | New_JAW-JT-DMK-8445 | JAW-JT-DMK-8445 | Central Java | Jawa Tengah | Demak | -6.9136 | 110.738 | New | New | New | Type B | MA | JAW-JT-DMK-8445 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | S000055724 | S000055725 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-13 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8453_1 | New_JAW-JT-DMK-8453 | JAW-JT-DMK-8453 | Central Java | Jawa Tengah | Demak | -6.8917 | 110.7503 | New | New | New | Type B | MA | JAW-JT-DMK-8453 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | S000055725 | S000055726 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-13 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8441_1 | New_JAW-JT-DMK-8441 | JAW-JT-DMK-8441 | Central Java | Jawa Tengah | Demak | -6.8717 | 110.7314 | New | New | New | Type B | MA | JAW-JT-DMK-8441 |  |  |  |  | - | - | - | - | New Purchase | New Ring 006 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020400 | S000055726 | S000055727 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-13 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8356_1 | New_JAW-JT-DMK-8356 | JAW-JT-DMK-8356 | Central Java | Jawa Tengah | Demak | -6.9093 | 110.5661 | New | New | New | Type B | MA | JAW-JT-DMK-8356 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | S000055728 | S000055729 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | Yes |  | 2026 | FO NY RFS | GIT | 2025-11-13 | 46 |  |  | 2025 | 2025-11-10 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8301_1 | New_JAW-JT-DMK-8301 | JAW-JT-DMK-8301 | Central Java | Jawa Tengah | Demak | -6.9106 | 110.5067 | New | New | New | Type B | MA | JAW-JT-DMK-8301 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | S000055729 | S000055730 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | Yes |  | 2026 | FO NY RFS | GIT | 2025-11-13 | 46 |  |  | 2025 | 2025-11-10 | 2025-11-10 | Approved | 2025-11-13 |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8344_1 | New_JAW-JT-DMK-8344 | JAW-JT-DMK-8344 | Central Java | Jawa Tengah | Demak | -6.924 | 110.5348 | New | New | New | Type B | MA | JAW-JT-DMK-8344 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | S000055730 | S000055731 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | Yes |  | 2026 | FO NY RFS | GIT | 2025-11-13 | 46 |  |  | 2025 | 2025-11-12 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8338_1 | New_JAW-JT-DMK-8338 | JAW-JT-DMK-8338 | Central Java | Jawa Tengah | Demak | -6.9128 | 110.5345 | New | New | New | Type B | MA | JAW-JT-DMK-8338 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | S000055731 | S000055732 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | Yes |  | 2026 | FO NY RFS | GIT | 2025-11-13 | 46 |  |  | 2025 | 2025-11-10 | 2025-11-10 | Approved | 2025-11-17 |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8306_1 | New_JAW-JT-DMK-8306 | JAW-JT-DMK-8306 | Central Java | Jawa Tengah | Demak | -6.8958 | 110.5115 | New | New | New | Type B | MA | JAW-JT-DMK-8306 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | S000055732 | S000055733 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | Yes |  | 2026 | FO NY RFS | GIT | 2025-11-13 | 46 |  |  | 2025 | 2025-11-08 | 2025-11-14 | Approved | 2025-11-17 |  | Submitted | Approved |  | Blok Akses, kompensasi 10jt | [27 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8329_1 | New_JAW-JT-DMK-8329 | JAW-JT-DMK-8329 | Central Java | Jawa Tengah | Demak | -6.8824 | 110.5326 | New | New | New | Type B | MA | JAW-JT-DMK-8329 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | S000055733 | S000055734 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | Yes |  | 2026 | FO NY RFS | GIT | 2025-11-13 | 46 |  |  | 2025 | 2025-11-10 | 2025-11-10 | Approved | 2025-11-17 |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8337_1 | New_JAW-JT-DMK-8337 | JAW-JT-DMK-8337 | Central Java | Jawa Tengah | Demak | -6.8692 | 110.5436 | New | New | New | Type B | MA | JAW-JT-DMK-8337 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | S000055734 | S000055735 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | Yes |  | 2026 | FO NY RFS | GIT | 2025-11-13 | 46 |  |  | 2025 | 2025-11-10 | 2025-11-10 | Approved | 2025-11-17 |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-4132_1 | New_JAW-JT-DMK-4132 | JAW-JT-DMK-4132 | Central Java | Jawa Tengah | Demak | -6.8836 | 110.5523 | New | New | New | Type B | MA | JAW-JT-DMK-4132 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | S000055735 | S000055736 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | Yes |  | 2026 | FO NY RFS | YPTT | 2025-11-13 | 46 |  |  | 2025 | 2025-11-17 | 2025-11-17 | Approved | 2025-11-22 |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | 1 | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8353_1 | New_JAW-JT-DMK-8353 | JAW-JT-DMK-8353 | Central Java | Jawa Tengah | Demak | -6.856 | 110.5629 | New | New | New | Type B | MA | JAW-JT-DMK-8353 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | S000055736 | S000055737 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | Yes |  | 2026 | FO NY RFS | GIT | 2025-11-13 | 46 |  |  | 2025 | 2025-11-10 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-0625_1 | New_JAW-JT-DMK-0625 | JAW-JT-DMK-0625 | Central Java | Jawa Tengah | Demak | -6.8312 | 110.5532 | New | New | New | Type B | MA | JAW-JT-DMK-0625 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | S000055737 | S000055738 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | Yes |  | 2026 | FO NY RFS | GIT | 2025-11-13 | 46 |  |  | 2025 | 2025-11-10 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8372_1 | New_JAW-JT-DMK-8372 | JAW-JT-DMK-8372 | Central Java | Jawa Tengah | Demak | -6.8508 | 110.5924 | New | New | New | Type B | MA | JAW-JT-DMK-8372 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | S000055738 | S000055739 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | Yes |  |  |  | GIT | 2025-11-14 | 46 |  |  | 2025 | 2025-11-19 | 2025-11-19 | Reviewing |  |  | Submitted | Approved |  | No BTS at site | [29 empty] | #N/A |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8368_1 | New_JAW-JT-DMK-8368 | JAW-JT-DMK-8368 | Central Java | Jawa Tengah | Demak | -6.8112 | 110.5882 | New | New | New | Type B | MA | JAW-JT-DMK-8368 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | S000055739 | S000055740 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | Yes |  | 2026 | FO NY RFS | GIT | 2025-11-14 | 46 |  |  | 2025 | 2025-11-13 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8370_1 | New_JAW-JT-DMK-8370 | JAW-JT-DMK-8370 | Central Java | Jawa Tengah | Demak | -6.8817 | 110.5905 | New | New | New | Type B | MA | JAW-JT-DMK-8370 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | S000055740 | S000055741 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | Yes |  |  |  | GIT | 2025-11-14 | 46 |  |  | 2025 | 2025-11-08 | 2025-11-19 | Reviewing |  |  | Submitted | Approved |  | No BTS at site | [29 empty] | #N/A |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-4011_1 | New_JAW-JT-DMK-4011 | JAW-JT-DMK-4011 | Central Java | Jawa Tengah | Demak | -6.8893 | 110.6479 | New | New | New | Type B | MA | JAW-JT-DMK-4011 |  |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020401 | S000055741 | S000055742 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | Yes |  | 2026 | FO NY RFS | GIT | 2025-11-14 | 46 |  |  | 2025 | 2025-11-12 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-DMK-8405_1 | New_JAW-JT-DMK-8405 | JAW-JT-DMK-8405 | Central Java | Jawa Tengah | Demak | -6.9062 | 110.6406 | New | New | New | Type B | MA | JAW-JT-DMK-8405 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | S000055743 | S000055744 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-14 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8417_1 | New_JAW-JT-DMK-8417 | JAW-JT-DMK-8417 | Central Java | Jawa Tengah | Demak | -6.9115 | 110.6617 | New | New | New | Type B | MA | JAW-JT-DMK-8417 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | S000055744 | S000055745 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  |  |  |  | 2025-11-14 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0626_1 | New_JAW-JT-DMK-0626 | JAW-JT-DMK-0626 | Central Java | Jawa Tengah | Demak | -6.9486 | 110.6548 | New | New | New | Type B | MA | JAW-JT-DMK-0626 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | S000055745 | S000055746 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-14 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-4026_1 | New_JAW-JT-DMK-4026 | JAW-JT-DMK-4026 | Central Java | Jawa Tengah | Demak | -6.9659 | 110.6451 | New | New | New | Type B | MA | JAW-JT-DMK-4026 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | S000055746 | S000055747 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-14 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8399_1 | New_JAW-JT-DMK-8399 | JAW-JT-DMK-8399 | Central Java | Jawa Tengah | Demak | -6.9557 | 110.6326 | New | New | New | Type B | MA | JAW-JT-DMK-8399 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | S000055747 | S000055748 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-14 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8397_1 | New_JAW-JT-DMK-8397 | JAW-JT-DMK-8397 | Central Java | Jawa Tengah | Demak | -6.9425 | 110.6318 | New | New | New | Type B | MA | JAW-JT-DMK-8397 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | S000055748 | S000055749 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-14 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8386_1 | New_JAW-JT-DMK-8386 | JAW-JT-DMK-8386 | Central Java | Jawa Tengah | Demak | -6.9595 | 110.6123 | New | New | New | Type B | MA | JAW-JT-DMK-8386 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | S000055749 | S000055750 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-14 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0627_1 | New_JAW-JT-DMK-0627 | JAW-JT-DMK-0627 | Central Java | Jawa Tengah | Demak | -6.9652 | 110.5688 | New | New | New | Type B | MA | JAW-JT-DMK-0627 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | S000055750 | S000055751 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-14 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8377_1 | New_JAW-JT-DMK-8377 | JAW-JT-DMK-8377 | Central Java | Jawa Tengah | Demak | -6.9501 | 110.5848 | New | New | New | Type B | MA | JAW-JT-DMK-8377 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | S000055751 | S000055752 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-14 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8373_1 | New_JAW-JT-DMK-8373 | JAW-JT-DMK-8373 | Central Java | Jawa Tengah | Demak | -6.9332 | 110.5939 | New | New | New | Type B | MA | JAW-JT-DMK-8373 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | S000055752 | S000055753 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-14 | 46 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-4010_1 | New_JAW-JT-DMK-4010 | JAW-JT-DMK-4010 | Central Java | Jawa Tengah | Demak | -6.9227 | 110.5836 | New | New | New | Type B | MA | JAW-JT-DMK-4010 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | S000055753 | S000055754 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-17 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8378_1 | New_JAW-JT-DMK-8378 | JAW-JT-DMK-8378 | Central Java | Jawa Tengah | Demak | -6.9101 | 110.5849 | New | New | New | Type B | MA | JAW-JT-DMK-8378 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | S000055754 | S000055755 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-17 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8384_1 | New_JAW-JT-DMK-8384 | JAW-JT-DMK-8384 | Central Java | Jawa Tengah | Demak | -6.9162 | 110.6095 | New | New | New | Type B | MA | JAW-JT-DMK-8384 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | S000055755 | S000055756 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-17 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8392_1 | New_JAW-JT-DMK-8392 | JAW-JT-DMK-8392 | Central Java | Jawa Tengah | Demak | -6.9108 | 110.6176 | New | New | New | Type B | MA | JAW-JT-DMK-8392 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | S000055756 | S000055757 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-17 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8402_1 | New_JAW-JT-DMK-8402 | JAW-JT-DMK-8402 | Central Java | Jawa Tengah | Demak | -6.8891 | 110.6367 | New | New | New | Type B | MA | JAW-JT-DMK-8402 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | S000055757 | S000055758 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-17 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8400_1 | New_JAW-JT-DMK-8400 | JAW-JT-DMK-8400 | Central Java | Jawa Tengah | Demak | -6.8861 | 110.6326 | New | New | New | Type B | MA | JAW-JT-DMK-8400 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | S000055758 | S000055759 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-17 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8407_1 | New_JAW-JT-DMK-8407 | JAW-JT-DMK-8407 | Central Java | Jawa Tengah | Demak | -6.8916 | 110.6433 | New | New | New | Type B | MA | JAW-JT-DMK-8407 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | S000055759 | S000055760 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-17 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8411_1 | New_JAW-JT-DMK-8411 | JAW-JT-DMK-8411 | Central Java | Jawa Tengah | Demak | -6.9008 | 110.6491 | New | New | New | Type B | MA | JAW-JT-DMK-8411 |  |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020402 | S000055760 | S000055761 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2026 | FO NY RFS | YPTT | 2025-11-17 | 47 |  |  | 2025 | 2025-11-19 | 2025-11-19 | Approved | 2025-11-22 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-4025_1 | New_JAW-JT-DMK-4025 | JAW-JT-DMK-4025 | Central Java | Jawa Tengah | Demak | -7.0358 | 110.5028 | New | New | New | Type B | MA | JAW-JT-DMK-4025 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | S000055762 | S000055763 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-17 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8290_1 | New_JAW-JT-DMK-8290 | JAW-JT-DMK-8290 | Central Java | Jawa Tengah | Demak | -7.0537 | 110.4983 | New | New | New | Type B | MA | JAW-JT-DMK-8290 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | S000055763 | S000055764 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-17 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8295_1 | New_JAW-JT-DMK-8295 | JAW-JT-DMK-8295 | Central Java | Jawa Tengah | Demak | -7.0634 | 110.5044 | New | New | New | Type B | MA | JAW-JT-DMK-8295 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | S000055764 | S000055765 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-17 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8289_1 | New_JAW-JT-DMK-8289 | JAW-JT-DMK-8289 | Central Java | Jawa Tengah | Demak | -7.0889 | 110.4979 | New | New | New | Type B | MA | JAW-JT-DMK-8289 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | S000055765 | S000055766 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-17 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8330_1 | New_JAW-JT-DMK-8330 | JAW-JT-DMK-8330 | Central Java | Jawa Tengah | Demak | -7.085 | 110.5327 | New | New | New | Type B | MA | JAW-JT-DMK-8330 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | S000055766 | S000055767 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-17 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8336_1 | New_JAW-JT-DMK-8336 | JAW-JT-DMK-8336 | Central Java | Jawa Tengah | Demak | -7.0812 | 110.5427 | New | New | New | Type B | MA | JAW-JT-DMK-8336 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | S000055767 | S000055768 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-17 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8335_1 | New_JAW-JT-DMK-8335 | JAW-JT-DMK-8335 | Central Java | Jawa Tengah | Demak | -7.0718 | 110.5393 | New | New | New | Type B | MA | JAW-JT-DMK-8335 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | S000055768 | S000055769 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-18 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8312_1 | New_JAW-JT-DMK-8312 | JAW-JT-DMK-8312 | Central Java | Jawa Tengah | Demak | -7.0398 | 110.5165 | New | New | New | Type B | MA | JAW-JT-DMK-8312 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | S000055769 | S000055770 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-18 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8333_1 | New_JAW-JT-DMK-8333 | JAW-JT-DMK-8333 | Central Java | Jawa Tengah | Demak | -7.0427 | 110.5386 | New | New | New | Type B | MA | JAW-JT-DMK-8333 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | S000055771 | S000055772 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-18 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8348_1 | New_JAW-JT-DMK-8348 | JAW-JT-DMK-8348 | Central Java | Jawa Tengah | Demak | -7.0559 | 110.5547 | New | New | New | Type B | MA | JAW-JT-DMK-8348 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | S000055772 | S000055773 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-18 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8349_1 | New_JAW-JT-DMK-8349 | JAW-JT-DMK-8349 | Central Java | Jawa Tengah | Demak | -7.0502 | 110.5576 | New | New | New | Type B | MA | JAW-JT-DMK-8349 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | S000055773 | S000055774 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-18 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0572_1 | New_JAW-JT-DMK-0572 | JAW-JT-DMK-0572 | Central Java | Jawa Tengah | Demak | -7.0438 | 110.5767 | New | New | New | Type B | MA | JAW-JT-DMK-0572 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | S000055774 | S000055775 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-18 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8361_1 | New_JAW-JT-DMK-8361 | JAW-JT-DMK-8361 | Central Java | Jawa Tengah | Demak | -7.0353 | 110.5736 | New | New | New | Type B | MA | JAW-JT-DMK-8361 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | S000055775 | S000055776 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-18 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-4013_1 | New_JAW-JT-DMK-4013 | JAW-JT-DMK-4013 | Central Java | Jawa Tengah | Demak | -6.9962 | 110.5686 | New | New | New | Type B | MA | JAW-JT-DMK-4013 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | S000055776 | S000055777 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-18 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8369_1 | New_JAW-JT-DMK-8369 | JAW-JT-DMK-8369 | Central Java | Jawa Tengah | Demak | -6.9986 | 110.5883 | New | New | New | Type B | MA | JAW-JT-DMK-8369 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | S000055777 | S000055778 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-18 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0615_1 | New_JAW-JT-DMK-0615 | JAW-JT-DMK-0615 | Central Java | Jawa Tengah | Demak | -7.0311 | 110.5889 | New | New | New | Type B | MA | JAW-JT-DMK-0615 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | S000055778 | S000055779 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-18 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8381_1 | New_JAW-JT-DMK-8381 | JAW-JT-DMK-8381 | Central Java | Jawa Tengah | Demak | -7.0337 | 110.6042 | New | New | New | Type B | MA | JAW-JT-DMK-8381 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | S000055779 | S000055780 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-18 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0623_1 | New_JAW-JT-DMK-0623 | JAW-JT-DMK-0623 | Central Java | Jawa Tengah | Demak | -6.9854 | 110.6047 | New | New | New | Type B | MA | JAW-JT-DMK-0623 |  |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | S000055780 | S000055781 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-18 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8285_1 | New_JAW-JT-DMK-8285 | JAW-JT-DMK-8285 | Central Java | Jawa Tengah | Demak | -7.0031 | 110.4958 | New | New | New | Type B | MA | JAW-JT-DMK-8285 |  |  |  |  | - | - | - | - | New Purchase | New Ring 010 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | S000055784 | S000055785 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | No |  |  |  |  | 2025-11-18 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8293_1 | New_JAW-JT-DMK-8293 | JAW-JT-DMK-8293 | Central Java | Jawa Tengah | Demak | -6.997 | 110.5029 | New | New | New | Type B | MA | JAW-JT-DMK-8293 |  |  |  |  | - | - | - | - | New Purchase | New Ring 010 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | S000055785 | S000055786 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | No |  |  |  |  | 2025-11-18 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8308_1 | New_JAW-JT-DMK-8308 | JAW-JT-DMK-8308 | Central Java | Jawa Tengah | Demak | -7.0072 | 110.5119 | New | New | New | Type B | MA | JAW-JT-DMK-8308 |  |  |  |  | - | - | - | - | New Purchase | New Ring 010 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | S000055786 | S000055787 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-19 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-4133_1 | New_JAW-JT-DMK-4133 | JAW-JT-DMK-4133 | Central Java | Jawa Tengah | Demak | -6.9959 | 110.5419 | New | New | New | Type B | MA | JAW-JT-DMK-4133 |  |  |  |  | - | - | - | - | New Purchase | New Ring 010 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | S000055787 | S000055788 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-19 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8340_1 | New_JAW-JT-DMK-8340 | JAW-JT-DMK-8340 | Central Java | Jawa Tengah | Demak | -6.9766 | 110.5451 | New | New | New | Type B | MA | JAW-JT-DMK-8340 |  |  |  |  | - | - | - | - | New Purchase | New Ring 010 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | S000055788 | S000055789 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-19 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8320_1 | New_JAW-JT-DMK-8320 | JAW-JT-DMK-8320 | Central Java | Jawa Tengah | Demak | -6.9856 | 110.5233 | New | New | New | Type B | MA | JAW-JT-DMK-8320 |  |  |  |  | - | - | - | - | New Purchase | New Ring 010 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | S000055789 | S000055790 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-19 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8309_1 | New_JAW-JT-DMK-8309 | JAW-JT-DMK-8309 | Central Java | Jawa Tengah | Demak | -6.9738 | 110.5125 | New | New | New | Type B | MA | JAW-JT-DMK-8309 |  |  |  |  | - | - | - | - | New Purchase | New Ring 010 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | S000055790 | S000055791 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-19 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8299_1 | New_JAW-JT-DMK-8299 | JAW-JT-DMK-8299 | Central Java | Jawa Tengah | Demak | -6.9622 | 110.5056 | New | New | New | Type B | MA | JAW-JT-DMK-8299 |  |  |  |  | - | - | - | - | New Purchase | New Ring 010 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | S000055791 | S000055792 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-19 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8303_1 | New_JAW-JT-DMK-8303 | JAW-JT-DMK-8303 | Central Java | Jawa Tengah | Demak | -6.9532 | 110.5084 | New | New | New | Type B | MA | JAW-JT-DMK-8303 |  |  |  |  | - | - | - | - | New Purchase | New Ring 010 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | S000055792 | S000055793 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-19 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-4009_1 | New_JAW-JT-DMK-4009 | JAW-JT-DMK-4009 | Central Java | Jawa Tengah | Demak | -6.9451 | 110.4968 | New | New | New | Type B | MA | JAW-JT-DMK-4009 |  |  |  |  | - | - | - | - | New Purchase | New Ring 010 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | S000055793 | S000055794 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-19 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8425_1 | New_JAW-JT-KDS-8425 | JAW-JT-KDS-8425 | Central Java | Jawa Tengah | Kudus | -6.752 | 110.8646 | New | New | New | Type B | MA | JAW-JT-KDS-8425 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | S000055646 | S000055647 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-19 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-3501_1 | New_JAW-JT-KDS-3501 | JAW-JT-KDS-3501 | Central Java | Jawa Tengah | Kudus | -6.6906 | 110.9154 | New | New | New | Type B | MA | JAW-JT-KDS-3501 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | S000055647 | S000055648 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-19 | 47 |  |  | 2025 | [5 empty] | Submitted | Submitted | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-3504_1 | New_JAW-JT-KDS-3504 | JAW-JT-KDS-3504 | Central Java | Jawa Tengah | Kudus | -6.6741 | 110.8771 | New | New | New | Type B | MA | JAW-JT-KDS-3504 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | S000055648 | S000055649 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-19 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-0852_1 | New_JAW-JT-KDS-0852 | JAW-JT-KDS-0852 | Central Java | Jawa Tengah | Kudus | -6.6979 | 110.8668 | New | New | New | Type B | MA | JAW-JT-KDS-0852 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | S000055649 | S000055650 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-19 | 47 |  |  | 2025 | [5 empty] | Submitted | Submitted | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8409_1 | New_JAW-JT-KDS-8409 | JAW-JT-KDS-8409 | Central Java | Jawa Tengah | Kudus | -6.7136 | 110.8443 | New | New | New | Type B | MA | JAW-JT-KDS-8409 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | S000055650 | S000055651 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-19 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8391_1 | New_JAW-JT-KDS-8391 | JAW-JT-KDS-8391 | Central Java | Jawa Tengah | Kudus | -6.7309 | 110.8303 | New | New | New | Type B | MA | JAW-JT-KDS-8391 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | S000055651 | S000055652 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-19 | 47 |  |  | 2025 | [5 empty] | Submitted | Submitted | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8408_1 | New_JAW-JT-KDS-8408 | JAW-JT-KDS-8408 | Central Java | Jawa Tengah | Kudus | -6.7293 | 110.844 | New | New | New | Type B | MA | JAW-JT-KDS-8408 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | S000055652 | S000055653 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | Yes |  |  |  |  | 2025-11-20 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8417_1 | New_JAW-JT-KDS-8417 | JAW-JT-KDS-8417 | Central Java | Jawa Tengah | Kudus | -6.7295 | 110.856 | New | New | New | Type B | MA | JAW-JT-KDS-8417 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | S000055653 | S000055654 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-20 | 47 |  |  | 2025 | [5 empty] | Submitted | Submitted | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8411_1 | New_JAW-JT-KDS-8411 | JAW-JT-KDS-8411 | Central Java | Jawa Tengah | Kudus | -6.7537 | 110.8453 | New | New | New | Type B | MA | JAW-JT-KDS-8411 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | S000055654 | S000055655 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-20 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8393_1 | New_JAW-JT-KDS-8393 | JAW-JT-KDS-8393 | Central Java | Jawa Tengah | Kudus | -6.773 | 110.8312 | New | New | New | Type B | MA | JAW-JT-KDS-8393 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | S000055655 | S000055656 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | Yes |  | 2026 | FO NY RFS | YPTT | 2025-11-20 | 47 |  |  | 2025 | 2025-11-22 | 2025-11-21 11:03:10 | Reviewing |  |  | Submitted | Submitted | [31 empty] | #N/A |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-0848_1 | New_JAW-JT-KDS-0848 | JAW-JT-KDS-0848 | Central Java | Jawa Tengah | Kudus | -6.7587 | 110.8233 | New | New | New | Type B | MA | JAW-JT-KDS-0848 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | S000055656 | S000055657 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-20 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8376_1 | New_JAW-JT-KDS-8376 | JAW-JT-KDS-8376 | Central Java | Jawa Tengah | Kudus | -6.7534 | 110.8158 | New | New | New | Type B | MA | JAW-JT-KDS-8376 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | S000055657 | S000055658 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-20 | 47 |  |  | 2025 | [5 empty] | Submitted | Submitted | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8366_1 | New_JAW-JT-KDS-8366 | JAW-JT-KDS-8366 | Central Java | Jawa Tengah | Kudus | -6.7781 | 110.7939 | New | New | New | Type B | MA | JAW-JT-KDS-8366 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | S000055658 | S000055659 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-20 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8405_1 | New_JAW-JT-KDS-8405 | JAW-JT-KDS-8405 | Central Java | Jawa Tengah | Kudus | -6.7867 | 110.8343 | New | New | New | Type B | MA | JAW-JT-KDS-8405 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | S000055659 | S000055660 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-20 | 47 |  |  | 2025 | [5 empty] | Submitted | Submitted | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8399_1 | New_JAW-JT-KDS-8399 | JAW-JT-KDS-8399 | Central Java | Jawa Tengah | Kudus | -6.8056 | 110.837 | New | New | New | Type B | MA | JAW-JT-KDS-8399 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | S000055660 | S000055661 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | Yes |  | 2026 | FO NY RFS | YPTT | 2025-11-20 | 47 |  |  | 2025 | 2025-11-21 | 2025-11-21 | Approved | 2025-11-22 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-4007_1 | New_JAW-JT-KDS-4007 | JAW-JT-KDS-4007 | Central Java | Jawa Tengah | Kudus | -6.8048 | 110.8527 | New | New | New | Type B | MA | JAW-JT-KDS-4007 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | S000055661 | S000055662 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-20 | 47 |  |  | 2025 | [5 empty] | Submitted | Submitted | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8430_1 | New_JAW-JT-KDS-8430 | JAW-JT-KDS-8430 | Central Java | Jawa Tengah | Kudus | -6.8083 | 110.8517 | New | New | New | Type B | MA | JAW-JT-KDS-8430 |  |  |  |  | - | - | - | - | New Purchase | New Ring 011 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | S000055662 | S000055663 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-20 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-4003_1 | New_JAW-JT-KDS-4003 | JAW-JT-KDS-4003 | Central Java | Jawa Tengah | Kudus | -6.8103 | 110.8721 | New | New | New | Type B | MA | JAW-JT-KDS-4003 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | S000055664 | S000055665 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-20 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8448_1 | New_JAW-JT-KDS-8448 | JAW-JT-KDS-8448 | Central Java | Jawa Tengah | Kudus | -6.8115 | 110.8845 | New | New | New | Type B | MA | JAW-JT-KDS-8448 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | S000055665 | S000055666 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-20 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-0862_1 | New_JAW-JT-KDS-0862 | JAW-JT-KDS-0862 | Central Java | Jawa Tengah | Kudus | -6.8294 | 110.8868 | New | New | New | Type B | MA | JAW-JT-KDS-0862 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | S000055666 | S000055667 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-20 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-28 | 48 | 2025-11-28 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8424_1 | New_JAW-JT-KDS-8424 | JAW-JT-KDS-8424 | Central Java | Jawa Tengah | Kudus | -6.8364 | 110.8634 | New | New | New | Type B | MA | JAW-JT-KDS-8424 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | S000055667 | S000055668 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-21 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-28 | 48 | 2025-11-28 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8433_1 | New_JAW-JT-KDS-8433 | JAW-JT-KDS-8433 | Central Java | Jawa Tengah | Kudus | -6.867 | 110.8667 | New | New | New | Type B | MA | JAW-JT-KDS-8433 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | S000055668 | S000055669 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-21 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-28 | 48 | 2025-11-28 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-3505_1 | New_JAW-JT-KDS-3505 | JAW-JT-KDS-3505 | Central Java | Jawa Tengah | Kudus | -6.8458 | 110.9003 | New | New | New | Type B | MA | JAW-JT-KDS-3505 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | S000055669 | S000055670 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-21 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-28 | 48 | 2025-11-28 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8464_1 | New_JAW-JT-KDS-8464 | JAW-JT-KDS-8464 | Central Java | Jawa Tengah | Kudus | -6.8367 | 110.9158 | New | New | New | Type B | MA | JAW-JT-KDS-8464 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | S000055670 | S000055671 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-21 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-28 | 48 | 2025-11-28 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8459_1 | New_JAW-JT-KDS-8459 | JAW-JT-KDS-8459 | Central Java | Jawa Tengah | Kudus | -6.8156 | 110.9012 | New | New | New | Type B | MA | JAW-JT-KDS-8459 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | S000055671 | S000055672 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-21 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-28 | 48 | 2025-11-28 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8442_1 | New_JAW-JT-KDS-8442 | JAW-JT-KDS-8442 | Central Java | Jawa Tengah | Kudus | -6.7876 | 110.8813 | New | New | New | Type B | MA | JAW-JT-KDS-8442 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | S000055672 | S000055673 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-21 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8451_1 | New_JAW-JT-KDS-8451 | JAW-JT-KDS-8451 | Central Java | Jawa Tengah | Kudus | -6.7939 | 110.8973 | New | New | New | Type B | MA | JAW-JT-KDS-8451 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | S000055673 | S000055674 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | No |  | 2026 | FO NY RFS | YPTT | 2025-11-21 | 47 |  |  | 2025 | 2025-11-21 | 2025-11-21 | Approved | 2025-11-22 |  | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8457_1 | New_JAW-JT-KDS-8457 | JAW-JT-KDS-8457 | Central Java | Jawa Tengah | Kudus | -6.7923 | 110.9082 | New | New | New | Type B | MA | JAW-JT-KDS-8457 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | S000055674 | S000055675 | 10. Ready ATP / RFS | 2025-12-14 | 50 | 2025-11-09 | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-21 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8472_1 | New_JAW-JT-KDS-8472 | JAW-JT-KDS-8472 | Central Java | Jawa Tengah | Kudus | -6.7905 | 110.9399 | New | New | New | Type B | MA | JAW-JT-KDS-8472 |  |  |  |  | - | - | - | - | New Purchase | New Ring 012 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020397 | S000055675 | S000055676 | 10. Ready ATP / RFS | 2025-12-14 | 50 | 2025-11-09 | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-21 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8312_1 | New_JAW-JT-PWD-8312 | JAW-JT-PWD-8312 | Central Java | Jawa Tengah | Grobogan | -6.9854 | 110.642 | New | New | New | Type B | MA | JAW-JT-PWD-8312 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | S000054284 | S000054285 | 12. NY TERMINATION | 2025-12-07 | 49 |  | #N/A | No |  | 2025-624 sites | FO NY RFS |  | 2025-11-21 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8325_1 | New_JAW-JT-PWD-8325 | JAW-JT-PWD-8325 | Central Java | Jawa Tengah | Grobogan | -6.9822 | 110.6672 | New | New | New | Type B | MA | JAW-JT-PWD-8325 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | S000054285 | S000054286 | 12. NY TERMINATION | 2025-12-07 | 49 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-21 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8329_1 | New_JAW-JT-PWD-8329 | JAW-JT-PWD-8329 | Central Java | Jawa Tengah | Grobogan | -7.002 | 110.6748 | New | New | New | Type B | MA | JAW-JT-PWD-8329 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | S000054286 | S000054287 | 12. NY TERMINATION | 2025-12-07 | 49 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-21 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-2001_1 | New_JAW-JT-PWD-2001 | JAW-JT-PWD-2001 | Central Java | Jawa Tengah | Grobogan | -7.0089 | 110.6461 | New | New | New | Type B | MA | JAW-JT-PWD-2001 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | S000054287 | S000054288 | 12. NY TERMINATION | 2025-12-07 | 49 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-21 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-0048_1 | New_JAW-JT-PWD-0048 | JAW-JT-PWD-0048 | Central Java | Jawa Tengah | Grobogan | -7.0231 | 110.6541 | New | New | New | Type B | MA | JAW-JT-PWD-0048 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | S000054288 | S000054289 | 12. NY TERMINATION | 2025-12-07 | 49 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-21 | 47 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8328_1 | New_JAW-JT-PWD-8328 | JAW-JT-PWD-8328 | Central Java | Jawa Tengah | Grobogan | -7.0423 | 110.6675 | New | New | New | Type B | MA | JAW-JT-PWD-8328 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | S000054289 | S000054290 | 12. NY TERMINATION | 2025-12-07 | 49 |  | #N/A | No |  | 2025-624 sites | FO NY RFS |  | 2025-11-24 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8324_1 | New_JAW-JT-PWD-8324 | JAW-JT-PWD-8324 | Central Java | Jawa Tengah | Grobogan | -7.0664 | 110.667 | New | New | New | Type B | MA | JAW-JT-PWD-8324 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | S000054290 | S000054283 | 12. NY TERMINATION | 2025-12-07 | 49 |  | #N/A | No |  | 2025-624 sites | FO NY RFS |  | 2025-11-24 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-4003_1 | New_JAW-JT-PWD-4003 | JAW-JT-PWD-4003 | Central Java | Jawa Tengah | Grobogan | -7.0664 | 110.6527 | New | New | New | Type B | MA | JAW-JT-PWD-4003 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | S000054283 | S000054291 | 12. NY TERMINATION | 2025-12-07 | 49 |  | #N/A | No |  | 2025-624 sites | FO NY RFS |  | 2025-11-24 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8309_1 | New_JAW-JT-PWD-8309 | JAW-JT-PWD-8309 | Central Java | Jawa Tengah | Grobogan | -7.0916 | 110.6385 | New | New | New | Type B | MA | JAW-JT-PWD-8309 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | S000054291 | S000054292 | 12. NY TERMINATION | 2025-12-07 | 49 |  | #N/A | No |  | 2025-624 sites | FO NY RFS |  | 2025-11-24 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8307_1 | New_JAW-JT-PWD-8307 | JAW-JT-PWD-8307 | Central Java | Jawa Tengah | Grobogan | -7.0936 | 110.6238 | New | New | New | Type B | MA | JAW-JT-PWD-8307 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | S000054292 | S000054293 | 12. NY TERMINATION | 2025-12-07 | 49 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-24 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8302_1 | New_JAW-JT-PWD-8302 | JAW-JT-PWD-8302 | Central Java | Jawa Tengah | Grobogan | -7.0621 | 110.6092 | New | New | New | Type B | MA | JAW-JT-PWD-8302 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | S000054293 | S000054294 | 12. NY TERMINATION | 2025-12-07 | 49 |  | #N/A | No |  | 2025-624 sites | FO NY RFS |  | 2025-11-24 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8295_1 | New_JAW-JT-PWD-8295 | JAW-JT-PWD-8295 | Central Java | Jawa Tengah | Grobogan | -7.0664 | 110.5954 | New | New | New | Type B | MA | JAW-JT-PWD-8295 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | S000054294 | S000054295 | 12. NY TERMINATION | 2025-12-07 | 49 |  | #N/A | No |  | 2025-624 sites | FO NY RFS |  | 2025-11-24 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8301_1 | New_JAW-JT-PWD-8301 | JAW-JT-PWD-8301 | Central Java | Jawa Tengah | Grobogan | -7.0485 | 110.6059 | New | New | New | Type B | MA | JAW-JT-PWD-8301 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | S000054295 | S000054296 | 12. NY TERMINATION | 2025-12-07 | 49 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-24 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8294_1 | New_JAW-JT-PWD-8294 | JAW-JT-PWD-8294 | Central Java | Jawa Tengah | Grobogan | -7.0727 | 110.5872 | New | New | New | Type B | MA | JAW-JT-PWD-8294 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | S000054296 | S000054297 | 12. NY TERMINATION | 2025-12-07 | 49 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-24 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8297_1 | New_JAW-JT-PWD-8297 | JAW-JT-PWD-8297 | Central Java | Jawa Tengah | Grobogan | -7.0827 | 110.5979 | New | New | New | Type B | MA | JAW-JT-PWD-8297 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | S000054297 | S000054298 | 12. NY TERMINATION | 2025-12-07 | 49 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-24 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-1534_1 | New_JAW-JT-PWD-1534 | JAW-JT-PWD-1534 | Central Java | Jawa Tengah | Grobogan | -7.0936 | 110.6037 | New | New | New | Type B | MA | JAW-JT-PWD-1534 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | S000054298 | S000054299 | 12. NY TERMINATION | 2025-12-07 | 49 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-24 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8298_1 | New_JAW-JT-PWD-8298 | JAW-JT-PWD-8298 | Central Java | Jawa Tengah | Grobogan | -7.1156 | 110.5995 | New | New | New | Type B | MA | JAW-JT-PWD-8298 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | S000054299 | S000054300 | 12. NY TERMINATION | 2025-12-07 | 49 |  | #N/A | No |  | 2025-624 sites | FO NY RFS |  | 2025-11-24 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8299_1 | New_JAW-JT-PWD-8299 | JAW-JT-PWD-8299 | Central Java | Jawa Tengah | Grobogan | -7.0928 | 110.5858 | New | New | New | Type B | MA | JAW-JT-PWD-8299 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | S000054300 | S000054301 | 12. NY TERMINATION | 2025-12-07 | 49 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-24 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8293_1 | New_JAW-JT-PWD-8293 | JAW-JT-PWD-8293 | Central Java | Jawa Tengah | Grobogan | -7.0884 | 110.5765 | New | New | New | Type B | MA | JAW-JT-PWD-8293 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | S000054301 | S000054302 | 12. NY TERMINATION | 2025-12-07 | 49 |  | #N/A | No |  | 2025-624 sites | FO NY RFS |  | 2025-11-25 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8676_1 | New_JAW-JT-SMG-8676 | JAW-JT-SMG-8676 | Central Java | Jawa Tengah | Kota Semarang | -7.0541 | 110.4782 | New | New | New | Type B | MA | JAW-JT-SMG-8676 |  |  |  |  | - | - | - | - | New Purchase | New Ring 013 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019850 | S000054302 | S000054303 | 12. NY TERMINATION | 2025-12-07 | 49 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2025-11-25 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8390_1 | New_JAW-JT-PWD-8390 | JAW-JT-PWD-8390 | Central Java | Jawa Tengah | Grobogan | -7.141 | 110.8576 | New | New | New | Type B | MA | JAW-JT-PWD-8390 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | S000054304 | S000054306 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-25 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8378_1 | New_JAW-JT-PWD-8378 | JAW-JT-PWD-8378 | Central Java | Jawa Tengah | Grobogan | -7.1787 | 110.8219 | New | New | New | Type B | MA | JAW-JT-PWD-8378 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | S000054306 | S000054307 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-25 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8372_1 | New_JAW-JT-PWD-8372 | JAW-JT-PWD-8372 | Central Java | Jawa Tengah | Grobogan | -7.1653 | 110.8055 | New | New | New | Type B | MA | JAW-JT-PWD-8372 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | S000054307 | S000054308 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-25 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8364_1 | New_JAW-JT-PWD-8364 | JAW-JT-PWD-8364 | Central Java | Jawa Tengah | Grobogan | -7.1675 | 110.7865 | New | New | New | Type B | MA | JAW-JT-PWD-8364 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | S000054308 | S000054309 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-25 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8352_1 | New_JAW-JT-PWD-8352 | JAW-JT-PWD-8352 | Central Java | Jawa Tengah | Grobogan | -7.1738 | 110.7627 | New | New | New | Type B | MA | JAW-JT-PWD-8352 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | S000054309 | S000054310 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-25 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8354_1 | New_JAW-JT-PWD-8354 | JAW-JT-PWD-8354 | Central Java | Jawa Tengah | Grobogan | -7.148 | 110.7638 | New | New | New | Type B | MA | JAW-JT-PWD-8354 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | S000054310 | S000054311 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-25 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8370_1 | New_JAW-JT-PWD-8370 | JAW-JT-PWD-8370 | Central Java | Jawa Tengah | Grobogan | -7.1341 | 110.7992 | New | New | New | Type B | MA | JAW-JT-PWD-8370 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | S000054311 | S000054305 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-25 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8367_1 | New_JAW-JT-PWD-8367 | JAW-JT-PWD-8367 | Central Java | Jawa Tengah | Grobogan | -7.1233 | 110.7912 | New | New | New | Type B | MA | JAW-JT-PWD-8367 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | S000054305 | S000054312 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-25 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8351_1 | New_JAW-JT-PWD-8351 | JAW-JT-PWD-8351 | Central Java | Jawa Tengah | Grobogan | -7.1054 | 110.7611 | New | New | New | Type B | MA | JAW-JT-PWD-8351 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | S000054312 | S000054313 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-25 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8347_1 | New_JAW-JT-PWD-8347 | JAW-JT-PWD-8347 | Central Java | Jawa Tengah | Grobogan | -7.1061 | 110.7417 | New | New | New | Type B | MA | JAW-JT-PWD-8347 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | S000054313 | S000054314 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-25 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8339_1 | New_JAW-JT-PWD-8339 | JAW-JT-PWD-8339 | Central Java | Jawa Tengah | Grobogan | -7.1122 | 110.7163 | New | New | New | Type B | MA | JAW-JT-PWD-8339 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | S000054314 | S000054315 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-11-25 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8334_1 | New_JAW-JT-PWD-8334 | JAW-JT-PWD-8334 | Central Java | Jawa Tengah | Grobogan | -7.0982 | 110.7037 | New | New | New | Type B | MA | JAW-JT-PWD-8334 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | S000054315 | S000054316 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  |  |  |  | 2025-11-26 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-0038_1 | New_JAW-JT-PWD-0038 | JAW-JT-PWD-0038 | Central Java | Jawa Tengah | Grobogan | -7.1036 | 110.6891 | New | New | New | Type B | MA | JAW-JT-PWD-0038 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | S000054316 | S000054317 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-26 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-1542_1 | New_JAW-JT-PWD-1542 | JAW-JT-PWD-1542 | Central Java | Jawa Tengah | Grobogan | -7.1286 | 110.6664 | New | New | New | Type B | MA | JAW-JT-PWD-1542 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | S000054317 | S000054318 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-26 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8314_1 | New_JAW-JT-PWD-8314 | JAW-JT-PWD-8314 | Central Java | Jawa Tengah | Grobogan | -7.1543 | 110.6467 | New | New | New | Type B | MA | JAW-JT-PWD-8314 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | S000054318 | S000054319 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-26 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-1537_1 | New_JAW-JT-PWD-1537 | JAW-JT-PWD-1537 | Central Java | Jawa Tengah | Grobogan | -7.1586 | 110.6326 | New | New | New | Type B | MA | JAW-JT-PWD-1537 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | S000054319 | S000054320 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-26 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-4109_1 | New_JAW-JT-PWD-4109 | JAW-JT-PWD-4109 | Central Java | Jawa Tengah | Grobogan | -7.1708 | 110.6336 | New | New | New | Type B | MA | JAW-JT-PWD-4109 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | S000054320 | S000054321 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-26 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8311_1 | New_JAW-JT-PWD-8311 | JAW-JT-PWD-8311 | Central Java | Jawa Tengah | Grobogan | -7.2105 | 110.6406 | New | New | New | Type B | MA | JAW-JT-PWD-8311 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | S000054321 | S000054322 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-11-26 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-2554_1 | New_JAW-JT-UNR-2554 | JAW-JT-UNR-2554 | Central Java | Jawa Tengah | Semarang | -7.2367 | 110.6153 | New | New | New | Type B | MA | JAW-JT-UNR-2554 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | S000054322 | S000054323 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-End Nov | FO NY RFS |  | 2025-11-26 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8558_1 | New_JAW-JT-UNR-8558 | JAW-JT-UNR-8558 | Central Java | Jawa Tengah | Semarang | -7.3155 | 110.5722 | New | New | New | Type B | MA | JAW-JT-UNR-8558 |  |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019851 | S000054323 | S000054324 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-End Nov | FO NY RFS |  | 2025-11-26 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8405_1 | New_JAW-JT-PWD-8405 | JAW-JT-PWD-8405 | Central Java | Jawa Tengah | Grobogan | -7.1518 | 110.8921 | New | New | New | Type B | MA | JAW-JT-PWD-8405 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | S000054325 | S000054326 | 12. NY TERMINATION | 2025-11-16 | 46 |  | #N/A | No |  | 2026 | FO NY RFS | GPA | 2025-11-26 | 48 |  |  | 2025 | 2025-11-11 |  |  |  |  | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-1566_1 | New_JAW-JT-PWD-1566 | JAW-JT-PWD-1566 | Central Java | Jawa Tengah | Grobogan | -7.1689 | 110.879 | New | New | New | Type B | MA | JAW-JT-PWD-1566 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | S000054326 | S000054327 | 12. NY TERMINATION | 2025-11-16 | 46 |  | #N/A | No |  | 2026 | FO NY RFS | GPA | 2025-11-26 | 48 |  |  | 2025 | 2025-11-10 | 2025-11-25 11:00:57 | Reviewing |  |  | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8402_1 | New_JAW-JT-PWD-8402 | JAW-JT-PWD-8402 | Central Java | Jawa Tengah | Grobogan | -7.1591 | 110.8687 | New | New | New | Type B | MA | JAW-JT-PWD-8402 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000018247 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-11-26 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8389_1 | New_JAW-JT-PWD-8389 | JAW-JT-PWD-8389 | Central Java | Jawa Tengah | Grobogan | -7.1655 | 110.8559 | New | New | New | Type B | MA | JAW-JT-PWD-8389 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | S000054328 | S000054329 | 12. NY TERMINATION | 2025-11-16 | 46 |  | #N/A | No |  | 2026 | FO NY RFS | GPA | 2025-11-26 | 48 |  |  | 2025 | 2025-11-11 | 2025-11-25 16:42:38 | Reviewing |  |  | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8384_1 | New_JAW-JT-PWD-8384 | JAW-JT-PWD-8384 | Central Java | Jawa Tengah | Grobogan | -7.1912 | 110.8423 | New | New | New | Type B | MA | JAW-JT-PWD-8384 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000018247 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-11-27 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-0019_1 | New_JAW-JT-PWD-0019 | JAW-JT-PWD-0019 | Central Java | Jawa Tengah | Grobogan | -7.1921 | 110.8206 | New | New | New | Type B | MA | JAW-JT-PWD-0019 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | S000054330 | S000054331 | 12. NY TERMINATION | 2025-11-16 | 46 |  | #N/A | No |  | 2026 | FO NY RFS | GPA | 2025-11-27 | 48 |  |  | 2025 | 2025-11-11 | 2025-11-23 13:01:59 | Reviewing |  |  | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8371_1 | New_JAW-JT-PWD-8371 | JAW-JT-PWD-8371 | Central Java | Jawa Tengah | Grobogan | -7.1778 | 110.8028 | New | New | New | Type B | MA | JAW-JT-PWD-8371 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | S000054331 | S000054332 | 12. NY TERMINATION | 2025-11-16 | 46 |  | #N/A | No |  | 2025-624 sites | FO NY RFS | GPA | 2025-11-27 | 48 |  |  | 2025 | 2025-11-11 | 2025-11-23 09:09:09 | Reviewing |  |  | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8366_1 | New_JAW-JT-PWD-8366 | JAW-JT-PWD-8366 | Central Java | Jawa Tengah | Grobogan | -7.1941 | 110.7871 | New | New | New | Type B | MA | JAW-JT-PWD-8366 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | S000054332 | S000054333 | 12. NY TERMINATION | 2025-11-16 | 46 |  | #N/A | No |  | 2025-624 sites | FO NY RFS | GPA | 2025-11-27 | 48 |  |  | 2025 |  | 2025-11-23 16:40:09 | Reviewing |  |  | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-BYL-8374_1 | New_JAW-JT-BYL-8374 | JAW-JT-BYL-8374 | Central Java | Jawa Tengah | Grobogan | -7.2022 | 110.7954 | New | New | New | Type B | MA | JAW-JT-BYL-8374 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_3 1x25G/10G LR + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | S000054333 | S000054334 | 12. NY TERMINATION | 2025-11-16 | 46 |  | #N/A | No |  | 2025-624 sites | FO NY RFS | GPA | 2025-11-27 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-2997_1 | New_JAW-JT-PWD-2997 | JAW-JT-PWD-2997 | Central Java | Jawa Tengah | Grobogan | -7.2456 | 110.8476 | New | New | New | Type B | MA | JAW-JT-PWD-2997 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000018247 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-11-27 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8412_1 | New_JAW-JT-PWD-8412 | JAW-JT-PWD-8412 | Central Java | Jawa Tengah | Grobogan | -7.2426 | 110.9033 | New | New | New | Type B | MA | JAW-JT-PWD-8412 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | S000054335 | S000054336 | 12. NY TERMINATION | 2025-11-16 | 46 |  | #N/A | No |  |  |  | GPA | 2025-11-27 | 48 |  |  | 2025 | 2025-11-10 | 2025-11-21 | Reviewing |  |  | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8442_1 | New_JAW-JT-PWD-8442 | JAW-JT-PWD-8442 | Central Java | Jawa Tengah | Grobogan | -7.2681 | 110.9323 | New | New | New | Type B | MA | JAW-JT-PWD-8442 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | S000054336 | S000054337 | 12. NY TERMINATION | 2025-11-16 | 46 |  | #N/A | No |  | 2026 | FO NY RFS | GPA | 2025-11-27 | 48 |  |  | 2025 | 2025-11-10 | 2025-11-22 16:50:21 | Reviewing |  |  | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-0004_1 | New_JAW-JT-PWD-0004 | JAW-JT-PWD-0004 | Central Java | Jawa Tengah | Grobogan | -7.2134 | 110.9442 | New | New | New | Type B | MA | JAW-JT-PWD-0004 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | S000054337 | S000054338 | 12. NY TERMINATION | 2025-11-16 | 46 |  | #N/A | No |  | 2026 | FO NY RFS | GPA | 2025-11-27 | 48 |  |  | 2025 | 2025-11-10 | 2025-11-17 | Approved | 2025-11-22 |  | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-1593_1 | New_JAW-JT-PWD-1593 | JAW-JT-PWD-1593 | Central Java | Jawa Tengah | Grobogan | -7.1941 | 111.0002 | New | New | New | Type B | MA | JAW-JT-PWD-1593 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | S000054338 | S000054339 | 12. NY TERMINATION | 2025-11-16 | 46 |  | #N/A | No |  | 2026 | FO NY RFS | GPA | 2025-11-27 | 48 |  |  | 2025 | 2025-11-10 | 2025-11-17 | Approved | 2025-11-22 |  | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8481_1 | New_JAW-JT-PWD-8481 | JAW-JT-PWD-8481 | Central Java | Jawa Tengah | Grobogan | -7.1688 | 110.9991 | New | New | New | Type B | MA | JAW-JT-PWD-8481 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | S000054339 | S000054340 | 12. NY TERMINATION | 2025-11-16 | 46 |  | #N/A | No |  | 2025-624 sites | FO NY RFS | GPA | 2025-11-27 | 48 |  |  | 2025 | 2025-11-10 | 2025-11-22 18:38:07 | Reviewing |  |  | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8474_1 | New_JAW-JT-PWD-8474 | JAW-JT-PWD-8474 | Central Java | Jawa Tengah | Grobogan | -7.1343 | 110.9903 | New | New | New | Type B | MA | JAW-JT-PWD-8474 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | S000054340 | S000054341 | 12. NY TERMINATION | 2025-11-16 | 46 |  | #N/A | No |  | 2026 | FO NY RFS | GPA | 2025-11-27 | 48 |  |  | 2025 | 2025-11-10 | 2025-11-19 | Approved | 2025-11-22 |  | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8472_1 | New_JAW-JT-PWD-8472 | JAW-JT-PWD-8472 | Central Java | Jawa Tengah | Grobogan | -7.1036 | 110.9805 | New | New | New | Type B | MA | JAW-JT-PWD-8472 |  |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019852 | S000054341 | S000054342 | 12. NY TERMINATION | 2025-11-16 | 46 |  | #N/A | No |  | 2025-624 sites | FO NY RFS | GPA | 2025-11-27 | 48 |  |  | 2025 | 2025-11-12 | 2025-11-22 23:49:37 | Reviewing |  |  | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-4001_1 | New_JAW-JT-PWD-4001 | JAW-JT-PWD-4001 | Central Java | Jawa Tengah | Grobogan | -7.1607 | 110.9029 | New | New | New | Type B | MA | JAW-JT-PWD-4001 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | S000054343 | S000054344 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-28 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8409_1 | New_JAW-JT-PWD-8409 | JAW-JT-PWD-8409 | Central Java | Jawa Tengah | Grobogan | -7.1809 | 110.8979 | New | New | New | Type B | MA | JAW-JT-PWD-8409 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | S000054344 | S000054345 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-28 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8392_1 | New_JAW-JT-PWD-8392 | JAW-JT-PWD-8392 | Central Java | Jawa Tengah | Grobogan | -7.2077 | 110.8633 | New | New | New | Type B | MA | JAW-JT-PWD-8392 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | S000054345 | S000054346 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-28 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-1571_1 | New_JAW-JT-PWD-1571 | JAW-JT-PWD-1571 | Central Java | Jawa Tengah | Grobogan | -7.2179 | 110.9044 | New | New | New | Type B | MA | JAW-JT-PWD-1571 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | S000054346 | S000054347 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-28 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8430_1 | New_JAW-JT-PWD-8430 | JAW-JT-PWD-8430 | Central Java | Jawa Tengah | Grobogan | -7.2105 | 110.9023 | New | New | New | Type B | MA | JAW-JT-PWD-8430 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | S000054347 | S000054348 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2025-624 sites | FO NY RFS |  | 2025-11-28 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8441_1 | New_JAW-JT-PWD-8441 | JAW-JT-PWD-8441 | Central Java | Jawa Tengah | Grobogan | -7.1828 | 110.9183 | New | New | New | Type B | MA | JAW-JT-PWD-8441 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | S000054348 | S000054349 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-28 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8423_1 | New_JAW-JT-PWD-8423 | JAW-JT-PWD-8423 | Central Java | Jawa Tengah | Grobogan | -7.1719 | 110.9125 | New | New | New | Type B | MA | JAW-JT-PWD-8423 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | S000054349 | S000054350 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-28 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8450_1 | New_JAW-JT-PWD-8450 | JAW-JT-PWD-8450 | Central Java | Jawa Tengah | Grobogan | -7.1739 | 110.9343 | New | New | New | Type B | MA | JAW-JT-PWD-8450 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | S000054350 | S000054351 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-28 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8453_1 | New_JAW-JT-PWD-8453 | JAW-JT-PWD-8453 | Central Java | Jawa Tengah | Grobogan | -7.1866 | 110.9459 | New | New | New | Type B | MA | JAW-JT-PWD-8453 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | S000054351 | S000054352 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-28 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8460_1 | New_JAW-JT-PWD-8460 | JAW-JT-PWD-8460 | Central Java | Jawa Tengah | Grobogan | -7.1602 | 110.9609 | New | New | New | Type B | MA | JAW-JT-PWD-8460 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | S000054352 | S000054353 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-28 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8468_1 | New_JAW-JT-PWD-8468 | JAW-JT-PWD-8468 | Central Java | Jawa Tengah | Grobogan | -7.1679 | 110.9743 | New | New | New | Type B | MA | JAW-JT-PWD-8468 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | S000054353 | S000054354 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2025-624 sites | FO NY RFS |  | 2025-11-28 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8456_1 | New_JAW-JT-PWD-8456 | JAW-JT-PWD-8456 | Central Java | Jawa Tengah | Grobogan | -7.1296 | 110.9549 | New | New | New | Type B | MA | JAW-JT-PWD-8456 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | S000054354 | S000054355 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-11-28 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8461_1 | New_JAW-JT-PWD-8461 | JAW-JT-PWD-8461 | Central Java | Jawa Tengah | Grobogan | -7.1054 | 110.9622 | New | New | New | Type B | MA | JAW-JT-PWD-8461 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | S000054355 | S000054356 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2025-624 sites | FO NY RFS |  | 2025-11-28 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-1576_1 | New_JAW-JT-PWD-1576 | JAW-JT-PWD-1576 | Central Java | Jawa Tengah | Grobogan | -7.0951 | 110.9419 | New | New | New | Type B | MA | JAW-JT-PWD-1576 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | S000054356 | S000054357 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2025-12-01 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8439_1 | New_JAW-JT-PWD-8439 | JAW-JT-PWD-8439 | Central Java | Jawa Tengah | Grobogan | -7.0844 | 110.9178 | New | New | New | Type B | MA | JAW-JT-PWD-8439 |  |  |  |  | - | - | - | - | New Purchase | New Ring 016 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019853 | S000054357 | S000054358 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2025-624 sites | FO NY RFS |  | 2025-12-01 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-0036_1 | New_JAW-JT-PWD-0036 | JAW-JT-PWD-0036 | Central Java | Jawa Tengah | Grobogan | -7.1602 | 111.0203 | New | New | New | Type B | MA | JAW-JT-PWD-0036 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056108 | S000056109 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-12-01 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8521_1 | New_JAW-JT-PWD-8521 | JAW-JT-PWD-8521 | Central Java | Jawa Tengah | Grobogan | -7.1592 | 111.0397 | New | New | New | Type B | MA | JAW-JT-PWD-8521 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056109 | S000056110 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-12-01 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8530_1 | New_JAW-JT-PWD-8530 | JAW-JT-PWD-8530 | Central Java | Jawa Tengah | Grobogan | -7.1822 | 111.0586 | New | New | New | Type B | MA | JAW-JT-PWD-8530 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056110 | S000056111 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-12-01 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-0027_1 | New_JAW-JT-PWD-0027 | JAW-JT-PWD-0027 | Central Java | Jawa Tengah | Grobogan | -7.1971 | 111.0699 | New | New | New | Type B | MA | JAW-JT-PWD-0027 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056111 | S000056112 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-12-01 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8555_1 | New_JAW-JT-PWD-8555 | JAW-JT-PWD-8555 | Central Java | Jawa Tengah | Grobogan | -7.2247 | 111.0861 | New | New | New | Type B | MA | JAW-JT-PWD-8555 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056112 | S000056113 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-12-01 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8538_1 | New_JAW-JT-PWD-8538 | JAW-JT-PWD-8538 | Central Java | Jawa Tengah | Grobogan | -7.1629 | 111.0768 | New | New | New | Type B | MA | JAW-JT-PWD-8538 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056113 | S000056114 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-12-01 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8548_1 | New_JAW-JT-PWD-8548 | JAW-JT-PWD-8548 | Central Java | Jawa Tengah | Grobogan | -7.1605 | 111.0898 | New | New | New | Type B | MA | JAW-JT-PWD-8548 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056114 | S000056115 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-12-01 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8556_1 | New_JAW-JT-PWD-8556 | JAW-JT-PWD-8556 | Central Java | Jawa Tengah | Grobogan | -7.1609 | 111.1035 | New | New | New | Type B | MA | JAW-JT-PWD-8556 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056115 | S000056116 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-12-01 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8558_1 | New_JAW-JT-PWD-8558 | JAW-JT-PWD-8558 | Central Java | Jawa Tengah | Grobogan | -7.1901 | 111.1076 | New | New | New | Type B | MA | JAW-JT-PWD-8558 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056116 | S000056117 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-12-01 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8570_1 | New_JAW-JT-PWD-8570 | JAW-JT-PWD-8570 | Central Java | Jawa Tengah | Grobogan | -7.1619 | 111.138 | New | New | New | Type B | MA | JAW-JT-PWD-8570 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056117 | S000056118 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS | YPTT | 2025-12-01 | 49 |  |  | 2025 | 2025-11-17 | 2025-11-17 | Approved | 2025-11-22 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8500_1 | New_JAW-JT-PWD-8500 | JAW-JT-PWD-8500 | Central Java | Jawa Tengah | Grobogan | -7.1839 | 111.1973 | New | New | New | Type B | MA | JAW-JT-PWD-8500 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056118 | S000056119 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-12-01 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8513_1 | New_JAW-JT-PWD-8513 | JAW-JT-PWD-8513 | Central Java | Jawa Tengah | Grobogan | -7.1899 | 111.2293 | New | New | New | Type B | MA | JAW-JT-PWD-8513 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056119 | S000056120 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-12-02 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8511_1 | New_JAW-JT-PWD-8511 | JAW-JT-PWD-8511 | Central Java | Jawa Tengah | Grobogan | -7.1563 | 111.2218 | New | New | New | Type B | MA | JAW-JT-PWD-8511 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056120 | S000056121 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-12-02 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-1620_1 | New_JAW-JT-PWD-1620 | JAW-JT-PWD-1620 | Central Java | Jawa Tengah | Grobogan | -7.1063 | 111.2031 | New | New | New | Type B | MA | JAW-JT-PWD-1620 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056121 | S000056122 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-12-02 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8496_1 | New_JAW-JT-PWD-8496 | JAW-JT-PWD-8496 | Central Java | Jawa Tengah | Grobogan | -7.079 | 111.1935 | New | New | New | Type B | MA | JAW-JT-PWD-8496 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056122 | S000056123 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS | YPTT | 2025-12-02 | 49 |  |  | 2025 | 2025-11-17 | 2025-11-17 | Approved | 2025-11-22 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8493_1 | New_JAW-JT-PWD-8493 | JAW-JT-PWD-8493 | Central Java | Jawa Tengah | Grobogan | -7.0635 | 111.1681 | New | New | New | Type B | MA | JAW-JT-PWD-8493 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056123 | S000056124 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-12-02 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8526_1 | New_JAW-JT-PWD-8526 | JAW-JT-PWD-8526 | Central Java | Jawa Tengah | Grobogan | -7.084 | 111.0531 | New | New | New | Type B | MA | JAW-JT-PWD-8526 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056124 | S000056125 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-12-02 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8516_1 | New_JAW-JT-PWD-8516 | JAW-JT-PWD-8516 | Central Java | Jawa Tengah | Grobogan | -7.0318 | 111.0298 | New | New | New | Type B | MA | JAW-JT-PWD-8516 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056125 | S000056126 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS | YPTT | 2025-12-02 | 49 |  |  | 2025 | 2025-11-17 | 2025-11-17 | Approved | 2025-11-22 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8477_1 | New_JAW-JT-PWD-8477 | JAW-JT-PWD-8477 | Central Java | Jawa Tengah | Grobogan | -7.055 | 110.9968 | New | New | New | Type B | MA | JAW-JT-PWD-8477 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056126 | S000056127 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-12-02 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8459_1 | New_JAW-JT-PWD-8459 | JAW-JT-PWD-8459 | Central Java | Jawa Tengah | Grobogan | -7.0628 | 110.9597 | New | New | New | Type B | MA | JAW-JT-PWD-8459 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056127 | S000056128 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-12-02 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8444_1 | New_JAW-JT-PWD-8444 | JAW-JT-PWD-8444 | Central Java | Jawa Tengah | Grobogan | -7.0394 | 110.9193 | New | New | New | Type B | MA | JAW-JT-PWD-8444 |  |  |  |  | - | - | - | - | New Purchase | New Ring 017 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020475 | S000056128 | S000056129 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-12-02 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8438_1 | New_JAW-JT-PWD-8438 | JAW-JT-PWD-8438 | Central Java | Jawa Tengah | Grobogan | -7.1393 | 110.9248 | New | New | New | Type B | MA | JAW-JT-PWD-8438 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | S000054359 | S000054360 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-12-02 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8440_1 | New_JAW-JT-PWD-8440 | JAW-JT-PWD-8440 | Central Java | Jawa Tengah | Grobogan | -7.1207 | 110.9295 | New | New | New | Type B | MA | JAW-JT-PWD-8440 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | S000054360 | S000054361 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-12-02 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8483_1 | New_JAW-JT-PWD-8483 | JAW-JT-PWD-8483 | Central Java | Jawa Tengah | Grobogan | -7.1207 | 111.0056 | New | New | New | Type B | MA | JAW-JT-PWD-8483 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | S000054361 | S000054362 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-12-02 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8522_1 | New_JAW-JT-PWD-8522 | JAW-JT-PWD-8522 | Central Java | Jawa Tengah | Grobogan | -7.1368 | 111.0419 | New | New | New | Type B | MA | JAW-JT-PWD-8522 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | S000054362 | S000054363 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-12-03 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8549_1 | New_JAW-JT-PWD-8549 | JAW-JT-PWD-8549 | Central Java | Jawa Tengah | Grobogan | -7.1326 | 111.0899 | New | New | New | Type B | MA | JAW-JT-PWD-8549 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | S000054363 | S000054364 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  |  |  |  | 2025-12-03 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8490_1 | New_JAW-JT-PWD-8490 | JAW-JT-PWD-8490 | Central Java | Jawa Tengah | Grobogan | -7.1458 | 111.1725 | New | New | New | Type B | MA | JAW-JT-PWD-8490 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | S000054364 | S000054365 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-12-03 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-3382_1 | New_JAW-JT-PWD-3382 | JAW-JT-PWD-3382 | Central Java | Jawa Tengah | Grobogan | -7.1565 | 111.1697 | New | New | New | Type B | MA | JAW-JT-PWD-3382 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | S000054365 | S000054366 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-12-03 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-1621_1 | New_JAW-JT-PWD-1621 | JAW-JT-PWD-1621 | Central Java | Jawa Tengah | Grobogan | -7.1805 | 111.219 | New | New | New | Type B | MA | JAW-JT-PWD-1621 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | S000054366 | S000054367 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  |  |  |  | 2025-12-03 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8512_1 | New_JAW-JT-PWD-8512 | JAW-JT-PWD-8512 | Central Java | Jawa Tengah | Grobogan | -7.1677 | 111.2233 | New | New | New | Type B | MA | JAW-JT-PWD-8512 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | S000054367 | S000054368 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-12-03 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8507_1 | New_JAW-JT-PWD-8507 | JAW-JT-PWD-8507 | Central Java | Jawa Tengah | Grobogan | -7.1389 | 111.2105 | New | New | New | Type B | MA | JAW-JT-PWD-8507 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | S000054368 | S000054369 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-12-03 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8492_1 | New_JAW-JT-PWD-8492 | JAW-JT-PWD-8492 | Central Java | Jawa Tengah | Grobogan | -7.1268 | 111.1803 | New | New | New | Type B | MA | JAW-JT-PWD-8492 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | S000054369 | S000054370 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-12-03 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8572_1 | New_JAW-JT-PWD-8572 | JAW-JT-PWD-8572 | Central Java | Jawa Tengah | Grobogan | -7.1007 | 111.1409 | New | New | New | Type B | MA | JAW-JT-PWD-8572 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | S000054370 | S000054371 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-12-03 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-0045_1 | New_JAW-JT-PWD-0045 | JAW-JT-PWD-0045 | Central Java | Jawa Tengah | Grobogan | -7.0827 | 111.1189 | New | New | New | Type B | MA | JAW-JT-PWD-0045 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | S000054371 | S000054372 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-12-03 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8533_1 | New_JAW-JT-PWD-8533 | JAW-JT-PWD-8533 | Central Java | Jawa Tengah | Grobogan | -7.0976 | 111.0524 | New | New | New | Type B | MA | JAW-JT-PWD-8533 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | S000054372 | S000054373 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-12-03 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8503_1 | New_JAW-JT-PWD-8503 | JAW-JT-PWD-8503 | Central Java | Jawa Tengah | Grobogan | -7.0698 | 111.0217 | New | New | New | Type B | MA | JAW-JT-PWD-8503 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | S000054373 | S000054374 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2025-12-03 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8471_1 | New_JAW-JT-PWD-8471 | JAW-JT-PWD-8471 | Central Java | Jawa Tengah | Grobogan | -7.0905 | 110.9791 | New | New | New | Type B | MA | JAW-JT-PWD-8471 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | S000054374 | S000054375 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-12-03 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8466_1 | New_JAW-JT-PWD-8466 | JAW-JT-PWD-8466 | Central Java | Jawa Tengah | Grobogan | -7.0857 | 110.9669 | New | New | New | Type B | MA | JAW-JT-PWD-8466 |  |  |  |  | - | - | - | - | New Purchase | New Ring 018 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019854 | S000054375 | S000054376 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2025-12-04 | 49 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-4015_1 | New_JAW-JT-JPA-4015 | JAW-JT-JPA-4015 | Central Java | Jawa Tengah | Jepara | -6.7068 | 110.7456 | New | New | New | Type B | MA | JAW-JT-JPA-4015 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | S000054205 | S000054206 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8441_1 | New_JAW-JT-JPA-8441 | JAW-JT-JPA-8441 | Central Java | Jawa Tengah | Jepara | -6.7303 | 110.8032 | New | New | New | Type B | MA | JAW-JT-JPA-8441 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | S000054206 | S000054207 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-0709_1 | New_JAW-JT-JPA-0709 | JAW-JT-JPA-0709 | Central Java | Jawa Tengah | Jepara | -6.6973 | 110.8248 | New | New | New | Type B | MA | JAW-JT-JPA-0709 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | S000054207 | S000054208 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8446_1 | New_JAW-JT-JPA-8446 | JAW-JT-JPA-8446 | Central Java | Jawa Tengah | Jepara | -6.6717 | 110.8231 | New | New | New | Type B | MA | JAW-JT-JPA-8446 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | S000054208 | S000054209 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-0714_1 | New_JAW-JT-JPA-0714 | JAW-JT-JPA-0714 | Central Java | Jawa Tengah | Jepara | -6.6508 | 110.7552 | New | New | New | Type B | MA | JAW-JT-JPA-0714 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | S000054209 | S000054210 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8399_1 | New_JAW-JT-JPA-8399 | JAW-JT-JPA-8399 | Central Java | Jawa Tengah | Jepara | -6.6397 | 110.7454 | New | New | New | Type B | MA | JAW-JT-JPA-8399 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | S000054210 | S000054211 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8407_1 | New_JAW-JT-JPA-8407 | JAW-JT-JPA-8407 | Central Java | Jawa Tengah | Jepara | -6.6306 | 110.7544 | New | New | New | Type B | MA | JAW-JT-JPA-8407 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | S000054211 | S000054212 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8388_1 | New_JAW-JT-JPA-8388 | JAW-JT-JPA-8388 | Central Java | Jawa Tengah | Jepara | -6.6073 | 110.7331 | New | New | New | Type B | MA | JAW-JT-JPA-8388 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | S000054212 | S000054213 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8348_1 | New_JAW-JT-JPA-8348 | JAW-JT-JPA-8348 | Central Java | Jawa Tengah | Jepara | -6.5979 | 110.7053 | New | New | New | Type B | MA | JAW-JT-JPA-8348 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | S000054213 | S000054214 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8398_1 | New_JAW-JT-JPA-8398 | JAW-JT-JPA-8398 | Central Java | Jawa Tengah | Jepara | -6.5866 | 110.7451 | New | New | New | Type B | MA | JAW-JT-JPA-8398 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | S000054214 | S000054215 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-0609_1 | New_JAW-JT-JPA-0609 | JAW-JT-JPA-0609 | Central Java | Jawa Tengah | Jepara | -6.5991 | 110.7759 | New | New | New | Type B | MA | JAW-JT-JPA-0609 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | S000054215 | S000054217 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-0693_1 | New_JAW-JT-JPA-0693 | JAW-JT-JPA-0693 | Central Java | Jawa Tengah | Jepara | -6.5779 | 110.7853 | New | New | New | Type B | MA | JAW-JT-JPA-0693 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | S000054217 | S000054218 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-0702_1 | New_JAW-JT-JPA-0702 | JAW-JT-JPA-0702 | Central Java | Jawa Tengah | Jepara | -6.5641 | 110.7581 | New | New | New | Type B | MA | JAW-JT-JPA-0702 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | S000054218 | S000054219 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8424_1 | New_JAW-JT-JPA-8424 | JAW-JT-JPA-8424 | Central Java | Jawa Tengah | Jepara | -6.542 | 110.7746 | New | New | New | Type B | MA | JAW-JT-JPA-8424 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | S000054219 | S000054216 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8435_1 | New_JAW-JT-JPA-8435 | JAW-JT-JPA-8435 | Central Java | Jawa Tengah | Jepara | -6.558 | 110.7922 | New | New | New | Type B | MA | JAW-JT-JPA-8435 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | S000054216 | S000054220 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8430_1 | New_JAW-JT-JPA-8430 | JAW-JT-JPA-8430 | Central Java | Jawa Tengah | Jepara | -6.5281 | 110.7832 | New | New | New | Type B | MA | JAW-JT-JPA-8430 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | S000054220 | S000054221 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8451_1 | New_JAW-JT-JPA-8451 | JAW-JT-JPA-8451 | Central Java | Jawa Tengah | Jepara | -6.5462 | 110.8564 | New | New | New | Type B | MA | JAW-JT-JPA-8451 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | S000054221 | S000054222 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-0708_1 | New_JAW-JT-JPA-0708 | JAW-JT-JPA-0708 | Central Java | Jawa Tengah | Jepara | -6.5154 | 110.8787 | New | New | New | Type B | MA | JAW-JT-JPA-0708 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | S000054222 | S000054223 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8461_1 | New_JAW-JT-JPA-8461 | JAW-JT-JPA-8461 | Central Java | Jawa Tengah | Jepara | -6.5226 | 110.8932 | New | New | New | Type B | MA | JAW-JT-JPA-8461 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | S000054223 | S000054224 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-0687_1 | New_JAW-JT-JPA-0687 | JAW-JT-JPA-0687 | Central Java | Jawa Tengah | Jepara | -6.5471 | 110.9028 | New | New | New | Type B | MA | JAW-JT-JPA-0687 |  |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019804 | S000054224 | S000054225 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JI-BKL-3125_1 | New_JAW-JI-BKL-3125 | JAW-JI-BKL-3125 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8907 | 110.3356 | New | New | New | Type B | MA | JAW-JI-BKL-3125 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020469 | [6 empty] | #N/A | [5 empty] | 2025-12-05 | 49 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3254_1 | New_JAW-JI-BKL-3254 | JAW-JI-BKL-3254 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8914 | 110.3283 | New | New | New | Type B | MA | JAW-JI-BKL-3254 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020469 | [6 empty] | #N/A | [5 empty] | 2025-12-05 | 49 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-3001_1 | New_JAW-YO-BTL-3001 | JAW-YO-BTL-3001 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8774 | 110.3161 | New | New | New | Type B | MA | JAW-YO-BTL-3001 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020469 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-05 | 49 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3283_1 | New_JAW-JI-BKL-3283 | JAW-JI-BKL-3283 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.902 | 110.2999 | New | New | New | Type B | MA | JAW-JI-BKL-3283 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020469 | [6 empty] | #N/A | [5 empty] | 2025-12-05 | 49 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3221_1 | New_JAW-JI-BKL-3221 | JAW-JI-BKL-3221 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8943 | 110.2963 | New | New | New | Type B | MA | JAW-JI-BKL-3221 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020469 | [6 empty] | #N/A | [5 empty] | 2025-12-05 | 49 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3280_1 | New_JAW-JI-BKL-3280 | JAW-JI-BKL-3280 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8843 | 110.295 | New | New | New | Type B | MA | JAW-JI-BKL-3280 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020469 | [6 empty] | #N/A | [5 empty] | 2025-12-22 | 52 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3276_1 | New_JAW-JI-BKL-3276 | JAW-JI-BKL-3276 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.863 | 110.2879 | New | New | New | Type B | MA | JAW-JI-BKL-3276 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020469 | [6 empty] | #N/A | [5 empty] | 2025-12-22 | 52 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3184_1 | New_JAW-JI-BKL-3184 | JAW-JI-BKL-3184 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8537 | 110.2686 | New | New | New | Type B | MA | JAW-JI-BKL-3184 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020469 | [6 empty] | #N/A | [5 empty] | 2025-12-22 | 52 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3273_1 | New_JAW-JI-BKL-3273 | JAW-JI-BKL-3273 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8518 | 110.2571 | New | New | New | Type B | MA | JAW-JI-BKL-3273 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020469 | [6 empty] | #N/A | [5 empty] | 2025-12-22 | 52 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0150_1 | New_JAW-YO-BTL-0150 | JAW-YO-BTL-0150 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8319 | 110.2734 | New | New | New | Type B | MA | JAW-YO-BTL-0150 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020469 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-22 | 52 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-8158_1 | New_JAW-YO-BTL-8158 | JAW-YO-BTL-8158 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8132 | 110.2819 | New | New | New | Type B | MA | JAW-YO-BTL-8158 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020469 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-22 | 52 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-SMN-0004_1 | New_JAW-YO-SMN-0004 | JAW-YO-SMN-0004 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.7998 | 110.2827 | New | New | New | Type B | MA | JAW-YO-SMN-0004 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_3 1x25G/10G LR + 1x10G ZR + 6x1G LR |  |  | R0000020469 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-22 | 52 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3257_1 | New_JAW-JI-BKL-3257 | JAW-JI-BKL-3257 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8123 | 110.2503 | New | New | New | Type B | MA | JAW-JI-BKL-3257 |  |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020469 | [6 empty] | #N/A | [5 empty] | 2025-12-22 | 52 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0013_1 | New_JAW-YO-BTL-0013 | JAW-YO-BTL-0013 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8833 | 110.3339 | New | New | New | Type B | MA | JAW-YO-BTL-0013 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-22 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3265_1 | New_JAW-JI-BKL-3265 | JAW-JI-BKL-3265 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8475 | 110.3392 | New | New | New | Type B | MA | JAW-JI-BKL-3265 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020470 | [6 empty] | #N/A | [5 empty] | 2025-12-22 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0153_1 | New_JAW-YO-BTL-0153 | JAW-YO-BTL-0153 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8394 | 110.3392 | New | New | New | Type B | MA | JAW-YO-BTL-0153 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-22 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3137_1 | New_JAW-JI-BKL-3137 | JAW-JI-BKL-3137 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.844 | 110.3325 | New | New | New | Type B | MA | JAW-JI-BKL-3137 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | [6 empty] | #N/A | [5 empty] | 2025-12-22 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3136_1 | New_JAW-JI-BKL-3136 | JAW-JI-BKL-3136 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8355 | 110.328 | New | New | New | Type B | MA | JAW-JI-BKL-3136 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | [6 empty] | #N/A | [5 empty] | 2025-12-22 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3191_1 | New_JAW-JI-BKL-3191 | JAW-JI-BKL-3191 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8284 | 110.3308 | New | New | New | Type B | MA | JAW-JI-BKL-3191 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | [6 empty] | #N/A | [5 empty] | 2025-12-23 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3146_1 | New_JAW-JI-BKL-3146 | JAW-JI-BKL-3146 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8254 | 110.3353 | New | New | New | Type B | MA | JAW-JI-BKL-3146 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | [6 empty] | #N/A | [5 empty] | 2025-12-23 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0035_1 | New_JAW-YO-BTL-0035 | JAW-YO-BTL-0035 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8232 | 110.3303 | New | New | New | Type B | MA | JAW-YO-BTL-0035 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-23 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0132_1 | New_JAW-YO-BTL-0132 | JAW-YO-BTL-0132 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8197 | 110.3234 | New | New | New | Type B | MA | JAW-YO-BTL-0132 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-23 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3240_1 | New_JAW-JI-BKL-3240 | JAW-JI-BKL-3240 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8113 | 110.3208 | New | New | New | Type B | MA | JAW-JI-BKL-3240 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | [6 empty] | #N/A |  |  |  |  | CCSI | 2025-12-23 | 52 |  |  | 2025 | 2025-11-11 |  |  |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-YO-BTL-0146_1 | New_JAW-YO-BTL-0146 | JAW-YO-BTL-0146 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8091 | 110.3216 | New | New | New | Type B | MA | JAW-YO-BTL-0146 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS | CCSI | 2025-12-23 | 52 |  |  | 2025 | 2025-11-11 | 2025-11-12 | Approved | 2025-11-22 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-JI-BKL-3156_1 | New_JAW-JI-BKL-3156 | JAW-JI-BKL-3156 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8087 | 110.3337 | New | New | New | Type B | MA | JAW-JI-BKL-3156 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | [6 empty] | #N/A | [5 empty] | 2025-12-23 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3230_1 | New_JAW-JI-BKL-3230 | JAW-JI-BKL-3230 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8125 | 110.3374 | New | New | New | Type B | MA | JAW-JI-BKL-3230 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | [6 empty] | #N/A | [5 empty] | 2025-12-23 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0008_1 | New_JAW-YO-BTL-0008 | JAW-YO-BTL-0008 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8174 | 110.3392 | New | New | New | Type B | MA | JAW-YO-BTL-0008 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-23 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0136_1 | New_JAW-YO-BTL-0136 | JAW-YO-BTL-0136 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8122 | 110.3447 | New | New | New | Type B | MA | JAW-YO-BTL-0136 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-23 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0684_1 | New_JAW-YO-YYK-0684 | JAW-YO-YYK-0684 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8011 | 110.3473 | New | New | New | Type B | MA | JAW-YO-YYK-0684 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-23 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8289_1 | New_JAW-YO-YYK-8289 | JAW-YO-YYK-8289 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7998 | 110.3517 | New | New | New | Type B | MA | JAW-YO-YYK-8289 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2025-12-23 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8270_1 | New_JAW-YO-YYK-8270 | JAW-YO-YYK-8270 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7975 | 110.3595 | New | New | New | Type B | MA | JAW-YO-YYK-8270 |  |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020470 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2025-12-23 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3268_1 | New_JAW-JI-BKL-3268 | JAW-JI-BKL-3268 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8726 | 110.4063 | New | New | New | Type B | MA | JAW-JI-BKL-3268 |  |  |  |  | - | - | - | - | New Purchase | New Ring 022 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020468 | [6 empty] | #N/A | [5 empty] | 2025-12-24 | 52 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3255_1 | New_JAW-JI-BKL-3255 | JAW-JI-BKL-3255 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8571 | 110.4 | New | New | New | Type B | MA | JAW-JI-BKL-3255 |  |  |  |  | - | - | - | - | New Purchase | New Ring 022 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020468 | [6 empty] | #N/A | [5 empty] | 2025-12-24 | 52 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0141_1 | New_JAW-YO-BTL-0141 | JAW-YO-BTL-0141 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8427 | 110.4003 | New | New | New | Type B | MA | JAW-YO-BTL-0141 |  |  |  |  | - | - | - | - | New Purchase | New Ring 022 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020468 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-24 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0576_1 | New_JAW-YO-YYK-0576 | JAW-YO-YYK-0576 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8317 | 110.4023 | New | New | New | Type B | MA | JAW-YO-YYK-0576 |  |  |  |  | - | - | - | - | New Purchase | New Ring 022 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020468 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2025-12-24 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8342_1 | New_JAW-YO-YYK-8342 | JAW-YO-YYK-8342 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.828 | 110.4029 | New | New | New | Type B | MA | JAW-YO-YYK-8342 |  |  |  |  | - | - | - | - | New Purchase | New Ring 022 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020468 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2025-12-24 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3234_1 | New_JAW-JI-BKL-3234 | JAW-JI-BKL-3234 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.826 | 110.4071 | New | New | New | Type B | MA | JAW-JI-BKL-3234 |  |  |  |  | - | - | - | - | New Purchase | New Ring 022 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020468 | [6 empty] | #N/A | [5 empty] | 2025-12-24 | 52 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3217_1 | New_JAW-JI-BKL-3217 | JAW-JI-BKL-3217 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8849 | 110.3637 | New | New | New | Type B | MA | JAW-JI-BKL-3217 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020471 | [6 empty] | #N/A | [5 empty] | 2025-12-24 | 52 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0621_1 | New_JAW-YO-BTL-0621 | JAW-YO-BTL-0621 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8725 | 110.3772 | New | New | New | Type B | MA | JAW-YO-BTL-0621 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020471 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-24 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0145_1 | New_JAW-YO-BTL-0145 | JAW-YO-BTL-0145 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8437 | 110.3911 | New | New | New | Type B | MA | JAW-YO-BTL-0145 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020471 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-24 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3155_1 | New_JAW-JI-BKL-3155 | JAW-JI-BKL-3155 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8337 | 110.3965 | New | New | New | Type B | MA | JAW-JI-BKL-3155 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020471 | [6 empty] | #N/A | [5 empty] | 2025-12-24 | 52 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8326_1 | New_JAW-YO-YYK-8326 | JAW-YO-YYK-8326 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8357 | 110.3903 | New | New | New | Type B | MA | JAW-YO-YYK-8326 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | [6 empty] | #N/A | [5 empty] | 2025-12-24 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3166_1 | New_JAW-JI-BKL-3166 | JAW-JI-BKL-3166 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.829 | 110.3809 | New | New | New | Type B | MA | JAW-JI-BKL-3166 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | [6 empty] | #N/A | [5 empty] | 2025-12-24 | 52 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0536_1 | New_JAW-YO-YYK-0536 | JAW-YO-YYK-0536 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8254 | 110.3768 | New | New | New | Type B | MA | JAW-YO-YYK-0536 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2025-12-24 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8301_1 | New_JAW-YO-YYK-8301 | JAW-YO-YYK-8301 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8205 | 110.3764 | New | New | New | Type B | MA | JAW-YO-YYK-8301 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2025-12-25 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0079_1 | New_JAW-YO-YYK-0079 | JAW-YO-YYK-0079 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8168 | 110.3806 | New | New | New | Type B | MA | JAW-YO-YYK-0079 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2025-12-25 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0064_1 | New_JAW-YO-YYK-0064 | JAW-YO-YYK-0064 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8157 | 110.3835 | New | New | New | Type B | MA | JAW-YO-YYK-0064 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2025-12-25 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0553_1 | New_JAW-YO-YYK-0553 | JAW-YO-YYK-0553 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8236 | 110.3858 | New | New | New | Type B | MA | JAW-YO-YYK-0553 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2025-12-25 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0072_1 | New_JAW-YO-YYK-0072 | JAW-YO-YYK-0072 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8266 | 110.3906 | New | New | New | Type B | MA | JAW-YO-YYK-0072 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2025-12-25 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0562_1 | New_JAW-YO-YYK-0562 | JAW-YO-YYK-0562 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8258 | 110.3912 | New | New | New | Type B | MA | JAW-YO-YYK-0562 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2025-12-25 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8335_1 | New_JAW-YO-YYK-8335 | JAW-YO-YYK-8335 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8244 | 110.3948 | New | New | New | Type B | MA | JAW-YO-YYK-8335 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2025-12-25 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0646_1 | New_JAW-YO-YYK-0646 | JAW-YO-YYK-0646 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8272 | 110.3974 | New | New | New | Type B | MA | JAW-YO-YYK-0646 |  |  |  |  | - | - | - | - | New Purchase | New Ring 023 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020471 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2025-12-25 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3248_1 | New_JAW-JI-BKL-3248 | JAW-JI-BKL-3248 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8155 | 110.4039 | New | New | New | Type B | MA | JAW-JI-BKL-3248 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A | [5 empty] | 2025-12-25 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3180_1 | New_JAW-JI-BKL-3180 | JAW-JI-BKL-3180 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8179 | 110.4082 | New | New | New | Type B | MA | JAW-JI-BKL-3180 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A | [5 empty] | 2025-12-25 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0089_1 | New_JAW-YO-BTL-0089 | JAW-YO-BTL-0089 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8129 | 110.4072 | New | New | New | Type B | MA | JAW-YO-BTL-0089 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-25 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0088_1 | New_JAW-YO-BTL-0088 | JAW-YO-BTL-0088 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8063 | 110.4038 | New | New | New | Type B | MA | JAW-YO-BTL-0088 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-25 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3178_1 | New_JAW-JI-BKL-3178 | JAW-JI-BKL-3178 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.7981 | 110.4047 | New | New | New | Type B | MA | JAW-JI-BKL-3178 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A | [5 empty] | 2025-12-25 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0087_1 | New_JAW-YO-BTL-0087 | JAW-YO-BTL-0087 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.7961 | 110.4032 | New | New | New | Type B | MA | JAW-YO-BTL-0087 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-26 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0085_1 | New_JAW-YO-BTL-0085 | JAW-YO-BTL-0085 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.7919 | 110.4014 | New | New | New | Type B | MA | JAW-YO-BTL-0085 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-26 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0584_1 | New_JAW-YO-BTL-0584 | JAW-YO-BTL-0584 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.7874 | 110.4098 | New | New | New | Type B | MA | JAW-YO-BTL-0584 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-26 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3153_1 | New_JAW-JI-BKL-3153 | JAW-JI-BKL-3153 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8008 | 110.4118 | New | New | New | Type B | MA | JAW-JI-BKL-3153 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A | [5 empty] | 2025-12-26 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0650_1 | New_JAW-YO-BTL-0650 | JAW-YO-BTL-0650 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.799 | 110.4167 | New | New | New | Type B | MA | JAW-YO-BTL-0650 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-26 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0592_1 | New_JAW-YO-BTL-0592 | JAW-YO-BTL-0592 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8107 | 110.4204 | New | New | New | Type B | MA | JAW-YO-BTL-0592 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-26 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3245_1 | New_JAW-JI-BKL-3245 | JAW-JI-BKL-3245 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8127 | 110.4154 | New | New | New | Type B | MA | JAW-JI-BKL-3245 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A | [5 empty] | 2025-12-26 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0103_1 | New_JAW-YO-BTL-0103 | JAW-YO-BTL-0103 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8179 | 110.4172 | New | New | New | Type B | MA | JAW-YO-BTL-0103 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-26 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3163_1 | New_JAW-JI-BKL-3163 | JAW-JI-BKL-3163 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8263 | 110.4183 | New | New | New | Type B | MA | JAW-JI-BKL-3163 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A | [5 empty] | 2025-12-26 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0148_1 | New_JAW-YO-BTL-0148 | JAW-YO-BTL-0148 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8293 | 110.4238 | New | New | New | Type B | MA | JAW-YO-BTL-0148 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-26 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3287_1 | New_JAW-JI-BKL-3287 | JAW-JI-BKL-3287 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8382 | 110.444 | New | New | New | Type B | MA | JAW-JI-BKL-3287 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A | [5 empty] | 2025-12-26 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0131_1 | New_JAW-YO-BTL-0131 | JAW-YO-BTL-0131 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8416 | 110.4501 | New | New | New | Type B | MA | JAW-YO-BTL-0131 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-26 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3267_1 | New_JAW-JI-BKL-3267 | JAW-JI-BKL-3267 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8305 | 110.4566 | New | New | New | Type B | MA | JAW-JI-BKL-3267 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A | [5 empty] | 2025-12-26 | 52 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0112_1 | New_JAW-YO-BTL-0112 | JAW-YO-BTL-0112 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8339 | 110.4634 | New | New | New | Type B | MA | JAW-YO-BTL-0112 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-29 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3277_1 | New_JAW-JI-BKL-3277 | JAW-JI-BKL-3277 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8333 | 110.4736 | New | New | New | Type B | MA | JAW-JI-BKL-3277 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A | [5 empty] | 2025-12-29 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0116_1 | New_JAW-YO-BTL-0116 | JAW-YO-BTL-0116 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8253 | 110.4808 | New | New | New | Type B | MA | JAW-YO-BTL-0116 |  |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020472 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-29 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3262_1 | New_JAW-JI-BKL-3262 | JAW-JI-BKL-3262 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9227 | 110.3959 | New | New | New | Type B | MA | JAW-JI-BKL-3262 |  |  |  |  | - | - | - | - | New Purchase | New Ring 025 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000019967 | [6 empty] | #N/A | [5 empty] | 2025-12-29 | 53 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-8159_1 | New_JAW-YO-BTL-8159 | JAW-YO-BTL-8159 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9188 | 110.4371 | New | New | New | Type B | MA | JAW-YO-BTL-8159 |  |  |  |  | - | - | - | - | New Purchase | New Ring 025 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000019967 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-29 | 53 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0682_1 | New_JAW-YO-BTL-0682 | JAW-YO-BTL-0682 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9097 | 110.4444 | New | New | New | Type B | MA | JAW-YO-BTL-0682 |  |  |  |  | - | - | - | - | New Purchase | New Ring 025 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019967 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-29 | 53 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3284_1 | New_JAW-JI-BKL-3284 | JAW-JI-BKL-3284 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9312 | 110.4453 | New | New | New | Type B | MA | JAW-JI-BKL-3284 |  |  |  |  | - | - | - | - | New Purchase | New Ring 025 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000019967 | [6 empty] | #N/A | [5 empty] | 2025-12-29 | 53 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3282_1 | New_JAW-JI-BKL-3282 | JAW-JI-BKL-3282 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9242 | 110.4725 | New | New | New | Type B | MA | JAW-JI-BKL-3282 |  |  |  |  | - | - | - | - | New Purchase | New Ring 025 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019967 | [6 empty] | #N/A | [5 empty] | 2025-12-29 | 53 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3214_1 | New_JAW-JI-BKL-3214 | JAW-JI-BKL-3214 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.898 | 110.4509 | New | New | New | Type B | MA | JAW-JI-BKL-3214 |  |  |  |  | - | - | - | - | New Purchase | New Ring 025 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019967 | [6 empty] | #N/A | [5 empty] | 2025-12-29 | 53 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3175_1 | New_JAW-JI-BKL-3175 | JAW-JI-BKL-3175 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8823 | 110.4523 | New | New | New | Type B | MA | JAW-JI-BKL-3175 |  |  |  |  | - | - | - | - | New Purchase | New Ring 025 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000019967 | [6 empty] | #N/A | [5 empty] | 2025-12-29 | 53 |  |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3261_1 | New_JAW-JI-BKL-3261 | JAW-JI-BKL-3261 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9316 | 110.3727 | New | New | New | Type B | MA | JAW-JI-BKL-3261 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000019968 | [6 empty] | #N/A | [5 empty] | 2025-12-29 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0076_1 | New_JAW-YO-BTL-0076 | JAW-YO-BTL-0076 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9522 | 110.3891 | New | New | New | Type B | MA | JAW-YO-BTL-0076 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019968 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-29 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3279_1 | New_JAW-JI-BKL-3279 | JAW-JI-BKL-3279 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9731 | 110.3763 | New | New | New | Type B | MA | JAW-JI-BKL-3279 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000019968 | [6 empty] | #N/A | [5 empty] | 2025-12-29 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3259_1 | New_JAW-JI-BKL-3259 | JAW-JI-BKL-3259 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9636 | 110.3576 | New | New | New | Type B | MA | JAW-JI-BKL-3259 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019968 | [6 empty] | #N/A | [5 empty] | 2025-12-30 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-3004_1 | New_JAW-YO-BTL-3004 | JAW-YO-BTL-3004 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9796 | 110.3433 | New | New | New | Type B | MA | JAW-YO-BTL-3004 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000019968 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-30 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-8157_1 | New_JAW-YO-BTL-8157 | JAW-YO-BTL-8157 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9874 | 110.3236 | New | New | New | Type B | MA | JAW-YO-BTL-8157 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019968 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-30 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0134_1 | New_JAW-YO-BTL-0134 | JAW-YO-BTL-0134 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -8.0202 | 110.3263 | New | New | New | Type B | MA | JAW-YO-BTL-0134 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019968 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-30 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3225_1 | New_JAW-JI-BKL-3225 | JAW-JI-BKL-3225 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9593 | 110.3225 | New | New | New | Type B | MA | JAW-JI-BKL-3225 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019968 | [6 empty] | #N/A | [5 empty] | 2025-12-30 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0149_1 | New_JAW-YO-BTL-0149 | JAW-YO-BTL-0149 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9434 | 110.3573 | New | New | New | Type B | MA | JAW-YO-BTL-0149 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019968 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-30 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-1584_1 | New_JAW-JT-PWD-1584 | JAW-JT-PWD-1584 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9158 | 110.3688 | New | New | New | Type B | MA | JAW-JT-PWD-1584 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019968 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-30 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0053_1 | New_JAW-YO-BTL-0053 | JAW-YO-BTL-0053 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8937 | 110.3499 | New | New | New | Type B | MA | JAW-YO-BTL-0053 |  |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000019968 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-30 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8312_1 | New_JAW-JT-BLA-8312 | JAW-JT-BLA-8312 | Central Java | Jawa Tengah | Blora | -6.9351 | 111.4975 | New | New | New | Type B | MA | JAW-JT-BLA-8312 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019802 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-30 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-0130_1 | New_JAW-JT-BLA-0130 | JAW-JT-BLA-0130 | Central Java | Jawa Tengah | Blora | -6.9223 | 111.4698 | New | New | New | Type B | MA | JAW-JT-BLA-0130 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019802 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-30 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-0160_1 | New_JAW-JT-BLA-0160 | JAW-JT-BLA-0160 | Central Java | Jawa Tengah | Blora | -6.9228 | 111.3708 | New | New | New | Type B | MA | JAW-JT-BLA-0160 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019802 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-30 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-0154_1 | New_JAW-JT-BLA-0154 | JAW-JT-BLA-0154 | Central Java | Jawa Tengah | Blora | -6.9429 | 111.2922 | New | New | New | Type B | MA | JAW-JT-BLA-0154 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019802 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-30 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8203_1 | New_JAW-JT-BLA-8203 | JAW-JT-BLA-8203 | Central Java | Jawa Tengah | Blora | -6.9419 | 111.2624 | New | New | New | Type B | MA | JAW-JT-BLA-8203 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019802 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-30 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-0133_1 | New_JAW-JT-BLA-0133 | JAW-JT-BLA-0133 | Central Java | Jawa Tengah | Blora | -6.9562 | 111.1774 | New | New | New | Type B | MA | JAW-JT-BLA-0133 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019802 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-31 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8348_1 | New_JAW-JT-BLA-8348 | JAW-JT-BLA-8348 | Central Java | Jawa Tengah | Blora | -6.9562 | 111.1204 | New | New | New | Type B | MA | JAW-JT-BLA-8348 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019802 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-31 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8350_1 | New_JAW-JT-BLA-8350 | JAW-JT-BLA-8350 | Central Java | Jawa Tengah | Blora | -6.9758 | 111.1585 | New | New | New | Type B | MA | JAW-JT-BLA-8350 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019802 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-31 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-3168_1 | New_JAW-JT-BLA-3168 | JAW-JT-BLA-3168 | Central Java | Jawa Tengah | Blora | -6.9891 | 111.2018 | New | New | New | Type B | MA | JAW-JT-BLA-3168 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019802 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-31 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8191_1 | New_JAW-JT-BLA-8191 | JAW-JT-BLA-8191 | Central Java | Jawa Tengah | Blora | -7.0745 | 111.2208 | New | New | New | Type B | MA | JAW-JT-BLA-8191 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019802 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-31 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8197_1 | New_JAW-JT-BLA-8197 | JAW-JT-BLA-8197 | Central Java | Jawa Tengah | Blora | -7.103 | 111.2502 | New | New | New | Type B | MA | JAW-JT-BLA-8197 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019802 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-31 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8201_1 | New_JAW-JT-BLA-8201 | JAW-JT-BLA-8201 | Central Java | Jawa Tengah | Blora | -7.1744 | 111.2598 | New | New | New | Type B | MA | JAW-JT-BLA-8201 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019802 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-31 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8199_1 | New_JAW-JT-BLA-8199 | JAW-JT-BLA-8199 | Central Java | Jawa Tengah | Blora | -7.1853 | 111.2569 | New | New | New | Type B | MA | JAW-JT-BLA-8199 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019802 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-31 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8208_1 | New_JAW-JT-BLA-8208 | JAW-JT-BLA-8208 | Central Java | Jawa Tengah | Blora | -7.2003 | 111.2754 | New | New | New | Type B | MA | JAW-JT-BLA-8208 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019802 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-31 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-0136_1 | New_JAW-JT-BLA-0136 | JAW-JT-BLA-0136 | Central Java | Jawa Tengah | Blora | -7.2117 | 111.2893 | New | New | New | Type B | MA | JAW-JT-BLA-0136 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019802 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-31 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8240_1 | New_JAW-JT-BLA-8240 | JAW-JT-BLA-8240 | Central Java | Jawa Tengah | Blora | -7.2166 | 111.3718 | New | New | New | Type B | MA | JAW-JT-BLA-8240 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019802 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-31 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-0127_1 | New_JAW-JT-BLA-0127 | JAW-JT-BLA-0127 | Central Java | Jawa Tengah | Blora | -7.2368 | 111.4419 | New | New | New | Type B | MA | JAW-JT-BLA-0127 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019802 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-31 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8315_1 | New_JAW-JT-BLA-8315 | JAW-JT-BLA-8315 | Central Java | Jawa Tengah | Blora | -7.2396 | 111.5091 | New | New | New | Type B | MA | JAW-JT-BLA-8315 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK |  | R0000019802 |  |  | 10. Ready ATP / RFS |  |  | 2025-11-09 | #N/A |  |  | 2026 | FO NY RFS |  | 2025-12-31 | 53 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8328_1 | New_JAW-JT-BLA-8328 | JAW-JT-BLA-8328 | Central Java | Jawa Tengah | Blora | -7.1869 | 111.5561 | New | New | New | Type B | MA | JAW-JT-BLA-8328 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK |  | R0000019802 |  |  | 10. Ready ATP / RFS |  |  | 2025-11-09 | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-01 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-0202_1 | New_JAW-JT-BLA-0202 | JAW-JT-BLA-0202 | Central Java | Jawa Tengah | Blora | -7.1608 | 111.5857 | New | New | New | Type B | MA | JAW-JT-BLA-0202 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK |  | R0000019802 |  |  | 10. Ready ATP / RFS |  |  | 2025-11-09 | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-01 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8302_1 | New_JAW-JT-BLA-8302 | JAW-JT-BLA-8302 | Central Java | Jawa Tengah | Blora | -6.9737 | 111.4685 | New | New | New | Type B | MA | JAW-JT-BLA-8302 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK |  | R0000019803 |  |  | 10. Ready ATP / RFS |  |  | 2025-11-09 | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-01 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8293_1 | New_JAW-JT-BLA-8293 | JAW-JT-BLA-8293 | Central Java | Jawa Tengah | Blora | -6.9649 | 111.4587 | New | New | New | Type B | MA | JAW-JT-BLA-8293 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK |  | R0000019803 |  |  | 10. Ready ATP / RFS |  |  | 2025-11-09 | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-01 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-0149_1 | New_JAW-JT-BLA-0149 | JAW-JT-BLA-0149 | Central Java | Jawa Tengah | Blora | -6.9716 | 111.4311 | New | New | New | Type B | MA | JAW-JT-BLA-0149 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK |  | R0000019803 |  |  | 10. Ready ATP / RFS |  |  | 2025-11-09 | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-01 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8256_1 | New_JAW-JT-BLA-8256 | JAW-JT-BLA-8256 | Central Java | Jawa Tengah | Blora | -6.9705 | 111.3927 | New | New | New | Type B | MA | JAW-JT-BLA-8256 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK |  | R0000019803 |  |  | 10. Ready ATP / RFS |  |  | 2025-11-09 | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-01 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8243_1 | New_JAW-JT-BLA-8243 | JAW-JT-BLA-8243 | Central Java | Jawa Tengah | Blora | -6.9672 | 111.3774 | New | New | New | Type B | MA | JAW-JT-BLA-8243 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK |  | R0000019803 |  |  | 10. Ready ATP / RFS |  |  | 2025-11-09 | #N/A | [5 empty] | 2026-01-01 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8225_1 | New_JAW-JT-BLA-8225 | JAW-JT-BLA-8225 | Central Java | Jawa Tengah | Blora | -6.9911 | 111.3243 | New | New | New | Type B | MA | JAW-JT-BLA-8225 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK |  | R0000019803 |  |  | 10. Ready ATP / RFS |  |  | 2025-11-09 | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-01 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8219_1 | New_JAW-JT-BLA-8219 | JAW-JT-BLA-8219 | Central Java | Jawa Tengah | Blora | -6.9855 | 111.3013 | New | New | New | Type B | MA | JAW-JT-BLA-8219 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019803 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-01 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8194_1 | New_JAW-JT-BLA-8194 | JAW-JT-BLA-8194 | Central Java | Jawa Tengah | Blora | -7.003 | 111.2439 | New | New | New | Type B | MA | JAW-JT-BLA-8194 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019803 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-01 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8193_1 | New_JAW-JT-BLA-8193 | JAW-JT-BLA-8193 | Central Java | Jawa Tengah | Blora | -7.0543 | 111.2399 | New | New | New | Type B | MA | JAW-JT-BLA-8193 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019803 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-01 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8204_1 | New_JAW-JT-BLA-8204 | JAW-JT-BLA-8204 | Central Java | Jawa Tengah | Blora | -7.0699 | 111.2634 | New | New | New | Type B | MA | JAW-JT-BLA-8204 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019803 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-01 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8209_1 | New_JAW-JT-BLA-8209 | JAW-JT-BLA-8209 | Central Java | Jawa Tengah | Blora | -7.084 | 111.2819 | New | New | New | Type B | MA | JAW-JT-BLA-8209 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019803 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-01 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8207_1 | New_JAW-JT-BLA-8207 | JAW-JT-BLA-8207 | Central Java | Jawa Tengah | Blora | -7.1067 | 111.2737 | New | New | New | Type B | MA | JAW-JT-BLA-8207 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019803 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-02 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8217_1 | New_JAW-JT-BLA-8217 | JAW-JT-BLA-8217 | Central Java | Jawa Tengah | Blora | -7.1834 | 111.3107 | New | New | New | Type B | MA | JAW-JT-BLA-8217 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000019803 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-02 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8223_1 | New_JAW-JT-BLA-8223 | JAW-JT-BLA-8223 | Central Java | Jawa Tengah | Blora | -7.191 | 111.3218 | New | New | New | Type B | MA | JAW-JT-BLA-8223 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019803 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-02 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8241_1 | New_JAW-JT-BLA-8241 | JAW-JT-BLA-8241 | Central Java | Jawa Tengah | Blora | -7.202 | 111.3725 | New | New | New | Type B | MA | JAW-JT-BLA-8241 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019803 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-02 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8271_1 | New_JAW-JT-BLA-8271 | JAW-JT-BLA-8271 | Central Java | Jawa Tengah | Blora | -7.2217 | 111.4211 | New | New | New | Type B | MA | JAW-JT-BLA-8271 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019803 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-02 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8297_1 | New_JAW-JT-BLA-8297 | JAW-JT-BLA-8297 | Central Java | Jawa Tengah | Blora | -7.2154 | 111.4524 | New | New | New | Type B | MA | JAW-JT-BLA-8297 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019803 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS | CCSI | 2026-01-02 | 1 |  |  | 2026 |  |  | Not Started |  |  | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-JT-BLA-8308_1 | New_JAW-JT-BLA-8308 | JAW-JT-BLA-8308 | Central Java | Jawa Tengah | Blora | -7.2267 | 111.4959 | New | New | New | Type B | MA | JAW-JT-BLA-8308 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019803 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-02 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8316_1 | New_JAW-JT-BLA-8316 | JAW-JT-BLA-8316 | Central Java | Jawa Tengah | Blora | -7.2135 | 111.5127 | New | New | New | Type B | MA | JAW-JT-BLA-8316 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000019803 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-02 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8326_1 | New_JAW-JT-BLA-8326 | JAW-JT-BLA-8326 | Central Java | Jawa Tengah | Blora | -7.1718 | 111.5543 | New | New | New | Type B | MA | JAW-JT-BLA-8326 |  |  |  |  | - | - | - | - | New Purchase | New Ring 028 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000019803 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-02 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8296_1 | New_JAW-JT-BLA-8296 | JAW-JT-BLA-8296 | Central Java | Jawa Tengah | Blora | -7.0037 | 111.4645 | New | New | New | Type B | MA | JAW-JT-BLA-8296 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-02 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8273_1 | New_JAW-JT-BLA-8273 | JAW-JT-BLA-8273 | Central Java | Jawa Tengah | Blora | -6.9973 | 111.4175 | New | New | New | Type B | MA | JAW-JT-BLA-8273 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-02 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8252_1 | New_JAW-JT-BLA-8252 | JAW-JT-BLA-8252 | Central Java | Jawa Tengah | Blora | -7.0048 | 111.3905 | New | New | New | Type B | MA | JAW-JT-BLA-8252 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-02 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8237_1 | New_JAW-JT-BLA-8237 | JAW-JT-BLA-8237 | Central Java | Jawa Tengah | Blora | -7.039 | 111.3594 | New | New | New | Type B | MA | JAW-JT-BLA-8237 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-02 | 1 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8232_1 | New_JAW-JT-BLA-8232 | JAW-JT-BLA-8232 | Central Java | Jawa Tengah | Blora | -7.0117 | 111.3504 | New | New | New | Type B | MA | JAW-JT-BLA-8232 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-05 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8222_1 | New_JAW-JT-BLA-8222 | JAW-JT-BLA-8222 | Central Java | Jawa Tengah | Blora | -7.0393 | 111.3023 | New | New | New | Type B | MA | JAW-JT-BLA-8222 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-05 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8212_1 | New_JAW-JT-BLA-8212 | JAW-JT-BLA-8212 | Central Java | Jawa Tengah | Blora | -7.0453 | 111.29 | New | New | New | Type B | MA | JAW-JT-BLA-8212 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-05 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8220_1 | New_JAW-JT-BLA-8220 | JAW-JT-BLA-8220 | Central Java | Jawa Tengah | Blora | -7.0694 | 111.3141 | New | New | New | Type B | MA | JAW-JT-BLA-8220 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-05 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8231_1 | New_JAW-JT-BLA-8231 | JAW-JT-BLA-8231 | Central Java | Jawa Tengah | Blora | -7.0451 | 111.3352 | New | New | New | Type B | MA | JAW-JT-BLA-8231 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-05 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8233_1 | New_JAW-JT-BLA-8233 | JAW-JT-BLA-8233 | Central Java | Jawa Tengah | Blora | -7.061 | 111.3549 | New | New | New | Type B | MA | JAW-JT-BLA-8233 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-05 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8253_1 | New_JAW-JT-BLA-8253 | JAW-JT-BLA-8253 | Central Java | Jawa Tengah | Blora | -7.0441 | 111.3914 | New | New | New | Type B | MA | JAW-JT-BLA-8253 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000020473 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-05 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8257_1 | New_JAW-JT-BLA-8257 | JAW-JT-BLA-8257 | Central Java | Jawa Tengah | Blora | -7.0944 | 111.3956 | New | New | New | Type B | MA | JAW-JT-BLA-8257 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000020473 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-05 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8279_1 | New_JAW-JT-BLA-8279 | JAW-JT-BLA-8279 | Central Java | Jawa Tengah | Blora | -7.1386 | 111.4331 | New | New | New | Type B | MA | JAW-JT-BLA-8279 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000020473 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-05 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-0166_1 | New_JAW-JT-BLA-0166 | JAW-JT-BLA-0166 | Central Java | Jawa Tengah | Blora | -7.1881 | 111.3917 | New | New | New | Type B | MA | JAW-JT-BLA-0166 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR |  |  | R0000020473 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-05 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8286_1 | New_JAW-JT-BLA-8286 | JAW-JT-BLA-8286 | Central Java | Jawa Tengah | Blora | -7.183 | 111.4497 | New | New | New | Type B | MA | JAW-JT-BLA-8286 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-05 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8307_1 | New_JAW-JT-BLA-8307 | JAW-JT-BLA-8307 | Central Java | Jawa Tengah | Blora | -7.1669 | 111.4948 | New | New | New | Type B | MA | JAW-JT-BLA-8307 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-05 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8309_1 | New_JAW-JT-BLA-8309 | JAW-JT-BLA-8309 | Central Java | Jawa Tengah | Blora | -7.1801 | 111.4964 | New | New | New | Type B | MA | JAW-JT-BLA-8309 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-05 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8325_1 | New_JAW-JT-BLA-8325 | JAW-JT-BLA-8325 | Central Java | Jawa Tengah | Blora | -7.1573 | 111.5503 | New | New | New | Type B | MA | JAW-JT-BLA-8325 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020473 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-06 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8336_1 | New_JAW-JT-BLA-8336 | JAW-JT-BLA-8336 | Central Java | Jawa Tengah | Blora | -7.1507 | 111.5783 | New | New | New | Type B | MA | JAW-JT-BLA-8336 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020473 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-06 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8339_1 | New_JAW-JT-BLA-8339 | JAW-JT-BLA-8339 | Central Java | Jawa Tengah | Blora | -7.1501 | 111.5901 | New | New | New | Type B | MA | JAW-JT-BLA-8339 |  |  |  |  | - | - | - | - | New Purchase | New Ring 029 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020473 | [6 empty] | #N/A | [5 empty] | 2026-01-06 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLT-8459_1 | New_JAW-JT-SLT-8459 | JAW-JT-SLT-8459 | Central Java | Jawa Tengah | Kota Salatiga | -7.3502 | 110.51 | New | New | New | Type B | MA | JAW-JT-SLT-8459 |  |  |  |  | - | - | - | - | New Purchase | New Ring 031 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020476 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-06 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLT-8455_1 | New_JAW-JT-SLT-8455 | JAW-JT-SLT-8455 | Central Java | Jawa Tengah | Kota Salatiga | -7.3389 | 110.5063 | New | New | New | Type B | MA | JAW-JT-SLT-8455 |  |  |  |  | - | - | - | - | New Purchase | New Ring 031 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020476 | [6 empty] | #N/A | [5 empty] | 2026-01-06 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLT-8446_1 | New_JAW-JT-SLT-8446 | JAW-JT-SLT-8446 | Central Java | Jawa Tengah | Kota Salatiga | -7.327 | 110.4994 | New | New | New | Type B | MA | JAW-JT-SLT-8446 |  |  |  |  | - | - | - | - | New Purchase | New Ring 031 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020476 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-06 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLT-8451_1 | New_JAW-JT-SLT-8451 | JAW-JT-SLT-8451 | Central Java | Jawa Tengah | Kota Salatiga | -7.3264 | 110.5052 | New | New | New | Type B | MA | JAW-JT-SLT-8451 |  |  |  |  | - | - | - | - | New Purchase | New Ring 031 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020476 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-06 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLT-2133_1 | New_JAW-JT-SLT-2133 | JAW-JT-SLT-2133 | Central Java | Jawa Tengah | Kota Salatiga | -7.3203 | 110.5108 | New | New | New | Type B | MA | JAW-JT-SLT-2133 |  |  |  |  | - | - | - | - | New Purchase | New Ring 031 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020476 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-06 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLT-8454_1 | New_JAW-JT-SLT-8454 | JAW-JT-SLT-8454 | Central Java | Jawa Tengah | Kota Salatiga | -7.3072 | 110.5061 | New | New | New | Type B | MA | JAW-JT-SLT-8454 |  |  |  |  | - | - | - | - | New Purchase | New Ring 031 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020476 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-06 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLT-2136_1 | New_JAW-JT-SLT-2136 | JAW-JT-SLT-2136 | Central Java | Jawa Tengah | Kota Salatiga | -7.3013 | 110.4908 | New | New | New | Type B | MA | JAW-JT-SLT-2136 |  |  |  |  | - | - | - | - | New Purchase | New Ring 031 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020476 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-06 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLT-8431_1 | New_JAW-JT-SLT-8431 | JAW-JT-SLT-8431 | Central Java | Jawa Tengah | Kota Salatiga | -7.2931 | 110.4769 | New | New | New | Type B | MA | JAW-JT-SLT-8431 |  |  |  |  | - | - | - | - | New Purchase | New Ring 031 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR |  |  | R0000020476 | [6 empty] | #N/A | [5 empty] | 2026-01-06 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-2350_1 | New_JAW-JT-SMG-2350 | JAW-JT-SMG-2350 | Central Java | Jawa Tengah | Kota Semarang | -6.9914 | 110.4151 | New | New | New | Type B | MA | JAW-JT-SMG-2350 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | S000056139 | S000056140 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-06 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8510_1 | New_JAW-JT-SMG-8510 | JAW-JT-SMG-8510 | Central Java | Jawa Tengah | Kota Semarang | -6.9936 | 110.4221 | New | New | New | Type B | MA | JAW-JT-SMG-8510 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | S000056140 | S000056141 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-06 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8506_1 | New_JAW-JT-SMG-8506 | JAW-JT-SMG-8506 | Central Java | Jawa Tengah | Kota Semarang | -6.9759 | 110.4214 | New | New | New | Type B | MA | JAW-JT-SMG-8506 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | S000056141 | S000056142 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  |  |  |  | 2026-01-07 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8523_1 | New_JAW-JT-SMG-8523 | JAW-JT-SMG-8523 | Central Java | Jawa Tengah | Kota Semarang | -6.9705 | 110.4252 | New | New | New | Type B | MA | JAW-JT-SMG-8523 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | S000056142 | S000056143 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  |  |  |  | 2026-01-07 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8571_1 | New_JAW-JT-SMG-8571 | JAW-JT-SMG-8571 | Central Java | Jawa Tengah | Kota Semarang | -6.9685 | 110.4341 | New | New | New | Type B | MA | JAW-JT-SMG-8571 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | S000056143 | S000056144 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-07 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8578_1 | New_JAW-JT-SMG-8578 | JAW-JT-SMG-8578 | Central Java | Jawa Tengah | Kota Semarang | -6.9655 | 110.4405 | New | New | New | Type B | MA | JAW-JT-SMG-8578 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | S000056144 | S000056145 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-07 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8599_1 | New_JAW-JT-SMG-8599 | JAW-JT-SMG-8599 | Central Java | Jawa Tengah | Kota Semarang | -6.9601 | 110.4474 | New | New | New | Type B | MA | JAW-JT-SMG-8599 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | S000056145 | S000056146 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-07 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8612_1 | New_JAW-JT-SMG-8612 | JAW-JT-SMG-8612 | Central Java | Jawa Tengah | Kota Semarang | -6.9641 | 110.4535 | New | New | New | Type B | MA | JAW-JT-SMG-8612 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | S000056146 | S000056147 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-07 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8617_1 | New_JAW-JT-SMG-8617 | JAW-JT-SMG-8617 | Central Java | Jawa Tengah | Kota Semarang | -6.9672 | 110.4567 | New | New | New | Type B | MA | JAW-JT-SMG-8617 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | S000056147 | S000056148 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-07 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8637_1 | New_JAW-JT-SMG-8637 | JAW-JT-SMG-8637 | Central Java | Jawa Tengah | Kota Semarang | -6.9671 | 110.4612 | New | New | New | Type B | MA | JAW-JT-SMG-8637 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | S000056148 | S000056149 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  |  |  |  | 2026-01-07 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8644_1 | New_JAW-JT-SMG-8644 | JAW-JT-SMG-8644 | Central Java | Jawa Tengah | Kota Semarang | -6.9712 | 110.464 | New | New | New | Type B | MA | JAW-JT-SMG-8644 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | S000056149 | S000056150 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-07 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-2558_1 | New_JAW-JT-SMG-2558 | JAW-JT-SMG-2558 | Central Java | Jawa Tengah | Kota Semarang | -6.9727 | 110.4716 | New | New | New | Type B | MA | JAW-JT-SMG-2558 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | S000056150 | S000056151 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-07 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8674_1 | New_JAW-JT-SMG-8674 | JAW-JT-SMG-8674 | Central Java | Jawa Tengah | Kota Semarang | -6.9766 | 110.4775 | New | New | New | Type B | MA | JAW-JT-SMG-8674 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | S000056151 | S000056152 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-07 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-3088_1 | New_JAW-JT-SMG-3088 | JAW-JT-SMG-3088 | Central Java | Jawa Tengah | Kota Semarang | -6.9821 | 110.477 | New | New | New | Type B | MA | JAW-JT-SMG-3088 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | S000056152 | S000056153 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-07 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-2556_1 | New_JAW-JT-SMG-2556 | JAW-JT-SMG-2556 | Central Java | Jawa Tengah | Kota Semarang | -6.9847 | 110.47 | New | New | New | Type B | MA | JAW-JT-SMG-2556 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | S000056153 | S000056154 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-07 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-2539_1 | New_JAW-JT-SMG-2539 | JAW-JT-SMG-2539 | Central Java | Jawa Tengah | Kota Semarang | -6.9823 | 110.4599 | New | New | New | Type B | MA | JAW-JT-SMG-2539 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | S000056154 | S000056155 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-08 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8616_1 | New_JAW-JT-SMG-8616 | JAW-JT-SMG-8616 | Central Java | Jawa Tengah | Kota Semarang | -6.9986 | 110.4567 | New | New | New | Type B | MA | JAW-JT-SMG-8616 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | S000056155 | S000056156 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  |  |  |  | 2026-01-08 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8627_1 | New_JAW-JT-SMG-8627 | JAW-JT-SMG-8627 | Central Java | Jawa Tengah | Kota Semarang | -7.0108 | 110.4581 | New | New | New | Type B | MA | JAW-JT-SMG-8627 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | S000056156 | S000056157 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-08 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8586_1 | New_JAW-JT-SMG-8586 | JAW-JT-SMG-8586 | Central Java | Jawa Tengah | Kota Semarang | -7.0079 | 110.4426 | New | New | New | Type B | MA | JAW-JT-SMG-8586 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | S000056157 | S000056158 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-08 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8598_1 | New_JAW-JT-SMG-8598 | JAW-JT-SMG-8598 | Central Java | Jawa Tengah | Kota Semarang | -7.0065 | 110.4471 | New | New | New | Type B | MA | JAW-JT-SMG-8598 |  |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020477 | S000056158 | S000056159 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-08 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-0621_1 | New_JAW-JT-SMG-0621 | JAW-JT-SMG-0621 | Central Java | Jawa Tengah | Kota Semarang | -7.0038 | 110.4387 | New | New | New | Type B | MA | JAW-JT-SMG-0621 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | S000054812 | S000054813 | 10. Ready ATP / RFS | 2025-11-23 | 47 | 2025-11-09 | #N/A | No |  | 2025-End Nov | FO NY RFS | YPTT | 2026-01-08 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-8566_1 | New_JAW-JT-SMG-8566 | JAW-JT-SMG-8566 | Central Java | Jawa Tengah | Kota Semarang | -7.006 | 110.4368 | New | New | New | Type B | MA | JAW-JT-SMG-8566 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | S000054813 | S000054814 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2025-End Nov | FO NY RFS | YPTT | 2026-01-08 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-8555_1 | New_JAW-JT-SMG-8555 | JAW-JT-SMG-8555 | Central Java | Jawa Tengah | Kota Semarang | -7.006 | 110.4315 | New | New | New | Type B | MA | JAW-JT-SMG-8555 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | S000054814 | S000054815 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2025-End Nov | FO NY RFS | YPTT | 2026-01-08 | 2 |  |  | 2026 | 2025-11-25 |  |  |  |  | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | HOLD | New__1 | New_ |  | Central Java |  |  | #N/A | #N/A | New | New | New | Type B | MA | [5 empty] | - | - | - | - | New Purchase | New Ring 033 | Propose Drop, NO SPK | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | #N/A | [6 empty] | #N/A | [5 empty] | 2026-01-08 | 2 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-2478_1 | New_JAW-JT-SMG-2478 | JAW-JT-SMG-2478 | Central Java | Jawa Tengah | Kota Semarang | -7.0351 | 110.4255 | New | New | New | Type B | MA | JAW-JT-SMG-2478 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | S000054815 | S000054816 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2025-End Nov | FO NY RFS | YPTT | 2026-01-08 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-8559_1 | New_JAW-JT-SMG-8559 | JAW-JT-SMG-8559 | Central Java | Jawa Tengah | Kota Semarang | -7.0475 | 110.419 | New | New | New | Type B | MA | JAW-JT-SMG-8559 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | S000054816 | S000054817 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2025-End Nov | FO NY RFS | YPTT | 2026-01-08 | 2 |  |  | 2026 | 2025-11-25 |  |  |  |  | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-0625_1 | New_JAW-JT-SMG-0625 | JAW-JT-SMG-0625 | Central Java | Jawa Tengah | Kota Semarang | -7.0442 | 110.3931 | New | New | New | Type B | MA | JAW-JT-SMG-0625 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | S000054817 | S000054818 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2025-End Nov | FO NY RFS | YPTT | 2026-01-08 | 2 |  |  | 2026 | 2025-11-13 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-8752_1 | New_JAW-JT-SMG-8752 | JAW-JT-SMG-8752 | Central Java | Jawa Tengah | Kota Semarang | -7.0484 | 110.396 | New | New | New | Type B | MA | JAW-JT-SMG-8752 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | S000054818 | S000054819 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2025-End Nov | FO NY RFS | YPTT | 2026-01-08 | 2 |  |  | 2026 | 2025-11-12 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-8430_1 | New_JAW-JT-SMG-8430 | JAW-JT-SMG-8430 | Central Java | Jawa Tengah | Kota Semarang | -7.0575 | 110.3947 | New | New | New | Type B | MA | JAW-JT-SMG-8430 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | S000054819 | S000054820 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2025-End Nov | FO NY RFS | YPTT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-13 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-8442_1 | New_JAW-JT-SMG-8442 | JAW-JT-SMG-8442 | Central Java | Jawa Tengah | Kota Semarang | -7.0593 | 110.3994 | New | New | New | Type B | MA | JAW-JT-SMG-8442 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | - | S000054821 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2025-End Nov | FO NY RFS | YPTT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-11 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-2963_1 | New_JAW-JT-SMG-2963 | JAW-JT-SMG-2963 | Central Java | Jawa Tengah | Kota Semarang | -7.0848 | 110.3878 | New | New | New | Type B | MA | JAW-JT-SMG-2963 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | S000054820 | S000054822 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2025-End Nov | FO NY RFS | YPTT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-10 | 2025-11-10 | Approved | 2025-11-17 |  | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-8415_1 | New_JAW-JT-SMG-8415 | JAW-JT-SMG-8415 | Central Java | Jawa Tengah | Kota Semarang | -7.09 | 110.3891 | New | New | New | Type B | MA | JAW-JT-SMG-8415 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | S000054822 | S000054823 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2025-End Nov | FO NY RFS | YPTT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-13 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-0611_1 | New_JAW-JT-SMG-0611 | JAW-JT-SMG-0611 | Central Java | Jawa Tengah | Kota Semarang | -7.1037 | 110.3892 | New | New | New | Type B | MA | JAW-JT-SMG-0611 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | S000054823 | S000054824 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2025-End Nov | FO NY RFS | YPTT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-14 | 2025-11-14 | Approved | 2025-11-17 |  | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-3064_1 | New_JAW-JT-SMG-3064 | JAW-JT-SMG-3064 | Central Java | Jawa Tengah | Kota Semarang | -7.0999 | 110.4048 | New | New | New | Type B | MA | JAW-JT-SMG-3064 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | S000054824 | S000054825 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2025-End Nov | FO NY RFS | YPTT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-11 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-SMG-0630_1 | New_JAW-JT-SMG-0630 | JAW-JT-SMG-0630 | Central Java | Jawa Tengah | Kota Semarang | -7.0941 | 110.4071 | New | New | New | Type B | MA | JAW-JT-SMG-0630 |  |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020168 | S000054825 | S000054826 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2025-End Nov | FO NY RFS | YPTT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-12 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [29 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-YO-YYK-0500_1 | New_JAW-YO-YYK-0500 | JAW-YO-YYK-0500 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7878 | 110.3642 | New | New | New | Type B | MA | JAW-YO-YYK-0500 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-09 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8283_1 | New_JAW-YO-YYK-8283 | JAW-YO-YYK-8283 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7881 | 110.3645 | New | New | New | Type B | MA | JAW-YO-YYK-8283 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-09 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0509_1 | New_JAW-YO-YYK-0509 | JAW-YO-YYK-0509 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7856 | 110.3666 | New | New | New | Type B | MA | JAW-YO-YYK-0509 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-09 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0511_1 | New_JAW-YO-YYK-0511 | JAW-YO-YYK-0511 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7827 | 110.3682 | New | New | New | Type B | MA | JAW-YO-YYK-0511 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-09 | 2 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0519_1 | New_JAW-YO-YYK-0519 | JAW-YO-YYK-0519 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7824 | 110.3696 | New | New | New | Type B | MA | JAW-YO-YYK-0519 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Propose Drop, NO SPK | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | #N/A | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-09 | 2 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0525_1 | New_JAW-YO-YYK-0525 | JAW-YO-YYK-0525 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7824 | 110.373 | New | New | New | Type B | MA | JAW-YO-YYK-0525 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS | CCSI | 2026-01-09 | 2 |  |  | 2026 |  |  | Not Started |  |  | Submitted | Approved |  | Site Already Dismantle | [29 empty] | #N/A |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-YO-YYK-0533_1 | New_JAW-YO-YYK-0533 | JAW-YO-YYK-0533 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7824 | 110.3771 | New | New | New | Type B | MA | JAW-YO-YYK-0533 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Propose Drop, NO SPK | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | #N/A | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-12 | 3 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0087_1 | New_JAW-YO-YYK-0087 | JAW-YO-YYK-0087 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7839 | 110.3772 | New | New | New | Type B | MA | JAW-YO-YYK-0087 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS | CCSI | 2026-01-12 | 3 |  |  | 2026 | 2025-11-10 | 2025-11-10 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | 1 | CCSI
1 | 2 | HOLD | New__2 | New_ |  | Central Java |  |  | #N/A | #N/A | New | New | New | Type B | MA | [5 empty] | - | - | - | - | New Purchase | New Ring 034 | Propose Drop, NO SPK | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | #N/A | [6 empty] | #N/A | [5 empty] | 2026-01-12 | 3 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8300_1 | New_JAW-YO-YYK-8300 | JAW-YO-YYK-8300 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7881 | 110.3758 | New | New | New | Type B | MA | JAW-YO-YYK-8300 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS | CCSI | 2026-01-12 | 3 |  |  | 2026 | 2025-11-21 | 2025-11-21 | Approved | 2025-11-22 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-YO-YYK-0077_1 | New_JAW-YO-YYK-0077 | JAW-YO-YYK-0077 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7871 | 110.3781 | New | New | New | Type B | MA | JAW-YO-YYK-0077 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-12 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8311_1 | New_JAW-YO-YYK-8311 | JAW-YO-YYK-8311 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7854 | 110.3805 | New | New | New | Type B | MA | JAW-YO-YYK-8311 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-12 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0544_1 | New_JAW-YO-YYK-0544 | JAW-YO-YYK-0544 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7825 | 110.3787 | New | New | New | Type B | MA | JAW-YO-YYK-0544 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-12 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0538_1 | New_JAW-YO-YYK-0538 | JAW-YO-YYK-0538 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7827 | 110.3802 | New | New | New | Type B | MA | JAW-YO-YYK-0538 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-12 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMN-2883_1 | New_JAW-JT-SMN-2883 | JAW-JT-SMN-2883 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7824 | 110.3817 | New | New | New | Type B | MA | JAW-JT-SMN-2883 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Propose Drop, NO SPK | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | #N/A | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS | CCSI | 2026-01-12 | 3 |  |  | 2026 | 2025-11-21 | 2025-11-21 | Approved | 2025-11-22 | [34 empty] | #N/A |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-YO-YYK-8339_1 | New_JAW-YO-YYK-8339 | JAW-YO-YYK-8339 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7845 | 110.3852 | New | New | New | Type B | MA | JAW-YO-YYK-8339 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-12 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8323_1 | New_JAW-YO-YYK-8323 | JAW-YO-YYK-8323 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7868 | 110.3887 | New | New | New | Type B | MA | JAW-YO-YYK-8323 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-12 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0557_1 | New_JAW-YO-YYK-0557 | JAW-YO-YYK-0557 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7827 | 110.3871 | New | New | New | Type B | MA | JAW-YO-YYK-0557 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-12 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0537_1 | New_JAW-YO-YYK-0537 | JAW-YO-YYK-0537 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.7771 | 110.3774 | New | New | New | Type B | MA | JAW-YO-YYK-0537 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-12 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-SMN-8387_1 | New_JAW-YO-SMN-8387 | JAW-YO-SMN-8387 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7759 | 110.3748 | New | New | New | Type B | MA | JAW-YO-SMN-8387 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-13 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-SMN-0080_1 | New_JAW-YO-SMN-0080 | JAW-YO-SMN-0080 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7782 | 110.3739 | New | New | New | Type B | MA | JAW-YO-SMN-0080 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-13 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-SMN-8378_1 | New_JAW-YO-SMN-8378 | JAW-YO-SMN-8378 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7704 | 110.366 | New | New | New | Type B | MA | JAW-YO-SMN-8378 |  |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020375 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-13 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0085_1 | New_JAW-YO-YYK-0085 | JAW-YO-YYK-0085 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7713 | 110.3553 | New | New | New | Type B | MA | JAW-YO-YYK-0085 |  |  |  |  | - | - | - | - | New Purchase | New Ring 035 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000019970 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-13 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8273_1 | New_JAW-YO-YYK-8273 | JAW-YO-YYK-8273 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7746 | 110.3609 | New | New | New | Type B | MA | JAW-YO-YYK-8273 |  |  |  |  | - | - | - | - | New Purchase | New Ring 035 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000019970 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-13 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0489_1 | New_JAW-YO-YYK-0489 | JAW-YO-YYK-0489 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7784 | 110.3607 | New | New | New | Type B | MA | JAW-YO-YYK-0489 |  |  |  |  | - | - | - | - | New Purchase | New Ring 035 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000019970 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-13 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-SMN-0177_1 | New_JAW-YO-SMN-0177 | JAW-YO-SMN-0177 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7778 | 110.3549 | New | New | New | Type B | MA | JAW-YO-SMN-0177 |  |  |  |  | - | - | - | - | New Purchase | New Ring 035 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000019970 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-13 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8268_1 | New_JAW-YO-YYK-8268 | JAW-YO-YYK-8268 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7806 | 110.351 | New | New | New | Type B | MA | JAW-YO-YYK-8268 |  |  |  |  | - | - | - | - | New Purchase | New Ring 035 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000019970 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-13 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0481_1 | New_JAW-YO-YYK-0481 | JAW-YO-YYK-0481 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7843 | 110.3544 | New | New | New | Type B | MA | JAW-YO-YYK-0481 |  |  |  |  | - | - | - | - | New Purchase | New Ring 035 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000019970 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-13 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8281_1 | New_JAW-YO-YYK-8281 | JAW-YO-YYK-8281 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7806 | 110.3623 | New | New | New | Type B | MA | JAW-YO-YYK-8281 |  |  |  |  | - | - | - | - | New Purchase | New Ring 035 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000019970 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-13 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0147_1 | New_JAW-YO-BTL-0147 | JAW-YO-BTL-0147 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8742 | 110.3471 | New | New | New | Type B | MA | JAW-YO-BTL-0147 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020319 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-13 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3243_1 | New_JAW-JI-BKL-3243 | JAW-JI-BKL-3243 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8588 | 110.3671 | New | New | New | Type B | MA | JAW-JI-BKL-3243 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020319 | [6 empty] | #N/A | [5 empty] | 2026-01-13 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3157_1 | New_JAW-JI-BKL-3157 | JAW-JI-BKL-3157 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8472 | 110.3589 | New | New | New | Type B | MA | JAW-JI-BKL-3157 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR |  |  | R0000020319 | [6 empty] | #N/A | [5 empty] | 2026-01-13 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3232_1 | New_JAW-JI-BKL-3232 | JAW-JI-BKL-3232 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8431 | 110.3513 | New | New | New | Type B | MA | JAW-JI-BKL-3232 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | [6 empty] | #N/A | [5 empty] | 2026-01-14 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8264_1 | New_JAW-YO-YYK-8264 | JAW-YO-YYK-8264 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8182 | 110.3559 | New | New | New | Type B | MA | JAW-YO-YYK-8264 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-14 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8282_1 | New_JAW-YO-YYK-8282 | JAW-YO-YYK-8282 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8176 | 110.3514 | New | New | New | Type B | MA | JAW-YO-YYK-8282 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-14 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0127_1 | New_JAW-YO-YYK-0127 | JAW-YO-YYK-0127 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8053 | 110.3563 | New | New | New | Type B | MA | JAW-YO-YYK-0127 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-14 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0075_1 | New_JAW-YO-YYK-0075 | JAW-YO-YYK-0075 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8079 | 110.3607 | New | New | New | Type B | MA | JAW-YO-YYK-0075 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-14 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8298_1 | New_JAW-YO-YYK-8298 | JAW-YO-YYK-8298 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.818 | 110.3732 | New | New | New | Type B | MA | JAW-YO-YYK-8298 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-14 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8302_1 | New_JAW-YO-YYK-8302 | JAW-YO-YYK-8302 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8105 | 110.3768 | New | New | New | Type B | MA | JAW-YO-YYK-8302 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-14 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0551_1 | New_JAW-YO-YYK-0551 | JAW-YO-YYK-0551 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8093 | 110.3829 | New | New | New | Type B | MA | JAW-YO-YYK-0551 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-14 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8340_1 | New_JAW-YO-YYK-8340 | JAW-YO-YYK-8340 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8126 | 110.3858 | New | New | New | Type B | MA | JAW-YO-YYK-8340 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-14 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8327_1 | New_JAW-YO-YYK-8327 | JAW-YO-YYK-8327 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8145 | 110.3911 | New | New | New | Type B | MA | JAW-YO-YYK-8327 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | [6 empty] | #N/A | [5 empty] | 2026-01-14 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0060_1 | New_JAW-YO-YYK-0060 | JAW-YO-YYK-0060 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8168 | 110.3966 | New | New | New | Type B | MA | JAW-YO-YYK-0060 |  |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020319 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-14 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0501_1 | New_JAW-YO-YYK-0501 | JAW-YO-YYK-0501 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7968 | 110.3649 | New | New | New | Type B | MA | JAW-YO-YYK-0501 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-14 | 3 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8286_1 | New_JAW-YO-YYK-8286 | JAW-YO-YYK-8286 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7978 | 110.3658 | New | New | New | Type B | MA | JAW-YO-YYK-8286 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS | CCSI | 2026-01-14 | 3 |  |  | 2026 | 2025-11-21 | 2025-11-21 | Approved | 2025-11-22 | [34 empty] | #N/A |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-YO-YYK-8315_1 | New_JAW-YO-YYK-8315 | JAW-YO-YYK-8315 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7981 | 110.3684 | New | New | New | Type B | MA | JAW-YO-YYK-8315 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-15 | 3 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0517_1 | New_JAW-YO-YYK-0517 | JAW-YO-YYK-0517 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7982 | 110.3689 | New | New | New | Type B | MA | JAW-YO-YYK-0517 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-15 | 3 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0065_1 | New_JAW-YO-YYK-0065 | JAW-YO-YYK-0065 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8017 | 110.3714 | New | New | New | Type B | MA | JAW-YO-YYK-0065 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-15 | 3 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0086_1 | New_JAW-YO-YYK-0086 | JAW-YO-YYK-0086 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7974 | 110.3724 | New | New | New | Type B | MA | JAW-YO-YYK-0086 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS | CCSI | 2026-01-15 | 3 |  |  | 2026 | 2025-11-10 | 2025-11-10 | Approved | 2025-11-17 | [34 empty] | #N/A |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-YO-YYK-8312_1 | New_JAW-YO-YYK-8312 | JAW-YO-YYK-8312 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7915 | 110.3816 | New | New | New | Type B | MA | JAW-YO-YYK-8312 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-15 | 3 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0556_1 | New_JAW-YO-YYK-0556 | JAW-YO-YYK-0556 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7899 | 110.3861 | New | New | New | Type B | MA | JAW-YO-YYK-0556 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-15 | 3 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8331_1 | New_JAW-YO-YYK-8331 | JAW-YO-YYK-8331 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7942 | 110.3926 | New | New | New | Type B | MA | JAW-YO-YYK-8331 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-15 | 3 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0558_1 | New_JAW-YO-YYK-0558 | JAW-YO-YYK-0558 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8016 | 110.3883 | New | New | New | Type B | MA | JAW-YO-YYK-0558 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-15 | 3 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8321_1 | New_JAW-YO-YYK-8321 | JAW-YO-YYK-8321 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8022 | 110.3885 | New | New | New | Type B | MA | JAW-YO-YYK-8321 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | [6 empty] | #N/A | [5 empty] | 2026-01-15 | 3 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8330_1 | New_JAW-YO-YYK-8330 | JAW-YO-YYK-8330 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8048 | 110.392 | New | New | New | Type B | MA | JAW-YO-YYK-8330 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-15 | 3 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8334_1 | New_JAW-YO-YYK-8334 | JAW-YO-YYK-8334 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8061 | 110.3947 | New | New | New | Type B | MA | JAW-YO-YYK-8334 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-15 | 3 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0082_1 | New_JAW-YO-YYK-0082 | JAW-YO-YYK-0082 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8067 | 110.3987 | New | New | New | Type B | MA | JAW-YO-YYK-0082 |  |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR |  |  | R0000020320 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-15 | 3 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8401_1 | New_JAW-JT-DMK-8401 | JAW-JT-DMK-8401 | Central Java | Jawa Tengah | Demak | -6.9193 | 110.6338 | Insert | New | New | Type B | MA | JAW-JT-DMK-8401 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | S000055782 | S000055783 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2026-01-15 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8390_1 | New_JAW-JT-DMK-8390 | JAW-JT-DMK-8390 | Central Java | Jawa Tengah | Demak | -6.7785 | 110.6215 | Insert | New | New | Type B | MA | JAW-JT-DMK-8390 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, NO SPK | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-16 | 3 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8408_1 | New_JAW-JT-DMK-8408 | JAW-JT-DMK-8408 | Central Java | Jawa Tengah | Demak | -6.8572 | 110.6438 | Insert | New | New | Type B | MA | JAW-JT-DMK-8408 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, NO SPK | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-16 | 3 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8314_1 | New_JAW-JT-DMK-8314 | JAW-JT-DMK-8314 | Central Java | Jawa Tengah | Demak | -7.0758 | 110.5172 | Insert | New | New | Type B | MA | JAW-JT-DMK-8314 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, NO SPK | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-16 | 3 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-4130_1 | New_JAW-JT-DMK-4130 | JAW-JT-DMK-4130 | Central Java | Jawa Tengah | Demak | -7.116 | 110.565 | Insert | New | New | Type B | MA | JAW-JT-DMK-4130 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, NO SPK | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-16 | 3 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8325_1 | New_JAW-JT-DMK-8325 | JAW-JT-DMK-8325 | Central Java | Jawa Tengah | Demak | -7.0447 | 110.5279 | Insert | New | New | Type B | MA | JAW-JT-DMK-8325 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020403 | S000055770 | S000055771 | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2026-01-16 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8326_1 | New_JAW-JT-DMK-8326 | JAW-JT-DMK-8326 | Central Java | Jawa Tengah | Demak | -7.0348 | 110.528 | Insert | New | New | Type B | MA | JAW-JT-DMK-8326 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, NO SPK | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-16 | 3 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8420_1 | New_JAW-JT-PWD-8420 | JAW-JT-PWD-8420 | Central Java | Jawa Tengah | Grobogan | -7.0144 | 110.9109 | Insert | New | New | Type B | MA | JAW-JT-PWD-8420 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020150 | S000054773 | S000054774 | 12. NY TERMINATION | 2025-11-16 | 46 |  | #N/A | Yes |  | 2026 | FO NY RFS | GPA | 2026-01-16 | 3 |  |  | 2026 | 2025-11-12 | 2025-11-23 12:18:25 | Reviewing | [33 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8455_1 | New_JAW-JT-PWD-8455 | JAW-JT-PWD-8455 | Central Java | Jawa Tengah | Grobogan | -7.0834 | 110.9477 | Insert | New | New | Type B | MA | JAW-JT-PWD-8455 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020151 | S000054775 | S000054776 | 12. NY TERMINATION | 2025-11-16 | 46 |  | #N/A | No |  | 2025-624 sites | FO NY RFS | GPA | 2026-01-16 | 3 |  |  | 2026 | 2025-11-13 | [35 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8545_1 | New_JAW-JT-PWD-8545 | JAW-JT-PWD-8545 | Central Java | Jawa Tengah | Grobogan | -7.0966 | 111.0817 | Insert | New | New | Type B | MA | JAW-JT-PWD-8545 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020152 | S000054777 | S000054778 | 12. NY TERMINATION | 2025-11-16 | 46 | 2025-11-09 | #N/A | Yes |  | 2025-624 sites | On Shcedule | GPA | 2026-01-16 | 3 |  |  | 2026 | 2025-11-13 | 2025-11-23 00:43:13 | Reviewing | [18 empty] | DCITS | [14 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8576_1 | New_JAW-JT-PWD-8576 | JAW-JT-PWD-8576 | Central Java | Jawa Tengah | Grobogan | -7.13 | 111.1469 | Insert | New | New | Type B | MA | JAW-JT-PWD-8576 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020152 | S000054778 | S000054779 | 12. NY TERMINATION | 2025-11-16 | 46 | 2025-11-09 | #N/A | Yes |  | 2025-624 sites | On Shcedule | GPA | 2026-01-16 | 3 |  |  | 2026 | 2025-11-12 | 2025-11-23 13:54:19 | Reviewing | [18 empty] | DCITS | [14 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8525_1 | New_JAW-JT-PWD-8525 | JAW-JT-PWD-8525 | Central Java | Jawa Tengah | Grobogan | -7.1101 | 111.0502 | Insert | New | New | Type B | MA | JAW-JT-PWD-8525 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020153 | S000054780 | S000054781 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2025-624 sites | FO NY RFS | GPA | 2026-01-16 | 3 |  |  | 2026 | [36 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8465_1 | New_JAW-JT-PWD-8465 | JAW-JT-PWD-8465 | Central Java | Jawa Tengah | Grobogan | -7.1155 | 110.9524 | Insert | New | New | Type B | MA | JAW-JT-PWD-8465 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020154 | S000054782 | S000054783 | 12. NY TERMINATION | 2025-11-23 | 47 | 2025-11-09 | #N/A | No |  | 2026 | On Shcedule | GPA | 2026-01-16 | 3 |  |  | 2026 | 2025-11-10 | 2025-11-17 | Approved | 2025-11-22 | [17 empty] | DCITS | [14 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8419_1 | New_JAW-JT-PWD-8419 | JAW-JT-PWD-8419 | Central Java | Jawa Tengah | Grobogan | -7.1205 | 110.9095 | Insert | New | New | Type B | MA | JAW-JT-PWD-8419 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020154 | S000054783 | S000054784 | 12. NY TERMINATION | 2025-11-23 | 47 | 2025-11-09 | #N/A | No |  | 2025-624 sites | On Shcedule | GPA | 2026-01-16 | 3 |  |  | 2026 | 2025-11-11 | 2025-11-21 | Approved | 2025-11-22 | [17 empty] | DCITS | [14 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8429_1 | New_JAW-JT-PWD-8429 | JAW-JT-PWD-8429 | Central Java | Jawa Tengah | Grobogan | -7.128 | 110.9165 | Insert | New | New | Type B | MA | JAW-JT-PWD-8429 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020155 | S000054785 | S000054786 | 12. NY TERMINATION | 2026-01-12 08:00 | 3 |  | #N/A | No |  |  |  |  | 2026-01-19 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8510_1 | New_JAW-JT-PWD-8510 | JAW-JT-PWD-8510 | Central Java | Jawa Tengah | Grobogan | -7.1045 | 111.0254 | Insert | New | New | Type B | MA | JAW-JT-PWD-8510 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_4 2x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020156 | S000054787 | S000054788 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2026-01-19 | 4 |  |  | 2026 | [36 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8527_1 | New_JAW-JT-PWD-8527 | JAW-JT-PWD-8527 | Central Java | Jawa Tengah | Grobogan | -7.1249 | 111.0559 | Insert | New | New | Type B | MA | JAW-JT-PWD-8527 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020156 | S000054788 | S000054789 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS |  | 2026-01-19 | 4 |  |  | 2026 | [36 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8559_1 | New_JAW-JT-PWD-8559 | JAW-JT-PWD-8559 | Central Java | Jawa Tengah | Grobogan | -7.1052 | 111.1078 | Insert | New | New | Type B | MA | JAW-JT-PWD-8559 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020157 | S000054790 | S000054791 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-624 sites | FO NY RFS |  | 2026-01-19 | 4 |  |  | 2026 | [36 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8534_1 | New_JAW-JT-PWD-8534 | JAW-JT-PWD-8534 | Central Java | Jawa Tengah | Grobogan | -7.0793 | 111.0705 | Insert | New | New | Type B | MA | JAW-JT-PWD-8534 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020158 | S000054792 | S000054793 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-624 sites | FO NY RFS |  | 2026-01-19 | 4 |  |  | 2026 | [36 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8497_1 | New_JAW-JT-PWD-8497 | JAW-JT-PWD-8497 | Central Java | Jawa Tengah | Grobogan | -7.0814 | 111.0208 | Insert | New | New | Type B | MA | JAW-JT-PWD-8497 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020159 | S000054794 | S000054795 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2026-01-19 | 4 |  |  | 2026 | [36 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8476_1 | New_JAW-JT-PWD-8476 | JAW-JT-PWD-8476 | Central Java | Jawa Tengah | Grobogan | -7.0815 | 110.9964 | Insert | New | New | Type B | MA | JAW-JT-PWD-8476 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-19 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8473_1 | New_JAW-JT-PWD-8473 | JAW-JT-PWD-8473 | Central Java | Jawa Tengah | Grobogan | -7.0653 | 110.9876 | Insert | New | New | Type B | MA | JAW-JT-PWD-8473 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-19 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8345_1 | New_JAW-JT-PWD-8345 | JAW-JT-PWD-8345 | Central Java | Jawa Tengah | Grobogan | -7.0356 | 110.7381 | Insert | New | New | Type B | MA | JAW-JT-PWD-8345 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020350 | S000055190 | S000055191 | 12. NY TERMINATION | 2025-11-09 | 45 | 2025-11-09 | #N/A | Yes |  | 2026 | On Shcedule | GPA | 2026-01-19 | 4 |  |  | 2026 | 2025-11-15 | 2025-11-22 23:19:59 | Reviewing | [18 empty] | DCITS | [14 empty] | 2025-11-14 | 46 | 2025-11-14 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8348_1 | New_JAW-JT-PWD-8348 | JAW-JT-PWD-8348 | Central Java | Jawa Tengah | Grobogan | -7.0537 | 110.7437 | Insert | New | New | Type B | MA | JAW-JT-PWD-8348 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020350 | S000055191 | S000055192 | 12. NY TERMINATION | 2025-11-09 | 45 | 2025-11-09 | #N/A | Yes |  | 2026 | On Shcedule | GPA | 2026-01-19 | 4 |  |  | 2026 | 2025-11-15 | [20 empty] | DCITS | [14 empty] | 2025-11-14 | 46 | 2025-11-14 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8365_1 | New_JAW-JT-PWD-8365 | JAW-JT-PWD-8365 | Central Java | Jawa Tengah | Grobogan | -7.0897 | 110.7869 | Insert | New | New | Type B | MA | JAW-JT-PWD-8365 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020160 | S000054796 | S000054797 | 12. NY TERMINATION | 2025-11-09 | 45 | 2025-11-09 | 2025-11-09 | No |  | 2026 | On Shcedule | GPA | 2026-01-19 | 4 |  |  | 2026 | 2025-11-25 |  |  |  |  | Submitted | Approved | [14 empty] | DCITS | [14 empty] | 2025-11-14 | 46 | 2025-11-14 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8374_1 | New_JAW-JT-PWD-8374 | JAW-JT-PWD-8374 | Central Java | Jawa Tengah | Grobogan | -7.068 | 110.8082 | Insert | New | New | Type B | MA | JAW-JT-PWD-8374 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020161 | S000054798 | S000054799 | 12. NY TERMINATION | 2025-11-09 | 45 |  | #N/A | No |  | 2026 | FO NY RFS | GPA | 2026-01-19 | 4 |  |  | 2026 | 2025-11-11 | [35 empty] | 2025-11-14 | 46 | 2025-11-14 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8427_1 | New_JAW-JT-PWD-8427 | JAW-JT-PWD-8427 | Central Java | Jawa Tengah | Grobogan | -7.0962 | 110.9143 | Insert | New | New | Type B | MA | JAW-JT-PWD-8427 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020162 | S000054800 | S000054801 | 12. NY TERMINATION | 2025-11-09 | 45 |  | #N/A | No |  | 2025-624 sites | FO NY RFS | GPA | 2026-01-19 | 4 |  |  | 2026 | 2025-11-12 | [35 empty] | 2025-11-14 | 46 | 2025-11-14 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-8379_1 | New_JAW-JT-PWD-8379 | JAW-JT-PWD-8379 | Central Java | Jawa Tengah | Grobogan | -7.0699 | 110.8249 | Insert | New | New | Type B | MA | JAW-JT-PWD-8379 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020163 | S000054802 | S000054803 | 12. NY TERMINATION | 2025-11-09 | 45 | 2025-11-09 | 2025-11-09 | No |  | 2026 | On Shcedule | GPA | 2026-01-20 | 4 |  |  | 2026 | 2025-11-12 |  |  |  |  | Submitted | Approved | [14 empty] | DCITS | [14 empty] | 2025-11-14 | 46 | 2025-11-14 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-8317_1 | New_JAW-JT-JPA-8317 | JAW-JT-JPA-8317 | Central Java | Jawa Tengah | Jepara | -6.585 | 110.6662 | Insert | New | New | Type B | MA | JAW-JT-JPA-8317 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019839 | S000054260 | S000054261 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2026-01-20 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8331_1 | New_JAW-JT-JPA-8331 | JAW-JT-JPA-8331 | Central Java | Jawa Tengah | Jepara | -6.6078 | 110.6796 | Insert | New | New | Type B | MA | JAW-JT-JPA-8331 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019840 | S000054262 | S000054263 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2026-01-20 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8464_1 | New_JAW-JT-JPA-8464 | JAW-JT-JPA-8464 | Central Java | Jawa Tengah | Jepara | -6.4933 | 110.9024 | Insert | New | New | Type B | MA | JAW-JT-JPA-8464 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019841 | S000054264 | S000054265 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2026-01-20 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8460_1 | New_JAW-JT-JPA-8460 | JAW-JT-JPA-8460 | Central Java | Jawa Tengah | Jepara | -6.5067 | 110.8922 | Insert | New | New | Type B | MA | JAW-JT-JPA-8460 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019841 | S000054265 | S000054266 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2026-01-20 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8367_1 | New_JAW-JT-JPA-8367 | JAW-JT-JPA-8367 | Central Java | Jawa Tengah | Jepara | -6.7496 | 110.714 | Insert | New | New | Type B | MA | JAW-JT-JPA-8367 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019842 | S000054267 | S000054268 | 12. NY TERMINATION | 2025-11-30 | 48 | 2025-11-09 | 2025-11-09 | No |  | 2026 | On Shcedule | DCITS | 2026-01-20 | 4 |  |  | 2026 | 2025-11-25 | 2025-11-25 06:25:00 | Reviewing |  |  | Submitted | Approved | [14 empty] | DCITS | [14 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8362_1 | New_JAW-JT-JPA-8362 | JAW-JT-JPA-8362 | Central Java | Jawa Tengah | Jepara | -6.5633 | 110.7121 | Insert | New | New | Type B | MA | JAW-JT-JPA-8362 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019843 | S000054269 | S000054270 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2026-01-20 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-3383_1 | New_JAW-JT-DMK-3383 | JAW-JT-DMK-3383 | Central Java | Jawa Tengah | Jepara | -6.7064 | 110.6223 | Insert | New | New | Type B | MA | JAW-JT-DMK-3383 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020456 | - | S000055963 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2026-01-20 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8303_1 | New_JAW-JT-JPA-8303 | JAW-JT-JPA-8303 | Central Java | Jawa Tengah | Jepara | -6.7118 | 110.6418 | Insert | New | New | Type B | MA | JAW-JT-JPA-8303 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020456 | S000055963 | S000055964 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2026-01-20 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8403_1 | New_JAW-JT-JPA-8403 | JAW-JT-JPA-8403 | Central Java | Jawa Tengah | Jepara | -6.6706 | 110.7478 | Insert | New | New | Type B | MA | JAW-JT-JPA-8403 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019844 | S000054271 | S000054272 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2026-01-20 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8354_1 | New_JAW-JT-JPA-8354 | JAW-JT-JPA-8354 | Central Java | Jawa Tengah | Jepara | -6.5711 | 110.7011 | Insert | New | New | Type B | MA | JAW-JT-JPA-8354 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019845 | S000054273 | S000054274 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2026-01-20 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8469_1 | New_JAW-JT-JPA-8469 | JAW-JT-JPA-8469 | Central Java | Jawa Tengah | Jepara | -6.4205 | 110.9727 | Insert | New | New | Type B | MA | JAW-JT-JPA-8469 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019846 | S000054275 | S000054276 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2026 | FO NY RFS | YPTT | 2026-01-20 | 4 |  |  | 2026 | 2025-11-21 | 2025-11-21 | Approved | 2025-11-22 | [34 empty] | #N/A |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-4117_1 | New_JAW-JT-JPA-4117 | JAW-JT-JPA-4117 | Central Java | Jawa Tengah | Jepara | -6.4932 | 110.8604 | Insert | New | New | Type B | MA | JAW-JT-JPA-4117 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020457 | S000055965 | S000055966 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2026 | FO NY RFS |  | 2026-01-20 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8340_1 | New_JAW-JT-JPA-8340 | JAW-JT-JPA-8340 | Central Java | Jawa Tengah | Jepara | -6.6646 | 110.6916 | Insert | New | New | Type B | MA | JAW-JT-JPA-8340 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020458 | S000055967 | S000055968 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2026 | FO NY RFS | YPTT | 2026-01-21 | 4 |  |  | 2026 | 2025-11-17 | 2025-11-17 | Approved | 2025-11-22 | [34 empty] | #N/A |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8314_1 | New_JAW-JT-JPA-8314 | JAW-JT-JPA-8314 | Central Java | Jawa Tengah | Jepara | -6.668 | 110.6639 | Insert | New | New | Type B | MA | JAW-JT-JPA-8314 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019847 | S000054277 | S000054278 | 12. NY TERMINATION | 2025-11-30 | 48 | 2025-11-09 | #N/A | No |  |  |  |  | 2026-01-21 | 4 |  |  | 2026 | [21 empty] | DCITS | [14 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8396_1 | New_JAW-JT-JPA-8396 | JAW-JT-JPA-8396 | Central Java | Jawa Tengah | Jepara | -6.4508 | 110.7423 | Insert | New | New | Type B | MA | JAW-JT-JPA-8396 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019848 | S000054279 | S000054280 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2026 | FO NY RFS |  | 2026-01-21 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-JPA-8333_1 | New_JAW-JT-JPA-8333 | JAW-JT-JPA-8333 | Central Java | Jawa Tengah | Jepara | -6.585 | 110.6811 | Insert | New | New | Type B | MA | JAW-JT-JPA-8333 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000019849 | S000054281 | S000054282 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  |  |  |  | 2026-01-21 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8265_1 | New_JAW-YO-YYK-8265 | JAW-YO-YYK-8265 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7945 | 110.3565 | Insert | New | New | Type B | MA | JAW-YO-YYK-8265 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | [9 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-21 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0166_1 | New_JAW-YO-BTL-0166 | JAW-YO-BTL-0166 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.7972 | 110.3459 | Insert | New | New | Type B | MA | JAW-YO-BTL-0166 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-21 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-SMN-0154_1 | New_JAW-YO-SMN-0154 | JAW-YO-SMN-0154 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8002 | 110.3316 | Insert | New | New | Type B | MA | JAW-YO-SMN-0154 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_3 1x25G/10G LR + 1x10G ZR + 6x1G LR | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-21 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8681_1 | New_JAW-JT-SMG-8681 | JAW-JT-SMG-8681 | Central Java | Jawa Tengah | Kota Semarang | -6.969 | 110.4811 | Insert | New | New | Type B | MA | JAW-JT-SMG-8681 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020410 | S000055800 | S000055801 | 12. NY TERMINATION | 2026-01-12 07:55 | 3 |  | #N/A | No |  |  |  |  | 2026-01-21 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8498_1 | New_JAW-JT-SMG-8498 | JAW-JT-SMG-8498 | Central Java | Jawa Tengah | Kota Semarang | -6.978 | 110.4169 | Insert | New | New | Type B | MA | JAW-JT-SMG-8498 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020411 | S000055803 | S000055802 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-21 | 4 |  |  | 2026 | [36 empty] | 2025-11-25 | 48 | 2025-11-25 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-2364_1 | New_JAW-JT-SMG-2364 | JAW-JT-SMG-2364 | Central Java | Jawa Tengah | Kota Semarang | -7.0076 | 110.3784 | Insert | New | New | Type B | MA | JAW-JT-SMG-2364 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020412 | S000055804 | S000055805 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | Yes |  | 2025-End Nov | FO NY RFS |  | 2026-01-21 | 4 |  |  | 2026 | [36 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8719_1 | New_JAW-JT-SMG-8719 | JAW-JT-SMG-8719 | Central Java | Jawa Tengah | Kota Semarang | -6.9838 | 110.357 | Insert | New | New | Type B | MA | JAW-JT-SMG-8719 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020413 | S000055806 | S000055807 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-21 | 4 |  |  | 2026 | [36 empty] | 2025-11-25 | 48 | 2025-11-25 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8725_1 | New_JAW-JT-SMG-8725 | JAW-JT-SMG-8725 | Central Java | Jawa Tengah | Kota Semarang | -6.9863 | 110.3478 | Insert | New | New | Type B | MA | JAW-JT-SMG-8725 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020414 | S000055808 | S000055809 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | No |  | 2025-End Nov | FO NY RFS | DCITS | 2026-01-21 | 4 |  |  | 2026 | 2025-11-22 |  | In Progress |  |  | Submitted | Approved | [29 empty] | 2025-11-25 | 48 | 2025-11-25 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-2521_1 | New_JAW-JT-SMG-2521 | JAW-JT-SMG-2521 | Central Java | Jawa Tengah | Kota Semarang | -7.0503 | 110.4453 | Insert | New | New | Type B | MA | JAW-JT-SMG-2521 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020415 | S000055810 | S000055811 | 12. NY TERMINATION | 2025-12-14 | 50 | 2025-11-09 | 2025-11-09 | No |  | 2025-End Nov | On Shcedule | DCITS | 2026-01-21 | 4 |  |  | 2026 | 2025-11-24 | 2025-11-21 16:33:40 | Reviewing |  |  | Submitted | Approved | [14 empty] | DCITS | [14 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-3472_1 | New_JAW-JT-SMG-3472 | JAW-JT-SMG-3472 | Central Java | Jawa Tengah | Kota Semarang | -7.0204 | 110.3359 | Insert | New | New | Type B | MA | JAW-JT-SMG-3472 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020416 | S000055812 | S000055813 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-22 | 4 |  |  | 2026 | [36 empty] | 2025-11-11 | 46 | 2025-11-11 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-2333_1 | New_JAW-JT-SMG-2333 | JAW-JT-SMG-2333 | Central Java | Jawa Tengah | Kota Semarang | -7.07 | 110.334 | Insert | New | New | Type B | MA | JAW-JT-SMG-2333 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020417 | S000055814 | S000055815 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-22 | 4 |  |  | 2026 | [36 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8726_1 | New_JAW-JT-SMG-8726 | JAW-JT-SMG-8726 | Central Java | Jawa Tengah | Kota Semarang | -7.0125 | 110.3774 | Insert | New | New | Type B | MA | JAW-JT-SMG-8726 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020418 | S000055816 | S000055817 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-22 | 4 |  |  | 2026 | [36 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8405_1 | New_JAW-JT-SMG-8405 | JAW-JT-SMG-8405 | Central Java | Jawa Tengah | Kota Semarang | -7.007 | 110.3691 | Insert | New | New | Type B | MA | JAW-JT-SMG-8405 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020418 | S000055817 | S000055818 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-22 | 4 |  |  | 2026 | [36 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8661_1 | New_JAW-JT-SMG-8661 | JAW-JT-SMG-8661 | Central Java | Jawa Tengah | Kota Semarang | -7.0196 | 110.4718 | Insert | New | New | Type B | MA | JAW-JT-SMG-8661 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020419 | S000055819 | S000055820 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-22 | 4 |  |  | 2026 | [36 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-8502_1 | New_JAW-JT-SMG-8502 | JAW-JT-SMG-8502 | Central Java | Jawa Tengah | Kota Semarang | -7.0016 | 110.4202 | Insert | New | New | Type B | MA | JAW-JT-SMG-8502 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020420 | S000055821 | S000055822 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-22 | 4 |  |  | 2026 | [36 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-8278_1 | New_JAW-YO-YYK-8278 | JAW-YO-YYK-8278 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7701 | 110.3616 | Insert | New | New | Type B | MA | JAW-YO-YYK-8278 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | [9 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-22 | 4 |  |  | 2026 | [36 empty] | 2025-11-25 | 48 | 2025-11-25 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8540_1 | New_JAW-JT-UNR-8540 | JAW-JT-UNR-8540 | Central Java | Jawa Tengah | Semarang | -7.2463 | 110.5255 | Insert | New | New | Type B | MA | JAW-JT-UNR-8540 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | [9 empty] | #N/A |  |  | Mid Dec 25 | FO NY RFS |  | 2026-01-22 | 4 |  |  | 2026 | [36 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8545_1 | New_JAW-JT-UNR-8545 | JAW-JT-UNR-8545 | Central Java | Jawa Tengah | Semarang | -7.2364 | 110.5374 | Insert | New | New | Type B | MA | JAW-JT-UNR-8545 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | [9 empty] | #N/A |  |  | Mid Dec 25 | FO NY RFS |  | 2026-01-22 | 4 |  |  | 2026 | [36 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8484_1 | New_JAW-JT-UNR-8484 | JAW-JT-UNR-8484 | Central Java | Jawa Tengah | Semarang | -7.1781 | 110.4276 | Insert | New | New | Type B | MA | JAW-JT-UNR-8484 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | [9 empty] | #N/A |  |  | Mid Dec 25 | FO NY RFS |  | 2026-01-22 | 4 |  |  | 2026 | [36 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-2693_1 | New_JAW-JT-UNR-2693 | JAW-JT-UNR-2693 | Central Java | Jawa Tengah | Semarang | -7.2106 | 110.4142 | Insert | New | New | Type B | MA | JAW-JT-UNR-2693 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | [9 empty] | #N/A |  |  | Mid Dec 25 | FO NY RFS |  | 2026-01-22 | 4 |  |  | 2026 | [36 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8518_1 | New_JAW-JT-UNR-8518 | JAW-JT-UNR-8518 | Central Java | Jawa Tengah | Semarang | -7.1853 | 110.4669 | Insert | New | New | Type B | MA | JAW-JT-UNR-8518 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | [9 empty] | #N/A |  |  | Mid Dec 25 | FO NY RFS |  | 2026-01-22 | 4 |  |  | 2026 | [36 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-4119_1 | New_JAW-JT-UNR-4119 | JAW-JT-UNR-4119 | Central Java | Jawa Tengah | Semarang | -7.2746 | 110.4825 | Insert | New | New | Type B | MA | JAW-JT-UNR-4119 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | [9 empty] | #N/A |  |  | Mid Dec 25 | FO NY RFS |  | 2026-01-22 | 4 |  |  | 2026 | [36 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-4118_1 | New_JAW-JT-UNR-4118 | JAW-JT-UNR-4118 | Central Java | Jawa Tengah | Semarang | -7.2568 | 110.5122 | Insert | New | New | Type B | MA | JAW-JT-UNR-4118 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, NO SPK | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | [9 empty] | #N/A |  |  | Mid Dec 25 | FO NY RFS |  | 2026-01-23 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8546_1 | New_JAW-JT-UNR-8546 | JAW-JT-UNR-8546 | Central Java | Jawa Tengah | Semarang | -7.4045 | 110.5388 | Insert | New | New | Type B | MA | JAW-JT-UNR-8546 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | [9 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-23 | 4 |  |  | 2026 | [36 empty] | 2025-11-18 | 47 | 2025-11-18 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8560_1 | New_JAW-JT-UNR-8560 | JAW-JT-UNR-8560 | Central Java | Jawa Tengah | Semarang | -7.4203 | 110.5865 | Insert | New | New | Type B | MA | JAW-JT-UNR-8560 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | [9 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-23 | 4 |  |  | 2026 | [36 empty] | 2025-11-25 | 48 | 2025-11-25 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8534_1 | New_JAW-JT-UNR-8534 | JAW-JT-UNR-8534 | Central Java | Jawa Tengah | Semarang | -7.2898 | 110.5145 | Insert | New | New | Type B | MA | JAW-JT-UNR-8534 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, MOCN Drop | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | [9 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-23 | 4 |  |  | 2026 | [36 empty] | 2025-11-25 | 48 | 2025-11-25 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-2792_1 | New_JAW-JT-UNR-2792 | JAW-JT-UNR-2792 | Central Java | Jawa Tengah | Semarang | -7.4759 | 110.6461 | Insert | New | New | Type B | MA | JAW-JT-UNR-2792 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | [9 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-23 | 4 |  |  | 2026 | [36 empty] | 2025-11-25 | 48 | 2025-11-25 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8535_1 | New_JAW-JT-UNR-8535 | JAW-JT-UNR-8535 | Central Java | Jawa Tengah | Semarang | -7.3945 | 110.5145 | Insert | New | New | Type B | MA | JAW-JT-UNR-8535 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, MOCN Drop | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | [9 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-23 | 4 |  |  | 2026 | [36 empty] | 2025-11-25 | 48 | 2025-11-25 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8573_1 | New_JAW-JT-UNR-8573 | JAW-JT-UNR-8573 | Central Java | Jawa Tengah | Semarang | -7.2352 | 110.3796 | Insert | New | New | Type B | MA | JAW-JT-UNR-8573 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_5 1x25G/10G ER + 1x10G ZR + 6x1G LR | [9 empty] | #N/A |  |  | Mid Dec 25 | FO NY RFS |  | 2026-01-23 | 4 |  |  | 2026 | [36 empty] | 2025-11-25 | 48 | 2025-11-25 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8473_1 | New_JAW-JT-UNR-8473 | JAW-JT-UNR-8473 | Central Java | Jawa Tengah | Semarang | -7.1218 | 110.417 | Insert | New | New | Type B | MA | JAW-JT-UNR-8473 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_2 1x25G/10G LR + 1x25G/10G ER + 6x1G LR | [9 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-23 | 4 |  |  | 2026 | [36 empty] | 2025-11-25 | 48 | 2025-11-25 |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-2699_1 | New_JAW-JT-UNR-2699 | JAW-JT-UNR-2699 | Central Java | Jawa Tengah | Semarang | -7.1398 | 110.4181 | Insert | New | New | Type B | MA | JAW-JT-UNR-2699 |  |  |  |  | - | - | - | - | New Purchase | Insert | Keep | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | [9 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS | CCSI | 2026-01-23 | 4 |  |  | 2026 | 2025-11-22 | 2025-11-22 11:05:51 | Reviewing | [33 empty] | 2025-11-25 | 48 | 2025-11-25 |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-JT-PKL-1322_1 | New_JAW-JT-PKL-1322 | JAW-JT-PKL-1322 | Central Java | Jawa Tengah | Kota Pekalongan | -6.8756 | 109.6686 | Insert | New | New | Type B | MA | JAW-JT-PKL-1322 |  |  |  |  | - | - | - | - | New Purchase | Insert | Propose Drop, NO SPK | 1 | Bundle_Type B_1 2x25G/10G LR + 6x1G LR | [9 empty] | #N/A | [5 empty] | 2026-01-23 | 4 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-3485_1 | New_JAW-JT-SMG-3485 | JAW-JT-SMG-3485 | Central Java | Jawa Tengah | Kota Semarang | -7.09636111111111 | 110.4175 | New | New | New | Type C | PAG | JAW-JT-SMG-3485 | Supernode Gombel |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000020395 | - | S000055626 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  |  |  | CCSI | 2026-01-23 | 4 |  |  | 2026 | 2025-11-24 | 2025-11-22 14:48:53 | Reviewing |  |  | Submitted | Approved | [29 empty] | 2025-11-24 | 48 | 2025-11-24 |  | Done | 1 | CCSI
1 | 1 | CLEAR | New_JAW-JT-KDL-0872_1 | New_JAW-JT-KDL-0872 | JAW-JT-KDL-0872 | Central Java | Jawa Tengah | Kendal | -6.9662 | 110.287 | New | New | New | Type C | PAG | JAW-JT-KDL-0872 | Mangkang |  |  |  | - | - | - | - | New Purchase | New Ring 003 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000020395 | S000055645 | - | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2025-624 sites | FO NY RFS | GPA | 2026-01-23 | 4 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-24 | 48 | 2025-11-24 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0612_1 | New_JAW-JT-DMK-0612 | JAW-JT-DMK-0612 | Central Java | Jawa Tengah | Demak | -6.8503 | 110.8054 | New | New | New | Type C | PAG | JAW-JT-DMK-0612 | Karanganyar Demak |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020396 | S000055663 | S000055677 | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | Yes |  | 2026 | FO NY RFS | GPA | 2026-01-23 | 4 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0602_1 | New_JAW-JT-DMK-0602 | JAW-JT-DMK-0602 | Central Java | Jawa Tengah | Demak | -6.8738 | 110.7173 | New | New | New | Type C | PAG | JAW-JT-DMK-0602 | Mpls - Gajah |  |  |  | - | - | - | - | New Purchase | New Ring 004 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000020396 | S000055692 | - | 12. NY TERMINATION | 2025-12-14 | 50 |  | #N/A | Yes |  | 2026 | FO NY RFS | GPA | 2026-01-26 | 5 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-0613_1 | New_JAW-JT-DMK-0613 | JAW-JT-DMK-0613 | Central Java | Jawa Tengah | Demak | -6.90943055555556 | 110.633 | New | New | New | Type C | PAG | JAW-JT-DMK-0613 | Supernode Demak |  |  |  | - | - | - | - | New Purchase | New Ring 007 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000020401 | - | S000055728 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | Yes |  |  |  | YPTT | 2026-01-26 | 5 |  |  | 2026 | 2025-11-22 | 2025-11-21 11:00:38 | Reviewing |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | 1 | #N/A | November
1 | 2 | CLEAR | New_JAW-JT-DMK-0602_2 | New_JAW-JT-DMK-0602 | JAW-JT-DMK-0602 | Central Java | Jawa Tengah | Demak | -6.8738 | 110.7173 | New | New | New | Type C | PAG | JAW-JT-DMK-0602 | Mpls - Gajah |  |  |  | - | - | - | - | New Purchase | New Ring 008 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000020402 | S000055761 | - | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | Yes |  | 2026 | FO NY RFS | GPA | 2026-01-26 | 5 |  |  | 2026 | [38 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-2526_1 | New_JAW-JT-SMG-2526 | JAW-JT-SMG-2526 | Central Java | Jawa Tengah | Kota Semarang | -6.9978 | 110.4478 | New | New | New | Type C | PAG | JAW-JT-SMG-2526 | Gayamsari |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000020403 | - | S000055762 | 10. Ready ATP / RFS | 2025-12-26 | 52 | 2025-11-09 | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-26 | 5 |  |  | 2026 | [5 empty] | Submitted | Approved | [29 empty] | 2025-11-27 | 48 | 2025-11-27 |  |  | #N/A | #N/A
1 | 2 | CLEAR | New_JAW-JT-DMK-0613_2 | New_JAW-JT-DMK-0613 | JAW-JT-DMK-0613 | Central Java | Jawa Tengah | Demak | -6.90943055555556 | 110.633 | New | New | New | Type C | PAG | JAW-JT-DMK-0613 | Supernode Demak |  |  |  | - | - | - | - | New Purchase | New Ring 009 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000020403 | S000055783 | - | 12. NY TERMINATION | 2025-12-26 | 52 |  | #N/A | No |  |  |  | YPTT | 2026-01-26 | 5 |  |  | 2026 | [38 empty] | #N/A |  | Done | 1 | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-1574_1 | New_JAW-JT-PWD-1574 | JAW-JT-PWD-1574 | Central Java | Jawa Tengah | Grobogan | -7.1394 | 110.9057 | New | New | New | Type C | PAG | JAW-JT-PWD-1574 | Toroh |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000019851 | - | S000054304 | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2026 | FO NY RFS | GPA | 2026-01-26 | 5 |  |  | 2026 | 2025-10-20 |  |  |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLT-2171_1 | New_JAW-JT-SLT-2171 | JAW-JT-SLT-2171 | Central Java | Jawa Tengah | Kota Salatiga | -7.3627 | 110.5156 | New | New | New | Type C | PAG | JAW-JT-SLT-2171 | Tingkir Salatiga |  |  |  | - | - | - | - | New Purchase | New Ring 014 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000019851 | S000054324 | - | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | Yes |  | 2025-End Nov | FO NY RFS | GIT | 2026-01-26 | 5 |  |  | 2026 | 2025-10-14 |  |  |  |  | Submitted | Approved | [29 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 2 | CLEAR | New_JAW-JT-PWD-1574_2 | New_JAW-JT-PWD-1574 | JAW-JT-PWD-1574 | Central Java | Jawa Tengah | Grobogan | -7.1394 | 110.9057 | New | New | New | Type C | PAG | JAW-JT-PWD-1574 | Toroh |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000019852 | - | S000054325 | 12. NY TERMINATION | 2025-11-16 | 46 |  | #N/A | No |  | 2026 | FO NY RFS | GPA | 2026-01-26 | 5 |  |  | 2026 | 2025-10-20 | [35 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PWD-1579_1 | New_JAW-JT-PWD-1579 | JAW-JT-PWD-1579 | Central Java | Jawa Tengah | Grobogan | -7.0717 | 110.917 | New | New | New | Type C | PAG | JAW-JT-PWD-1579 | Mpls - Purwodadi |  |  |  | - | - | - | - | New Purchase | New Ring 015 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000019852 | S000054342 | - | 12. NY TERMINATION | 2025-11-16 | 46 |  | #N/A | No |  | 2026 | FO NY RFS | GPA | 2026-01-26 | 5 |  |  | 2026 | 2025-10-25 |  |  |  |  | Submitted | Approved | [29 empty] | 2025-11-18 | 47 | 2025-11-18 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-JPA-0641_1 | New_JAW-JT-JPA-0641 | JAW-JT-JPA-0641 | Central Java | Jawa Tengah | Jepara | -6.6431 | 110.7124 | New | New | New | Type C | PAG | JAW-JT-JPA-0641 | Ngabul |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000019804 | - | S000054205 | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  | 2026 | FO NY RFS | Mingze | 2026-01-26 | 5 |  |  | 2026 |  |  | Not Started | [33 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-JT-PTI-1459_1 | New_JAW-JT-PTI-1459 | JAW-JT-PTI-1459 | Central Java | Jawa Tengah | Pati | -6.5355 | 110.9487 | New | New | New | Type C | PAG | JAW-JT-PTI-1459 | Cluwak Pati |  |  |  | - | - | - | - | New Purchase | New Ring 019 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000019804 | S000054225 | - | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  |  |  | Mingze | 2026-01-26 | 5 |  |  | 2026 |  |  | Not Started | [33 empty] | 2025-11-23 | 47 | 2025-11-23 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | New_JAW-YO-BTL-0048_1 | New_JAW-YO-BTL-0048 | JAW-YO-BTL-0048 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8864 | 110.3462 | New | New | New | Type C | PAG | JAW-YO-BTL-0048 | Bantul |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020319 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-26 | 5 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-WAT-0365_1 | New_JAW-YO-WAT-0365 | JAW-YO-WAT-0365 | Central Java | Daerah Istimewa Yogyakarta | Kulon Progo | -7.8573 | 110.1609 | New | New | New | Type C | #N/A | JAW-YO-WAT-0365 | Mpls - Wates |  |  |  | - | - | - | - | New Purchase | New Ring 020 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | #N/A | [6 empty] | #N/A | [5 empty] | 2026-01-26 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | CLEAR | New_JAW-YO-BTL-0048_2 | New_JAW-YO-BTL-0048 | JAW-YO-BTL-0048 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8864 | 110.3462 | New | New | New | Type C | PAG | JAW-YO-BTL-0048 | Bantul |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020319 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-27 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0492_1 | New_JAW-YO-YYK-0492 | JAW-YO-YYK-0492 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7893 | 110.3595 | New | New | New | Type C | PAG | JAW-YO-YYK-0492 | Mpls - Patok Yogyakartara |  |  |  | - | - | - | - | New Purchase | New Ring 021 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020320 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-27 | 5 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0074_1 | New_JAW-YO-BTL-0074 | JAW-YO-BTL-0074 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9223 | 110.382 | New | New | New | Type C | PAG | JAW-YO-BTL-0074 | Imogiri |  |  |  | - | - | - | - | New Purchase | New Ring 022 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000019967 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-27 | 5 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-YYK-0084_1 | New_JAW-YO-YYK-0084 | JAW-YO-YYK-0084 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8209 | 110.401 | New | New | New | Type C | PAG | JAW-YO-YYK-0084 | Kota Gede |  |  |  | - | - | - | - | New Purchase | New Ring 022 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020330 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-27 | 5 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | CLEAR | New_JAW-YO-YYK-0084_2 | New_JAW-YO-YYK-0084 | JAW-YO-YYK-0084 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8209 | 110.401 | New | New | New | Type C | PAG | JAW-YO-YYK-0084 | Kota Gede |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020330 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-27 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-BTL-0115_1 | New_JAW-YO-BTL-0115 | JAW-YO-BTL-0115 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8518 | 110.4749 | New | New | New | Type C | MA | JAW-YO-BTL-0115 | Patukkota |  |  |  | - | - | - | - | New Purchase | New Ring 024 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | #N/A | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-27 | 5 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | CLEAR | New_JAW-YO-BTL-0074_2 | New_JAW-YO-BTL-0074 | JAW-YO-BTL-0074 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9223 | 110.382 | New | New | New | Type C | PAG | JAW-YO-BTL-0074 | Imogiri |  |  |  | - | - | - | - | New Purchase | New Ring 025 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000019967 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-27 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | CLEAR | New_JAW-YO-BTL-0115_2 | New_JAW-YO-BTL-0115 | JAW-YO-BTL-0115 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8518 | 110.4749 | New | New | New | Type C | MA | JAW-YO-BTL-0115 | Patukkota |  |  |  | - | - | - | - | New Purchase | New Ring 025 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | #N/A | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-27 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 3 | CLEAR | New_JAW-YO-BTL-0074_3 | New_JAW-YO-BTL-0074 | JAW-YO-BTL-0074 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9223 | 110.382 | New | New | New | Type C | PAG | JAW-YO-BTL-0074 | Imogiri |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000019967 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-27 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 3 | CLEAR | New_JAW-YO-BTL-0048_3 | New_JAW-YO-BTL-0048 | JAW-YO-BTL-0048 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8864 | 110.3462 | New | New | New | Type C | PAG | JAW-YO-BTL-0048 | Bantul |  |  |  | - | - | - | - | New Purchase | New Ring 026 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020319 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-27 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-0184_1 | New_JAW-JT-BLA-0184 | JAW-JT-BLA-0184 | Central Java | Jawa Tengah | Blora | -6.9741 | 111.4834 | New | New | New | Type C | #N/A | JAW-JT-BLA-0184 | Geneng Blora |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK |  | R0000019802 |  |  | 10. Ready ATP / RFS |  |  | 2025-11-09 | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-27 | 5 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-3489_1 | New_JAW-JT-BLA-3489 | JAW-JT-BLA-3489 | Central Java | Jawa Tengah | Blora | -7.1473 | 111.5926 | New | New | New | Type C | #N/A | JAW-JT-BLA-3489 |  |  |  |  | - | - | - | - | New Purchase | New Ring 027 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | #N/A | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-27 | 5 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | CLEAR | New_JAW-JT-SLT-2171_2 | New_JAW-JT-SLT-2171 | JAW-JT-SLT-2171 | Central Java | Jawa Tengah | Kota Salatiga | -7.3627 | 110.5156 | New | New | New | Type C | PAG | JAW-JT-SLT-2171 | Tingkir Salatiga |  |  |  | - | - | - | - | New Purchase | New Ring 031 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020476 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS | GIT | 2026-01-27 | 5 |  |  | 2026 | 2025-10-14 | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-2731_1 | New_JAW-JT-UNR-2731 | JAW-JT-UNR-2731 | Central Java | Jawa Tengah | Semarang | -7.2666 | 110.4551 | New | New | New | Type C | PAG | JAW-JT-UNR-2731 | Tuntang |  |  |  | - | - | - | - | New Purchase | New Ring 031 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | #N/A | [6 empty] | #N/A |  |  | Mid Dec 25 | FO NY RFS |  | 2026-01-28 | 5 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SMG-2406_1 | New_JAW-JT-SMG-2406 | JAW-JT-SMG-2406 | Central Java | Jawa Tengah | Kota Semarang | -6.9856 | 110.4079 | New | New | New | Type C | PAG | JAW-JT-SMG-2406 | Simpang Lima |  |  |  | - | - | #N/A | #N/A | New Purchase | New Ring 032 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | SPK OK | R0000020404 | S000055794 | S000056139 | 12. NY TERMINATION | 2025-12-02 | 49 |  | #N/A | No |  | 2025-End Nov | FO NY RFS | GIT | 2026-01-28 | 5 |  |  | 2026 | 2025-10-16 | [35 empty] | 2025-11-24 | 48 | 2025-11-24 |  |  | #N/A | #N/A
1 | 2 | CLEAR | New_JAW-JT-SMG-2526_2 | New_JAW-JT-SMG-2526 | JAW-JT-SMG-2526 | Central Java | Jawa Tengah | Kota Semarang | -6.9978 | 110.4478 | New | New | New | Type C | PAG | JAW-JT-SMG-2526 | Gayamsari |  |  |  | - | - | - | - | New Purchase | New Ring 032 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000020477 | S000056159 | - | 12. NY TERMINATION | 2025-11-30 | 48 |  | #N/A | No |  | 2025-End Nov | FO NY RFS |  | 2026-01-28 | 5 |  |  | 2026 | [36 empty] | 2025-11-23 | 47 | 2025-11-23 |  |  | #N/A | #N/A
1 | 3 | CLEAR | New_JAW-JT-SMG-2526_3 | New_JAW-JT-SMG-2526 | JAW-JT-SMG-2526 | Central Java | Jawa Tengah | Kota Semarang | -6.9978 | 110.4478 | New | New | New | Type C | PAG | JAW-JT-SMG-2526 | Gayamsari |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000020168 | - | S000054812 | 10. Ready ATP / RFS | 2025-11-23 | 47 | 2025-11-09 | #N/A | No |  | 2025-End Nov | FO NY RFS | YPTT | 2026-01-28 | 5 |  |  | 2026 |  |  | Not Started | [33 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | #N/A | #N/A | November
1 | 2 | CLEAR | New_JAW-JT-SMG-3485_2 | New_JAW-JT-SMG-3485 | JAW-JT-SMG-3485 | Central Java | Jawa Tengah | Kota Semarang | -7.09636111111111 | 110.4175 | New | New | New | Type C | PAG | JAW-JT-SMG-3485 | Supernode Gombel |  |  |  | - | - | - | - | New Purchase | New Ring 033 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR | PT IFORTE SOLUSI INFOTEK | PAG Existing,Waiting DRM | R0000020168 | S000054826 | - | 12. NY TERMINATION | 2025-11-23 | 47 |  | #N/A | No |  |  |  | CCSI | 2026-01-28 | 5 |  |  | 2026 | 2025-11-24 | 2025-11-22 14:54:57 | Reviewing | [33 empty] | 2025-11-11 | 46 | 2025-11-11 |  | Done | 1 | CCSI | November
1 | 2 | CLEAR | New_JAW-YO-YYK-0492_2 | New_JAW-YO-YYK-0492 | JAW-YO-YYK-0492 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7893 | 110.3595 | New | New | New | Type C | PAG | JAW-YO-YYK-0492 | Mpls - Patok Yogyakartara |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020320 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-28 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-SMN-0179_1 | New_JAW-YO-SMN-0179 | JAW-YO-SMN-0179 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.7666 | 110.361 | New | New | New | Type C | PAG | JAW-YO-SMN-0179 | Kricak |  |  |  | - | - | - | - | New Purchase | New Ring 034 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000019970 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-28 | 5 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 4 | CLEAR | New_JAW-YO-BTL-0048_4 | New_JAW-YO-BTL-0048 | JAW-YO-BTL-0048 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.8864 | 110.3462 | New | New | New | Type C | PAG | JAW-YO-BTL-0048 | Bantul |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020319 | [6 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-01-28 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 3 | CLEAR | New_JAW-YO-YYK-0084_3 | New_JAW-YO-YYK-0084 | JAW-YO-YYK-0084 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8209 | 110.401 | New | New | New | Type C | PAG | JAW-YO-YYK-0084 | Kota Gede |  |  |  | - | - | - | - | New Purchase | New Ring 036 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020330 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-28 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 3 | CLEAR | New_JAW-YO-YYK-0492_3 | New_JAW-YO-YYK-0492 | JAW-YO-YYK-0492 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7893 | 110.3595 | New | New | New | Type C | PAG | JAW-YO-YYK-0492 | Mpls - Patok Yogyakartara |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020320 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-28 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 4 | CLEAR | New_JAW-YO-YYK-0084_4 | New_JAW-YO-YYK-0084 | JAW-YO-YYK-0084 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.8209 | 110.401 | New | New | New | Type C | PAG | JAW-YO-YYK-0084 | Kota Gede |  |  |  | - | - | - | - | New Purchase | New Ring 037 | Keep | 2 | Bundle_Type C_1 1x100GLR + 1x100G ER + 4x25G/10G LR + 2x25G/10G ER + 2x25G/10G ZR + 8x1G LR |  |  | R0000020330 | [6 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-01-28 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BNR-8262_1 | New_JAW-JT-BNR-8262 | JAW-JT-BNR-8262 | Central Java | Jawa Tengah | Banjarnegara | -7.4707 | 109.4749 | Insert | New | New | Type A | MA | JAW-JT-BNR-8262 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-28 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BTG-8308_1 | New_JAW-JT-BTG-8308 | JAW-JT-BTG-8308 | Central Java | Jawa Tengah | Batang | -6.9756 | 109.8668 | Insert | New | New | Type A | MA | JAW-JT-BTG-8308 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-28 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8429_1 | New_JAW-JT-CLP-8429 | JAW-JT-CLP-8429 | Central Java | Jawa Tengah | Cilacap | -7.6905 | 109.3379 | Insert | New | New | Type A | MA | JAW-JT-CLP-8429 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-29 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KLN-8338_1 | New_JAW-JT-KLN-8338 | JAW-JT-KLN-8338 | Central Java | Jawa Tengah | Klaten | -7.7556 | 110.4954 | Insert | New | New | Type A | MA | JAW-JT-KLN-8338 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-29 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PML-8435_1 | New_JAW-JT-PML-8435 | JAW-JT-PML-8435 | Central Java | Jawa Tengah | Pemalang | -7.0689 | 109.3678 | Insert | New | New | Type A | MA | JAW-JT-PML-8435 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-29 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PML-8436_1 | New_JAW-JT-PML-8436 | JAW-JT-PML-8436 | Central Java | Jawa Tengah | Pemalang | -7.0652 | 109.3799 | Insert | New | New | Type A | MA | JAW-JT-PML-8436 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-29 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-WNO-8318_1 | New_JAW-YO-WNO-8318 | JAW-YO-WNO-8318 | Central Java | Daerah Istimewa Yogyakarta | GunungKidul | -7.9453 | 110.5506 | Insert | New | New | Type A | MA | JAW-YO-WNO-8318 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-29 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JI-BKL-3177_1 | New_JAW-JI-BKL-3177 | JAW-JI-BKL-3177 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9306 | 110.4678 | Insert | New | New | Type A | MA | JAW-JI-BKL-3177 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-29 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-MKD-8431_1 | New_JAW-JT-MKD-8431 | JAW-JT-MKD-8431 | Central Java | Jawa Tengah | Magelang | -7.6136 | 110.2472 | Insert | New | New | Type A | MA | JAW-JT-MKD-8431 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-29 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8581_1 | New_JAW-JT-CLP-8581 | JAW-JT-CLP-8581 | Central Java | Jawa Tengah | Cilacap | -7.6675 | 109.1667 | Insert | New | New | Type A | MA | JAW-JT-CLP-8581 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-29 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8537_1 | New_JAW-JT-CLP-8537 | JAW-JT-CLP-8537 | Central Java | Jawa Tengah | Cilacap | -7.298 | 108.7871 | Insert | New | New | Type A | MA | JAW-JT-CLP-8537 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-29 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8487_1 | New_JAW-JT-CLP-8487 | JAW-JT-CLP-8487 | Central Java | Jawa Tengah | Cilacap | -7.6193 | 109.1185 | Insert | New | New | Type A | MA | JAW-JT-CLP-8487 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-29 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8371_1 | New_JAW-JT-PWT-8371 | JAW-JT-PWT-8371 | Central Java | Jawa Tengah | Banyumas | -7.4632 | 109.2684 | Insert | New | New | Type A | MA | JAW-JT-PWT-8371 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-29 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLW-8422_1 | New_JAW-JT-SLW-8422 | JAW-JT-SLW-8422 | Central Java | Jawa Tengah | Tegal | -6.8976 | 109.1902 | Insert | New | New | Type A | MA | JAW-JT-SLW-8422 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-29 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLW-8316_1 | New_JAW-JT-SLW-8316 | JAW-JT-SLW-8316 | Central Java | Jawa Tengah | Tegal | -6.9238 | 109.3256 | Insert | New | New | Type A | MA | JAW-JT-SLW-8316 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-29 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLW-8429_1 | New_JAW-JT-SLW-8429 | JAW-JT-SLW-8429 | Central Java | Jawa Tengah | Tegal | -7.1391 | 109.1752 | Insert | New | New | Type A | MA | JAW-JT-SLW-8429 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-30 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SLW-8378_1 | New_JAW-JT-SLW-8378 | JAW-JT-SLW-8378 | Central Java | Jawa Tengah | Tegal | -6.9244 | 109.138 | Insert | New | New | Type A | MA | JAW-JT-SLW-8378 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-30 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-WNO-8327_1 | New_JAW-YO-WNO-8327 | JAW-YO-WNO-8327 | Central Java | Daerah Istimewa Yogyakarta | GunungKidul | -7.9878 | 110.5772 | Insert | New | New | Type A | MA | JAW-YO-WNO-8327 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-30 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BYL-8300_1 | New_JAW-JT-BYL-8300 | JAW-JT-BYL-8300 | Central Java | Jawa Tengah | Boyolali | -7.5738 | 110.6754 | Insert | New | New | Type A | MA | JAW-JT-BYL-8300 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-30 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KBM-8461_1 | New_JAW-JT-KBM-8461 | JAW-JT-KBM-8461 | Central Java | Jawa Tengah | Kebumen | -7.744 | 109.5868 | Insert | New | New | Type A | MA | JAW-JT-KBM-8461 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-30 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8634_1 | New_JAW-JT-CLP-8634 | JAW-JT-CLP-8634 | Central Java | Jawa Tengah | Cilacap | -7.4826 | 108.7949 | Insert | New | New | Type A | MA | JAW-JT-CLP-8634 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-30 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8454_1 | New_JAW-JT-PWT-8454 | JAW-JT-PWT-8454 | Central Java | Jawa Tengah | Banyumas | -7.5348 | 109.1195 | Insert | New | New | Type A | MA | JAW-JT-PWT-8454 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-30 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KBM-8491_1 | New_JAW-JT-KBM-8491 | JAW-JT-KBM-8491 | Central Java | Jawa Tengah | Kebumen | -7.6824 | 109.6605 | Insert | New | New | Type A | MA | JAW-JT-KBM-8491 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, MOCN Drop | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-30 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-WAT-8302_1 | New_JAW-YO-WAT-8302 | JAW-YO-WAT-8302 | Central Java | Daerah Istimewa Yogyakarta | Kulon Progo | -7.8856 | 110.1754 | Insert | New | New | Type A | MA | JAW-YO-WAT-8302 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-30 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8463_1 | New_JAW-JT-PWT-8463 | JAW-JT-PWT-8463 | Central Java | Jawa Tengah | Banyumas | -7.5382 | 109.1608 | Insert | New | New | Type A | MA | JAW-JT-PWT-8463 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-30 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8490_1 | New_JAW-JT-PWT-8490 | JAW-JT-PWT-8490 | Central Java | Jawa Tengah | Banyumas | -7.5493 | 109.2151 | Insert | New | New | Type A | MA | JAW-JT-PWT-8490 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-30 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BYL-8372_1 | New_JAW-JT-BYL-8372 | JAW-JT-BYL-8372 | Central Java | Jawa Tengah | Boyolali | -7.53 | 110.8098 | Insert | New | New | Type A | MA | JAW-JT-BYL-8372 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | 2025-11-05 | [5 empty] | 2026-01-30 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-RBG-8476_1 | New_JAW-JT-RBG-8476 | JAW-JT-RBG-8476 | Central Java | Jawa Tengah | Rembang | -6.7458 | 111.4809 | Insert | New | New | Type A | MA | JAW-JT-RBG-8476 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-01-30 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BBS-9156_1 | New_JAW-JT-BBS-9156 | JAW-JT-BBS-9156 | Central Java | Jawa Tengah | Brebes | -6.9669 | 109.0634 | Insert | New | New | Type A | MA | JAW-JT-BBS-9156 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-02 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8391_1 | New_JAW-JT-CLP-8391 | JAW-JT-CLP-8391 | Central Java | Jawa Tengah | Cilacap | -7.6401 | 109.226 | Insert | New | New | Type A | MA | JAW-JT-CLP-8391 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-02 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8604_1 | New_JAW-JT-CLP-8604 | JAW-JT-CLP-8604 | Central Java | Jawa Tengah | Cilacap | -7.5634 | 108.7578 | Insert | New | New | Type A | MA | JAW-JT-CLP-8604 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-02 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8633_1 | New_JAW-JT-CLP-8633 | JAW-JT-CLP-8633 | Central Java | Jawa Tengah | Cilacap | -7.6328 | 109.2124 | Insert | New | New | Type A | MA | JAW-JT-CLP-8633 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-02 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BBS-9167_1 | New_JAW-JT-BBS-9167 | JAW-JT-BBS-9167 | Central Java | Jawa Tengah | Brebes | -7.0291 | 108.9948 | Insert | New | New | Type A | MA | JAW-JT-BBS-9167 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-02 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BBS-9185_1 | New_JAW-JT-BBS-9185 | JAW-JT-BBS-9185 | Central Java | Jawa Tengah | Brebes | -6.9807 | 108.8531 | Insert | New | New | Type A | MA | JAW-JT-BBS-9185 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-02 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8349_1 | New_JAW-JT-BLA-8349 | JAW-JT-BLA-8349 | Central Java | Jawa Tengah | Blora | -6.9512 | 111.1388 | Insert | New | New | Type A | MA | JAW-JT-BLA-8349 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-02-02 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8506_1 | New_JAW-JT-CLP-8506 | JAW-JT-CLP-8506 | Central Java | Jawa Tengah | Cilacap | -7.7337 | 109.0097 | Insert | New | New | Type A | MA | JAW-JT-CLP-8506 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-02 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8508_1 | New_JAW-JT-CLP-8508 | JAW-JT-CLP-8508 | Central Java | Jawa Tengah | Cilacap | -7.7037 | 109.02 | Insert | New | New | Type A | MA | JAW-JT-CLP-8508 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-02 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8528_1 | New_JAW-JT-CLP-8528 | JAW-JT-CLP-8528 | Central Java | Jawa Tengah | Cilacap | -7.3242 | 108.7378 | Insert | New | New | Type A | MA | JAW-JT-CLP-8528 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-02 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8542_1 | New_JAW-JT-CLP-8542 | JAW-JT-CLP-8542 | Central Java | Jawa Tengah | Cilacap | -7.4603 | 108.8015 | Insert | New | New | Type A | MA | JAW-JT-CLP-8542 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-02 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8558_1 | New_JAW-JT-CLP-8558 | JAW-JT-CLP-8558 | Central Java | Jawa Tengah | Cilacap | -7.5833 | 108.9084 | Insert | New | New | Type A | MA | JAW-JT-CLP-8558 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-02 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8575_1 | New_JAW-JT-CLP-8575 | JAW-JT-CLP-8575 | Central Java | Jawa Tengah | Cilacap | -7.296 | 108.7562 | Insert | New | New | Type A | MA | JAW-JT-CLP-8575 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-02 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8618_1 | New_JAW-JT-CLP-8618 | JAW-JT-CLP-8618 | Central Java | Jawa Tengah | Cilacap | -7.4856 | 108.841 | Insert | New | New | Type A | MA | JAW-JT-CLP-8618 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-03 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8200_1 | New_JAW-JT-BLA-8200 | JAW-JT-BLA-8200 | Central Java | Jawa Tengah | Blora | -7.0242 | 111.2572 | Insert | New | New | Type A | MA | JAW-JT-BLA-8200 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-02-03 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8299_1 | New_JAW-JT-BLA-8299 | JAW-JT-BLA-8299 | Central Java | Jawa Tengah | Blora | -6.933 | 111.4712 | Insert | New | New | Type A | MA | JAW-JT-BLA-8299 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-02-03 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-MKD-8373_1 | New_JAW-JT-MKD-8373 | JAW-JT-MKD-8373 | Central Java | Jawa Tengah | Magelang | -7.5403 | 110.1714 | Insert | New | New | Type A | MA | JAW-JT-MKD-8373 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-03 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8315_1 | New_JAW-JT-DMK-8315 | JAW-JT-DMK-8315 | Central Java | Jawa Tengah | Demak | -7.0646 | 110.5199 | Insert | New | New | Type A | MA | JAW-JT-DMK-8315 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-02-03 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8363_1 | New_JAW-JT-DMK-8363 | JAW-JT-DMK-8363 | Central Java | Jawa Tengah | Demak | -6.8472 | 110.5776 | Insert | New | New | Type A | MA | JAW-JT-DMK-8363 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | 2025-11-17 |  |  | 2026 | FO NY RFS |  | 2026-02-03 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8434_1 | New_JAW-JT-DMK-8434 | JAW-JT-DMK-8434 | Central Java | Jawa Tengah | Demak | -6.8683 | 110.7011 | Insert | New | New | Type A | MA | JAW-JT-DMK-8434 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | 2025-11-17 |  |  | 2026 | FO NY RFS |  | 2026-02-03 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-RBG-8437_1 | New_JAW-JT-RBG-8437 | JAW-JT-RBG-8437 | Central Java | Jawa Tengah | Rembang | -6.7114 | 111.3338 | Insert | New | New | Type A | MA | JAW-JT-RBG-8437 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-03 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8310_1 | New_JAW-JT-DMK-8310 | JAW-JT-DMK-8310 | Central Java | Jawa Tengah | Demak | -7.0206 | 110.5126 | Insert | New | New | Type A | MA | JAW-JT-DMK-8310 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-02-03 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWR-8510_1 | New_JAW-JT-PWR-8510 | JAW-JT-PWR-8510 | Central Java | Jawa Tengah | Purworejo | -7.7009 | 109.9036 | Insert | New | New | Type A | MA | JAW-JT-PWR-8510 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-03 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8213_1 | New_JAW-JT-BLA-8213 | JAW-JT-BLA-8213 | Central Java | Jawa Tengah | Blora | -7.0251 | 111.2929 | Insert | New | New | Type A | MA | JAW-JT-BLA-8213 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-02-03 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8269_1 | New_JAW-JT-BLA-8269 | JAW-JT-BLA-8269 | Central Java | Jawa Tengah | Blora | -7.2012 | 111.4162 | Insert | New | New | Type A | MA | JAW-JT-BLA-8269 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-02-03 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BLA-8280_1 | New_JAW-JT-BLA-8280 | JAW-JT-BLA-8280 | Central Java | Jawa Tengah | Blora | -7.1908 | 111.4184 | Insert | New | New | Type A | MA | JAW-JT-BLA-8280 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-02-03 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWD-8552_1 | New_JAW-JT-PWD-8552 | JAW-JT-PWD-8552 | Central Java | Jawa Tengah | Grobogan | -7.0754 | 111.0954 | Insert | New | New | Type A | MA | JAW-JT-PWD-8552 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-02-04 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8476_1 | New_JAW-JT-UNR-8476 | JAW-JT-UNR-8476 | Central Java | Jawa Tengah | Semarang | -7.3772 | 110.4219 | Insert | New | New | Type A | MA | JAW-JT-UNR-8476 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A |  |  | Mid Dec 25 | FO NY RFS |  | 2026-02-04 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8365_1 | New_JAW-JT-PWT-8365 | JAW-JT-PWT-8365 | Central Java | Jawa Tengah | Banyumas | -7.3443 | 109.2796 | Insert | New | New | Type A | MA | JAW-JT-PWT-8365 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-04 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SGN-8471_1 | New_JAW-JT-SGN-8471 | JAW-JT-SGN-8471 | Central Java | Jawa Tengah | Sragen | -7.346 | 110.8365 | Insert | New | New | Type A | MA | JAW-JT-SGN-8471 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-04 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KRG-8323_1 | New_JAW-JT-KRG-8323 | JAW-JT-KRG-8323 | Central Java | Jawa Tengah | Karanganyar | -7.5518 | 110.9846 | Insert | New | New | Type A | MA | JAW-JT-KRG-8323 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-04 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BNR-8310_1 | New_JAW-JT-BNR-8310 | JAW-JT-BNR-8310 | Central Java | Jawa Tengah | Banjarnegara | -7.373 | 109.6089 | Insert | New | New | Type A | MA | JAW-JT-BNR-8310 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-04 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BNR-8322_1 | New_JAW-JT-BNR-8322 | JAW-JT-BNR-8322 | Central Java | Jawa Tengah | Banjarnegara | -7.4219 | 109.6626 | Insert | New | New | Type A | MA | JAW-JT-BNR-8322 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-04 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BNR-8327_1 | New_JAW-JT-BNR-8327 | JAW-JT-BNR-8327 | Central Java | Jawa Tengah | Banjarnegara | -7.4749 | 109.6868 | Insert | New | New | Type A | MA | JAW-JT-BNR-8327 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-04 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BNR-8350_1 | New_JAW-JT-BNR-8350 | JAW-JT-BNR-8350 | Central Java | Jawa Tengah | Banjarnegara | -7.4086 | 109.7859 | Insert | New | New | Type A | MA | JAW-JT-BNR-8350 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-04 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8534_1 | New_JAW-JT-CLP-8534 | JAW-JT-CLP-8534 | Central Java | Jawa Tengah | Cilacap | -7.716 | 109.0158 | Insert | New | New | Type A | MA | JAW-JT-CLP-8534 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-04 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-CLP-8550_1 | New_JAW-JT-CLP-8550 | JAW-JT-CLP-8550 | Central Java | Jawa Tengah | Cilacap | -7.6473 | 108.9717 | Insert | New | New | Type A | MA | JAW-JT-CLP-8550 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-04 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8361_1 | New_JAW-JT-PWT-8361 | JAW-JT-PWT-8361 | Central Java | Jawa Tengah | Banyumas | -7.3612 | 109.2757 | Insert | New | New | Type A | MA | JAW-JT-PWT-8361 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-04 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PWT-8458_1 | New_JAW-JT-PWT-8458 | JAW-JT-PWT-8458 | Central Java | Jawa Tengah | Banyumas | -7.4058 | 109.1416 | Insert | New | New | Type A | MA | JAW-JT-PWT-8458 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-04 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KJN-8440_1 | New_JAW-JT-KJN-8440 | JAW-JT-KJN-8440 | Central Java | Jawa Tengah | Pekalongan | -6.9265 | 109.6562 | Insert | New | New | Type A | MA | JAW-JT-KJN-8440 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-05 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-MKD-8467_1 | New_JAW-JT-MKD-8467 | JAW-JT-MKD-8467 | Central Java | Jawa Tengah | Magelang | -7.4299 | 110.2948 | Insert | New | New | Type A | MA | JAW-JT-MKD-8467 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-05 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-DMK-8379_1 | New_JAW-JT-DMK-8379 | JAW-JT-DMK-8379 | Central Java | Jawa Tengah | Demak | -6.9175 | 110.5982 | Insert | New | New | Type A | MA | JAW-JT-DMK-8379 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-02-05 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-MKD-8416_1 | New_JAW-JT-MKD-8416 | JAW-JT-MKD-8416 | Central Java | Jawa Tengah | Magelang | -7.5439 | 110.2316 | Insert | New | New | Type A | MA | JAW-JT-MKD-8416 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-05 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-YO-SMN-8354_1 | New_JAW-YO-SMN-8354 | JAW-YO-SMN-8354 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.6514 | 110.3476 | Insert | New | New | Type A | MA | JAW-YO-SMN-8354 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-02-05 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PML-8442_1 | New_JAW-JT-PML-8442 | JAW-JT-PML-8442 | Central Java | Jawa Tengah | Pemalang | -7.034 | 109.3838 | Insert | New | New | Type A | MA | JAW-JT-PML-8442 |  |  |  |  | - | - | - | - | Redeploy | Keep | Propose Drop, NO SPK | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-05 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KDS-8398_1 | New_JAW-JT-KDS-8398 | JAW-JT-KDS-8398 | Central Java | Jawa Tengah | Kudus | -6.816 | 110.8334 | Insert | New | New | Type A | MA | JAW-JT-KDS-8398 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A |  |  | 2026 | FO NY RFS |  | 2026-02-05 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SKH-8460_1 | New_JAW-JT-SKH-8460 | JAW-JT-SKH-8460 | Central Java | Jawa Tengah | Sukoharjo | -7.5678 | 110.7518 | Insert | New | New | Type A | MA | JAW-JT-SKH-8460 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-05 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8572_1 | New_JAW-JT-UNR-8572 | JAW-JT-UNR-8572 | Central Java | Jawa Tengah | Semarang | -7.3119 | 110.3624 | Insert | New | New | Type A | MA | JAW-JT-UNR-8572 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | 2025-10-12 |  |  | Mid Dec 25 | FO NY RFS |  | 2026-02-05 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BYL-8312_1 | New_JAW-JT-BYL-8312 | JAW-JT-BYL-8312 | Central Java | Jawa Tengah | Boyolali | -7.5306 | 110.6961 | Insert | New | New | Type A | MA | JAW-JT-BYL-8312 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | 2025-10-26 | [5 empty] | 2026-02-05 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BYL-8326_1 | New_JAW-JT-BYL-8326 | JAW-JT-BYL-8326 | Central Java | Jawa Tengah | Boyolali | -7.3551 | 110.7025 | Insert | New | New | Type A | MA | JAW-JT-BYL-8326 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | 2025-10-19 | [5 empty] | 2026-02-05 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-BYL-8360_1 | New_JAW-JT-BYL-8360 | JAW-JT-BYL-8360 | Central Java | Jawa Tengah | Boyolali | -7.4897 | 110.7789 | Insert | New | New | Type A | MA | JAW-JT-BYL-8360 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-05 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-PTI-8522_1 | New_JAW-JT-PTI-8522 | JAW-JT-PTI-8522 | Central Java | Jawa Tengah | Pati | -6.9494 | 111.0712 | Insert | New | New | Type A | MA | JAW-JT-PTI-8522 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-05 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SGN-8452_1 | New_JAW-JT-SGN-8452 | JAW-JT-SGN-8452 | Central Java | Jawa Tengah | Sragen | -7.389 | 110.8007 | Insert | New | New | Type A | MA | JAW-JT-SGN-8452 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | 2025-11-02 | [5 empty] | 2026-02-06 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SGN-8515_1 | New_JAW-JT-SGN-8515 | JAW-JT-SGN-8515 | Central Java | Jawa Tengah | Sragen | -7.285 | 110.9163 | Insert | New | New | Type A | MA | JAW-JT-SGN-8515 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-06 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SKH-8449_1 | New_JAW-JT-SKH-8449 | JAW-JT-SKH-8449 | Central Java | Jawa Tengah | Sukoharjo | -7.6043 | 110.7555 | Insert | New | New | Type A | MA | JAW-JT-SKH-8449 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-06 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SKH-8535_1 | New_JAW-JT-SKH-8535 | JAW-JT-SKH-8535 | Central Java | Jawa Tengah | Sukoharjo | -7.7022 | 110.8525 | Insert | New | New | Type A | MA | JAW-JT-SKH-8535 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-06 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-UNR-8563_1 | New_JAW-JT-UNR-8563 | JAW-JT-UNR-8563 | Central Java | Jawa Tengah | Semarang | -7.3687 | 110.604 | Insert | New | New | Type A | MA | JAW-JT-UNR-8563 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A |  |  | 2025-End Nov | FO NY RFS |  | 2026-02-06 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-SKH-8477_1 | New_JAW-JT-SKH-8477 | JAW-JT-SKH-8477 | Central Java | Jawa Tengah | Sukoharjo | -7.6579 | 110.7901 | Insert | New | New | Type A | MA | JAW-JT-SKH-8477 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | 2025-10-19 | [5 empty] | 2026-02-06 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | New_JAW-JT-KRG-8259_1 | New_JAW-JT-KRG-8259 | JAW-JT-KRG-8259 | Central Java | Jawa Tengah | Karanganyar | -7.5277 | 110.7683 | Insert | New | New | Type A | MA | JAW-JT-KRG-8259 |  |  |  |  | - | - | - | - | Redeploy | Keep | Keep | 3 | 0 | [9 empty] | #N/A | [5 empty] | 2026-02-06 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | HOLD | Service Migration__1 | Service Migration_ |  | Central Java |  |  | #N/A | #N/A | Service Migration | Service Migration | Service Migration | Type A | MA | [5 empty] | - | - | - | - | Redeploy | SF Enterprise(Reuse 6120H-WA) | #N/A |  | 0 | [9 empty] | #N/A | [5 empty] | 2025-10-15 | 42 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | HOLD | Service Migration__2 | Service Migration_ |  | Central Java |  |  | #N/A | #N/A | Service Migration | Service Migration | Service Migration | Type A | MA | [5 empty] | - | - | - | - | Redeploy | SF Enterprise(Reuse 6120H-WA) | #N/A |  | 0 | [9 empty] | #N/A | [5 empty] | 2025-10-22 | 43 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 3 | HOLD | Service Migration__3 | Service Migration_ |  | Central Java |  |  | #N/A | #N/A | Service Migration | Service Migration | Service Migration | Type A | MA | [5 empty] | - | - | - | - | Redeploy | JAW-YO-YYK-0492(Reuse 6120H-WA) | #N/A |  | 0 | [9 empty] | #N/A | [5 empty] | 2025-10-29 | 44 | October |  | 2025 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0538_1 | Swap_JAW-JT-DMK-0538 | JAW-JT-DMK-0538 | Central Java | Jawa Tengah | Demak | -6.9443 | 110.4857 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0538 | Nyangkringan Genuk | TBG | IBS¦SMG_01N023 | Central Java Ring 91A | MA-JTDMK0538-01H | 10.206.27.103 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-17 | Approved | 2025-11-07 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110201 | 2025-11-02 | 2025-11-04 | done | done | done | done | done | done | YPTT | 2025-11-02 | 44 | 2025-11-04 | 2025-11-01 | 2025-11-03 | XLWO-20251103-00001154 |  | 2025-11-05 | 2025-11-09 | 2025-11-05 | 45 | 2025-11-09 | 45 | FALSE | 2025-11-09 | 45 | 2025-11-09 | 2025-11-09 | Done | #N/A | #N/A | November | 2025-11-14 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0546_1 | Swap_JAW-JT-DMK-0546 | JAW-JT-DMK-0546 | Central Java | Jawa Tengah | Demak | -7.0195 | 110.5035 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0546 | Bandungrejo Mranggen | DMT | ISAT¦14DMK034 | Central Java Ring 91A | MA-JTDMK0546-01H | 10.206.27.100 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-14 | 2025-10-15 | Approved | 2025-10-17 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110202 | 2025-11-02 | 2025-11-04 | done | done | done | done | done | done | GPA | 2025-11-02 | 44 | 2025-11-04 | 2025-11-01 | 2025-11-03 | XLWO-20251103-00001154 |  | 2025-11-05 | 2025-11-09 | 2025-11-05 | 45 | 2025-11-09 | 45 | FALSE | 2025-11-09 | 45 | 2025-11-09 | 2025-11-09 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0554_1 | Swap_JAW-JT-DMK-0554 | JAW-JT-DMK-0554 | Central Java | Jawa Tengah | Demak | -7.0472 | 110.518 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0554 | Kalitengah Mranggen Demak | DMT | DMT¦NO TP ID | Central Java Ring 91A | MA-JTDMK0554-01H | 10.206.27.99 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-14 | 2025-10-15 | Approved | 2025-10-17 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110206 | 2025-11-02 | 2025-11-04 | done | done | done | done | done | done | GPA | 2025-11-02 | 44 | 2025-11-04 | 2025-11-01 | 2025-11-03 | XLWO-20251103-00001154 |  | 2025-11-05 | 2025-11-09 | 2025-11-05 | 45 | 2025-11-09 | 45 | FALSE | 2025-11-09 | 45 | 2025-11-09 | 2025-11-09 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0561_1 | Swap_JAW-JT-DMK-0561 | JAW-JT-DMK-0561 | Central Java | Jawa Tengah | Demak | -7.0117 | 110.535 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0561 | Tegalarum Mranggen | TBG | SKP¦NO TP ID | Central Java Ring 91A | MA-JTDMK0561-01H | 10.206.27.101 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-25 | Approved | 2025-10-17 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110207 | 2025-11-02 | 2025-11-04 | done | done | done | done | done | done | GPA | 2025-11-02 | 44 | 2025-11-04 | 2025-11-01 | 2025-11-03 | XLWO-20251103-00001154 |  | 2025-11-05 | 2025-11-09 | 2025-11-05 | 45 | 2025-11-09 | 45 | FALSE | 2025-11-09 | 45 | 2025-11-09 | 2025-11-09 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0582_1 | Swap_JAW-JT-DMK-0582 | JAW-JT-DMK-0582 | Central Java | Jawa Tengah | Demak | -6.9056 | 110.6227 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0582 | Mangunjiwan Demak | Protelindo | STP¦JTDM0004 | Central Java Ring 91A | MA-JTDMK0582-01H | 10.206.27.104 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-14 | 2025-10-15 | Approved | 2025-10-17 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110209 | 2025-11-02 | 2025-11-04 | done | done | done | done | done | done | GPA | 2025-11-02 | 44 | 2025-11-04 | 2025-11-01 | 2025-11-03 | XLWO-20251103-00001154 |  | 2025-11-05 | 2025-11-07 | 2025-11-05 | 45 | 2025-11-09 | 45 | FALSE | 2025-11-09 | 45 | 2025-11-09 | 2025-11-07 | Done | #N/A | #N/A | November | 2025-11-14 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0589_1 | Swap_JAW-JT-DMK-0589 | JAW-JT-DMK-0589 | Central Java | Jawa Tengah | Demak | -6.8853 | 110.6421 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0589 | Betokan Demak | Protelindo | PRT¦JAW-CJV-0271-H-B | Central Java Ring 91A | MA-JTDMK0589-01H | 10.206.27.105 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-14 | 2025-10-15 | Approved | 2025-10-17 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110211 | 2025-11-02 | 2025-11-04 | done | done | done | done | done | done | GPA | 2025-11-02 | 44 | 2025-11-04 | 2025-11-01 | 2025-11-03 | XLWO-20251103-00001154 |  | 2025-11-05 | 2025-11-09 | 2025-11-05 | 45 | 2025-11-09 | 45 | FALSE | 2025-11-09 | 45 | 2025-11-09 | 2025-11-09 | Done | #N/A | #N/A | November | 2025-11-14 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-3210_1 | Swap_JAW-JT-DMK-3210 | JAW-JT-DMK-3210 | Central Java | Jawa Tengah | Demak | -6.9787 | 110.5061 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-3210 | MAKAM MBAH JAGO | TBG | TBG¦140014109 | Central Java Ring 91A | MA-JTDMK3210-01H | 10.206.27.102 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | Done | Access Limit due to community | Done | Done | 2025-11-02 | DOEID25110234 | 2025-11-02 | 2025-11-04 | done | done | done | done | done | done | YPTT | 2025-11-02 | 44 | 2025-11-05 | 2025-11-01 | 2025-11-03 | XLWO-20251103-00001154 |  | 2025-11-05 | 2025-11-09 | 2025-11-05 | 45 | 2025-11-09 | 45 | FALSE | 2025-11-09 | 45 | 2025-11-09 | 2025-11-09 | Done | #N/A | #N/A | November | 2025-11-14 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0537_1 | Swap_JAW-JT-DMK-0537 | JAW-JT-DMK-0537 | Central Java | Jawa Tengah | Demak | -6.8739 | 110.7881 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0537 | TUWANG DEMAK | Protelindo |  | Central Java Ring 103A | MA-JTDMK0537-01H | 10.206.29.157 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 3 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107LZ | 2025-11-13 | 2025-11-13 | done | done | done | done | done | done | GPA | 2025-11-13 | 46 | 2025-11-13 |  | 2025-11-10 | XLWO-20251110-00001853 |  | 2025-11-16 | 2025-11-13 | 2025-11-16 | 46 | 2025-11-16 | 46 | TRUE | 2025-11-13 | 46 | 2025-11-13 | 2025-11-13 | Done | #N/A | #N/A | November | 2025-11-14 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0568_1 | Swap_JAW-JT-DMK-0568 | JAW-JT-DMK-0568 | Central Java | Jawa Tengah | Demak | -6.8722 | 110.5687 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0568 | Sidorejo Karang Tengah | Protelindo |  | Central Java Ring 103A | MA-JTDMK0568-01H | 10.206.29.150 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 3 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-23 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-11 |  | Done | Done | 2025-11-08 | DOEID251107M0 | 2025-11-13 | 2025-11-12 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-13 | 46 | 2025-11-12 |  | 2025-11-10 | XLWO-20251110-00001853 |  | 2025-11-16 | 2025-11-12 | 2025-11-16 | 46 | 2025-11-16 | 46 | TRUE | 2025-11-12 | 46 | 2025-11-12 | 2025-11-12 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0569_1 | Swap_JAW-JT-DMK-0569 | JAW-JT-DMK-0569 | Central Java | Jawa Tengah | Demak | -6.8411 | 110.572 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0569 | Purworejo Bonang | TBG |  | Central Java Ring 103A | MA-JTDMK0569-01H | 10.206.29.151 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 3 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-31 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-11 |  | Done | Done | 2025-11-08 | DOEID251107M2 | 2025-11-13 | 2025-11-12 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-13 | 46 | 2025-11-12 |  | 2025-11-10 | XLWO-20251110-00001853 |  | 2025-11-16 | 2025-11-12 | 2025-11-16 | 46 | 2025-11-16 | 46 | TRUE | 2025-11-12 | 46 | 2025-11-12 | 2025-11-12 | Done | #N/A | #N/A | November | 2025-11-15 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0573_1 | Swap_JAW-JT-DMK-0573 | JAW-JT-DMK-0573 | Central Java | Jawa Tengah | Demak | -6.8846 | 110.5903 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0573 | Derekan | Centratama |  | Central Java Ring 103A | MA-JTDMK0573-01H | 10.206.29.149 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 3 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-11 |  | Done | Done | 2025-11-08 | DOEID251107M3 | 2025-11-13 | 2025-11-12 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-13 | 46 | 2025-11-12 |  | 2025-11-10 | XLWO-20251110-00001853 |  | 2025-11-16 | 2025-11-12 | 2025-11-16 | 46 | 2025-11-16 | 46 | TRUE | 2025-11-12 | 46 | 2025-11-12 | 2025-11-12 | Done | #N/A | #N/A | November | 2025-11-15 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0578_1 | Swap_JAW-JT-DMK-0578 | JAW-JT-DMK-0578 | Central Java | Jawa Tengah | Demak | -6.7975 | 110.6097 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0578 | Wedung Demak | Protelindo |  | Central Java Ring 103A | MA-JTDMK0578-01H | 10.206.29.153 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 3 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-23 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107M5 | 2025-11-13 | 2025-11-13 | done | done | done | done | done | done | GPA | 2025-11-13 | 46 | 2025-11-13 |  | 2025-11-10 | XLWO-20251110-00001853 |  | 2025-11-16 | 2025-11-13 | 2025-11-16 | 46 | 2025-11-16 | 46 | TRUE | 2025-11-13 | 46 | 2025-11-13 | 2025-11-13 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0579_1 | Swap_JAW-JT-DMK-0579 | JAW-JT-DMK-0579 | Central Java | Jawa Tengah | Demak | -6.8639 | 110.6116 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0579 | Karang Mlati Demak | DMT |  | Central Java Ring 103A | MA-JTDMK0579-01H | 10.206.29.155 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 3 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-14 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107M7 | 2025-11-14 | 2025-11-13 | done | done | done | done | done | done | GPA | 2025-11-14 | 46 | 2025-11-13 |  | 2025-11-10 | XLWO-20251110-00001853 |  | 2025-11-17 | 2025-11-13 | 2025-11-17 | 47 | 2025-11-17 | 47 | TRUE | 2025-11-13 | 46 | 2025-11-13 | 2025-11-13 | Done | #N/A | #N/A | November | 2025-11-14 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0583_1 | Swap_JAW-JT-DMK-0583 | JAW-JT-DMK-0583 | Central Java | Jawa Tengah | Demak | -6.8343 | 110.6297 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0583 | Weding Demak | TBG |  | Central Java Ring 103A | MA-JTDMK0583-01H | 10.206.29.154 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 3 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-24 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107M8 | 2025-11-14 | 2025-11-13 | done | done | done | done | done | done | GPA | 2025-11-14 | 46 | 2025-11-13 |  | 2025-11-10 | XLWO-20251110-00001853 |  | 2025-11-17 | 2025-11-13 | 2025-11-17 | 47 | 2025-11-17 | 47 | TRUE | 2025-11-13 | 46 | 2025-11-13 | 2025-11-13 | Done | #N/A | #N/A | November | 2025-11-15 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0598_1 | Swap_JAW-JT-DMK-0598 | JAW-JT-DMK-0598 | Central Java | Jawa Tengah | Demak | -6.8802 | 110.6919 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0598 | Mrisen Wonosalam | Others |  | Central Java Ring 103A | MA-JTDMK0598-01H | 10.206.29.156 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 3 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-15 | 2025-10-15 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107M9 | 2025-11-14 | 2025-11-13 | done | done | done | done | done | done | GPA | 2025-11-14 | 46 | 2025-11-13 |  | 2025-11-10 | XLWO-20251110-00001853 |  | 2025-11-17 | 2025-11-13 | 2025-11-17 | 47 | 2025-11-17 | 47 | TRUE | 2025-11-13 | 46 | 2025-11-13 | 2025-11-13 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-2971_1 | Swap_JAW-JT-DMK-2971 | JAW-JT-DMK-2971 | Central Java | Jawa Tengah | Demak | -6.826 | 110.5955 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-2971 | Poncoharjo Bonang | TBG |  | Central Java Ring 103A | MA-JTDMK2971-01H | 10.206.29.152 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 3 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-26 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-11 |  | Done | Done | 2025-11-08 | DOEID251107MB | 2025-11-14 | 2025-11-12 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-14 | 46 | 2025-11-12 |  | 2025-11-10 | XLWO-20251110-00001853 |  | 2025-11-17 | 2025-11-12 | 2025-11-17 | 47 | 2025-11-17 | 47 | TRUE | 2025-11-12 | 46 | 2025-11-12 | 2025-11-12 | Done | #N/A | #N/A | November | 2025-11-14 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0612_1 | Swap_JAW-JT-DMK-0612 | JAW-JT-DMK-0612 | Central Java | Jawa Tengah | Demak | -6.8503 | 110.8054 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-DMK-0612 | Karanganyar Demak | Centratama |  | Central Java Ring 103 | PAG-JTDMK0612-02H | 10.206.29.148 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 3 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107LV | 2025-11-10 | 2025-11-13 | done | done | done | done | done | done | GPA | 2025-11-10 | 46 | 2025-11-13 |  | 2025-11-12 | XLWO-20251112-00001203 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 46 | 2025-11-13 | 46 | TRUE | 2025-11-13 | 46 | 2025-11-13 | 2025-11-13 | Done | #N/A | #N/A | November | 2025-11-20 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0613_1 | Swap_JAW-JT-DMK-0613 | JAW-JT-DMK-0613 | Central Java | Jawa Tengah | Demak | -6.90943055555556 | 110.633 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-DMK-0613 | Supernode Demak | 0 |  | Central Java Ring 103 | PAG-JTDMK0613-02H | 10.206.29.147 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 3 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-11-03 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107LX | 2025-11-10 | 2025-11-13 | done | done | done | done | done | done | GPA | 2025-11-10 | 46 | 2025-11-13 |  | 2025-11-12 | XLWO-20251112-00001203 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 46 | 2025-11-13 | 46 | TRUE | 2025-11-13 | 46 | 2025-11-13 | 2025-11-13 | Done | #N/A | #N/A | November | 2025-11-20 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-SMG-2406_1 | Swap_JAW-JT-SMG-2406 | JAW-JT-SMG-2406 | Central Java | Jawa Tengah | Kota Semarang | -6.9856 | 110.4079 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-SMG-2406 | Simpang Lima | DMT |  | Central Java Ring 114 | PAG-JTSMG2406-03H | 10.219.36.1 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | On Schedule Swap | GIT | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-17 | Approved | 2025-11-13 |  | Submitted | Approved | [14 empty] | GIT | [14 empty] | 2025-11-26 | 48 | 2025-11-26 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0552_1 | Swap_JAW-JT-DMK-0552 | JAW-JT-DMK-0552 | Central Java | Jawa Tengah | Demak | -7.0276 | 110.5174 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-DMK-0552 | Mranggen | TBG | IBS¦NO TP ID | Central Java Ring 25 | PAG-YG2295-01H | 10.219.208.5 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep | 2 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-21 | 2025-10-21 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-06 |  | Done | Done | Done | DOEID25110261 | 2025-11-06 | 2025-11-05 | Done | Done | Done | Done | Done | Done | Mingze | 2025-11-06 | 45 | 2025-11-08 | 2025-11-09 | 2025-11-10 | XLWO-20251106-00001543 |  | 2025-11-09 | 2025-11-10 | 2025-11-09 | 45 | 2025-11-09 | 45 | TRUE | 2025-11-10 | 46 | 2025-11-10 | 2025-11-10 | Done | #N/A | #N/A | November | 2025-11-09 |  | 2025-11-15
1 | 2 | CLEAR | Swap_JAW-JT-DMK-0613_2 | Swap_JAW-JT-DMK-0613 | JAW-JT-DMK-0613 | Central Java | Jawa Tengah | Demak | -6.90943055555556 | 110.633 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-DMK-0613 | Supernode Demak | 0 | 0 | Central Java Ring 25 | PAG-YGSN0076-01H | 10.219.208.4 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep | 2 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-11-03 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-06 |  | Done | Done | Done | DOEID251107QG | 2025-11-06 | 2025-11-09 | Done | Done | Done | Done | Done | Done | GCI | 2025-11-06 | 45 | 2025-11-09 | 2025-11-09 | 2025-11-10 | XLWO-20251110-00000708 |  | 2025-11-09 | 2025-11-10 | 2025-11-09 | 45 | 2025-11-09 | 45 | TRUE | 2025-11-10 | 46 | 2025-11-10 | 2025-11-10 | Done | #N/A | #N/A | November | 2025-11-14
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0571_1 | Swap_JAW-JT-DMK-0571 | JAW-JT-DMK-0571 | Central Java | Jawa Tengah | Demak | -6.9239 | 110.5726 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0571 | Batu Demak | Protelindo | PRT¦JAW-JT-DMK-0571 | Central Java Ring 25C | MA-YG2454-01H | 10.219.208.29 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-10 | 41 | October | Oct | 2025 | 2025-10-13 | 2025-10-15 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-06 |  | Done | Done | Done | DOEID25110215 | 2025-11-06 | 2025-11-05 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-06 | 45 | 2025-11-07 |  | 2025-11-08 | XLWO-20251108-00000248 |  | 2025-11-09 | 2025-11-10 | 2025-11-09 | 45 | 2025-11-10 | 46 | FALSE | 2025-11-10 | 46 | 2025-11-10 | 2025-11-10 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-SMG-0536_1 | Swap_JAW-JT-SMG-0536 | JAW-JT-SMG-0536 | Central Java | Jawa Tengah | Kota Semarang | -7.0203 | 110.4818 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SMG-0536 | Pedurungan Kidul | DMT | LJA¦NO TP ID | Central Java Ring 25C | MA-YG2531380-01H | 10.219.208.26 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | No Issue | GPA | 2025-10-10 | 41 | October | Oct | 2025 | 2025-10-10 | 2025-10-30 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-06 |  | Done | Done | Done | DOEID25110218 | 2025-11-06 | 2025-11-05 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-06 | 45 | 2025-11-07 |  | 2025-11-08 | XLWO-20251108-00000248 |  | 2025-11-09 | 2025-11-10 | 2025-11-09 | 45 | 2025-11-10 | 46 | FALSE | 2025-11-10 | 46 | 2025-11-10 | 2025-11-10 | Done | #N/A | #N/A | November | 2025-11-20 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-SMG-0540_1 | Swap_JAW-JT-SMG-0540 | JAW-JT-SMG-0540 | Central Java | Jawa Tengah | Kota Semarang | -6.948 | 110.4916 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SMG-0540 | Charoen Pokhpand | Protelindo | PRT¦JAW-CJV-0563-H-P | Central Java Ring 25C | MA-YG3533581G-01H | 10.219.208.30 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | No Issue | GPA | 2025-10-10 | 41 | October | Oct | 2025 | 2025-10-10 | 2025-10-12 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-06 |  | Done | Done | Done | DOEID25110265 | 2025-11-06 | 2025-11-05 | Done | Done | Done | Done | Done | Done | GCI | 2025-11-06 | 45 | 2025-11-08 |  | 2025-11-08 | XLWO-20251108-00000248 |  | 2025-11-09 | 2025-11-10 | 2025-11-09 | 45 | 2025-11-10 | 46 | FALSE | 2025-11-10 | 46 | 2025-11-10 | 2025-11-10 | Done | #N/A | #N/A | November | 2025-11-14
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0542_1 | Swap_JAW-JT-DMK-0542 | JAW-JT-DMK-0542 | Central Java | Jawa Tengah | Demak | -7.0532 | 110.4921 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0542 | Kebonbatur Mranggen | Centratama |  | Central Java Ring 25C | MA-YG3533826G-01H | 10.219.208.33 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-11 | 41 | October | Oct | 2025 | 2025-10-10 | 2025-10-12 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-09 |  | Done | Done | 2025-11-08 | DOEID251107OL | 2025-11-07 | 2025-11-10 | done | done | done | done | done | done | YPTT | 2025-11-07 | 45 | 2025-11-10 |  | 2025-11-08 | XLWO-20251108-00000248 |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | 46 | 2025-11-10 | 46 | TRUE | 2025-11-10 | 46 | 2025-11-10 | 2025-11-10 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0539_1 | Swap_JAW-JT-DMK-0539 | JAW-JT-DMK-0539 | Central Java | Jawa Tengah | Demak | -7.0366 | 110.4884 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0539 | Plamongan Pucang Gading | Centratama |  | Central Java Ring 25C | MA-YGB490-01H | 10.219.208.27 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-11 | 41 | October | Oct | 2025 | 2025-10-11 | 2025-10-15 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-09 |  | Done | Done | 2025-11-08 | DOEID251107ON | 2025-11-07 | 2025-11-10 | done | done | done | done | done | done | YPTT | 2025-11-07 | 45 | 2025-11-10 |  | 2025-11-08 | XLWO-20251108-00000248 |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | 46 | 2025-11-10 | 46 | TRUE | 2025-11-10 | 46 | 2025-11-10 | 2025-11-10 | Done | #N/A | #N/A | November | 2025-11-20
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0551_1 | Swap_JAW-JT-DMK-0551 | JAW-JT-DMK-0551 | Central Java | Jawa Tengah | Demak | -6.9443 | 110.5094 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0551 | Sayung Demak | Protelindo |  | Central Java Ring 25C | MA-YGBD45-01H | 10.219.208.24 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | On Schedule Swap | GPA | 2025-10-10 | 41 | October | Oct | 2025 | 2025-10-11 | 2025-10-15 | Approved | 2025-10-17 |  | Submitted | Approved | Done | Site Flooding | Done | Done | 2025-11-08 | DOEID251107OP | 2025-11-07 | [7 empty] | YPTT | 2025-11-07 | 45 |  |  | 2025-11-08 | XLWO-20251108-00000248 |  | 2025-11-10 |  | 2025-11-10 | 46 | 2025-11-10 | 46 | TRUE |  | 1 | Need Replan |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0548_1 | Swap_JAW-JT-DMK-0548 | JAW-JT-DMK-0548 | Central Java | Jawa Tengah | Demak | -7.0411 | 110.5051 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0548 | Kalitengah Mranggen | Protelindo |  | Central Java Ring 25C | MA-YGDMK0548-01H | 10.219.208.28 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-11 | 41 | October | Oct | 2025 | 2025-10-11 | 2025-10-12 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107O6 | 2025-11-07 | 2025-11-11 | Done | Done | Done | Done | Done | Done | Mingze | 2025-11-07 | 45 | 2025-11-11 |  | 2025-11-08 | XLWO-20251108-00000248 |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 46 | 2025-11-11 | 46 | FALSE | 2025-11-11 | 46 | 2025-11-11 | 2025-11-11 | Done | #N/A | #N/A | November | 2025-11-18 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-SMG-3126_1 | Swap_JAW-JT-SMG-3126 | JAW-JT-SMG-3126 | Central Java | Jawa Tengah | Kota Semarang | -7.0247 | 110.4882 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SMG-3126 | Rusunawa Plamongan Sari | Protelindo |  | Central Java Ring 25C | MA-YGSMG3126-01H | 10.219.208.32 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | No Issue | GPA | 2025-10-10 | 41 | October | Oct | 2025 | 2025-10-11 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107O8 | 2025-11-07 | 2025-11-11 | Done | Done | Done | Done | Done | Done | Mingze | 2025-11-07 | 45 | 2025-11-11 |  | 2025-11-08 | XLWO-20251108-00000248 |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 46 | 2025-11-11 | 46 | FALSE | 2025-11-11 | 46 | 2025-11-11 | 2025-11-11 | Done | #N/A | #N/A | November
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1579_1 | Swap_JAW-JT-PWD-1579 | JAW-JT-PWD-1579 | Central Java | Jawa Tengah | Grobogan | -7.0717 | 110.917 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-PWD-1579 | Mpls - Purwodadi | Others |  | Central Java Ring 28 | PAG-SM2249-01H | 10.219.208.52 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 5 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2026 | On Schedule Swap | GPA | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-25 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107MG | 2025-11-20 | 2025-11-12 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-20 | 47 | 2025-11-12 |  |  |  |  | 2025-11-23 |  | 2025-11-23 | 47 | 2025-11-23 | 47 | TRUE | 2025-11-20 | 47 | 2025-11-20 |  | Done | #N/A | #N/A | November | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1574_1 | Swap_JAW-JT-PWD-1574 | JAW-JT-PWD-1574 | Central Java | Jawa Tengah | Grobogan | -7.1394 | 110.9057 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-PWD-1574 | Toroh | Protelindo |  | Central Java Ring 28 | PAG-SMB317-01H | 10.219.209.11 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 5 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-20 | 2025-11-17 | Approved | 2025-11-22 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107MI | 2025-11-20 | 2025-11-12 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-20 | 47 | 2025-11-12 |  | 2025-11-10 | XLWO-20251112-00000909 |  | 2025-11-23 | 2025-11-17 | 2025-11-23 | 47 | 2025-11-23 | 47 | TRUE | 2025-11-17 | 47 | 2025-11-17 | 2025-11-17 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-PWD-0608_1 | Swap_JAW-JT-PWD-0608 | JAW-JT-PWD-0608 | Central Java | Jawa Tengah | Grobogan | -7.0213 | 110.7637 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-0608 | Godong | Protelindo |  | Central Java Ring 28C | MA-SM2298-01H | 10.219.208.51 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-18 | 2025-10-29 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107MK | 2025-11-20 | 2025-11-12 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-20 | 47 | 2025-11-12 |  | 2025-11-10 | XLWO-20251112-00000914 |  | 2025-11-23 | 2025-11-17 | 2025-11-23 | 47 | 2025-11-23 | 47 | TRUE | 2025-11-17 | 47 | 2025-11-17 | 2025-11-17 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1604_1 | Swap_JAW-JT-PWD-1604 | JAW-JT-PWD-1604 | Central Java | Jawa Tengah | Grobogan | -7.0776 | 111.0899 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1604 | Wirosari | Protelindo |  | Central Java Ring 28C | MA-SM2451-01H | 10.219.208.75 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Propose Drop, MOCN Drop | 5 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-18 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1600_1 | Swap_JAW-JT-PWD-1600 | JAW-JT-PWD-1600 | Central Java | Jawa Tengah | Grobogan | -7.0894 | 111.0489 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1600 | Tjrejowirosaric-Prtlnd | Protelindo |  | Central Java Ring 28C | MA-SM2531242-01H | 10.219.208.76 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-18 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107ML | 2025-11-20 | 2025-11-12 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-20 | 47 | 2025-11-12 |  | 2025-11-10 | XLWO-20251112-00000914 |  | 2025-11-23 | 2025-11-17 | 2025-11-23 | 47 | 2025-11-23 | 47 | TRUE | 2025-11-17 | 47 | 2025-11-17 | 2025-11-17 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1548_1 | Swap_JAW-JT-PWD-1548 | JAW-JT-PWD-1548 | Central Java | Jawa Tengah | Grobogan | -7.0646 | 110.7747 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1548 | Anggaswangi | DMT |  | Central Java Ring 28C | MA-SM2531512-01H | 10.219.208.54 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle | PT IFORTE SOLUSI INFOTEK | [7 empty] | 2025-11-09 | 2025-11-09 |  |  | 2026 | No Issue | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-18 | 2025-10-30 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-16 |  | Done | Done | Done | DOEID25111401 | 2025-11-21 | 2025-11-17 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-21 | 47 | 2025-11-17 |  | 2025-11-10 | XLWO-20251112-00000914 |  | 2025-11-24 | 2025-11-17 | 2025-11-24 | 48 | 2025-11-24 | 48 | TRUE | 2025-11-17 | 47 | 2025-11-17 | 2025-11-17 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1556_1 | Swap_JAW-JT-PWD-1556 | JAW-JT-PWD-1556 | Central Java | Jawa Tengah | Grobogan | -7.1063 | 110.8077 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1556 | Jipang Grobogan | TBG |  | Central Java Ring 28C | MA-SM2533112-01H | 10.219.208.56 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-20 | 2025-10-26 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-16 |  | Done | Done | Done | DOEID25111402 | 2025-11-21 | 2025-11-17 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-21 | 47 | 2025-11-17 |  | 2025-11-10 | XLWO-20251112-00000914 |  | 2025-11-24 | 2025-11-17 | 2025-11-24 | 48 | 2025-11-24 | 48 | TRUE | 2025-11-17 | 47 | 2025-11-17 | 2025-11-17 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1563_1 | Swap_JAW-JT-PWD-1563 | JAW-JT-PWD-1563 | Central Java | Jawa Tengah | Grobogan | -7.0567 | 110.8623 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1563 | Pulorejo | Protelindo |  | Central Java Ring 28C | MA-SM2534713-01H | 10.219.208.70 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-18 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-17 |  | Done | Done | Done | DOEID25111404 | 2025-11-21 | 2025-11-18 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-21 | 47 | 2025-11-18 |  |  |  |  | 2025-11-24 | 2025-11-18 | 2025-11-24 | 48 | 2025-11-24 | 48 | TRUE | 2025-11-18 | 47 | 2025-11-18 | 2025-11-18 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1590_1 | Swap_JAW-JT-PWD-1590 | JAW-JT-PWD-1590 | Central Java | Jawa Tengah | Grobogan | -7.1166 | 110.9681 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1590 | Nambuhan | TBG |  | Central Java Ring 28C | MA-SM2534778-01H | 10.219.208.73 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-18 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-17 |  | Done | Done | Done | DOEID25111405 | 2025-11-21 | 2025-11-18 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-21 | 47 | 2025-11-18 |  |  |  |  | 2025-11-24 | 2025-11-18 | 2025-11-24 | 48 | 2025-11-24 | 48 | TRUE | 2025-11-18 | 47 | 2025-11-18 | 2025-11-18 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1562_1 | Swap_JAW-JT-PWD-1562 | JAW-JT-PWD-1562 | Central Java | Jawa Tengah | Grobogan | -7.0852 | 110.8688 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1562 | Kluwan Penawangan | TBG |  | Central Java Ring 28C | MA-SM3533265G-01H | 10.219.208.58 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-26 | 2025-10-26 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-17 |  | Done | Done | Done | DOEID25111407 | 2025-11-21 | 2025-11-18 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-21 | 47 | 2025-11-18 |  |  |  |  | 2025-11-24 | 2025-11-18 | 2025-11-24 | 48 | 2025-11-24 | 48 | TRUE | 2025-11-18 | 47 | 2025-11-18 | 2025-11-18 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1586_1 | Swap_JAW-JT-PWD-1586 | JAW-JT-PWD-1586 | Central Java | Jawa Tengah | Grobogan | -7.1147 | 110.9371 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1586 | Kedungrejo Purwodadi | Others |  | Central Java Ring 28C | MA-SM3533386G-01H | 10.219.208.72 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-18 | 2025-11-01 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-17 |  | Done | Done | Done | DOEID25111409 | 2025-11-21 | 2025-11-18 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-21 | 47 | 2025-11-18 |  |  |  |  | 2025-11-24 | 2025-11-18 | 2025-11-24 | 48 | 2025-11-24 | 48 | TRUE | 2025-11-18 | 47 | 2025-11-18 | 2025-11-18 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1602_1 | Swap_JAW-JT-PWD-1602 | JAW-JT-PWD-1602 | Central Java | Jawa Tengah | Grobogan | -7.1297 | 111.0734 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1602 | Pulo Kulon | Protelindo |  | Central Java Ring 28C | MA-SMBD77-01H | 10.219.208.74 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-11-03 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-17 |  | Done | Done | Done | DOEID25111410 | 2025-11-21 | 2025-11-18 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-21 | 47 | 2025-11-18 |  |  |  |  | 2025-11-24 | 2025-11-18 | 2025-11-24 | 48 | 2025-11-24 | 48 | TRUE | 2025-11-18 | 47 | 2025-11-18 | 2025-11-18 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-PWD-0001_1 | Swap_JAW-JT-PWD-0001 | JAW-JT-PWD-0001 | Central Java | Jawa Tengah | Grobogan | -7.1327 | 111.0919 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-0001 | Grabagan Tuko | Centratama |  | Central Java Ring 28E | MA-JTPWD0001-01H | 10.206.30.18 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-30 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-17 |  | Done | Done | Done | DOEID25111444 | 2025-11-22 | 2025-11-18 | Done | Done | Done | Done | Done | Done | GIT | 2025-11-22 | 47 | 2025-11-18 |  |  |  |  | 2025-11-25 | 2025-11-18 | 2025-11-25 | 48 | 2025-11-25 | 48 | TRUE | 2025-11-18 | 47 | 2025-11-18 | 2025-11-18 | Done | #N/A | #N/A | November | 2025-11-19
1 | 1 | CLEAR | Swap_JAW-JT-PWD-0007_1 | Swap_JAW-JT-PWD-0007 | JAW-JT-PWD-0007 | Central Java | Jawa Tengah | Grobogan | -7.1289 | 111.0192 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-0007 | PULOKULON JETAK | Protelindo |  | Central Java Ring 28E | MA-JTPWD0007-01H | 10.206.30.17 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-17 |  | Done | Done | Done | DOEID25111445 | 2025-11-22 | 2025-11-18 | Done | Done | Done | Done | Done | Done | GIT | 2025-11-22 | 47 | 2025-11-18 |  |  |  |  | 2025-11-25 | 2025-11-18 | 2025-11-25 | 48 | 2025-11-25 | 48 | TRUE | 2025-11-18 | 47 | 2025-11-18 | 2025-11-18 | Done | #N/A | #N/A | November | 2025-11-19
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1589_1 | Swap_JAW-JT-PWD-1589 | JAW-JT-PWD-1589 | Central Java | Jawa Tengah | Grobogan | -7.0773 | 110.9656 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1589 | Mahayan Purwodadi | Others |  | Central Java Ring 28E | MA-JTPWD1589-01H | 10.206.30.23 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-21 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-17 |  | Done | Done | Done | DOEID25111453 | 2025-11-22 | 2025-11-18 | Done | Done | Done | Done | Done | Done | YPTT | 2025-11-22 | 47 | 2025-11-18 |  |  | XLWO-20251112-00000914 |  | 2025-11-25 | 2025-11-19 | 2025-11-25 | 48 | 2025-11-25 | 48 | TRUE | 2025-11-19 | 47 | 2025-11-19 | 2025-11-19 | Done | #N/A | #N/A | November | 2025-11-20
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1591_1 | Swap_JAW-JT-PWD-1591 | JAW-JT-PWD-1591 | Central Java | Jawa Tengah | Grobogan | -7.021 | 110.9695 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1591 | Lebak Grobogan | TBG |  | Central Java Ring 28E | MA-JTPWD1591-01H | 10.206.30.22 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-22 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-17 |  | Done | Done | Done | DOEID25111455 | 2025-11-22 | 2025-11-18 | Done | Done | Done | Done | Done | Done | YPTT | 2025-11-22 | 47 | 2025-11-18 |  |  | XLWO-20251112-00000914 |  | 2025-11-25 | 2025-11-19 | 2025-11-25 | 48 | 2025-11-25 | 48 | TRUE | 2025-11-19 | 47 | 2025-11-19 | 2025-11-19 | Done | #N/A | #N/A | November | 2025-11-20
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1592_1 | Swap_JAW-JT-PWD-1592 | JAW-JT-PWD-1592 | Central Java | Jawa Tengah | Grobogan | -7.1227 | 110.9932 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1592 | Sembungharjo Pulokulon | Protelindo |  | Central Java Ring 28E | MA-JTPWD1592-01H | 10.206.30.16 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Propose Drop, MOCN Drop | 5 | TypeB 6120H-SC Chassis Bundle | PT IFORTE SOLUSI INFOTEK | [7 empty] | 2025-11-09 | #N/A |  |  |  |  | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-11-17 | Approved | 2025-11-22 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1599_1 | Swap_JAW-JT-PWD-1599 | JAW-JT-PWD-1599 | Central Java | Jawa Tengah | Grobogan | -6.9723 | 111.0385 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1599 | Gunung Gading Kemaduhbatur | TBG |  | Central Java Ring 28E | MA-JTPWD1599-01H | 10.206.30.21 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-18 |  | Done | Done | Done | DOEID25111433 | 2025-11-22 | 2025-11-19 | Done | Done | Done | Done | Done | Done | Mingze | 2025-11-22 | 47 | 2025-11-19 |  |  | XLWO-20251112-00000914 |  | 2025-11-25 | 2025-11-19 | 2025-11-25 | 48 | 2025-11-25 | 48 | TRUE | 2025-11-19 | 47 | 2025-11-19 | 2025-11-19 | Done | #N/A | #N/A | November | 2025-11-20
1 | 1 | CLEAR | Swap_JAW-JT-PWD-1608_1 | Swap_JAW-JT-PWD-1608 | JAW-JT-PWD-1608 | Central Java | Jawa Tengah | Grobogan | -6.9593 | 111.1013 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-1608 | Tegalrejo Wirosari | Others |  | Central Java Ring 28E | MA-JTPWD1608-01H | 10.206.30.20 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-11-06 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-18 |  | Done | Done | Done | DOEID25111434 | 2025-11-22 | 2025-11-19 | Done | Done | Done | Done | Done | Done | Mingze | 2025-11-22 | 47 | 2025-11-19 |  |  | XLWO-20251112-00000914 |  | 2025-11-25 | 2025-11-19 | 2025-11-25 | 48 | 2025-11-25 | 48 | TRUE | 2025-11-19 | 47 | 2025-11-19 | 2025-11-19 | Done | #N/A | #N/A | November | 2025-11-20
1 | 1 | CLEAR | Swap_JAW-JT-PWD-3387_1 | Swap_JAW-JT-PWD-3387 | JAW-JT-PWD-3387 | Central Java | Jawa Tengah | Grobogan | -7.0094 | 111.1154 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PWD-3387 | KARANGASEM GROBOGAN | TBG |  | Central Java Ring 28E | MA-JTPWD3387-01H | 10.206.30.19 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 5 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-24 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-18 |  | Done | Done | Done | DOEID251113PG | 2025-11-22 | 2025-11-19 | Done | Done | Done | Done | Done | Done | GCI | 2025-11-22 | 47 | 2025-11-19 |  |  | XLWO-20251112-00000914 |  | 2025-11-25 | 2025-11-19 | 2025-11-25 | 48 | 2025-11-25 | 48 | TRUE | 2025-11-19 | 47 | 2025-11-19 | 2025-11-19 | Done | #N/A | #N/A | November | 2025-11-20
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1993_1 | Swap_JAW-JT-SKH-1993 | JAW-JT-SKH-1993 | Central Java | Jawa Tengah | Sukoharjo | -7.7298 | 110.854 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1993 | Daleman | Protelindo |  | Central Java Ring 30E | MA-SM2534573-01H | 10.206.6.30 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-18 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1989_1 | Swap_JAW-JT-SKH-1989 | JAW-JT-SKH-1989 | Central Java | Jawa Tengah | Sukoharjo | -7.6928 | 110.8451 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1989 | Sukoharjo Selatan | Protelindo |  | Central Java Ring 30E | MA-SM253EG34-01H | 10.206.6.29 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-1068_1 | Swap_JAW-JT-KLN-1068 | JAW-JT-KLN-1068 | Central Java | Jawa Tengah | Klaten | -7.6443 | 110.7534 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-1068 | Wadung Getas Wonosari | Centratama |  | Central Java Ring 30E | MA-SM3533153G-01H | 10.206.6.34 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-18 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1958_1 | Swap_JAW-JT-SKH-1958 | JAW-JT-SKH-1958 | Central Java | Jawa Tengah | Sukoharjo | -7.6053 | 110.7889 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1958 | Sanggrahan Grogol | Others |  | Central Java Ring 30E | MA-SM3533198G-01H | 10.206.6.35 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-1057_1 | Swap_JAW-JT-KLN-1057 | JAW-JT-KLN-1057 | Central Java | Jawa Tengah | Klaten | -7.6998 | 110.7068 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-1057 | Pedan | Protelindo |  | Central Java Ring 30E | MA-SMB210-01H | 10.206.6.33 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-21 | 2025-10-21 | Approved | 2025-10-17 |  | Submitted | Approved |  | Proposed Hotswap | [29 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1982_1 | Swap_JAW-JT-SKH-1982 | JAW-JT-SKH-1982 | Central Java | Jawa Tengah | Sukoharjo | -7.7648 | 110.834 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1982 | Bulu Sukoharjo | Protelindo |  | Central Java Ring 30E | MA-SMB245-01H | 10.206.6.31 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-18 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1964_1 | Swap_JAW-JT-SKH-1964 | JAW-JT-SKH-1964 | Central Java | Jawa Tengah | Sukoharjo | -7.7562 | 110.8061 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1964 | Puron Bulu | #N/A |  | Central Java Ring 30E | MA-SMB436-01H | 10.206.9.126 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-1041_1 | Swap_JAW-JT-KLN-1041 | JAW-JT-KLN-1041 | Central Java | Jawa Tengah | Klaten | -7.7358 | 110.6628 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-1041 | Trucuk | Protelindo |  | Central Java Ring 30E | MA-SMBD73-01H | 10.206.6.32 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-14 | 42 | October | Oct | 2025 |  |  | In Progress |  |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-MGG-1158_1 | Swap_JAW-JT-MGG-1158 | JAW-JT-MGG-1158 | Central Java | Jawa Tengah | Kota Magelang | -7.4796 | 110.2269 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-MGG-1158 | Mpls - Magelang | Protelindo |  | Central Java Ring 33 | PAG-YG2238-01H | 10.206.1.232 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GIT | 2025-10-15 | 42 | October | Oct | 2025 | 2025-10-28 | 2025-10-28 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SLT-2171_1 | Swap_JAW-JT-SLT-2171 | JAW-JT-SLT-2171 | Central Java | Jawa Tengah | Kota Salatiga | -7.3627 | 110.5156 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-SLT-2171 | Tingkir Salatiga | Centratama |  | Central Java Ring 33 | PAG-YGB239-02H | 10.206.1.231 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | On Schedule Swap | GIT | 2025-10-14 | 42 | October | Oct | 2025 | 2025-10-14 | 2025-10-22 | Approved | 2025-11-13 |  | Submitted | Approved | [14 empty] | GIT | [14 empty] | 2025-11-27 | 48 | 2025-11-27 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1938_1 | Swap_JAW-JT-SKH-1938 | JAW-JT-SKH-1938 | Central Java | Jawa Tengah | Sukoharjo | -7.5578 | 110.7527 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1938 | Pabelan | Protelindo |  | Central Java Ring 35E | MA-YO2533646-01H | 10.206.27.30 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1909_1 | Swap_JAW-JT-SKH-1909 | JAW-JT-SKH-1909 | Central Java | Jawa Tengah | Sukoharjo | -7.5482 | 110.7438 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1909 | PEREMPATAN KARTASURA RELOCATION | Others |  | Central Java Ring 35E | MA-YO2533654-01H | 10.206.27.31 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-3651_1 | Swap_JAW-JT-SKH-3651 | JAW-JT-SKH-3651 | Central Java | Jawa Tengah | Sukoharjo | -7.5556 | 110.7428 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-3651 | PUCANGAN KARTASURA RELOCATION | Protelindo |  | Central Java Ring 35E | MA-YO3531536G-01H | 10.206.27.33 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1937_1 | Swap_JAW-JT-SKH-1937 | JAW-JT-SKH-1937 | Central Java | Jawa Tengah | Sukoharjo | -7.5724 | 110.7473 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1937 | NGADIREJO KARTASURA | Protelindo |  | Central Java Ring 35E | MA-YO3533353G-01H | 10.206.27.34 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-16 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1931_1 | Swap_JAW-JT-SKH-1931 | JAW-JT-SKH-1931 | Central Java | Jawa Tengah | Sukoharjo | -7.5508 | 110.7374 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1931 | Kartasura | Protelindo |  | Central Java Ring 35E | MA-YOB424-01H | 10.206.27.32 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1502_1 | Swap_JAW-JT-PTI-1502 | JAW-JT-PTI-1502 | Central Java | Jawa Tengah | Pati | -6.5843 | 111.0637 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1502 | Margotuhu Kidul | Others |  | Central Java Ring 45D | MA-SM2533109-01H | 10.219.27.117 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID251117L9 | 2025-11-23 | 2025-11-24 | Done | Done | Done | Done | Done | Done | GCI |  | 1 | 2025-11-24 |  |  | XLWO-20251121-00000441 |  | 2025-11-24 | 2025-11-24 | 2025-11-24 |  |  |  |  | 2025-11-24 | 48 | 2025-11-24 | 2025-11-24 | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-4012_1 | Swap_JAW-JT-PTI-4012 | JAW-JT-PTI-4012 | Central Java | Jawa Tengah | Pati | -6.7025 | 111.1243 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-4012 | LANGGENHARJO JUWANA RELOCATION | Protelindo |  | Central Java Ring 45D | MA-SM2534237-01H | 10.219.27.118 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID251117LB | 2025-11-23 | 2025-11-24 | Done | Done | Done | Done | Done | Done | GCI |  | 1 | 2025-11-24 |  |  | XLWO-20251121-00000441 |  | 2025-11-24 | 2025-11-24 | 2025-11-24 |  |  |  |  | 2025-11-24 | 48 | 2025-11-24 | 2025-11-24 | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1499_1 | Swap_JAW-JT-PTI-1499 | JAW-JT-PTI-1499 | Central Java | Jawa Tengah | Pati | -6.7207 | 111.0571 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1499 | Bapoh Pati | Protelindo |  | Central Java Ring 45D | MA-SM2534245-01H | 10.206.26.80 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID251117LD | 2025-11-23 | 2025-11-24 | Done | Done | Done | Done | Done | Done | GCI |  | 1 | 2025-11-24 |  |  | XLWO-20251121-00000441 |  | 2025-11-24 | 2025-11-24 | 2025-11-24 |  |  |  |  | 2025-11-24 | 48 | 2025-11-24 | 2025-11-24 | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1484_1 | Swap_JAW-JT-PTI-1484 | JAW-JT-PTI-1484 | Central Java | Jawa Tengah | Pati | -6.5769 | 111.0397 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1484 | Bancaran Kedung Sari C-Prtldo | Protelindo |  | Central Java Ring 45D | MA-SM253EH80-01H | 10.219.27.116 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID251117K0 | 2025-11-23 | 2025-11-24 | Done | Done | Done | Done | Done | Done | Mingze |  | 1 | 2025-11-24 |  |  | XLWO-20251121-00000441 |  | 2025-11-24 | 2025-11-24 | 2025-11-24 |  |  |  |  | 2025-11-24 | 48 | 2025-11-24 | 2025-11-24 | Done | #N/A | #N/A |  | 2025-11-25
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1512_1 | Swap_JAW-JT-PTI-1512 | JAW-JT-PTI-1512 | Central Java | Jawa Tengah | Pati | -6.6673 | 111.101 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1512 | Juwanatayuasmppnc-Prtldo | Protelindo |  | Central Java Ring 45D | MA-SM253EH81-01H | 10.206.26.81 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-26 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID251117K2 | 2025-11-23 | 2025-11-24 | Done | Done | Done | Done | Done | Done | Mingze |  | 1 | 2025-11-24 |  |  | XLWO-20251121-00000441 |  | 2025-11-24 | 2025-11-24 | 2025-11-24 |  |  |  |  | 2025-11-24 | 48 | 2025-11-24 | 2025-11-24 | Done | #N/A | #N/A |  | 2025-11-25
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1504_1 | Swap_JAW-JT-PTI-1504 | JAW-JT-PTI-1504 | Central Java | Jawa Tengah | Pati | -6.687 | 111.0679 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1504 | Panggungroyom Wedarijaksa | DMT |  | Central Java Ring 45D | MA-SM3533138G-01H | 10.219.27.114 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Propose Drop, MOCN Drop | 10 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-26 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1478_1 | Swap_JAW-JT-PTI-1478 | JAW-JT-PTI-1478 | Central Java | Jawa Tengah | Pati | -6.7336 | 111.0158 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1478 | SIDOKERTO PATI | TBG |  | Central Java Ring 45D | MA-SM3533367G-01H | 10.219.27.112 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID251117LF |  | 2025-11-23 | Done | Done | Done | Done | Done | Done | GCI |  |  | 2025-11-21 |  | 2025-11-21 | XLWO-20251121-00000441 |  |  | 2025-11-23 | [5 empty] | 2025-11-23 | 47 | 2025-11-23 | 2025-11-23 | Done | #N/A | #N/A |  | 2025-11-24
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1490_1 | Swap_JAW-JT-PTI-1490 | JAW-JT-PTI-1490 | Central Java | Jawa Tengah | Pati | -6.7239 | 111.0501 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1490 | Mulyoharjo Pati | TBG |  | Central Java Ring 45D | MA-SM3534387G-01H | 10.219.27.113 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID251117K3 |  | 2025-11-23 | Done | Done | Done | Done | Done | Done | Mingze |  |  | 2025-11-23 |  | 2025-11-21 | XLWO-20251121-00000441 |  |  | 2025-11-23 | [5 empty] | 2025-11-23 | 47 | 2025-11-23 | 2025-11-23 | Done | #N/A | #N/A |  | 2025-11-25
1 | 1 | CLEAR | Swap_JAW-JT-PTI-3318_1 | Swap_JAW-JT-PTI-3318 | JAW-JT-PTI-3318 | Central Java | Jawa Tengah | Pati | -6.6256 | 111.0505 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-3318 | Masjidd Almutaqin | TBG |  | Central Java Ring 45D | MA-SM3535362G-01H | 10.219.27.115 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-25 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID251117K5 |  | 2025-11-23 | Done | Done | Done | Done | Done | Done | Mingze |  |  | 2025-11-23 |  | 2025-11-21 | XLWO-20251121-00000441 |  |  | 2025-11-23 | [5 empty] | 2025-11-23 | 47 | 2025-11-23 | 2025-11-23 | Done | #N/A | #N/A |  | 2025-11-24
1 | 1 | CLEAR | Swap_JAW-JT-KDL-3487_1 | Swap_JAW-JT-KDL-3487 | JAW-JT-KDL-3487 | Central Java | Jawa Tengah | Kendal | -6.96536111111111 | 110.270188888889 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-KDL-3487 | Supernode Mangkang | 0 |  | Central Java Ring 66 | PAG-SM2110-02H | #N/A | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-11-07 | 2025-11-08 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0098_1 | Swap_JAW-JT-BBS-0098 | JAW-JT-BBS-0098 | Central Java | Jawa Tengah | Brebes | -6.956 | 108.9988 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0098 | Kebon Agung Brebes | DMT |  | Central Java Ring 70B | MA-SM2531437-01H | 10.206.1.162 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-31 | 2025-10-31 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0063_1 | Swap_JAW-JT-BBS-0063 | JAW-JT-BBS-0063 | Central Java | Jawa Tengah | Brebes | -6.9141 | 108.8981 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0063 | Sutamaja Brebes | Others |  | Central Java Ring 70B | MA-SM2531611-01H | 10.206.1.165 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-11-06 | 2025-11-06 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0086_1 | Swap_JAW-JT-BBS-0086 | JAW-JT-BBS-0086 | Central Java | Jawa Tengah | Brebes | -6.9259 | 108.9776 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0086 | Siwungkuk Brebes | Protelindo |  | Central Java Ring 70B | MA-SM2531753-01H | 10.206.1.164 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-11-06 | 2025-11-06 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0031_1 | Swap_JAW-JT-BBS-0031 | JAW-JT-BBS-0031 | Central Java | Jawa Tengah | Brebes | -6.9637 | 108.8483 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0031 | Ciawi Banjarharjo | Protelindo |  | Central Java Ring 70B | MA-SM2531759-01H | 10.206.9.252 | ATN910C-G | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-11-03 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0111_1 | Swap_JAW-JT-BBS-0111 | JAW-JT-BBS-0111 | Central Java | Jawa Tengah | Brebes | -6.9664 | 109.0227 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0111 | Jatibarang Barat Brebes | Others |  | Central Java Ring 70B | MA-SM2531858-01H | 10.206.9.251 | ATN910C-G | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-31 | 2025-10-31 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0115_1 | Swap_JAW-JT-BBS-0115 | JAW-JT-BBS-0115 | Central Java | Jawa Tengah | Brebes | -6.944 | 109.0285 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0115 | Bojong Jatibarang | Others |  | Central Java Ring 70B | MA-SM2531874-01H | 10.206.13.110 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-22 | 2025-10-30 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0038_1 | Swap_JAW-JT-BBS-0038 | JAW-JT-BBS-0038 | Central Java | Jawa Tengah | Brebes | -6.9444 | 108.862 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0038 | Kubangpari | Others |  | Central Java Ring 70B | MA-SM2531938-01H | 10.206.1.166 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-11-03 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0106_1 | Swap_JAW-JT-BBS-0106 | JAW-JT-BBS-0106 | Central Java | Jawa Tengah | Brebes | -6.9304 | 109.0145 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0106 | Jagalempeni Brebes | Protelindo |  | Central Java Ring 70B | MA-SM2532933-01H | 10.206.1.163 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-11-07 | 2025-11-07 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0082_1 | Swap_JAW-JT-BBS-0082 | JAW-JT-BBS-0082 | Central Java | Jawa Tengah | Brebes | -7.2554 | 108.9569 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0082 | Cibentang Brebes | Others |  | Central Java Ring 70B | MA-SM253C087-01H | 10.206.1.171 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-20 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0085_1 | Swap_JAW-JT-BBS-0085 | JAW-JT-BBS-0085 | Central Java | Jawa Tengah | Brebes | -6.9663 | 108.9744 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0085 | Siandong | Others |  | Central Java Ring 70B | MA-SM3531949G-01H | 10.206.1.161 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-31 | 2025-10-31 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-3005_1 | Swap_JAW-JT-BBS-3005 | JAW-JT-BBS-3005 | Central Java | Jawa Tengah | Brebes | -6.9503 | 108.987 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-3005 | SITANGGAL LARANGAN | Protelindo |  | Central Java Ring 70B | MA-SM3535245G-01H | 10.206.13.238 | ATN910C-G | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-31 | 2025-10-31 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-3332_1 | Swap_JAW-JT-BBS-3332 | JAW-JT-BBS-3332 | Central Java | Jawa Tengah | Brebes | -6.9067 | 109.0084 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-3332 | Tanjungsari Wanasari | TBG |  | Central Java Ring 70B | MA-SM3535589G-01H | 10.206.13.152 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-20 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0069_1 | Swap_JAW-JT-BBS-0069 | JAW-JT-BBS-0069 | Central Java | Jawa Tengah | Brebes | -7.2121 | 108.9155 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0069 | Bantarkawung | TBG |  | Central Java Ring 70B | MA-SMB416-01H | 10.206.1.170 | ATN910C-G | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-20 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0009_1 | Swap_JAW-JT-BBS-0009 | JAW-JT-BBS-0009 | Central Java | Jawa Tengah | Brebes | -7.1712 | 108.7993 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0009 | Salem Brebes | Protelindo |  | Central Java Ring 70B | MA-SMB417-01H | 10.206.1.168 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-11-21 | 2025-11-21 | Approved | 2025-11-22 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0015_1 | Swap_JAW-JT-BBS-0015 | JAW-JT-BBS-0015 | Central Java | Jawa Tengah | Brebes | -7.077 | 108.816 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type B | MA | JAW-JT-BBS-0015 | Bandungsari | Others |  | Central Java Ring 70B | MA-SMD993-01H | 10.206.1.167 | ATN910C-F | Huawei | New Purchase | Ring Capacity | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-20 | 43 | October | Oct | 2025 | 2025-11-03 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SLW-2239_1 | Swap_JAW-JT-SLW-2239 | JAW-JT-SLW-2239 | Central Java | Jawa Tengah | Tegal | -6.9788 | 109.1403 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-SLW-2239 | Slawi | Protelindo |  | Central Java Ring 76 | PAG-SM2312-01H | 10.206.1.109 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GIT | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-14 | 2025-10-22 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SLW-2207_1 | Swap_JAW-JT-SLW-2207 | JAW-JT-SLW-2207 | Central Java | Jawa Tengah | Tegal | -7.0484 | 109.1005 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-SLW-2207 | Balapulang | Protelindo |  | Central Java Ring 76 | PAG-SM2481-01H | 10.206.1.110 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GIT | 2025-10-18 | 42 | October | Oct | 2025 | 2025-10-14 | 2025-10-22 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-YO-YYK-0492_1 | Swap_JAW-YO-YYK-0492 | JAW-YO-YYK-0492 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7893 | 110.3595 | Swap | Swap Only | Swap | Type C | PAG | JAW-YO-YYK-0492 | Mpls - Patok Yogyakartara | Direct Lease |  | Central Java Ring 79 | PAG-SM2236-04H | 10.206.13.51 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 13 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | On Schedule Swap | YPTT | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-25 | 2025-10-25 | Approved | 2025-11-13 |  | Submitted | Approved | [14 empty] | GPA | [14 empty] | 2025-11-27 | 48 | 2025-11-27 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2150_1 | Swap_JAW-JT-SKT-2150 | JAW-JT-SKT-2150 | Central Java | Jawa Tengah | Kota Surakarta | -7.5587 | 110.8275 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKT-2150 | SOLO RELOCATION | DMT |  | Central Java Ring 79 | PAG-SMSN0070-04H | 10.206.13.57 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 13 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | On Schedule Swap | YPTT | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-15 | 2025-10-16 | Approved | 2025-11-13 |  | Submitted | Approved | [14 empty] | YPTT | [14 empty] | 2025-11-27 | 48 | 2025-11-27 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-0999_1 | Swap_JAW-JT-KLN-0999 | JAW-JT-KLN-0999 | Central Java | Jawa Tengah | Klaten | -7.7418 | 110.5526 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-0999 | Rejoso Jogonalan | DMT |  | Central Java Ring 79A | MA-JTKLN0999-01H | 10.206.29.18 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 13 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-15 | 42 | October | Oct | 2025 | 2025-11-14 | 2025-11-14 | Approved | 2025-11-17 |  | Submitted | Approved | [14 empty] | YPTT | [14 empty] | 2025-11-30 | 48 | 2025-11-30 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-YO-SMN-0336_1 | Swap_JAW-YO-SMN-0336 | JAW-YO-SMN-0336 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.7736 | 110.467 | Swap | Swap Only | Swap | Type B | MA | JAW-YO-SMN-0336 | Dogongan Tirtomartani | Protelindo |  | Central Java Ring 79A | MA-SM2533607-01H | 10.206.13.58 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 13 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | On Schedule Swap | YPTT | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-20 | 2025-10-21 | Approved | 2025-10-17 |  | Submitted | Approved | [14 empty] | YPTT | [14 empty] | 2025-11-27 | 48 | 2025-11-27 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1941_1 | Swap_JAW-JT-SKH-1941 | JAW-JT-SKH-1941 | Central Java | Jawa Tengah | Sukoharjo | -7.5787 | 110.7616 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1941 | Moyang Gumpang | DMT |  | Central Java Ring 79A | MA-SM2533631-01H | 10.206.13.55 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 13 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-17 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [14 empty] | GPA | [14 empty] | 2025-11-30 | 48 | 2025-11-30 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-0997_1 | Swap_JAW-JT-KLN-0997 | JAW-JT-KLN-0997 | Central Java | Jawa Tengah | Klaten | -7.7503 | 110.5406 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-0997 | Somopuro Jogonalan | Centratama |  | Central Java Ring 79A | MA-SM3533317G-01H | 10.206.13.53 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 13 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-15 | 42 | October | Oct | 2025 | 2025-11-14 | 2025-11-14 | Approved | 2025-11-17 |  | Submitted | Approved | [14 empty] | GIT | [14 empty] | 2025-11-30 | 48 | 2025-11-30 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1926_1 | Swap_JAW-JT-SKH-1926 | JAW-JT-SKH-1926 | Central Java | Jawa Tengah | Klaten | -7.596 | 110.7215 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1926 | KAGOKAN SUKOHARJO | TBG |  | Central Java Ring 79A | MA-SM3534921G-01H | 10.206.13.54 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 13 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-15 | 42 | October | Oct | 2025 | 2025-10-20 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | [14 empty] | GIT | [14 empty] | 2025-11-30 | 48 | 2025-11-30 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-3292_1 | Swap_JAW-JT-KLN-3292 | JAW-JT-KLN-3292 | Central Java | Jawa Tengah | Klaten | -7.7313 | 110.5711 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-3292 | Sumyang Jagonalang | DMT |  | Central Java Ring 79A | MA-SM3535395G-01H | 10.206.13.59 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 13 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-15 | 42 | October | Oct | 2025 | 2025-10-21 | 2025-10-21 | Approved | 2025-10-17 |  | Submitted | Approved | [14 empty] | GCI | [14 empty] | 2025-11-30 | 48 | 2025-11-30 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-3177_1 | Swap_JAW-JT-SKH-3177 | JAW-JT-SKH-3177 | Central Java | Jawa Tengah | Sukoharjo | -7.5674 | 110.7762 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-3177 | MAKAMHAJI GATAK | TBG |  | Central Java Ring 79A | MA-SM3535497G-01H | 10.206.13.219 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Propose Drop, MOCN Drop | 13 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-20 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | [14 empty] | GCI | [14 empty] | 2025-11-30 | 48 | 2025-11-30 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2066_1 | Swap_JAW-JT-SKT-2066 | JAW-JT-SKT-2066 | Central Java | Jawa Tengah | Kota Surakarta | -7.56 | 110.8079 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKT-2066 | Manahan | Protelindo |  | Central Java Ring 79A | MA-SMB407-01H | 10.206.13.56 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 13 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | On Schedule Swap | YPTT | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-19 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | [14 empty] | GCI | [14 empty] | 2025-11-30 | 48 | 2025-11-30 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PBG-1276_1 | Swap_JAW-JT-PBG-1276 | JAW-JT-PBG-1276 | Central Java | Jawa Tengah | Purbalingga | -7.3873 | 109.3623 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-PBG-1276 | Purbalngga | Protelindo |  | Central Java Ring 80 | PAG-SM2333-04H | 10.206.9.195 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GIT | 2025-10-16 | 42 | October | Oct | 2025 | 2025-11-03 | 2025-11-03 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PML-1365_1 | Swap_JAW-JT-PML-1365 | JAW-JT-PML-1365 | Central Java | Jawa Tengah | Pemalang | -7.1009 | 109.3267 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-PML-1365 | Randudongkal | Protelindo |  | Central Java Ring 80 | PAG-SM2431-02H | 10.206.9.194 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GIT | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-21 | 2025-10-21 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-JPA-0619_1 | Swap_JAW-JT-JPA-0619 | JAW-JT-JPA-0619 | Central Java | Jawa Tengah | Jepara | -6.5942 | 110.6638 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-JPA-0619 | Jepara | Protelindo |  | MBH Central Java Ring 12A | MA-JTJPA0619-01H | 10.219.39.11 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 4 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-30 | 2025-10-30 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-15 |  | Done | Done | 2025-11-08 | DOEID251107NR | 2025-11-16 | 2025-11-16 | done | done | done | done | done | done | GIT | 2025-11-16 | 46 | 2025-11-16 |  | 2025-11-10 | XLWO-20251110-00001850 |  | 2025-11-19 | 2025-11-16 | 2025-11-19 | 47 | 2025-11-19 | 47 | TRUE | 2025-11-16 | 46 | 2025-11-16 | 2025-11-16 | Done | #N/A | #N/A | November | 2025-11-18 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-JPA-0651_1 | Swap_JAW-JT-JPA-0651 | JAW-JT-JPA-0651 | Central Java | Jawa Tengah | Jepara | -6.7307 | 110.723 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-JPA-0651 | Pecangaan | Protelindo |  | MBH Central Java Ring 12A | MA-JTJPA0651-01H | 10.219.37.24 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 4 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-24 | 2025-10-24 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-15 |  | Done | Done | 2025-11-08 | DOEID251107NS | 2025-11-16 | 2025-11-16 | done | done | done | done | done | done | GIT | 2025-11-16 | 46 | 2025-11-16 |  | 2025-11-10 | XLWO-20251110-00001850 |  | 2025-11-19 | 2025-11-16 | 2025-11-19 | 47 | 2025-11-19 | 47 | TRUE | 2025-11-16 | 46 | 2025-11-16 | 2025-11-16 | Done | #N/A | #N/A | November | 2025-11-18 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-JPA-0635_1 | Swap_JAW-JT-JPA-0635 | JAW-JT-JPA-0635 | Central Java | Jawa Tengah | Jepara | -6.6883 | 110.7073 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-JPA-0635 | Pecangaan Kota | Centratama |  | MBH Central Java Ring 12A | MA-JTJPA0635-01H | 10.219.37.25 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 4 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-14 | 2025-10-22 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-14 |  | Done | Done | 2025-11-08 | DOEID251107MC | 2025-11-16 | 2025-11-14 | done | done | done | done | done | done | GPA | 2025-11-16 | 46 | 2025-11-14 |  | 2025-11-10 | XLWO-20251110-00001850 |  | 2025-11-19 | 2025-11-16 | 2025-11-19 | 47 | 2025-11-19 | 47 | TRUE | 2025-11-16 | 46 | 2025-11-16 | 2025-11-16 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-JPA-0647_1 | Swap_JAW-JT-JPA-0647 | JAW-JT-JPA-0647 | Central Java | Jawa Tengah | Jepara | -6.7837 | 110.7226 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-JPA-0647 | Welahan | Centratama |  | MBH Central Java Ring 12A | MA-JTJPA0647-01H | 10.219.37.231 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 4 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2025-10-22 | 43 | October | Oct | 2025 | 2025-11-04 | 2025-11-04 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-12 |  | Done | Done | 2025-11-08 | DOEID251107ME | 2025-11-16 | 2025-11-13 | done | done | done | done | done | done | GPA | 2025-11-16 | 46 | 2025-11-13 |  | 2025-11-10 | XLWO-20251110-00001850 |  | 2025-11-19 | 2025-11-13 | 2025-11-19 | 47 | 2025-11-19 | 47 | TRUE | 2025-11-13 | 46 | 2025-11-13 | 2025-11-13 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1497_1 | Swap_JAW-JT-PTI-1497 | JAW-JT-PTI-1497 | Central Java | Jawa Tengah | Pati | -6.5364 | 111.0546 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1497 | Tayu | Others |  | MBH Central Java Ring 12A | MA-JTPTI1497-01H | 10.219.37.55 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 4 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-26 | 2025-10-26 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-15 |  | Done | Done | 2025-11-08 | DOEID251107NT | 2025-11-17 | 2025-11-16 | done | done | done | done | done | done | GIT | 2025-11-17 | 47 | 2025-11-16 |  | 2025-11-10 | XLWO-20251110-00001850 |  | 2025-11-20 | 2025-11-16 | 2025-11-20 | 47 | 2025-11-20 | 47 | TRUE | 2025-11-16 | 46 | 2025-11-16 | 2025-11-16 | Done | #N/A | #N/A | November | 2025-11-18 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1505_1 | Swap_JAW-JT-PTI-1505 | JAW-JT-PTI-1505 | Central Java | Jawa Tengah | Pati | -6.6661 | 111.0683 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1505 | Trangkil | Protelindo |  | MBH Central Java Ring 12A | MA-JTPTI1505-01H | 10.219.37.234 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 4 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-25 | 2025-10-25 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-15 |  | Done | Done | 2025-11-08 | DOEID251107NV | 2025-11-17 | 2025-11-16 | done | done | done | done | done | done | GIT | 2025-11-17 | 47 | 2025-11-16 |  | 2025-11-10 | XLWO-20251110-00001850 |  | 2025-11-20 | 2025-11-16 | 2025-11-20 | 47 | 2025-11-20 | 47 | TRUE | 2025-11-16 | 46 | 2025-11-16 | 2025-11-16 | Done | #N/A | #N/A | November | 2025-11-18 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-JPA-0628_1 | Swap_JAW-JT-JPA-0628 | JAW-JT-JPA-0628 | Central Java | Jawa Tengah | Jepara | -6.5686 | 110.6869 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-JPA-0628 | Mambak | Protelindo |  | MBH central Java Ring 12A | MA-JTJPA0628-01H | 10.219.37.253 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 4 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-27 | 2025-10-27 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-15 |  | Done | Done | 2025-11-08 | DOEID251107OY | 2025-11-17 | 2025-11-15 | done | done | done | done | done | done | YPTT | 2025-11-17 | 47 | 2025-11-15 |  | 2025-11-10 | XLWO-20251110-00001850 |  | 2025-11-20 | 2025-11-16 | 2025-11-20 | 47 | 2025-11-20 | 47 | TRUE | 2025-11-16 | 46 | 2025-11-16 | 2025-11-16 | Done | #N/A | #N/A | November | 2025-11-17 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-JPA-0672_1 | Swap_JAW-JT-JPA-0672 | JAW-JT-JPA-0672 | Central Java | Jawa Tengah | Jepara | -6.4821 | 110.8654 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-JPA-0672 | Keling | Protelindo |  | MBH Central Java Ring 12A | MA-JTJPA0672-01H | 10.219.37.54 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep | 4 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-29 | 2025-10-29 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-15 |  | Done | Done | 2025-11-08 | DOEID251107OW | 2025-11-15 | 2025-11-15 | done | done | done | done | done | done | YPTT | 2025-11-15 | 46 | 2025-11-15 |  | 2025-11-10 | XLWO-20251110-00001850 |  | 2025-11-18 | 2025-11-16 | 2025-11-18 | 47 | 2025-11-18 | 47 | TRUE | 2025-11-16 | 46 | 2025-11-16 | 2025-11-16 | Done | #N/A | #N/A | November | 2025-11-20
1 | 1 | CLEAR | Swap_JAW-JT-JPA-0638_1 | Swap_JAW-JT-JPA-0638 | JAW-JT-JPA-0638 | Central Java | Jawa Tengah | Jepara | -6.5274 | 110.7113 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-JPA-0638 | Mlonggo | Protelindo |  | MBH Central Java Ring 12A | MA-JTJPA0638-01H | 10.219.37.53 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 4 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-14 | 2025-10-22 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-15 |  | Done | Done | 2025-11-08 | DOEID251107NP | 2025-11-15 | 2025-11-16 | done | done | done | done | done | done | GIT | 2025-11-15 | 46 | 2025-11-16 |  | 2025-11-10 | XLWO-20251110-00001850 |  | 2025-11-18 | 2025-11-16 | 2025-11-18 | 47 | 2025-11-18 | 47 | TRUE | 2025-11-16 | 46 | 2025-11-16 | 2025-11-16 | Done | #N/A | #N/A | November | 2025-11-18 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-JPA-0629_1 | Swap_JAW-JT-JPA-0629 | JAW-JT-JPA-0629 | Central Java | Jawa Tengah | Jepara | -6.6204 | 110.6881 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-JPA-0629 | Tahunan | Centratama |  | MBH Central Java Ring 12A | MA-JTJPA0629-01H | 10.219.37.26 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 4 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-27 | 2025-10-27 | Approved | 2025-10-17 |  | Submitted | Approved | 2025-11-15 |  | Done | Done | 2025-11-08 | DOEID251107NQ | 2025-11-15 | 2025-11-16 | done | done | done | done | done | done | GIT | 2025-11-15 | 46 | 2025-11-16 |  | 2025-11-10 | XLWO-20251110-00001850 |  | 2025-11-18 | 2025-11-16 | 2025-11-18 | 47 | 2025-11-18 | 47 | TRUE | 2025-11-16 | 46 | 2025-11-16 | 2025-11-16 | Done | #N/A | #N/A | November | 2025-11-18 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-MKD-1216_1 | Swap_JAW-JT-MKD-1216 | JAW-JT-MKD-1216 | Central Java | Jawa Tengah | Magelang | -7.3834 | 110.2549 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-MKD-1216 | Secang | Others |  | MBH Central Java Ring 13E | MA-JTMKD1216-01H | 10.219.37.13 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GIT | 2025-10-15 | 42 | October | Oct | 2025 | 2025-10-25 | 2025-10-25 | Approved | 2025-10-17 |  | Submitted | Approved | [14 empty] | GIT | [14 empty] | 2025-11-27 | 48 | 2025-11-27 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-2662_1 | Swap_JAW-JT-UNR-2662 | JAW-JT-UNR-2662 | Central Java | Jawa Tengah | Semarang | -7.2183 | 110.3467 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-2662 | Candi Ambarawa | TBG |  | MBH Central Java Ring 13E | MA-JTUNR2662-01H | 10.219.37.129 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | Mid Dec 25 | On Schedule Swap | GIT | 2025-10-28 | 44 | October | Oct | 2025 | 2025-10-25 | 2025-10-25 | Approved | 2025-10-17 |  | Submitted | Approved | [6 empty] | 2025-11-23 | 2025-11-24 |  |  | Done |  | Done | 2.0. Permit Done | GIT | 2025-11-25 |  | 2025-11-25 | [11 empty] | 2025-11-25 | 48 | 2025-11-25 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-2663_1 | Swap_JAW-JT-UNR-2663 | JAW-JT-UNR-2663 | Central Java | Jawa Tengah | Semarang | -7.3046 | 110.3562 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-2663 | Bedono | Protelindo |  | MBH Central Java Ring 13E | MA-JTUNR2663-01H | 10.219.37.12 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | Mid Dec 25 | On Schedule Swap | GIT | 2025-10-28 | 44 | October | Oct | 2025 | 2025-10-23 | 2025-10-23 | Approved | 2025-10-17 |  | Submitted | Approved | [6 empty] | 2025-11-23 | 2025-11-24 |  |  | Done |  | Done | 2.0. Permit Done | GIT | 2025-11-25 |  | 2025-11-25 | [11 empty] | 2025-11-25 | 48 | 2025-11-25 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-2665_1 | Swap_JAW-JT-UNR-2665 | JAW-JT-UNR-2665 | Central Java | Jawa Tengah | Semarang | -7.2234 | 110.3672 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-2665 | Bandungan | Protelindo |  | MBH Central Java Ring 13E | MA-JTUNR2665-01H | 10.219.37.224 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | Mid Dec 25 | On Schedule Swap | GIT | 2025-10-28 | 44 | October | Oct | 2025 | 2025-10-25 | 2025-10-25 | Approved | 2025-10-17 |  | Submitted | Approved | [6 empty] | 2025-11-23 | 2025-11-24 |  |  | Done |  | Done | 2.0. Permit Done | GPA | 2025-11-25 |  | 2025-11-25 | [11 empty] | 2025-11-25 | 48 | 2025-11-25 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-2666_1 | Swap_JAW-JT-UNR-2666 | JAW-JT-UNR-2666 | Central Java | Jawa Tengah | Semarang | -7.2744 | 110.3695 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-2666 | Jambu | TBG |  | MBH Central Java Ring 13E | MA-JTUNR2666-01H | 10.219.37.245 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | Mid Dec 25 | On Schedule Swap | GIT | 2025-10-27 | 44 | October | Oct | 2025 | 2025-10-20 | 2025-10-24 | Approved | 2025-10-17 |  | Submitted | Approved | [6 empty] | 2025-11-23 | 2025-11-24 |  |  | Done |  | Done | 2.0. Permit Done | GIT | 2025-11-25 |  | 2025-11-25 | [11 empty] | 2025-11-25 | 48 | 2025-11-25 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-2682_1 | Swap_JAW-JT-UNR-2682 | JAW-JT-UNR-2682 | Central Java | Jawa Tengah | Semarang | -7.2518 | 110.4013 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-2682 | Kota Ambarawa Reloc | TBG |  | MBH Central Java Ring 13E | MA-JTUNR2682-01H | 10.219.37.241 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | Mid Dec 25 | On Schedule Swap | GIT | 2025-10-27 | 44 | October | Oct | 2025 | 2025-10-20 | 2025-10-21 | Approved | 2025-10-17 |  | Submitted | Approved | [6 empty] | 2025-11-23 | 2025-11-24 |  |  | Done |  | Done | 2.0. Permit Done | GIT | 2025-11-25 |  | 2025-11-25 | [11 empty] | 2025-11-25 | 48 | 2025-11-25 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-2690_1 | Swap_JAW-JT-UNR-2690 | JAW-JT-UNR-2690 | Central Java | Jawa Tengah | Semarang | -7.2737 | 110.412 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-2690 | Pojoksari Ambarawa | Protelindo |  | MBH Central Java Ring 13E | MA-JTUNR2690-01H | 10.219.37.243 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | Mid Dec 25 | On Schedule Swap | GIT | 2025-10-27 | 44 | October | Oct | 2025 | 2025-10-17 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | [6 empty] | 2025-11-23 | 2025-11-24 |  |  | Done |  | Done | 2.0. Permit Done | YPTT | 2025-11-25 |  | 2025-11-25 | [11 empty] | 2025-11-25 | 48 | 2025-11-25 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-3316_1 | Swap_JAW-JT-UNR-3316 | JAW-JT-UNR-3316 | Central Java | Jawa Tengah | Semarang | -7.2571 | 110.4237 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-3316 | Tambakboyo Ambarawa | TBG |  | MBH Central Java Ring 13E | MA-JTUNR3316-01H | 10.219.37.244 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | Mid Dec 25 | On Schedule Swap | GIT | 2025-10-27 | 44 | October | Oct | 2025 | 2025-10-17 | 2025-10-22 | Approved | 2025-10-17 |  | Submitted | Approved | [14 empty] | GIT | [14 empty] | 2025-11-26 | 48 | 2025-11-26 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-3338_1 | Swap_JAW-JT-UNR-3338 | JAW-JT-UNR-3338 | Central Java | Jawa Tengah | Semarang | -7.2717 | 110.4 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-3338 | Merpati Ambarawa | Others |  | MBH Central Java Ring 13E | MA-JTUNR3338-01H | 10.219.37.242 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | Mid Dec 25 | On Schedule Swap | GIT | 2025-10-28 | 44 | October | Oct | 2025 | 2025-10-23 | 2025-10-23 | Approved | 2025-10-17 |  | Submitted | Approved | [14 empty] | GIT | [14 empty] | 2025-11-26 | 48 | 2025-11-26 |  | Done | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-KDL-3487_2 | Swap_JAW-JT-KDL-3487 | JAW-JT-KDL-3487 | Central Java | Jawa Tengah | Kendal | -6.96536111111111 | 110.270188888889 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-KDL-3487 | Supernode Mangkang | 0 |  | Central Java Ring 05 | PAG-JTSMG2526-03H | 10.219.36.2 | ATN910C | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-20 | 43 | October |  | 2025 | 2025-11-08 | 2025-11-08 | Approved | 2025-11-17 | [34 empty] | #N/A |  | NY | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BNR-0237_1 | Swap_JAW-JT-BNR-0237 | JAW-JT-BNR-0237 | Central Java | Jawa Tengah | Banjarnegara | -7.396 | 109.697 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-BNR-0237 | Banjarnegara | Protelindo |  | Central Java Ring 101 | PAG-JTBNR0237-05H | 10.206.54.34 | ATN910C | Huawei | New Purchase | Linknet NNI,PAG1 | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | CCSI | 2025-11-26 | 48 |  |  | 2025 | 2025-10-29 | 2025-10-29 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PWT-1716_1 | Swap_JAW-JT-PWT-1716 | JAW-JT-PWT-1716 | Central Java | Jawa Tengah | Banyumas | -7.4218 | 109.2214 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-PWT-1716 | Mpls - Purwokerto | Direct Lease |  | Central Java Ring 101 | PAG-JTPWT1716-07H | 10.206.54.33 | ATN910C | Huawei | New Purchase | Linknet NNI,PAG2 | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-16 | 42 | October | Oct | 2025 | 2025-10-17 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | NY | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1923_1 | Swap_JAW-JT-SKH-1923 | JAW-JT-SKH-1923 | Central Java | Jawa Tengah | Sukoharjo | -7.68366944444444 | 110.8363 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKH-1923 | Supernode Solo | 0 |  | Central Java Ring 11 | PAG-YGSN0070-06H | 10.219.36.22 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A | [5 empty] | 2025-11-26 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PBG-1263_1 | Swap_JAW-JT-PBG-1263 | JAW-JT-PBG-1263 | Central Java | Jawa Tengah | Purbalingga | -7.2267 | 109.3257 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-PBG-1263 | Karang Reja Purbalingga | Protelindo |  | Central Java Ring 119 | PAG-JTPBG1263-02H | 10.206.30.179 | ATN910C | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | CCSI | 2025-11-26 | 48 |  |  | 2025 | 2025-11-07 | 2025-11-10 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PML-1427_1 | Swap_JAW-JT-PML-1427 | JAW-JT-PML-1427 | Central Java | Jawa Tengah | Pemalang | -7.0136 | 109.4904 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-PML-1427 | Bodeh Pemalang | Centratama |  | Central Java Ring 119 | PAG-JTPML1427-02H | 10.206.30.180 | ATN910C | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | CCSI | 2025-11-26 | 48 |  |  | 2025 | 2025-10-25 | 2025-10-30 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-TGL-2576_1 | Swap_JAW-JT-TGL-2576 | JAW-JT-TGL-2576 | Central Java | Jawa Tengah | Kota Tegal | -6.877 | 109.1045 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-TGL-2576 | Sumur Panggang | Protelindo |  | Central Java Ring 13A | PAG-SM2483-01H | 10.219.217.72 | NE40E(V8) | Huawei | New Purchase | Linknet NNI,PAG1 | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-17 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-TGL-2600_1 | Swap_JAW-JT-TGL-2600 | JAW-JT-TGL-2600 | Central Java | Jawa Tengah | Kota Tegal | -6.8618 | 109.143 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-TGL-2600 | HUT Tegal | Direct Lease |  | Central Java Ring 14 | PAG-SM2309-01H | 10.219.217.73 | NE40E(V8) | Huawei | New Purchase | Linknet NNI,PAG2 | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-17 | 42 | October | Oct | 2025 | 2025-10-16 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-YO-SMN-0067_1 | Swap_JAW-YO-SMN-0067 | JAW-YO-SMN-0067 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.6449 | 110.4231 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-YO-SMN-0067 | Kaliurang | Protelindo |  | Central Java Ring 16 | PAG-YG2265-01H | 10.219.217.16 | ATN910C-B | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | PT IFORTE SOLUSI INFOTEK | [7 empty] | 2025-11-09 | #N/A |  |  | 2025-End Nov | On Schedule Swap |  | 2025-11-27 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [14 empty] | YPTT | [14 empty] | 2025-11-27 | 48 | 2025-11-27 |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-YO-SMN-0292_1 | Swap_JAW-YO-SMN-0292 | JAW-YO-SMN-0292 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.7645 | 110.4236 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-YO-SMN-0292 | Kalasan | Others |  | Central Java Ring 16 | PAG-YG2271-01H | 10.219.217.17 | ATN910C-B | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2026 | On Schedule Swap |  | 2025-11-27 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [14 empty] | GPA | [14 empty] | 2025-11-27 | 48 | 2025-11-27 |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-YO-BTL-0074_1 | Swap_JAW-YO-BTL-0074 | JAW-YO-BTL-0074 | Central Java | Daerah Istimewa Yogyakarta | Bantul | -7.9223 | 110.382 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-YO-BTL-0074 | Imogiri | Centratama |  | Central Java Ring 21 | PAG-YG2276-01H | 10.219.217.157 | ATN910C-B | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2026 | Plan Swap December |  | 2025-11-27 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-YO-WNO-0012_1 | Swap_JAW-YO-WNO-0012 | JAW-YO-WNO-0012 | Central Java | Daerah Istimewa Yogyakarta | Gunungkidul | -7.9688 | 110.5969 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-YO-WNO-0012 | WONOSARI RELOCATION | Protelindo |  | Central Java Ring 21 | PAG-YG2278-02H | 10.219.217.158 | ATN910C-B | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A | [5 empty] | 2025-11-27 | 48 |  |  | 2025 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-SKT-2150_2 | Swap_JAW-JT-SKT-2150 | JAW-JT-SKT-2150 | Central Java | Jawa Tengah | Kota Surakarta | -7.5587 | 110.8275 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKT-2150 | SOLO RELOCATION | DMT |  | Central Java Ring 24 | PAG-YG2225-01H | 10.219.221.225 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 12 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December | YPTT | 2025-10-20 | 43 | October | Oct | 2025 | 2025-10-15 |  | Not Started |  |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2125_1 | Swap_JAW-JT-SKT-2125 | JAW-JT-SKT-2125 | Central Java | Jawa Tengah | Kota Surakarta | -7.5558 | 110.8441 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKT-2125 | Tentara Pelajar | Centratama |  | Central Java Ring 24 | PAG-YG2370-01H | 10.219.221.226 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 12 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December | YPTT | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-19 | 2025-10-20 | Approved | 2025-10-17 |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2081_1 | Swap_JAW-JT-SKT-2081 | JAW-JT-SKT-2081 | Central Java | Jawa Tengah | Kota Surakarta | -7.5677 | 110.8173 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKT-2081 | Gajahmada Solo | Protelindo |  | Central Java Ring 24B | MA-YG2371-01H | 10.219.221.37 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch | Keep | 12 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December | YPTT | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-17 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [14 empty] | YPTT | [14 empty] | 2025-11-29 |  | 2025-11-29 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-2141_1 | Swap_JAW-JT-KRG-2141 | JAW-JT-KRG-2141 | Central Java | Jawa Tengah | Karanganyar | -7.5551 | 110.8749 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-2141 | Ngringo Palur | Protelindo |  | Central Java Ring 24B | MA-YG2533616-01H | 10.219.221.241 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch | Keep | 12 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-18 | 2025-10-18 | Approved | 2025-10-17 |  | Submitted | Approved | [14 empty] | YPTT | [14 empty] | 2025-11-29 |  | 2025-11-29 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2074_1 | Swap_JAW-JT-SKT-2074 | JAW-JT-SKT-2074 | Central Java | Jawa Tengah | Kota Surakarta | -7.5586 | 110.8141 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKT-2074 | Mt Haryono Solo | TBG |  | Central Java Ring 24B | MA-YG2533622-01H | 10.219.221.236 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch | Keep | 12 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December | YPTT | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-17 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [14 empty] | YPTT | [14 empty] | 2025-11-29 |  | 2025-11-29 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2071_1 | Swap_JAW-JT-SKT-2071 | JAW-JT-SKT-2071 | Central Java | Jawa Tengah | Kota Surakarta | -7.536 | 110.8109 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKT-2071 | #N/A | Direct Lease |  | Central Java Ring 24B | MA-YG2533636-01H | 10.219.221.240 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch | Keep | 12 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December | YPTT | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-17 | 2025-10-17 | Approved | 2025-10-17 |  | Submitted | Approved | [14 empty] | YPTT | [14 empty] | 2025-11-29 |  | 2025-11-29 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-2060_1 | Swap_JAW-JT-KRG-2060 | JAW-JT-KRG-2060 | Central Java | Jawa Tengah | Karanganyar | -7.5358 | 110.8001 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-2060 | Banyuanyar2 | Protelindo |  | Central Java Ring 24B | MA-YG2533644-01H | 10.219.221.239 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch | Keep | 12 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-14 | 2025-10-15 | Approved | 2025-10-17 |  | Submitted | Approved | [14 empty] | YPTT | [14 empty] | 2025-11-29 |  | 2025-11-29 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-2139_1 | Swap_JAW-JT-KRG-2139 | JAW-JT-KRG-2139 | Central Java | Jawa Tengah | Karanganyar | -7.5647 | 110.8683 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-2139 | Puncang Sawit | TBG |  | Central Java Ring 24B | MA-YG2533661-01H | 10.219.221.242 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch | Keep | 12 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-15 | 2025-10-16 | Approved | 2025-10-17 |  | Submitted | Approved | [14 empty] | YPTT | [14 empty] | 2025-11-29 |  | 2025-11-29 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-2140_1 | Swap_JAW-JT-KRG-2140 | JAW-JT-KRG-2140 | Central Java | Jawa Tengah | Karanganyar | -7.5669 | 110.8737 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-2140 | Palur Mall | Centratama |  | Central Java Ring 24B | MA-YG253PX299-01H | 10.206.13.6 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 12 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-14 | 2025-10-15 | Approved | 2025-10-17 |  | Submitted | Approved | [14 empty] | YPTT | [14 empty] | 2025-11-29 |  | 2025-11-29 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2075_1 | Swap_JAW-JT-SKT-2075 | JAW-JT-SKT-2075 | Central Java | Jawa Tengah | Kota Surakarta | -7.5498 | 110.8153 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKT-2075 | Tirtonadi | Protelindo |  | Central Java Ring 24B | MA-YG3533625G-01H | 10.219.221.235 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch | Keep | 12 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December | YPTT | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-16 | 2025-10-16 | Approved | 2025-10-17 |  | Submitted | Approved | [14 empty] | YPTT | [14 empty] | 2025-11-29 |  | 2025-11-29 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-2052_1 | Swap_JAW-JT-KRG-2052 | JAW-JT-KRG-2052 | Central Java | Jawa Tengah | Karanganyar | -7.5368 | 110.7925 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-2052 | Sumber Surakarta | Centratama |  | Central Java Ring 24B | MA-YGB408-01H | 10.219.221.238 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch | Keep | 12 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-10-24 | 43 | October | Oct | 2025 | 2025-10-14 | 2025-10-15 | Approved | 2025-11-07 |  | Submitted | Approved | [14 empty] | YPTT | [14 empty] | 2025-11-29 |  | 2025-11-29 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0540_1 | Swap_JAW-JT-DMK-0540 | JAW-JT-DMK-0540 | Central Java | Jawa Tengah | Demak | -6.9871 | 110.6834 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0540 | SARIMULYO DEMAK | Protelindo |  | Central Java Ring 25D | MA-JTDMK0540-01H | 10.206.29.160 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-24 | 2025-10-31 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107O8 | 2025-11-08 | 2025-11-11 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-08 | 45 | 2025-11-11 |  | 2025-11-10 | XLWO-20251110-00001844 |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | 46 | 2025-11-11 | 46 | TRUE | 2025-11-11 | 46 | 2025-11-11 | 2025-11-11 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0562_1 | Swap_JAW-JT-DMK-0562 | JAW-JT-DMK-0562 | Central Java | Jawa Tengah | Demak | -6.9586 | 110.5453 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0562 | Perampelan Sayung | DMT |  | Central Java Ring 25D | MA-JTDMK0562-01H | 10.206.29.162 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-25 | 2025-10-25 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-09 |  | Done | Done | 2025-11-08 | DOEID251107LN | 2025-11-08 | 2025-11-10 | done | done | done | done | done | done | GPA | 2025-11-08 | 45 | 2025-11-10 |  | 2025-11-10 | XLWO-20251110-00001844 |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | 46 | 2025-11-11 | 46 | TRUE | 2025-11-11 | 46 | 2025-11-11 | 2025-11-11 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0565_1 | Swap_JAW-JT-DMK-0565 | JAW-JT-DMK-0565 | Central Java | Jawa Tengah | Demak | -7.0929 | 110.5591 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0565 | Jragung Karangawen Demak | TBG |  | Central Java Ring 25D | MA-JTDMK0565-01H | 10.206.29.164 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-24 | 2025-10-31 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-09 |  | Done | Done | 2025-11-08 | DOEID251107LO | 2025-11-08 | 2025-11-10 | done | done | done | done | done | done | GPA | 2025-11-08 | 45 | 2025-11-10 |  | 2025-11-10 | XLWO-20251110-00001844 |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | 46 | 2025-11-11 | 46 | TRUE | 2025-11-11 | 46 | 2025-11-11 | 2025-11-11 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0575_1 | Swap_JAW-JT-DMK-0575 | JAW-JT-DMK-0575 | Central Java | Jawa Tengah | Demak | -7.0521 | 110.5961 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0575 | Rejosari Karangawen | TBG |  | Central Java Ring 25D | MA-JTDMK0575-01H | 10.206.29.163 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-24 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107LP | 2025-11-09 | 2025-11-11 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-09 | 45 | 2025-11-11 |  | 2025-11-10 | XLWO-20251110-00001844 |  | 2025-11-12 | 2025-11-11 | 2025-11-12 | 46 | 2025-11-12 | 46 | TRUE | 2025-11-11 | 46 | 2025-11-11 | 2025-11-11 | Done | #N/A | #N/A | November | 2025-11-16 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0584_1 | Swap_JAW-JT-DMK-0584 | JAW-JT-DMK-0584 | Central Java | Jawa Tengah | Demak | -6.9283 | 110.6297 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0584 | Ploso Demak | DMT |  | Central Java Ring 25D | MA-JTDMK0584-01H | 10.206.29.159 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-25 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107LR | 2025-11-09 | 2025-11-11 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-09 | 45 | 2025-11-11 |  | 2025-11-10 | XLWO-20251110-00001844 |  | 2025-11-12 | 2025-11-11 | 2025-11-12 | 46 | 2025-11-12 | 46 | TRUE | 2025-11-11 | 46 | 2025-11-11 | 2025-11-11 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0593_1 | Swap_JAW-JT-DMK-0593 | JAW-JT-DMK-0593 | Central Java | Jawa Tengah | Demak | -6.912 | 110.658 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0593 | Mojodemak Wonosalam | Centratama |  | Central Java Ring 25D | MA-JTDMK0593-01H | 10.206.29.158 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-25 | 2025-10-25 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107LS | 2025-11-09 | 2025-11-11 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-09 | 45 | 2025-11-11 |  | 2025-11-10 | XLWO-20251110-00001844 |  | 2025-11-12 | 2025-11-11 | 2025-11-12 | 46 | 2025-11-12 | 46 | TRUE | 2025-11-11 | 46 | 2025-11-11 | 2025-11-11 | Done | #N/A | #N/A | November | 2025-11-20 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-1543_1 | Swap_JAW-JT-DMK-1543 | JAW-JT-DMK-1543 | Central Java | Jawa Tengah | Demak | -7.0185 | 110.6963 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-1543 | Kebonagung (Colocated Hcpt) | Protelindo |  | Central Java Ring 25D | MA-JTDMK1543-01H | 10.206.29.161 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-22 | 43 | October | Oct | 2025 | 2025-10-25 | 2025-11-10 | Approved | 2025-11-13 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107LT | 2025-11-09 | 2025-11-11 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-09 | 45 | 2025-11-11 |  | 2025-11-10 | XLWO-20251110-00001844 |  | 2025-11-12 | 2025-11-11 | 2025-11-12 | 46 | 2025-11-12 | 46 | TRUE | 2025-11-11 | 46 | 2025-11-11 | 2025-11-11 | Done | #N/A | #N/A | November | 2025-11-20 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0564_1 | Swap_JAW-JT-DMK-0564 | JAW-JT-DMK-0564 | Central Java | Jawa Tengah | Demak | -7.12 | 110.5526 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0564 | Jragung Karangawen | TBG |  | Central Java Ring 25E | MA-JTDMK0564-01H | 10.206.29.172 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-11-03 | 45 |  |  | 2025 | 2025-10-24 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107OQ | 2025-11-09 | 2025-11-11 | Done | Done | Done | Done | Done | Done | YPTT | 2025-11-09 | 45 | 2025-11-11 |  | 2025-11-11 | XLWO-20251111-00000513 |  | 2025-11-12 | 2025-11-12 | 2025-11-12 | 46 | 2025-11-12 | 46 | TRUE | 2025-11-12 | 46 | 2025-11-12 | 2025-11-12 | Done | #N/A | #N/A | November | 2025-11-17 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0567_1 | Swap_JAW-JT-DMK-0567 | JAW-JT-DMK-0567 | Central Java | Jawa Tengah | Demak | -7.0651 | 110.567 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0567 | Tlogorejo Karangawen | Others |  | Central Java Ring 25E | MA-JTDMK0567-01H | 10.206.29.171 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-11-03 | 45 |  |  | 2025 | 2025-10-24 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107OR | 2025-11-09 | 2025-11-11 | Done | Done | Done | Done | Done | Done | YPTT | 2025-11-09 | 45 | 2025-11-11 |  | 2025-11-11 | XLWO-20251111-00000513 |  | 2025-11-12 | 2025-11-12 | 2025-11-12 | 46 | 2025-11-12 | 46 | TRUE | 2025-11-12 | 46 | 2025-11-12 | 2025-11-12 | Done | #N/A | #N/A | November | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0577_1 | Swap_JAW-JT-DMK-0577 | JAW-JT-DMK-0577 | Central Java | Jawa Tengah | Demak | -7.0048 | 110.5959 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0577 | Pundenarum Karangawen | Protelindo |  | Central Java Ring 25E | MA-JTDMK0577-01H | 10.206.29.169 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-11-03 | 45 |  |  | 2025 | 2025-10-26 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107OS | 2025-11-10 | 2025-11-11 | Done | Done | Done | Done | Done | Done | YPTT | 2025-11-10 | 46 | 2025-11-11 |  | 2025-11-11 | XLWO-20251111-00000513 |  | 2025-11-13 | 2025-11-12 | 2025-11-13 | 46 | 2025-11-13 | 46 | TRUE | 2025-11-12 | 46 | 2025-11-12 | 2025-11-12 | Done | #N/A | #N/A | November | 2025-11-18 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0580_1 | Swap_JAW-JT-DMK-0580 | JAW-JT-DMK-0580 | Central Java | Jawa Tengah | Demak | -6.9468 | 110.6122 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0580 | Beberan Panggang | Centratama |  | Central Java Ring 25E | MA-JTDMK0580-01H | 10.206.29.167 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Propose Drop, MOCN Drop | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-11-03 | 45 |  |  | 2025 | 2025-10-22 | 2025-10-22 | Approved | 2025-11-07 |  | Submitted | Approved | [19 empty] | 2025-11-11 | XLWO-20251111-00000513 | [10 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0595_1 | Swap_JAW-JT-DMK-0595 | JAW-JT-DMK-0595 | Central Java | Jawa Tengah | Demak | -6.9278 | 110.6729 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0595 | Wonosalam | Protelindo |  | Central Java Ring 25E | MA-JTDMK0595-01H | 10.206.29.166 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-11-03 | 45 |  |  | 2025 | 2025-10-25 | 2025-10-25 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-11 |  | Done | Done | 2025-11-08 | DOEID251107OU | 2025-11-10 | 2025-11-11 | Done | Done | Done | Done | Done | Done | YPTT | 2025-11-10 | 46 | 2025-11-11 |  | 2025-11-11 | XLWO-20251111-00000513 |  | 2025-11-13 | 2025-11-12 | 2025-11-13 | 46 | 2025-11-13 | 46 | TRUE | 2025-11-12 | 46 | 2025-11-12 | 2025-11-12 | Done | #N/A | #N/A | November | 2025-11-19 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-2970_1 | Swap_JAW-JT-DMK-2970 | JAW-JT-DMK-2970 | Central Java | Jawa Tengah | Demak | -7.0236 | 110.7356 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-2970 | Werdoyo Kebonagung | TBG |  | Central Java Ring 25E | MA-JTDMK2970-01H | 10.206.29.168 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-11-03 | 45 |  |  | 2025 | 2025-10-25 | 2025-11-03 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107OA | 2025-11-10 | 2025-11-11 | Done | Done | Done | Done | Done | Done | Mingze | 2025-11-10 | 46 | 2025-11-11 |  | 2025-11-11 | XLWO-20251111-00000513 |  | 2025-11-13 | 2025-11-12 | 2025-11-13 | 46 | 2025-11-13 | 46 | TRUE | 2025-11-12 | 46 | 2025-11-12 | 2025-11-12 | Done | #N/A | #N/A | November | 2025-11-14 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-2972_1 | Swap_JAW-JT-DMK-2972 | JAW-JT-DMK-2972 | Central Java | Jawa Tengah | Demak | -7.0091 | 110.5567 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-2972 | Candisari Mranggen | TBG |  | Central Java Ring 25E | MA-JTDMK2972-01H | 10.206.29.170 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 2 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-11-03 | 45 |  |  | 2025 | 2025-10-26 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-10 |  | Done | Done | 2025-11-08 | DOEID251107OB | 2025-11-10 | 2025-11-11 | Done | Done | Done | Done | Done | Done | Mingze | 2025-11-10 | 46 | 2025-11-11 |  | 2025-11-11 | XLWO-20251111-00000513 |  | 2025-11-13 | 2025-11-12 | 2025-11-13 | 46 | 2025-11-13 | 46 | TRUE | 2025-11-12 | 46 | 2025-11-12 | 2025-11-12 | Done | #N/A | #N/A | November | 2025-11-14 |  | 2025-11-21
1 | 2 | CLEAR | Swap_JAW-JT-PBG-1276_2 | Swap_JAW-JT-PBG-1276 | JAW-JT-PBG-1276 | Central Java | Jawa Tengah | Purbalingga | -7.3873 | 109.3623 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-PBG-1276 | Purbalngga | Protelindo |  | Central Java Ring 27 | PAG-SM2333-02H | 10.219.208.124 | NE40E(V8) | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GIT | 2025-10-16 | 42 | October |  | 2025 | 2025-11-03 | [37 empty] | #N/A |  | NY | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-BNR-0237_2 | Swap_JAW-JT-BNR-0237 | JAW-JT-BNR-0237 | Central Java | Jawa Tengah | Banjarnegara | -7.396 | 109.697 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-BNR-0237 | Banjarnegara | Protelindo |  | Central Java Ring 27 | PAG-SM2342-02H | 10.219.208.123 | NE40E(V8) | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | CCSI | 2025-12-04 | 49 |  |  | 2025 | 2025-10-29 | 2025-10-29 | Approved | 2025-11-07 | [34 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1984_1 | Swap_JAW-JT-SKH-1984 | JAW-JT-SKH-1984 | Central Java | Jawa Tengah | Sukoharjo | -7.6784 | 110.8379 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKH-1984 | HUT Sukoharjo | Others |  | Central Java Ring 30 | PAG-SM2263-01H | 10.206.1.244 | NE40E(V8) | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 14 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | Mingze | 2025-12-04 | 49 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 3 | CLEAR | Swap_JAW-JT-SKT-2150_3 | Swap_JAW-JT-SKT-2150 | JAW-JT-SKT-2150 | Central Java | Jawa Tengah | Kota Surakarta | -7.5587 | 110.8275 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKT-2150 | SOLO RELOCATION | DMT |  | Central Java Ring 30 | PAG-SMSN0070-07H | 10.206.1.245 | NE40E(V8) | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 14 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December | YPTT | 2025-10-20 | 43 | October |  | 2025 | 2025-10-15 |  | In Progress |  |  | Submitted | Approved | [31 empty] | 0 |  | NY | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1969_1 | Swap_JAW-JT-SKH-1969 | JAW-JT-SKH-1969 | Central Java | Jawa Tengah | Sukoharjo | -7.6907 | 110.8105 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1969 | Combongan Sukoharjo | DMT |  | Central Java Ring 30B | MA-SM2319-01H | 10.206.6.0 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | Mingze | 2025-12-04 | 49 |  |  | 2025 | 2025-11-12 | 2025-11-18 | Approved | 2025-11-22 |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1968_1 | Swap_JAW-JT-SKH-1968 | JAW-JT-SKH-1968 | Central Java | Jawa Tengah | Sukoharjo | -7.7139 | 110.8113 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1968 | Banmati Sukoharjo (C-Indosat) | DMT |  | Central Java Ring 30B | MA-SM2531501-01H | 10.206.6.1 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | Mingze | 2025-12-05 | 49 |  |  | 2025 | 2025-11-12 | 2025-11-18 | Approved | 2025-11-22 |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-YO-WNO-0473_1 | Swap_JAW-YO-WNO-0473 | JAW-YO-WNO-0473 | Central Java | Jawa Tengah | Sukoharjo | -7.6189 | 110.7681 | Swap | Swap Only | Swap | Type B | MA | JAW-YO-WNO-0473 | Teloyo Wonosari Klaten | Protelindo |  | Central Java Ring 30B | MA-SM2533081-01H | 10.206.6.3 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1980_1 | Swap_JAW-JT-SKH-1980 | JAW-JT-SKH-1980 | Central Java | Jawa Tengah | Sukoharjo | -7.6816 | 110.8318 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1980 | Jetis Sukoharjo | Others |  | Central Java Ring 30B | MA-SM3533197G-01H | 10.206.1.255 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1939_1 | Swap_JAW-JT-SKH-1939 | JAW-JT-SKH-1939 | Central Java | Jawa Tengah | Sukoharjo | -7.7333 | 110.7585 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1939 | SISWODIPURAN | TBG |  | Central Java Ring 30B | MA-SM3534708G-01H | 10.206.6.2 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | Mingze | 2025-12-05 | 49 |  |  | 2025 | 2025-11-12 | 2025-11-18 | Approved | 2025-11-22 |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1985_1 | Swap_JAW-JT-SKH-1985 | JAW-JT-SKH-1985 | Central Java | Jawa Tengah | Sukoharjo | -7.743 | 110.84 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1985 | Lawu Nguter | DMT |  | Central Java Ring 30D | MA-SM3533158G-01H | 10.206.6.13 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | Mingze | 2025-12-05 | 49 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1965_1 | Swap_JAW-JT-SKH-1965 | JAW-JT-SKH-1965 | Central Java | Jawa Tengah | Sukoharjo | -7.6008 | 110.8064 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1965 | Kwarasan Grogol | TBG |  | Central Java Ring 30D | MA-SM3533199G-01H | 10.206.6.18 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | Mingze | 2025-12-05 | 49 |  |  | 2025 | 2025-11-18 | 2025-11-18 | Approved | 2025-11-22 |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-1067_1 | Swap_JAW-JT-KLN-1067 | JAW-JT-KLN-1067 | Central Java | Jawa Tengah | Klaten | -7.7332 | 110.7378 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-1067 | Soka Karangdowo | Protelindo |  | Central Java Ring 30D | MA-SM3533228G-01H | 10.206.6.14 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | Mingze | 2025-12-22 | 52 |  |  | 2025 | 2025-11-01 | 2025-11-04 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-1058_1 | Swap_JAW-JT-KLN-1058 | JAW-JT-KLN-1058 | Central Java | Jawa Tengah | Klaten | -7.7127 | 110.7059 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-1058 | Beji Pedan | Protelindo |  | Central Java Ring 30D | MA-SM3533230G-01H | 10.206.6.15 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | Mingze | 2025-12-22 | 52 |  |  | 2025 | 2025-11-18 | 2025-11-18 | Approved | 2025-11-22 |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1987_1 | Swap_JAW-JT-SKH-1987 | JAW-JT-SKH-1987 | Central Java | Jawa Tengah | Sukoharjo | -7.6856 | 110.8416 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1987 | Gayam Sukoharjo | DMT |  | Central Java Ring 30D | MA-SM3533355G-01H | 10.206.6.11 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | Mingze | 2025-12-22 | 52 |  |  | 2025 | 2025-11-12 | 2025-11-18 | Approved | 2025-11-22 |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1943_1 | Swap_JAW-JT-SKH-1943 | JAW-JT-SKH-1943 | Central Java | Jawa Tengah | Sukoharjo | -7.6056 | 110.7656 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1943 | DUWET KLATEN | TBG |  | Central Java Ring 30D | MA-SM3534925G-01H | 10.206.6.17 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | Mingze | 2025-12-22 | 52 |  |  | 2025 | 2025-11-18 | 2025-11-18 | Approved | 2025-11-22 |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-1995_1 | Swap_JAW-JT-SKH-1995 | JAW-JT-SKH-1995 | Central Java | Jawa Tengah | Sukoharjo | -7.7086 | 110.8553 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-1995 | Kepuh Sukoharjo | Protelindo |  | Central Java Ring 30D | MA-SMB254-01H | 10.206.6.12 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | Mingze | 2025-12-22 | 52 |  |  | 2025 | 2025-11-18 | 2025-11-18 | Approved | 2025-11-22 |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-1066_1 | Swap_JAW-JT-KLN-1066 | JAW-JT-KLN-1066 | Central Java | Jawa Tengah | Klaten | -7.6759 | 110.7349 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-1066 | Ketitang Juwiring | Protelindo |  | Central Java Ring 30D | MA-SMBD85-01H | 10.206.6.16 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 14 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | Mingze | 2025-12-22 | 52 |  |  | 2025 | 2025-11-01 | 2025-11-04 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | 0 |  | Done | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-UNR-2663_2 | Swap_JAW-JT-UNR-2663 | JAW-JT-UNR-2663 | Central Java | Jawa Tengah | Semarang | -7.3046 | 110.3562 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-UNR-2663 | Bedono | Protelindo |  | Central Java Ring 31 | PAG-SM2384-01H | 10.219.214.223 | NE40E(V8) | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | Mid Dec 25 | Plan Swap December | GIT | 2025-10-28 | 44 | October |  | 2025 | 2025-10-22 | [37 empty] | #N/A |  | NY | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-2694_1 | Swap_JAW-JT-UNR-2694 | JAW-JT-UNR-2694 | Central Java | Jawa Tengah | Semarang | -7.2513 | 110.4144 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-UNR-2694 | Doplang | Others |  | Central Java Ring 31 | PAG-SM2531825-01H | 10.219.214.222 | NE40E(V8) | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | Mid Dec 25 | On Schedule Swap | Mingze | 2025-12-23 | 52 |  |  | 2025 | 2025-11-03 | 2025-11-03 | Approved | 2025-11-07 |  | Submitted | Approved | [14 empty] | Mingze | [14 empty] | 2025-11-27 | 48 | 2025-11-27 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2035_1 | Swap_JAW-JT-SKT-2035 | JAW-JT-SKT-2035 | Central Java | Jawa Tengah | Kota Surakarta | -7.546 | 110.78 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKT-2035 | Baturan Reloc | Protelindo |  | Central Java Ring 34 | PAG-SM2369-01H | 10.219.209.196 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December | CCSI | 2025-12-23 | 52 |  |  | 2025 | 2025-10-29 | 2025-11-01 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-SLT-2171_2 | Swap_JAW-JT-SLT-2171 | JAW-JT-SLT-2171 | Central Java | Jawa Tengah | Kota Salatiga | -7.3627 | 110.5156 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SLT-2171 | Tingkir Salatiga | Centratama |  | Central Java Ring 34 | PAG-SMB239-02H | 10.219.209.197 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December | GIT | 2025-10-14 | 42 | October |  | 2025 | 2025-10-14 |  | Not Started |  |  | Submitted | Approved | [31 empty] | #N/A |  | NY | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-1082_1 | Swap_JAW-JT-BYL-1082 | JAW-JT-BYL-1082 | Central Java | Jawa Tengah | Boyolali | -7.4624 | 110.8029 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-1082 | Kalioso | Protelindo |  | Central Java Ring 34A | MA-JTBYL1082-01H | 10.206.27.43 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-06 | 45 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved |  | Site Will Be Reloc | [12 empty] | GPA | [14 empty] | 2025-11-28 | 48 | 2025-11-28 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0351_1 | Swap_JAW-JT-BYL-0351 | JAW-JT-BYL-0351 | Central Java | Jawa Tengah | Boyolali | -7.3566 | 110.733 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0351 | Sumberagung Klego | DMT |  | Central Java Ring 34A | MA-SM2531902-01H | 10.219.209.201 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-11-12 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [14 empty] | YPTT | [14 empty] | 2025-11-28 | 48 | 2025-11-28 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0331_1 | Swap_JAW-JT-BYL-0331 | JAW-JT-BYL-0331 | Central Java | Jawa Tengah | Boyolali | -7.3511 | 110.6586 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0331 | Klimas Karanggede | TBG |  | Central Java Ring 34A | MA-SM2533750-01H | 10.219.209.202 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-10-31 | 2025-10-31 | Approved | 2025-11-07 |  | Submitted | Approved | [14 empty] | YPTT | [14 empty] | 2025-11-28 | 48 | 2025-11-28 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0339_1 | Swap_JAW-JT-BYL-0339 | JAW-JT-BYL-0339 | Central Java | Jawa Tengah | Boyolali | -7.3569 | 110.6902 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0339 | Klego Boyolali | Protelindo |  | Central Java Ring 34A | MA-SM3531903G-01H | 10.219.209.208 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-10-31 | 2025-10-31 | Approved | 2025-11-07 |  | Submitted | Approved | [14 empty] | GPA | [14 empty] | 2025-11-28 | 48 | 2025-11-28 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0332_1 | Swap_JAW-JT-BYL-0332 | JAW-JT-BYL-0332 | Central Java | Jawa Tengah | Boyolali | -7.3112 | 110.66 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0332 | Wonosegoro | DMT |  | Central Java Ring 34A | MA-SM3531904G-01H | 10.219.209.209 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-11-04 | 2025-11-04 | Approved | 2025-11-07 |  | Submitted | Approved | [14 empty] | Mingze | [14 empty] | 2025-11-28 | 48 | 2025-11-28 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-1912_1 | Swap_JAW-JT-BYL-1912 | JAW-JT-BYL-1912 | Central Java | Jawa Tengah | Boyolali | -7.4282 | 110.7599 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-1912 | Galeh Tangen | Protelindo |  | Central Java Ring 34A | MA-SM3533174G-01H | 10.219.209.199 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-11-06 | 2025-11-06 | Approved | 2025-11-07 |  | Submitted | Approved | [14 empty] | Mingze | [14 empty] | 2025-11-28 | 48 | 2025-11-28 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0324_1 | Swap_JAW-JT-BYL-0324 | JAW-JT-BYL-0324 | Central Java | Jawa Tengah | Boyolali | -7.4058 | 110.7456 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0324 | Repaking Wonosegoro | DMT |  | Central Java Ring 34A | MA-SM3534046G-01H | 10.219.209.206 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-11-07 | 2025-11-10 | Approved | 2025-11-13 |  | Submitted | Approved | [14 empty] | GPA | [14 empty] | 2025-11-28 | 48 | 2025-11-28 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-2977_1 | Swap_JAW-JT-BYL-2977 | JAW-JT-BYL-2977 | Central Java | Jawa Tengah | Boyolali | -7.3789 | 110.7494 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-2977 | Beji Andong | TBG |  | Central Java Ring 34A | MA-SM3535223G-01H | 10.219.209.207 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-11-10 | 2025-11-10 | Approved | 2025-11-13 |  | Submitted | Approved | [14 empty] | GPA | [14 empty] | 2025-11-28 | 48 | 2025-11-28 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-3357_1 | Swap_JAW-JT-UNR-3357 | JAW-JT-UNR-3357 | Central Java | Jawa Tengah | Semarang | -7.3631 | 110.5348 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-3357 | Barukan Tengaran | Protelindo |  | Central Java Ring 34A | MA-SM3535594G-01H | 10.219.209.204 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | On Schedule Swap | Mingze | 2025-12-25 | 52 |  |  | 2025 | 2025-11-03 | 2025-11-03 | Approved | 2025-11-07 |  | Submitted | Approved | [14 empty] | Mingze | [14 empty] | 2025-11-26 | 48 | 2025-11-26 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0360_1 | Swap_JAW-JT-BYL-0360 | JAW-JT-BYL-0360 | Central Java | Jawa Tengah | Boyolali | -7.3747 | 110.7688 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0360 | Andong Boyolali | Protelindo |  | Central Java Ring 34A | MA-SMB372-01H | 10.219.209.200 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-10-31 | 2025-10-31 | Approved | 2025-11-07 |  | Submitted | Approved | [14 empty] | GIT | [14 empty] | 2025-11-28 | 48 | 2025-11-28 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-2785_1 | Swap_JAW-JT-UNR-2785 | JAW-JT-UNR-2785 | Central Java | Jawa Tengah | Semarang | -7.3671 | 110.5949 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-2785 | Medayu Suruh | TBG |  | Central Java Ring 34A | MA-SMBD40-01H | 10.219.209.210 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | On Schedule Swap | Mingze | 2025-12-25 | 52 |  |  | 2025 | 2025-11-21 | 2025-11-21 | Approved | 2025-11-22 |  | Submitted | Approved | [14 empty] | GCI | [14 empty] | 2025-11-26 | 48 | 2025-11-26 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0355_1 | Swap_JAW-JT-BYL-0355 | JAW-JT-BYL-0355 | Central Java | Jawa Tengah | Boyolali | -7.3067 | 110.7517 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0355 | Kemusu Boyolali | Protelindo |  | Central Java Ring 34A | MA-JTBYL0355-01H | 10.206.27.44 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-06 | 45 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [14 empty] | GIT | [14 empty] | 2025-11-28 | 48 | 2025-11-28 |  | Done | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-SKT-2035_2 | Swap_JAW-JT-SKT-2035 | JAW-JT-SKT-2035 | Central Java | Jawa Tengah | Kota Surakarta | -7.546 | 110.78 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKT-2035 | Baturan Reloc | Protelindo |  | Central Java Ring 35 | PAG-BD2369-02H | 10.219.209.211 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December | CCSI | 2025-12-25 | 52 |  |  | 2025 | 2025-10-29 | 2025-11-01 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-1055_1 | Swap_JAW-JT-KLN-1055 | JAW-JT-KLN-1055 | Central Java | Jawa Tengah | Klaten | -7.6166 | 110.7014 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-KLN-1055 | Kota Delanggu | Centratama |  | Central Java Ring 35 | PAG-BD2401-01H | 10.219.209.212 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | Mingze | 2025-12-25 | 52 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0346_1 | Swap_JAW-JT-BYL-0346 | JAW-JT-BYL-0346 | Central Java | Jawa Tengah | Boyolali | -7.5554 | 110.7137 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0346 | Delanggu | Protelindo |  | Central Java Ring 35B | MA-BD2230-01H | 10.219.209.226 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-10-29 | 2025-10-29 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0306_1 | Swap_JAW-JT-BYL-0306 | JAW-JT-BYL-0306 | Central Java | Jawa Tengah | Boyolali | -7.5772 | 110.5868 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0306 | Tambak Tulung | TBG |  | Central Java Ring 35B | MA-BD2533753-01H | 10.219.209.230 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-11-01 | 2025-11-01 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0311_1 | Swap_JAW-JT-BYL-0311 | JAW-JT-BYL-0311 | Central Java | Jawa Tengah | Boyolali | -7.5464 | 110.607 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0311 | Siswodipuran Boyolali Boyolali | Protelindo |  | Central Java Ring 35B | MA-BD3533157G-01H | 10.219.209.229 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-11-01 | 2025-11-01 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-0350_1 | Swap_JAW-JT-KRG-0350 | JAW-JT-KRG-0350 | Central Java | Jawa Tengah | Karanganyar | -7.5299 | 110.7286 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-0350 | Ngesrep Ngemplak | Protelindo |  | Central Java Ring 35B | MA-BD3533466G-01H | 10.219.209.225 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | Mingze | 2025-12-26 | 52 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0341_1 | Swap_JAW-JT-BYL-0341 | JAW-JT-BYL-0341 | Central Java | Jawa Tengah | Boyolali | -7.5245 | 110.6941 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0341 | Trayu Banyudono | DMT |  | Central Java Ring 35B | MA-BD3533869G-01H | 10.219.209.227 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-10-30 | 2025-10-30 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-3428_1 | Swap_JAW-JT-KRG-3428 | JAW-JT-KRG-3428 | Central Java | Jawa Tengah | Karanganyar | -7.5439 | 110.7538 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-3428 | Puri Permata AdiSucipto | DMT |  | Central Java Ring 35B | MA-BD3535643G-01H | 10.219.209.224 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | Mingze | 2025-12-26 | 52 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0335_1 | Swap_JAW-JT-BYL-0335 | JAW-JT-BYL-0335 | Central Java | Jawa Tengah | Boyolali | -7.5696 | 110.6759 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0335 | Sawit Boyolali | Centratama |  | Central Java Ring 35B | MA-SMD920-01H | 10.206.26.174 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-06 | 45 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-1078_1 | Swap_JAW-JT-KRG-1078 | JAW-JT-KRG-1078 | Central Java | Jawa Tengah | Karanganyar | -7.5308 | 110.7773 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-1078 | Gdgncolomaduc-Prtldo | Protelindo |  | Central Java Ring 35C | MA-BD253EH83-01H | 10.219.209.231 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | Mingze | 2025-12-29 | 53 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0348_1 | Swap_JAW-JT-BYL-0348 | JAW-JT-BYL-0348 | Central Java | Jawa Tengah | Boyolali | -7.4291 | 110.7201 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0348 | Pojok Nogosari | DMT |  | Central Java Ring 35C | MA-BD3531901G-01H | 10.219.209.233 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-06 | 45 |  |  | 2025 | 2025-10-30 | 2025-10-30 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0305_1 | Swap_JAW-JT-BYL-0305 | JAW-JT-BYL-0305 | Central Java | Jawa Tengah | Boyolali | -7.5401 | 110.5837 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0305 | Pusporenggo Musuk | Protelindo |  | Central Java Ring 35C | MA-BD3533237G-01H | 10.219.209.242 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-10 | 46 |  |  | 2025 | 2025-10-30 | 2025-10-30 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0329_1 | Swap_JAW-JT-BYL-0329 | JAW-JT-BYL-0329 | Central Java | Jawa Tengah | Boyolali | -7.5149 | 110.6568 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0329 | Krasak Teras | DMT |  | Central Java Ring 35C | MA-BD3533339G-01H | 10.219.209.235 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-10 | 46 |  |  | 2025 | 2025-11-07 | 2025-11-07 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0328_1 | Swap_JAW-JT-BYL-0328 | JAW-JT-BYL-0328 | Central Java | Jawa Tengah | Boyolali | -7.5375 | 110.6547 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0328 | Banyudono2 | DMT |  | Central Java Ring 35C | MA-BD3533649G-01H | 10.219.209.239 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-10 | 46 |  |  | 2025 | 2025-11-01 | 2025-11-01 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0347_1 | Swap_JAW-JT-BYL-0347 | JAW-JT-BYL-0347 | Central Java | Jawa Tengah | Boyolali | -7.5163 | 110.7167 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0347 | Ngargorejo Ngemplak | DMT |  | Central Java Ring 35C | MA-BD3533861G-01H | 10.219.209.234 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-10 | 46 |  |  | 2025 | 2025-11-03 | 2025-11-03 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0317_1 | Swap_JAW-JT-BYL-0317 | JAW-JT-BYL-0317 | Central Java | Jawa Tengah | Boyolali | -7.5522 | 110.6251 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0317 | BUTUH MOJOSONGO | Others |  | Central Java Ring 35C | MA-BD3534095G-01H | 10.219.209.241 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-10 | 46 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0326_1 | Swap_JAW-JT-BYL-0326 | JAW-JT-BYL-0326 | Central Java | Jawa Tengah | Boyolali | -7.5799 | 110.6503 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0326 | KADIRESO TERAS | TBG |  | Central Java Ring 35C | MA-BD3534374G-01H | 10.219.209.243 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-10 | 46 |  |  | 2025 | 2025-10-30 | 2025-10-31 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0357_1 | Swap_JAW-JT-BYL-0357 | JAW-JT-BYL-0357 | Central Java | Jawa Tengah | Boyolali | -7.4454 | 110.7564 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0357 | NOGOSARI BOYOLALI | TBG |  | Central Java Ring 35C | MA-BDBD02-01H | 10.219.209.232 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-10 | 46 |  |  | 2025 |  |  | In Progress |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0215_1 | Swap_JAW-JT-BYL-0215 | JAW-JT-BYL-0215 | Central Java | Jawa Tengah | Boyolali | -7.5489 | 110.6613 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0215 | Teras Salakan | DMT |  | Central Java Ring 35C | MA-JTBYL0215-01H | 10.206.26.176 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-10 | 46 |  |  | 2025 | 2025-11-07 | 2025-11-07 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BYL-0224_1 | Swap_JAW-JT-BYL-0224 | JAW-JT-BYL-0224 | Central Java | Jawa Tengah | Boyolali | -7.462 | 110.6743 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-BYL-0224 | BANGAK SIMO | TBG |  | Central Java Ring 35C | MA-JTBYL0224-01H | 10.206.26.175 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | YPTT | 2025-11-10 | 46 |  |  | 2025 | 2025-11-07 | 2025-11-07 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PML-1443_1 | Swap_JAW-JT-PML-1443 | JAW-JT-PML-1443 | Central Java | Jawa Tengah | Pemalang | -6.8984 | 109.5301 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-PML-1443 | Comal | Centratama |  | Central Java Ring 41 | PAG-SM2304-01H | 10.219.26.147 | NE40E(V8) | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | CCSI | 2025-12-31 | 53 |  |  | 2025 | 2025-10-24 | 2025-10-30 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PML-1393_1 | Swap_JAW-JT-PML-1393 | JAW-JT-PML-1393 | Central Java | Jawa Tengah | Pemalang | -6.8877 | 109.3893 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-PML-1393 | Mpls - Pemalang | Direct Lease |  | Central Java Ring 41 | PAG-SM2307-01H | 10.219.26.146 | NE40E(V8) | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | CCSI | 2025-12-31 | 53 |  |  | 2025 | 2025-10-24 | 2025-10-30 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2087_1 | Swap_JAW-JT-SKT-2087 | JAW-JT-SKT-2087 | Central Java | Jawa Tengah | Kota Surakarta | -7.5327 | 110.8207 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKT-2087 | Jetak | Protelindo |  | Central Java Ring 43 | PAG-YG2368-01H | 10.219.26.103 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December | CCSI | 2025-12-31 | 53 |  |  | 2025 | 2025-10-30 | 2025-11-01 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2062_1 | Swap_JAW-JT-SKT-2062 | JAW-JT-SKT-2062 | Central Java | Jawa Tengah | Kota Surakarta | -7.5498 | 110.8044 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKT-2062 | Banyuanyar | Protelindo |  | Central Java Ring 43 | PAG-YG2439-03H | 10.219.26.102 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December | CCSI | 2025-12-31 | 53 |  |  | 2025 | 2025-10-30 | 2025-11-01 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1892_1 | Swap_JAW-JT-SGN-1892 | JAW-JT-SGN-1892 | Central Java | Jawa Tengah | Sragen | -7.4176 | 111.0188 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1892 | Sragen Reloc | TBG |  | Central Java Ring 43A | MA-YG2267-01H | 10.219.26.105 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2025-12-31 | 53 |  |  | 2025 | 2025-11-08 | 2025-11-16 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1898_1 | Swap_JAW-JT-SGN-1898 | JAW-JT-SGN-1898 | Central Java | Jawa Tengah | Sragen | -7.4186 | 111.0326 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1898 | Sragen Wetan (Collocated Protelindo) | Protelindo |  | Central Java Ring 43A | MA-YG2531109-01H | 10.219.26.106 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2025-12-31 | 53 |  |  | 2025 | 2025-11-07 | 2025-11-13 14:45:23 | Reviewing |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1871_1 | Swap_JAW-JT-SGN-1871 | JAW-JT-SGN-1871 | Central Java | Jawa Tengah | Sragen | -7.4091 | 110.9441 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1871 | Gawan Tanon | Protelindo |  | Central Java Ring 43A | MA-YG2531314-01H | 10.219.26.114 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-01 | 1 |  |  | 2026 | 2025-11-07 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1910_1 | Swap_JAW-JT-SGN-1910 | JAW-JT-SGN-1910 | Central Java | Jawa Tengah | Sragen | -7.3827 | 111.0862 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1910 | Toyogo Sambung Macan | Protelindo |  | Central Java Ring 43A | MA-YG2531913-01H | 10.219.26.108 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-01 | 1 |  |  | 2026 | 2025-11-07 | 2025-11-13 14:45:17 | Reviewing |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1885_1 | Swap_JAW-JT-SGN-1885 | JAW-JT-SGN-1885 | Central Java | Jawa Tengah | Sragen | -7.4314 | 111.0051 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1885 | Jatibatu Sragen | TBG |  | Central Java Ring 43A | MA-YG2533963-01H | 10.219.26.104 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-01 | 1 |  |  | 2026 | 2025-11-08 | 2025-11-16 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-1093_1 | Swap_JAW-JT-KRG-1093 | JAW-JT-KRG-1093 | Central Java | Jawa Tengah | Karanganyar | -7.5118 | 110.911 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-1093 | Kebak Kramat Utara | Protelindo |  | Central Java Ring 43A | MA-YG2534858-01H | 10.219.26.116 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-01 | 1 |  |  | 2026 | 2025-11-07 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1862_1 | Swap_JAW-JT-SGN-1862 | JAW-JT-SGN-1862 | Central Java | Jawa Tengah | Sragen | -7.3011 | 110.9066 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1862 | Tlogotirto | TBG |  | Central Java Ring 43A | MA-YG2534872-01H | 10.219.26.113 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-01 | 1 |  |  | 2026 | 2025-11-10 | 2025-11-17 | Approved | 2025-11-22 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1905_1 | Swap_JAW-JT-SGN-1905 | JAW-JT-SGN-1905 | Central Java | Jawa Tengah | Sragen | -7.3607 | 111.0608 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1905 | Pasar Made | Protelindo |  | Central Java Ring 43A | MA-YG3533156G-01H | 10.219.26.110 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-01 | 1 |  |  | 2026 | 2025-11-07 |  | In Progress |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1870_1 | Swap_JAW-JT-SGN-1870 | JAW-JT-SGN-1870 | Central Java | Jawa Tengah | Sragen | -7.4384 | 110.9431 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1870 | BENTAK SIDOHARJO | DMT |  | Central Java Ring 43A | MA-YG3533243G-01H | 10.219.26.115 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-02 | 1 |  |  | 2026 | 2025-11-09 | 2025-11-17 | Approved | 2025-11-22 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1879_1 | Swap_JAW-JT-SGN-1879 | JAW-JT-SGN-1879 | Central Java | Jawa Tengah | Sragen | -7.3512 | 110.9851 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1879 | Pilangsari Gesi | DMT |  | Central Java Ring 43A | MA-YG3533866G-01H | 10.219.26.112 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-02 | 1 |  |  | 2026 | 2025-11-08 | 2025-11-13 14:45:13 | Reviewing |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-2982_1 | Swap_JAW-JT-KRG-2982 | JAW-JT-KRG-2982 | Central Java | Jawa Tengah | Karanganyar | -7.5181 | 110.87 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-2982 | KARANGTURI GONDANGREJO | Protelindo |  | Central Java Ring 43A | MA-YG3535265G-01H | 10.219.26.117 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-02 | 1 |  |  | 2026 | 2025-11-10 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-3400_1 | Swap_JAW-JT-SGN-3400 | JAW-JT-SGN-3400 | Central Java | Jawa Tengah | Sragen | -7.365 | 111.0225 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-3400 | Klandungan | Protelindo |  | Central Java Ring 43A | MA-YG3535557G9-01H | 10.219.26.111 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-02 | 1 |  |  | 2026 | 2025-11-08 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-2113_1 | Swap_JAW-JT-KRG-2113 | JAW-JT-KRG-2113 | Central Java | Jawa Tengah | Karanganyar | -7.5322 | 110.8359 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-2113 | Jayawijaya Solo | Centratama |  | Central Java Ring 43C | MA-SM3534702G-01H | 10.206.26.192 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-02 | 1 |  |  | 2026 | 2025-11-10 | 2025-11-16 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1880_1 | Swap_JAW-JT-SGN-1880 | JAW-JT-SGN-1880 | Central Java | Jawa Tengah | Sragen | -7.4103 | 110.9864 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1880 | Singopadu | Protelindo |  | Central Java Ring 43C | MA-YG2531823-01H | 10.219.26.132 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-02 | 1 |  |  | 2026 | 2025-11-09 |  | In Progress |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1869_1 | Swap_JAW-JT-SGN-1869 | JAW-JT-SGN-1869 | Central Java | Jawa Tengah | Sragen | -7.3722 | 110.9424 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1869 | Suwatu Sragen | DMT |  | Central Java Ring 43C | MA-YG2531909-01H | 10.219.26.133 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-05 | 2 |  |  | 2026 | 2025-11-08 | 2025-11-13 14:45:28 | Reviewing |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1854_1 | Swap_JAW-JT-SGN-1854 | JAW-JT-SGN-1854 | Central Java | Jawa Tengah | Sragen | -7.3958 | 110.8589 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1854 | Peleman Sragen | DMT |  | Central Java Ring 43C | MA-YG3531912G-01H | 10.219.26.136 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-05 | 2 |  |  | 2026 | 2025-11-11 | 2025-11-17 | Approved | 2025-11-22 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1857_1 | Swap_JAW-JT-SGN-1857 | JAW-JT-SGN-1857 | Central Java | Jawa Tengah | Sragen | -7.4566 | 110.8917 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1857 | Gedongan Plupuh | Protelindo |  | Central Java Ring 43C | MA-YG3531989G-01H | 10.219.26.143 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-05 | 2 |  |  | 2026 | 2025-11-07 |  | In Progress |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1865_1 | Swap_JAW-JT-SGN-1865 | JAW-JT-SGN-1865 | Central Java | Jawa Tengah | Sragen | -7.4839 | 110.9129 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1865 | Sidodadi Masaran | Others |  | Central Java Ring 43C | MA-YG3533192G-01H | 10.219.26.145 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-05 | 2 |  |  | 2026 | 2025-11-09 |  | In Progress |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1858_1 | Swap_JAW-JT-SGN-1858 | JAW-JT-SGN-1858 | Central Java | Jawa Tengah | Sragen | -7.4019 | 110.8918 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1858 | Karangasem Tanon | Protelindo |  | Central Java Ring 43C | MA-YG3533239G-01H | 10.219.26.135 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-05 | 2 |  |  | 2026 | 2025-11-08 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1863_1 | Swap_JAW-JT-SGN-1863 | JAW-JT-SGN-1863 | Central Java | Jawa Tengah | Sragen | -7.4188 | 110.9122 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1863 | Sambirejo Plupuh | Centratama |  | Central Java Ring 43C | MA-YG3533325G-01H | 10.219.26.134 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-06 | 2 |  |  | 2026 | 2025-11-10 |  | In Progress |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-1852_1 | Swap_JAW-JT-SGN-1852 | JAW-JT-SGN-1852 | Central Java | Jawa Tengah | Sragen | -7.4233 | 110.845 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-1852 | BRANGKAL GEMOLONG | TBG |  | Central Java Ring 43C | MA-YG3534097G-01H | 10.219.26.140 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-06 | 2 |  |  | 2026 | 2025-11-08 |  | In Progress |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-3255_1 | Swap_JAW-JT-SGN-3255 | JAW-JT-SGN-3255 | Central Java | Jawa Tengah | Sragen | -7.3984 | 110.8386 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-3255 | Tegaldowo Gemolong | TBG |  | Central Java Ring 43C | MA-YG3535555G-01H | 10.219.26.137 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-06 | 2 |  |  | 2026 | 2025-11-08 | 2025-11-12 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SGN-3340_1 | Swap_JAW-JT-SGN-3340 | JAW-JT-SGN-3340 | Central Java | Jawa Tengah | Sragen | -7.4491 | 110.9195 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SGN-3340 | PRINGANOM MASARAN | Protelindo |  | Central Java Ring 43C | MA-YG3535608G-01H | 10.219.26.142 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GCI | 2026-01-06 | 2 |  |  | 2026 | 2025-11-09 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1480_1 | Swap_JAW-JT-PTI-1480 | JAW-JT-PTI-1480 | Central Java | Jawa Tengah | Pati | -6.7527 | 111.0354 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-PTI-1480 | Pati | Others |  | Central Java Ring 45 | PAG-SM2244-01H | 10.219.27.86 | NE40E(V8) | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 10 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-24 |  | In Progress |  |  | Submitted | Approved | Done |  | Done | Done | Done | DOEID251117NN | [8 empty] | YPTT | [14 empty] | 2025-11-26 | 48 | 2025-11-26 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1520_1 | Swap_JAW-JT-PTI-1520 | JAW-JT-PTI-1520 | Central Java | Jawa Tengah | Pati | -6.7188 | 111.1446 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-PTI-1520 | Juana | Protelindo |  | Central Java Ring 45 | PAG-SM2245-01H | 10.219.27.87 | NE40E(V8) | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 10 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-11-07 | 2025-10-24 | Approved | 2025-11-22 |  | Submitted | Approved | Done |  | Done | Done | Done | DOEID251117OB | [8 empty] | GPA | [14 empty] | 2025-11-26 | 48 | 2025-11-26 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1536_1 | Swap_JAW-JT-PTI-1536 | JAW-JT-PTI-1536 | Central Java | Jawa Tengah | Pati | -6.7228 | 111.128 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1536 | JUWANA BARAT RELOCATION | Protelindo |  | Central Java Ring 45F | MA-JTPTI1536-01H | 10.206.54.188 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-26 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID251117NP | 2025-11-23 | 2025-11-24 | Done | Done | Done | Done | Done | Done | YPTT |  | 1 | 2025-11-24 |  |  | XLWO-20251123-00000052 |  | 2025-11-24 | 2025-11-24 | 2025-11-24 |  |  |  |  | 2025-11-24 | 48 | 2025-11-24 | 2025-11-24 | Done | #N/A | #N/A |  | 2025-11-25
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1405_1 | Swap_JAW-JT-PTI-1405 | JAW-JT-PTI-1405 | Central Java | Jawa Tengah | Pati | -6.825 | 111.133 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1405 | TRIGUNO PUCAKWANGI | DMT |  | Central Java Ring 45F | MA-JTPTI1405-01H | 10.206.54.185 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-30 | 2025-10-30 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID251117NR | 2025-11-23 | 2025-11-24 | Done | Done | Done | Done | Done | Done | YPTT |  | 1 | 2025-11-24 |  |  | XLWO-20251123-00000052 |  | 2025-11-24 | 2025-11-24 | 2025-11-24 |  |  |  |  | 2025-11-24 | 48 | 2025-11-24 | 2025-11-24 | Done | #N/A | #N/A |  | 2025-11-25
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1406_1 | Swap_JAW-JT-PTI-1406 | JAW-JT-PTI-1406 | Central Java | Jawa Tengah | Pati | -6.7739 | 111.076 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1406 | KEDUNGMULYO JAKENAN | Protelindo |  | Central Java Ring 45F | MA-JTPTI1406-01H | 10.206.54.186 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-24 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID251117OD | 2025-11-23 | 2025-11-24 | Done | Done | Done | Done | Done | Done | GPA |  | 1 | 2025-11-24 |  |  | XLWO-20251123-00000052 |  | 2025-11-24 | 2025-11-24 | 2025-11-24 |  |  |  |  | 2025-11-24 | 48 | 2025-11-24 | 2025-11-24 | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1498_1 | Swap_JAW-JT-PTI-1498 | JAW-JT-PTI-1498 | Central Java | Jawa Tengah | Pati | -6.7836 | 111.0556 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1498 | Banjarsari Gabus Pati | Protelindo |  | Central Java Ring 45F | MA-JTPTI1498-01H | 10.206.54.182 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-24 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID251117O5 | 2025-11-23 | 2025-11-24 | Done | Done | Done | Done | Done | Done | GIT |  | 1 | 2025-11-24 |  |  | XLWO-20251123-00000052 |  | 2025-11-24 | 2025-11-24 | 2025-11-24 |  |  |  |  | 2025-11-24 | 48 | 2025-11-24 | 2025-11-24 | Done | #N/A | #N/A |  | 2025-11-25
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1508_1 | Swap_JAW-JT-PTI-1508 | JAW-JT-PTI-1508 | Central Java | Jawa Tengah | Pati | -6.8543 | 111.0789 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1508 | Angkatan Kidul Pati | TBG |  | Central Java Ring 45F | MA-JTPTI1508-01H | 10.206.54.184 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-24 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID251117O7 | 2025-11-23 | 2025-11-24 | Done | Done | Done | Done | Done | Done | GIT |  | 1 | 2025-11-24 |  |  | XLWO-20251123-00000052 |  | 2025-11-24 | 2025-11-24 | 2025-11-24 |  |  |  |  | 2025-11-24 | 48 | 2025-11-24 | 2025-11-24 | Done | #N/A | #N/A |  | 2025-11-25
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1514_1 | Swap_JAW-JT-PTI-1514 | JAW-JT-PTI-1514 | Central Java | Jawa Tengah | Pati | -6.7705 | 111.113 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1514 | Tambahmulyo Jakenan | DMT |  | Central Java Ring 45F | MA-JTPTI1514-01H | 10.206.54.187 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-24 | 2025-10-30 | Approved | 2025-11-07 |  | Submitted | Approved | Done |  | Done | Done | Done | DOEID251117K7 | 2025-11-23 | 2025-11-24 |  |  | Done |  | Done | 2.0. Permit Done | Mingze | 2025-11-25 |  | 2025-11-25 | [11 empty] | 2025-11-25 | 48 | 2025-11-25 |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-3325_1 | Swap_JAW-JT-PTI-3325 | JAW-JT-PTI-3325 | Central Java | Jawa Tengah | Pati | -6.854 | 111.0558 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-3325 | Angkatan Lor Tambakromo | Protelindo |  | Central Java Ring 45F | MA-JTPTI3325-01H | 10.206.54.183 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 10 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-24 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | Done |  | Done | Done | Done | DOEID251117K9 | 2025-11-23 | 2025-11-24 |  |  | Done |  | Done | 2.0. Permit Done | Mingze | 2025-11-25 |  | 2025-11-25 | [11 empty] | 2025-11-25 | 48 | 2025-11-25 |  | Done | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-DMK-0612_2 | Swap_JAW-JT-DMK-0612 | JAW-JT-DMK-0612 | Central Java | Jawa Tengah | Demak | -6.8503 | 110.8054 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-DMK-0612 | Karanganyar Demak | Centratama |  | Central Java Ring 46 | PAG-SM2395-03H | 10.206.7.235 | NE40E(V8) | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 6 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2026 | On Schedule Swap | GPA | 2025-10-16 | 42 | October |  | 2026 |  |  | Not Started |  |  | Submitted | Approved | Done |  | Done | Done | Done | DOEID25111411 | 2025-11-23 | [7 empty] | GPA | 2025-11-23 | 47 | [5 empty] | 2025-11-26 |  | 2025-11-26 | 48 | 2025-11-26 | 48 | TRUE | 2025-11-20 | 47 | 2025-11-20 |  | NY | #N/A | #N/A | November
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0925_1 | Swap_JAW-JT-KDS-0925 | JAW-JT-KDS-0925 | Central Java | Jawa Tengah | Kudus | -6.8057 | 110.8798 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-KDS-0925 | Ngembal Kulon | Centratama |  | Central Java Ring 46 | PAG-SMBC35-01H | 10.206.7.241 | NE40E(V8) | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 6 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2026 | On Schedule Swap | GIT | 2026-01-08 | 2 |  |  | 2026 | 2025-11-13 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | Done |  | Done | Done | Done | DOEID25111413 | 2025-11-23 | [7 empty] | GPA | 2025-11-23 | 47 | [5 empty] | 2025-11-26 |  | 2025-11-26 | 48 | 2025-11-26 | 48 | TRUE | 2025-11-20 | 47 | 2025-11-20 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0917_1 | Swap_JAW-JT-KDS-0917 | JAW-JT-KDS-0917 | Central Java | Jawa Tengah | Kudus | -6.8079 | 110.8631 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0917 | Rendeng Kudus | Protelindo |  | Central Java Ring 46E | MA-SM2534241-01H | 10.206.7.155 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 6 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-14 | 2025-11-14 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-19 |  | Done | Done | Done | DOEID25111415 | 2025-11-23 | 2025-11-20 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-23 | 47 | 2025-11-20 |  |  | XLWO-20251112-00000910 |  | 2025-11-26 | 2025-11-20 | 2025-11-26 | 48 | 2025-11-26 | 48 | TRUE | 2025-11-20 | 47 | 2025-11-20 | 2025-11-20 | Done | #N/A | #N/A | November | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-KDS-2020_1 | Swap_JAW-JT-KDS-2020 | JAW-JT-KDS-2020 | Central Java | Jawa Tengah | Kudus | -6.7987 | 110.8136 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-2020 | KARANGAMPEL KUDUS Relocation | Others |  | Central Java Ring 46E | MA-SM2535018-01H | 10.206.7.254 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 6 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-11 | 2025-11-14 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-19 |  | Done | Done | Done | DOEID25111417 | 2025-11-23 | 2025-11-20 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-23 | 47 | 2025-11-20 |  |  | XLWO-20251112-00000910 |  | 2025-11-26 | 2025-11-20 | 2025-11-26 | 48 | 2025-11-26 | 48 | TRUE | 2025-11-20 | 47 | 2025-11-20 | 2025-11-20 | Done | #N/A | #N/A | November | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0887_1 | Swap_JAW-JT-KDS-0887 | JAW-JT-KDS-0887 | Central Java | Jawa Tengah | Kudus | -6.8034 | 110.826 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0887 | Prambatan Kudus | TBG |  | Central Java Ring 46E | MA-SM253A286-01H | 10.206.8.134 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 6 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-11 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-19 |  | Done | Done | Done | DOEID25111418 | 2025-11-23 | 2025-11-20 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-23 | 47 | 2025-11-20 |  |  | XLWO-20251112-00000910 |  | 2025-11-26 | 2025-11-20 | 2025-11-26 | 48 | 2025-11-26 | 48 | TRUE | 2025-11-20 | 47 | 2025-11-20 | 2025-11-20 | Done | #N/A | #N/A | November | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0908_1 | Swap_JAW-JT-KDS-0908 | JAW-JT-KDS-0908 | Central Java | Jawa Tengah | Kudus | -6.8039 | 110.8486 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0908 | Diponegoro Ngangguk (Collocated Protelindo) | Protelindo |  | Central Java Ring 46E | MA-SM253EH79-01H | 10.206.7.154 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 6 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-11 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-19 |  | Done | Done | Done | DOEID25111446 | 2025-11-23 | 2025-11-20 | Done | Done | Done | Done | Done | Done | GIT | 2025-11-23 | 47 | 2025-11-20 |  |  | XLWO-20251112-00000910 |  | 2025-11-26 | 2025-11-20 | 2025-11-26 | 48 | 2025-11-26 | 48 | TRUE | 2025-11-20 | 47 | 2025-11-20 | 2025-11-20 | Done | #N/A | #N/A | November | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0878_1 | Swap_JAW-JT-KDS-0878 | JAW-JT-KDS-0878 | Central Java | Jawa Tengah | Kudus | -6.7999 | 110.7867 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0878 | Kedungdowo Kaliwungu | DMT |  | Central Java Ring 46E | MA-SM3533373G-01H | 10.206.7.252 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 6 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2026-01-09 | 2 |  |  | 2026 | 2025-11-11 | 2025-11-19 | Approved | 2025-11-22 |  | Submitted | Approved | 2025-11-19 |  | Done | Done | Done | DOEID25111448 | 2025-11-23 | 2025-11-20 | Done | Done | Done | Done | Done | Done | GIT | 2025-11-23 | 47 | 2025-11-20 |  |  | XLWO-20251112-00000910 |  | 2025-11-26 | 2025-11-20 | 2025-11-26 | 48 | 2025-11-26 | 48 | TRUE | 2025-11-20 | 47 | 2025-11-20 | 2025-11-20 | Done | #N/A | #N/A | November | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0879_1 | Swap_JAW-JT-KDS-0879 | JAW-JT-KDS-0879 | Central Java | Jawa Tengah | Kudus | -6.7892 | 110.7944 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0879 | Kaliwungu Kudus | Centratama |  | Central Java Ring 46E | MA-SMBD84-01H | 10.206.7.253 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 6 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2026-01-12 | 3 |  |  | 2026 | 2025-11-11 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-19 |  | Done | Done | Done | DOEID25111435 | 2025-11-23 | 2025-11-20 | Done | Done | Done | Done | Done | Done | Mingze | 2025-11-23 | 47 | 2025-11-20 |  |  | XLWO-20251112-00000910 |  | 2025-11-26 | 2025-11-20 | 2025-11-26 | 48 | 2025-11-26 | 48 | TRUE | 2025-11-20 | 47 | 2025-11-20 | 2025-11-20 | Done | #N/A | #N/A | November | 2025-11-25
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0902_1 | Swap_JAW-JT-KDS-0902 | JAW-JT-KDS-0902 | Central Java | Jawa Tengah | Kudus | -6.8084 | 110.8422 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0902 | Ramayana Kudus | DHOST |  | Central Java Ring 46E | MA-SMPX271-01H | 10.206.7.255 | ATN910C-F | Huawei | New Purchase | Swap impact Stitch | Keep | 6 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2026-01-12 | 3 |  |  | 2026 | 2025-11-11 | 2025-11-19 | Approved | 2025-11-22 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID25111436 | 2025-11-23 | 2025-11-23 | Done | Done | Done | Done | Done | Done | Mingze | 2025-11-23 | 47 | 2025-11-21 |  | 2025-11-21 | XLWO-20251112-00001200 |  | 2025-11-26 | 2025-11-23 | 2025-11-26 | 48 | 2025-11-26 | 48 | TRUE | 2025-11-23 | 47 | 2025-11-20 | 2025-11-23 | Done | #N/A | #N/A | November | 2025-11-25
1 | 3 | CLEAR | Swap_JAW-JT-BNR-0237_3 | Swap_JAW-JT-BNR-0237 | JAW-JT-BNR-0237 | Central Java | Jawa Tengah | Banjarnegara | -7.396 | 109.697 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-BNR-0237 | Banjarnegara | Protelindo |  | Central Java Ring 52 | PAG-SM2342-04H | 10.206.1.27 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | CCSI | 2026-01-12 | 3 |  |  | 2026 | 2025-10-29 | 2025-10-29 | Approved | 2025-11-07 | [34 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KBM-0770_1 | Swap_JAW-JT-KBM-0770 | JAW-JT-KBM-0770 | Central Java | Jawa Tengah | Kebumen | -7.7234 | 109.794 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-KBM-0770 | Mpls - Prembun | Protelindo |  | Central Java Ring 52 | PAG-YG2282-03H | 10.206.1.26 | ATN910C-B | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-12 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KDL-0797_1 | Swap_JAW-JT-KDL-0797 | JAW-JT-KDL-0797 | Central Java | Jawa Tengah | Kendal | -6.9708 | 110.0789 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-KDL-0797 | Mpls - Weleri | Centratama |  | Central Java Ring 54 | PAG-SM2303-01H | 10.206.0.30 | NE40E(V8) | Huawei | New Purchase | New Ring 001 | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2025-624 sites | Plan Swap December | GPA | 2025-11-10 | 46 |  |  | 2026 | 2025-10-30 | 2025-10-30 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-1137_1 | Swap_JAW-JT-KRG-1137 | JAW-JT-KRG-1137 | Central Java | Jawa Tengah | Karanganyar | -7.6186 | 111.0751 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-KRG-1137 | Karangpandan | Protelindo |  | Central Java Ring 56 | PAG-SM2473-01H | 10.206.1.41 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-13 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-2019_1 | Swap_JAW-JT-SKH-2019 | JAW-JT-SKH-2019 | Central Java | Jawa Tengah | Sukoharjo | -7.5817 | 110.9032 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-SKH-2019 | Jaten Karanganyar | Protelindo |  | Central Java Ring 56 | PAG-SMCH90-03H | 10.206.1.40 | ATN910C-B | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-13 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-1090_1 | Swap_JAW-JT-KRG-1090 | JAW-JT-KRG-1090 | Central Java | Jawa Tengah | Karanganyar | -7.5189 | 110.9081 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-1090 | Kebak Kramat Relocation | DMT |  | Central Java Ring 56E | MA-JTKRG1090-01H | 10.206.27.61 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-13 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-1098_1 | Swap_JAW-JT-KRG-1098 | JAW-JT-KRG-1098 | Central Java | Jawa Tengah | Karanganyar | -7.5534 | 110.9379 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-1098 | Kalijirak | Centratama |  | Central Java Ring 56E | MA-JTKRG1098-01H | 10.206.27.68 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-13 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-1126_1 | Swap_JAW-JT-KRG-1126 | JAW-JT-KRG-1126 | Central Java | Jawa Tengah | Karanganyar | -7.5731 | 111.0233 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-1126 | Kecamatan Mojogedang | Protelindo |  | Central Java Ring 56E | MA-JTKRG1126-01H | 10.206.27.64 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-13 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-2142_1 | Swap_JAW-JT-KRG-2142 | JAW-JT-KRG-2142 | Central Java | Jawa Tengah | Karanganyar | -7.5451 | 110.975 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-2142 | KALIBOTO MOJOGEDANG KARANGANYAR | DMT |  | Central Java Ring 56E | MA-JTKRG2142-01H | 10.206.27.63 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-14 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KRG-2146_1 | Swap_JAW-JT-KRG-2146 | JAW-JT-KRG-2146 | Central Java | Jawa Tengah | Karanganyar | -7.5544 | 110.9914 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KRG-2146 | MOJOGEDANG RELOCATION | Protelindo |  | Central Java Ring 56E | MA-JTKRG2146-01H | 10.206.27.69 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Propose Drop, MOCN Drop |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-14 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-YO-WAT-0365_1 | Swap_JAW-YO-WAT-0365 | JAW-YO-WAT-0365 | Central Java | Daerah Istimewa Yogyakarta | Kulon Progo | -7.8573 | 110.1609 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-YO-WAT-0365 | Mpls - Wates | Protelindo |  | Central Java Ring 58 | PAG-YG2280-04H | 10.206.0.161 | ATN910C-B | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-14 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-KBM-0770_2 | Swap_JAW-JT-KBM-0770 | JAW-JT-KBM-0770 | Central Java | Jawa Tengah | Kebumen | -7.7234 | 109.794 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-KBM-0770 | Mpls - Prembun | Protelindo |  | Central Java Ring 58 | PAG-YG2282-02H | 10.206.0.160 | ATN910C-G | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-14 | 3 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0101_1 | Swap_JAW-JT-BBS-0101 | JAW-JT-BBS-0101 | Central Java | Jawa Tengah | Brebes | -7.2491 | 109.0068 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-BBS-0101 | Bumiayu | Centratama |  | Central Java Ring 70 | PAG-SM2340-01H | 10.206.1.99 | NE40E(V8) | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-11-10 | 46 |  |  | 2026 | 2025-10-29 | 2025-10-29 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-BBS-0076_1 | Swap_JAW-JT-BBS-0076 | JAW-JT-BBS-0076 | Central Java | Jawa Tengah | Brebes | -6.9406 | 108.944 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-BBS-0076 | Slatri Brebes | Others |  | Central Java Ring 70 | PAG-SM2532932-01H | 10.206.1.98 | NE40E(V8) | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-11-10 | 46 |  |  | 2026 | 2025-11-07 | 2025-11-07 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-1037_1 | Swap_JAW-JT-KLN-1037 | JAW-JT-KLN-1037 | Central Java | Jawa Tengah | Klaten | -7.6918 | 110.6409 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-KLN-1037 | Klaten | Protelindo |  | Central Java Ring 72 | PAG-YG2231-01H | 10.219.27.149 | ATN910C-F | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-15 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KLN-0989_1 | Swap_JAW-JT-KLN-0989 | JAW-JT-KLN-0989 | Central Java | Jawa Tengah | Klaten | -7.7508 | 110.5159 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-KLN-0989 | Prambanan | Protelindo |  | Central Java Ring 72 | PAG-YG2232-01H | 10.219.27.148 | ATN910C-B | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-15 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PWT-1773_1 | Swap_JAW-JT-PWT-1773 | JAW-JT-PWT-1773 | Central Java | Jawa Tengah | Banyumas | -7.4028 | 109.2861 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-PWT-1773 | Kembaran | Centratama |  | Central Java Ring 83 | PAG-JTPWT1773-03H | 10.206.28.210 | ATN910C | Huawei | New Purchase | Linknet NNI,PAG1 | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-17 | 42 | October | Oct | 2026 | 2025-10-18 | 2025-10-18 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-10-22 |  | 2025-10-20 | 2025-10-21 | 2025-10-21 | DOEID251021MR |  | 2025-10-22 | 2025-10-20 | 2025-10-20 | done | 2025-10-21 | 2025-10-22 | done | GPA |  |  | 2025-10-22 | 2025-10-20 | 2025-10-23 | XLWO-20251023-00000400 | RFC-20251023-00000264 | 2025-10-29 | 2025-11-05 | 2025-10-29 | [6 empty] | #N/A | 2025-11-05 | Done | #N/A | #N/A |  | 2025-11-05 |  | 2025-11-15
1 | 2 | CLEAR | Swap_JAW-JT-PWT-1716_2 | Swap_JAW-JT-PWT-1716 | JAW-JT-PWT-1716 | Central Java | Jawa Tengah | Banyumas | -7.4218 | 109.2214 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-PWT-1716 | Mpls - Purwokerto | Direct Lease |  | Central Java Ring 83 | PAG-JTPWT1716-05H | 10.206.28.211 | ATN910C | Huawei | New Purchase | Linknet NNI,PAG2 | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-17 | 42 | October | Oct | 2026 | 2025-10-17 | 2025-10-20 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-10-22 | Need 15m Power Cable | 2025-10-20 | 2025-10-21 | 2025-10-21 | DOEID251021MR |  | 2025-10-22 | 2025-10-20 | 2025-10-20 | done | 2025-10-21 | 2025-10-22 | done | GPA |  |  | 2025-10-22 | 2025-10-20 | 2025-10-23 | XLWO-20251023-00000400 | RFC-20251023-00000264 |  | 2025-10-27 | [7 empty] | #N/A | 2025-10-27 | Done | #N/A | #N/A |  | 2025-10-29 |  | 2025-11-15
1 | 3 | CLEAR | Swap_JAW-JT-DMK-0612_3 | Swap_JAW-JT-DMK-0612 | JAW-JT-DMK-0612 | Central Java | Jawa Tengah | Demak | -6.8503 | 110.8054 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-DMK-0612 | Karanganyar Demak | Centratama |  | Central Java Ring 87 | PAG-JTDMK0612-03H | 10.206.29.173 | ATN910C | Huawei | New Purchase | HRAN Upgrade | Keep | 9 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2026 | Plan Swap December | GPA | 2025-10-16 | 42 | October |  | 2026 |  |  | Not Started | [23 empty] | XLWO-20251023-00000401 | [11 empty] | #N/A |  | NY | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-PTI-1480_2 | Swap_JAW-JT-PTI-1480 | JAW-JT-PTI-1480 | Central Java | Jawa Tengah | Pati | -6.7527 | 111.0354 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-PTI-1480 | Pati | Others |  | Central Java Ring 87 | PAG-JTPTI1480-02H | 10.206.29.174 | ATN910C | Huawei | New Purchase | HRAN Upgrade | Keep | 9 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-24 |  | In Progress | [35 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0888_1 | Swap_JAW-JT-KDS-0888 | JAW-JT-KDS-0888 | Central Java | Jawa Tengah | Kudus | -6.9344 | 110.8272 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0888 | Kutuk Kidul Pati | Protelindo |  | Central Java Ring 87A | MA-JTKDS0888-01H | 10.206.29.177 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 9 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | Plan Swap December |  | 2026-01-16 | 3 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1407_1 | Swap_JAW-JT-PTI-1407 | JAW-JT-PTI-1407 | Central Java | Jawa Tengah | Pati | -6.9384 | 110.8854 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1407 | SUKOLILO BALEADI | Centratama |  | Central Java Ring 87A | MA-JTPTI1407-01H | 10.206.29.179 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 9 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-26 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-3349_1 | Swap_JAW-JT-PTI-3349 | JAW-JT-PTI-3349 | Central Java | Jawa Tengah | Pati | -6.787 | 111.0169 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-3349 | Penambuhan Martgorejo | Protelindo |  | Central Java Ring 87A | MA-JTPTI3349-01H | 10.206.29.182 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 9 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-23 | 2025-10-23 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0884_1 | Swap_JAW-JT-KDS-0884 | JAW-JT-KDS-0884 | Central Java | Jawa Tengah | Kudus | -6.8836 | 110.8171 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0884 | Undaan Lor Undaan | TBG |  | Central Java Ring 87A | MA-JTKDS0884-01H | 10.206.29.175 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 9 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | Plan Swap December |  | 2026-01-19 | 4 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1403_1 | Swap_JAW-JT-PTI-1403 | JAW-JT-PTI-1403 | Central Java | Jawa Tengah | Pati | -6.9646 | 110.8298 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1403 | PRAWOTO | Centratama |  | Central Java Ring 87A | MA-JTPTI1403-01H | 10.206.29.178 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 9 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-26 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1419_1 | Swap_JAW-JT-PTI-1419 | JAW-JT-PTI-1419 | Central Java | Jawa Tengah | Pati | -6.9515 | 110.9547 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1419 | NURUL SALAM | TBG |  | Central Java Ring 87A | MA-JTPTI1419-01H | 10.206.29.180 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 9 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-26 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-PTI-1468_1 | Swap_JAW-JT-PTI-1468 | JAW-JT-PTI-1468 | Central Java | Jawa Tengah | Pati | -6.8361 | 111.0118 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1468 | Sundoluhur Pati | Protelindo |  | Central Java Ring 87A | MA-JTPTI1468-01H | 10.206.29.181 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 9 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-24 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KDS-3476_1 | Swap_JAW-JT-KDS-3476 | JAW-JT-KDS-3476 | Central Java | Jawa Tengah | Kudus | -6.9135 | 110.8246 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-3476 | Undaan Kudus Relocation | Protelindo |  | Central Java Ring 87A | MA-JTKDS3476-01H | 10.206.29.176 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 9 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | Plan Swap December |  | 2026-01-19 | 4 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-KDS-0925_2 | Swap_JAW-JT-KDS-0925 | JAW-JT-KDS-0925 | Central Java | Jawa Tengah | Kudus | -6.8057 | 110.8798 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-KDS-0925 | Ngembal Kulon | Centratama |  | Central Java Ring 88 | PAG-JTKDS0925-02H | 10.206.29.190 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 7 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2026 | On Schedule Swap | GIT | 2026-01-20 | 4 |  |  | 2026 | 2025-11-13 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | Done |  | Done | Done | Done | DOEID25111420 | 2025-11-24 | [7 empty] | GPA | 2025-11-24 | 48 | [5 empty] | 2025-11-27 |  | 2025-11-27 | 48 | 2025-11-27 | 48 | TRUE | 2025-11-26 | 48 | 2025-11-26 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0942_1 | Swap_JAW-JT-KDS-0942 | JAW-JT-KDS-0942 | Central Java | Jawa Tengah | Kudus | -6.7958 | 110.9612 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-KDS-0942 | Jekulo | Protelindo |  | Central Java Ring 88 | PAG-JTKDS0942-01H | 10.206.29.191 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 7 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2026 | On Schedule Swap | GIT | 2026-01-20 | 4 |  |  | 2026 | 2025-11-12 | 2025-11-14 | Approved | 2025-11-17 |  | Submitted | Approved | Done |  | Done | Done | Done | DOEID25111422 | 2025-11-24 | [7 empty] | GPA | 2025-11-24 | 48 | [5 empty] | 2025-11-27 |  | 2025-11-27 | 48 | 2025-11-27 | 48 | TRUE | 2025-11-26 | 48 | 2025-11-26 |  | Done | #N/A | #N/A | November
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0856_1 | Swap_JAW-JT-KDS-0856 | JAW-JT-KDS-0856 | Central Java | Jawa Tengah | Kudus | -6.8163 | 110.9457 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0856 | SIDOMULYO JEKULO | DMT |  | Central Java Ring 88A | MA-JTKDS0856-01H | 10.206.29.203 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2026-01-20 | 4 |  |  | 2026 | 2025-11-13 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-21 |  | Done | Done | Done | DOEID25111456 | 2025-11-24 | 2025-11-21 | done | done | done | done | done | done | YPTT | 2025-11-24 | 48 | 2025-11-21 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-27 | 2025-11-21 | 2025-11-27 | 48 | 2025-11-27 | 48 | TRUE | 2025-11-21 | 47 | 2025-11-21 | 2025-11-21 | Done | #N/A | #N/A | November | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0861_1 | Swap_JAW-JT-KDS-0861 | JAW-JT-KDS-0861 | Central Java | Jawa Tengah | Kudus | -6.8188 | 110.9212 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0861 | BULUNGCANGKRING JEKULO | DMT |  | Central Java Ring 88A | MA-JTKDS0861-01H | 10.206.29.201 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2026-01-20 | 4 |  |  | 2026 | 2025-11-12 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-21 |  | Done | Done | Done | DOEID25111457 | 2025-11-24 | 2025-11-21 | done | done | done | done | done | done | YPTT | 2025-11-24 | 48 | 2025-11-21 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-27 | 2025-11-21 | 2025-11-27 | 48 | 2025-11-27 | 48 | TRUE | 2025-11-21 | 47 | 2025-11-21 | 2025-11-21 | Done | #N/A | #N/A | November | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0940_1 | Swap_JAW-JT-KDS-0940 | JAW-JT-KDS-0940 | Central Java | Jawa Tengah | Kudus | -6.821 | 110.933 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0940 | Bulung Kulon Jekulo | TBG |  | Central Java Ring 88A | MA-JTKDS0940-01H | 10.206.29.202 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2026-01-20 | 4 |  |  | 2026 | 2025-11-12 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-21 |  | Done | Done | Done | DOEID25111438 | 2025-11-24 | 2025-11-21 | done | done | done | done | done | done | Mingze | 2025-11-24 | 48 | 2025-11-21 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-27 | 2025-11-21 | 2025-11-27 | 48 | 2025-11-27 | 48 | TRUE | 2025-11-21 | 47 | 2025-11-21 | 2025-11-21 | Done | #N/A | #N/A | November | 2025-11-25
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0859_1 | Swap_JAW-JT-KDS-0859 | JAW-JT-KDS-0859 | Central Java | Jawa Tengah | Kudus | -6.8036 | 110.8699 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0859 | PANGLIMA BESAR DERSALAM | Protelindo |  | Central Java Ring 88A | MA-JTKDS0859-01H | 10.206.29.193 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2026-01-21 | 4 |  |  | 2026 | 2025-11-12 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID25111440 | 2025-11-24 | 2025-11-23 | Done | Done | Done | Done | Done | Done | Mingze | 2025-11-24 | 48 | 2025-11-21 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-27 | 2025-11-23 | 2025-11-27 | 48 | 2025-11-27 | 48 | TRUE | 2025-11-23 | 47 | 2025-11-23 | 2025-11-23 | Done | #N/A | #N/A | November | 2025-11-25
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0860_1 | Swap_JAW-JT-KDS-0860 | JAW-JT-KDS-0860 | Central Java | Jawa Tengah | Kudus | -6.7815 | 110.8763 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0860 | KAYUAPU WETAN BAE | Others |  | Central Java Ring 88A | MA-JTKDS0860-01H | 10.206.29.192 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2026-01-21 | 4 |  |  | 2026 | 2025-11-13 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID251113PH | 2025-11-24 | 2025-11-23 | Done | Done | Done | Done | Done | Done | GCI | 2025-11-24 | 48 | 2025-11-21 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-27 | 2025-11-23 | 2025-11-27 | 48 | 2025-11-27 | 48 | TRUE | 2025-11-23 | 47 | 2025-11-23 | 2025-11-23 | Done | #N/A | #N/A | November | 2025-11-24
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0857_1 | Swap_JAW-JT-KDS-0857 | JAW-JT-KDS-0857 | Central Java | Jawa Tengah | Kudus | -6.8285 | 110.9132 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0857 | JEKULO RAYA SADANG | DMT |  | Central Java Ring 88A | MA-JTKDS0857-01H | 10.206.29.200 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2026-01-21 | 4 |  |  | 2026 | 2025-11-12 | 2025-11-14 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-21 |  | Done | Done | Done | DOEID25111449 | 2025-11-27 | 2025-11-21 | done | done | done | done | done | done | GIT | 2025-11-27 | 48 | 2025-11-21 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-30 | 2025-11-21 | 2025-11-30 | 48 | 2025-11-30 | 48 | TRUE | 2025-11-21 | 47 | 2025-11-21 | 2025-11-21 | Done | #N/A | #N/A | November | 2025-11-24
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0863_1 | Swap_JAW-JT-KDS-0863 | JAW-JT-KDS-0863 | Central Java | Jawa Tengah | Kudus | -6.8384 | 110.8682 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0863 | GULANG KULON MEJOBO | DMT |  | Central Java Ring 88A | MA-JTKDS0863-01H | 10.206.29.199 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2026-01-21 | 4 |  |  | 2026 | 2025-11-11 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-21 |  | Done | Done | Done | DOEID25111451 | 2025-11-27 | 2025-11-21 | done | done | done | done | done | done | GIT | 2025-11-27 | 48 | 2025-11-21 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-30 | 2025-11-21 | 2025-11-30 | 48 | 2025-11-30 | 48 | TRUE | 2025-11-21 | 47 | 2025-11-21 | 2025-11-21 | Done | #N/A | #N/A | November | 2025-11-24
1 | 1 | CLEAR | Swap_JAW-JT-KDS-0907_1 | Swap_JAW-JT-KDS-0907 | JAW-JT-KDS-0907 | Central Java | Jawa Tengah | Kudus | -6.8361 | 110.8479 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0907 | LORAM KULON JATI | TBG |  | Central Java Ring 88A | MA-JTKDS0907-01H | 10.206.29.197 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2026-01-21 | 4 |  |  | 2026 | 2025-11-11 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-21 |  | Done | Done | Done | DOEID25111458 | 2025-11-27 | 2025-11-21 | done | done | done | done | done | done | YPTT | 2025-11-27 | 48 | 2025-11-21 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-30 | 2025-11-21 | 2025-11-30 | 48 | 2025-11-30 | 48 | TRUE | 2025-11-21 | 47 | 2025-11-21 | 2025-11-21 | Done | #N/A | #N/A | November | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-KDS-3101_1 | Swap_JAW-JT-KDS-3101 | JAW-JT-KDS-3101 | Central Java | Jawa Tengah | Kudus | -6.8314 | 110.8518 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-3101 | MEJOBO KUDUS RELOCATION | TBG |  | Central Java Ring 88A | MA-JTKDS3101-01H | 10.206.29.198 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2026-01-22 | 4 |  |  | 2026 | 2025-11-11 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID25111460 | 2025-11-21 | 2025-11-24 | done | done | done | done | done | done | YPTT | 2025-11-21 | 47 | 2025-11-24 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-24 | 2025-11-24 | 2025-11-30 | 48 | 2025-11-30 | 48 | TRUE | 2025-11-24 | 48 | 2025-11-24 | 2025-11-24 | Done | #N/A | #N/A | November | 2025-11-25
1 | 1 | CLEAR | Swap_JAW-JT-KDS-3183_1 | Swap_JAW-JT-KDS-3183 | JAW-JT-KDS-3183 | Central Java | Jawa Tengah | Kudus | -6.8249 | 110.8381 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-3183 | GETASPEJATEN JATI | DMT |  | Central Java Ring 88A | MA-JTKDS3183-01H | 10.206.29.196 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2026-01-22 | 4 |  |  | 2026 | 2025-11-11 | 2025-11-13 | Approved | 2025-11-17 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID25111441 | 2025-11-27 | 2025-11-23 | Done | Done | Done | Done | Done | Done | Mingze | 2025-11-27 | 48 | 2025-11-21 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-30 | 2025-11-23 | 2025-11-30 | 48 | 2025-11-30 | 48 | TRUE | 2025-11-23 | 47 | 2025-11-23 | 2025-11-23 | Done | #N/A | #N/A | November
1 | 1 | CLEAR | Swap_JAW-JT-KDS-3449_1 | Swap_JAW-JT-KDS-3449 | JAW-JT-KDS-3449 | Central Java | Jawa Tengah | Kudus | -6.8042 | 110.8565 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-3449 | Jl Candi Prambanan Timur (Tol Manyaran) | TBG |  | Central Java Ring 88A | MA-JTKDS3449-01H | 10.206.29.194 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 7 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GIT | 2026-01-22 | 4 |  |  | 2026 | 2025-11-19 | 2025-11-19 | Approved | 2025-11-22 |  | Submitted | Approved | 2025-11-23 |  | Done | Done | Done | DOEID25111442 | 2025-11-27 | 2025-11-23 | Done | Done | Done | Done | Done | Done | Mingze | 2025-11-27 | 48 | 2025-11-21 |  | 2025-11-12 | XLWO-20251112-00001199 |  | 2025-11-30 | 2025-11-23 | 2025-11-30 | 48 | 2025-11-30 | 48 | TRUE | 2025-11-23 | 47 | 2025-11-23 | 2025-11-23 | Done | #N/A | #N/A | November | 2025-11-25
1 | 2 | CLEAR | Swap_JAW-JT-DMK-0552_2 | Swap_JAW-JT-DMK-0552 | JAW-JT-DMK-0552 | Central Java | Jawa Tengah | Demak | -7.0276 | 110.5174 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-DMK-0552 | Mranggen | TBG | IBS¦NO TP ID | Central Java Ring 91 | PAG-JTDMK0552-02H | 10.206.27.97 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 1 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-10-24 | 43 | October |  | 2026 | 2025-10-31 | 2025-10-31 | Approved | 2025-11-07 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110259 | 2025-11-02 | 2025-11-04 | done | done | done | done | done | done | Mingze | 2025-11-02 | 44 | 2025-11-04 | 2025-11-01 | 2025-11-03 | XLWO-20251103-00002369 |  | 2025-11-05 | 2025-11-06 | 2025-11-05 | 45 | 2025-11-06 | 45 | FALSE | 2025-11-06 | 45 | 2025-11-06 | 2025-11-06 | Done | #N/A | #N/A | November | 2025-11-08 |  | 2025-11-15
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0602_1 | Swap_JAW-JT-DMK-0602 | JAW-JT-DMK-0602 | Central Java | Jawa Tengah | Demak | -6.8738 | 110.7173 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-DMK-0602 | Mpls - Gajah | Protelindo | PRT¦JAW-JT-DMK-0602 | Central Java Ring 91 | PAG-SM2395-02H | 10.206.27.98 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 1 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-11-03 | 45 |  |  | 2026 | 2025-10-12 | 2025-10-13 | Approved | 2025-11-07 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110263 | 2025-11-02 | 2025-11-04 | done | done | done | done | done | done | GPA | 2025-11-02 | 44 | 2025-11-04 | 2025-11-01 | 2025-11-03 | XLWO-20251103-00002369 |  | 2025-11-05 | 2025-11-06 | 2025-11-05 | 45 | 2025-11-06 | 45 | FALSE | 2025-11-06 | 45 | 2025-11-06 | 2025-11-06 | Done | #N/A | #N/A | November | 2025-11-20 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0547_1 | Swap_JAW-JT-DMK-0547 | JAW-JT-DMK-0547 | Central Java | Jawa Tengah | Demak | -6.9916 | 110.5118 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0547 | BRUMBUNG MRANGGEN | DMT | DMT¦M00-JT-65441 | Central Java Ring 91B | MA-JTDMK0547-01H | 10.206.27.108 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-11-03 | 45 |  |  | 2026 | 2025-10-24 | 2025-10-25 | Approved | 2025-11-07 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110219 | 2025-11-03 | 2025-11-06 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-03 | 45 | 2025-11-06 | 2025-11-03 | 2025-11-05 | XLWO-20251105-00000156 |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | 45 | 2025-11-06 | 45 | TRUE | 2025-11-06 | 45 | 2025-11-06 | 2025-11-06 | Done | #N/A | #N/A | November | 2025-11-15 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0549_1 | Swap_JAW-JT-DMK-0549 | JAW-JT-DMK-0549 | Central Java | Jawa Tengah | Demak | -7.0532 | 110.5066 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0549 | Kebonrojo | Centratama | ISAT¦14SMG112 | Central Java Ring 91B | MA-JTDMK0549-01H | 10.206.27.106 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-11-03 | 45 |  |  | 2026 | 2025-10-23 | 2025-10-29 | Approved | 2025-11-07 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110221 | 2025-11-03 | 2025-11-06 | Done | Done | Done | Done | Done | Done | GPA | 2025-11-03 | 45 | 2025-11-06 | 2025-11-03 | 2025-11-05 | XLWO-20251105-00000156 |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | 45 | 2025-11-06 | 45 | TRUE | 2025-11-06 | 45 | 2025-11-06 | 2025-11-06 | Done | #N/A | #N/A | November | 2025-11-15 |  | 2025-11-22
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0558_1 | Swap_JAW-JT-DMK-0558 | JAW-JT-DMK-0558 | Central Java | Jawa Tengah | Demak | -7.0289 | 110.5322 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0558 | Kembang Arum Mranggen C-Prtd | Protelindo | PRT¦JAW-CJV-0273-H-P | Central Java Ring 91B | MA-JTDMK0558-01H | 10.206.27.107 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-11-03 | 45 |  |  | 2026 | 2025-10-26 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110238 | 2025-11-03 | 2025-11-05 | done | done | done | Done | done | done | Mingze | 2025-11-03 | 45 | 2025-11-05 | 2025-11-03 | 2025-11-05 | XLWO-20251105-00000156 |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | 45 | 2025-11-06 | 45 | TRUE | 2025-11-06 | 45 | 2025-11-06 | 2025-11-06 | Done | #N/A | #N/A | November | 2025-11-09 |  | 2025-11-15
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0559_1 | Swap_JAW-JT-DMK-0559 | JAW-JT-DMK-0559 | Central Java | Jawa Tengah | Demak | -6.9324 | 110.534 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0559 | Gemulak Sayung | Protelindo | PRT¦JAW-CJV-0459-H-P | Central Java Ring 91B | MA-JTDMK0559-01H | 10.206.27.110 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-11-03 | 45 |  |  | 2026 | 2025-10-25 | 2025-10-26 | Approved | 2025-11-07 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110239 | 2025-11-03 | 2025-11-05 | done | done | done | Done | done | done | Mingze | 2025-11-03 | 45 | 2025-11-05 | 2025-11-03 | 2025-11-05 | XLWO-20251105-00000156 |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | 45 | 2025-11-06 | 45 | TRUE | 2025-11-06 | 45 | 2025-11-06 | 2025-11-06 | Done | #N/A | #N/A | November | 2025-11-09 |  | 2025-11-15
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0585_1 | Swap_JAW-JT-DMK-0585 | JAW-JT-DMK-0585 | Central Java | Jawa Tengah | Demak | -6.8914 | 110.6309 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0585 | Mangunjiwan Demak | TBG | IBS¦SMG_01N039 | Central Java Ring 91B | MA-JTDMK0585-01H | 10.206.27.111 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-11-03 | 45 |  |  | 2026 | 2025-10-22 | 2025-10-22 | Approved | 2025-11-07 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110235 | 2025-11-03 | 2025-11-05 | done | done | done | Done | done | done | YPTT | 2025-11-03 | 45 | 2025-11-05 | 2025-11-03 | 2025-11-05 | XLWO-20251105-00000156 |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | 45 | 2025-11-06 | 45 | TRUE | 2025-11-06 | 45 | 2025-11-06 | 2025-11-06 | Done | #N/A | #N/A | November | 2025-11-09 |  | 2025-11-21
1 | 1 | CLEAR | Swap_JAW-JT-DMK-0596_1 | Swap_JAW-JT-DMK-0596 | JAW-JT-DMK-0596 | Central Java | Jawa Tengah | Demak | -6.8827 | 110.6766 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0596 | Bolo Demak | Protelindo | ISAT¦14DMK031 | Central Java Ring 91B | MA-SM2531529-01H | 10.206.27.112 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 1 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | No Issue | GPA | 2025-11-03 | 45 |  |  | 2026 | 2025-10-25 | 2025-10-25 | Approved | 2025-11-07 |  | Submitted | Approved | Done |  | Done | Done | 2025-11-02 | DOEID25110237 | 2025-11-03 | 2025-11-05 | done | done | done | Done | done | done | YPTT | 2025-11-03 | 45 | 2025-11-05 | 2025-11-03 | 2025-11-05 | XLWO-20251105-00000156 |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | 45 | 2025-11-06 | 45 | TRUE | 2025-11-06 | 45 | 2025-11-06 | 2025-11-06 | Done | #N/A | #N/A | November | 2025-11-09 |  | 2025-11-21
1 | 2 | CLEAR | Swap_JAW-JT-KDL-0797_2 | Swap_JAW-JT-KDL-0797 | JAW-JT-KDL-0797 | Central Java | Jawa Tengah | Kendal | -6.9708 | 110.0789 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-KDL-0797 | Mpls - Weleri | Centratama |  | Central Java Ring 92 | PAG-JTKDL0797-02H | 10.206.29.229 | ATN910C | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2025-624 sites | Plan Swap December | GPA | 2025-11-10 | 46 |  |  | 2026 | 2025-10-30 | 2025-10-30 | Approved | 2025-11-07 | [34 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-KDL-0872_1 | Swap_JAW-JT-KDL-0872 | JAW-JT-KDL-0872 | Central Java | Jawa Tengah | Kendal | -6.9662 | 110.287 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-KDL-0872 | Mangkang | Centratama |  | Central Java Ring 92 | PAG-JTKDL0872-02H | 10.206.29.230 | ATN910C | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2025-624 sites | Plan Swap December | GPA | 2025-11-10 | 46 |  |  | 2026 |  |  | In Progress |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-2703_1 | Swap_JAW-JT-UNR-2703 | JAW-JT-UNR-2703 | Central Java | Jawa Tengah | Semarang | -7.1818 | 110.4226 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-UNR-2703 | Karangjati | Protelindo |  | Central Java Ring 93 | PAG-JTUNR2703-04H | 10.206.30.235 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | Mid Dec 25 | On Schedule Swap | GCI | 2026-01-26 | 5 |  |  | 2026 | 2025-11-19 |  | Not Started |  |  | Submitted | Approved | [14 empty] | GCI | [14 empty] | 2025-11-27 | 48 | 2025-11-27 |  |  | #N/A | #N/A
1 | 3 | CLEAR | Swap_JAW-JT-PTI-1480_3 | Swap_JAW-JT-PTI-1480 | JAW-JT-PTI-1480 | Central Java | Jawa Tengah | Pati | -6.7527 | 111.0354 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-PTI-1480 | Pati | Others |  | CENTRAL Ring 12B | MA-SM2244-01 | #N/A | ACX2200 | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-10-24 |  | In Progress | [35 empty] | #N/A |  | Done | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-KDS-0942_2 | Swap_JAW-JT-KDS-0942 | JAW-JT-KDS-0942 | Central Java | Jawa Tengah | Kudus | -6.7958 | 110.9612 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDS-0942 | Jekulo | Protelindo |  | CENTRAL Ring 12B | MA-SM2289-01 | #N/A | ACX2200 | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | Plan Swap December | GIT | 2026-01-27 | 5 |  |  | 2026 | 2025-11-12 | [37 empty] | #N/A |  |  | #N/A | #N/A
1 | 4 | CLEAR | Swap_JAW-JT-DMK-0612_4 | Swap_JAW-JT-DMK-0612 | JAW-JT-DMK-0612 | Central Java | Jawa Tengah | Demak | -6.8503 | 110.8054 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-DMK-0612 | Karanganyar Demak | Centratama |  | CENTRAL Ring 12B | MA-SMBC26-01 | #N/A | ACX2200 | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | Plan Swap December | GPA | 2025-10-16 | 42 | October |  | 2026 |  |  | Not Started | [35 empty] | #N/A |  | Done | #N/A | #N/A
1 | 3 | CLEAR | Swap_JAW-JT-SLT-2171_3 | Swap_JAW-JT-SLT-2171 | JAW-JT-SLT-2171 | Central Java | Jawa Tengah | Kota Salatiga | -7.3627 | 110.5156 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SLT-2171 | Tingkir Salatiga | Centratama |  | CENTRAL Ring 13F | MA-SMB239-01 | #N/A | ACX2200 | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December | GIT | 2025-10-14 | 42 | October |  | 2026 | 2025-10-14 |  | Not Started | [35 empty] | #N/A |  | NY | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-UNR-2721_1 | Swap_JAW-JT-UNR-2721 | JAW-JT-UNR-2721 | Central Java | Jawa Tengah | Semarang | -7.3741 | 110.4436 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-UNR-2721 | Getasan | Centratama |  | CENTRAL Ring 13F | MA-SMB321-01 | #N/A | ACX2200 | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | Mid Dec 25 | Plan Swap December |  | 2026-01-27 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 3 | CLEAR | Swap_JAW-JT-KDL-3487_3 | Swap_JAW-JT-KDL-3487 | JAW-JT-KDL-3487 | Central Java | Jawa Tengah | Kendal | -6.96536111111111 | 110.270188888889 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KDL-3487 | Supernode Mangkang | 0 |  | CENTRAL Ring 3A | MA-SMSN0074-01 | #N/A | ACX2200 | Juniper | New Purchase | Swap Cisco | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-20 | 43 | October |  | 2026 | 2025-11-10 | 2025-11-10 | Approved | 2025-11-17 | [34 empty] | #N/A |  | NY | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-YO-YYK-0492_2 | Swap_JAW-YO-YYK-0492 | JAW-YO-YYK-0492 | Central Java | Daerah Istimewa Yogyakarta | Kota Yogyakarta | -7.7893 | 110.3595 | Swap | Swap Only | Swap | Type C | PAG | JAW-YO-YYK-0492 | Mpls - Patok Yogyakartara | Direct Lease |  | MBH Central Java Ring 11 | PAG-YOYYK0492-01H | 10.219.36.21 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December | YPTT | 2025-10-20 | 43 | October |  | 2026 |  |  | In Progress | [35 empty] | #N/A |  | NY | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SMG-2526_1 | Swap_JAW-JT-SMG-2526 | JAW-JT-SMG-2526 | Central Java | Jawa Tengah | Kota Semarang | -6.9978 | 110.4478 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-SMG-2526 | Gayamsari | Others |  | MBH Central Java Ring 114 | PAG-JTSMG2526-02H | 10.206.30.234 | ATN910C | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | PT IFORTE SOLUSI INFOTEK | [7 empty] | 2025-11-09 | #N/A |  |  | 2025-End Nov | On Schedule Swap | GCI | 2026-01-28 | 5 |  |  | 2026 | 2025-11-24 |  | Not Started |  |  | Submitted | Approved | [14 empty] | GCI | [14 empty] | 2025-11-27 | 48 | 2025-11-27 |  |  | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-KLN-1037_2 | Swap_JAW-JT-KLN-1037 | JAW-JT-KLN-1037 | Central Java | Jawa Tengah | Klaten | -7.6918 | 110.6409 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-1037 | Klaten | Protelindo |  | MBH Central Java Ring 11A | MA-JTKLN1037-01H | 10.219.37.49 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-28 | 5 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-KLN-1055_2 | Swap_JAW-JT-KLN-1055 | JAW-JT-KLN-1055 | Central Java | Jawa Tengah | Klaten | -7.6166 | 110.7014 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-1055 | Kota Delanggu | Centratama |  | MBH Central Java Ring 11A | MA-JTKLN1055-01H | 10.219.37.3 | ATN910C-G | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  |  |  | Mingze | 2026-01-28 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKH-2031_1 | Swap_JAW-JT-SKH-2031 | JAW-JT-SKH-2031 | Central Java | Jawa Tengah | Sukoharjo | -7.5592 | 110.7637 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKH-2031 | Karangasem | Protelindo |  | MBH Central Java Ring 11A | MA-JTSKH2031-01H | 10.219.37.94 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-28 | 5 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 3 | CLEAR | Swap_JAW-JT-SKT-2035_3 | Swap_JAW-JT-SKT-2035 | JAW-JT-SKT-2035 | Central Java | Jawa Tengah | Kota Surakarta | -7.546 | 110.78 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKT-2035 | Baturan Reloc | Protelindo |  | MBH Central Java Ring 11A | MA-JTSKT2035-01H | 10.219.37.120 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December | CCSI | 2026-01-29 | 5 |  |  | 2026 | 2025-10-29 | 2025-11-01 | Approved | 2025-11-07 | [34 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SKT-2048_1 | Swap_JAW-JT-SKT-2048 | JAW-JT-SKT-2048 | Central Java | Jawa Tengah | Kota Surakarta | -7.5619 | 110.7922 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKT-2048 | Purwosari Solo | Protelindo |  | MBH Central Java Ring 11A | MA-JTSKT2048-01H | 10.219.37.95 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December | CCSI | 2026-01-29 | 5 |  |  | 2026 | 2025-10-31 | 2025-11-01 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-SKT-2062_2 | Swap_JAW-JT-SKT-2062 | JAW-JT-SKT-2062 | Central Java | Jawa Tengah | Kota Surakarta | -7.5498 | 110.8044 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SKT-2062 | Banyuanyar | Protelindo |  | MBH Central Java Ring 11A | MA-JTSKT2062-01H | 10.219.37.121 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December | CCSI | 2026-01-29 | 5 |  |  | 2026 | 2025-10-30 | 2025-11-01 | Approved | 2025-11-07 | [34 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-YO-SMN-0311_1 | Swap_JAW-YO-SMN-0311 | JAW-YO-SMN-0311 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.7827 | 110.4368 | Swap | Swap Only | Swap | Type B | MA | JAW-YO-SMN-0311 | Adisucipto | Centratama |  | MBH Central Java Ring 11A | MA-YOSMN0311-01H | 10.219.37.249 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | On Schedule Swap |  | 2026-01-29 | 5 |  |  | 2026 | [5 empty] | Submitted | Approved | [14 empty] | YPTT | [14 empty] | 2025-11-30 | 48 | 2025-11-30 |  |  | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-KLN-0989_2 | Swap_JAW-JT-KLN-0989 | JAW-JT-KLN-0989 | Central Java | Jawa Tengah | Klaten | -7.7508 | 110.5159 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-KLN-0989 | Prambanan | Protelindo |  | MBH Central Java Ring 11A | MA-JTKLN0989-01H | 10.219.37.20 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-01-29 | 5 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-YO-SMN-0338_1 | Swap_JAW-YO-SMN-0338 | JAW-YO-SMN-0338 | Central Java | Daerah Istimewa Yogyakarta | Sleman | -7.7621 | 110.4724 | Swap | Swap Only | Swap | Type B | MA | JAW-YO-SMN-0338 | Candi Kalasan | Others |  | MBH Central Java Ring 11A | MA-YOSMN0338-01H | 10.219.37.116 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep |  | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2026 | On Schedule Swap |  | 2026-01-30 | 5 |  |  | 2026 | [5 empty] | Submitted | Approved | [14 empty] | YPTT | [14 empty] | 2025-11-30 | 48 | 2025-11-30 |  |  | #N/A | #N/A
1 | 3 | CLEAR | Swap_JAW-JT-DMK-0613_3 | Swap_JAW-JT-DMK-0613 | JAW-JT-DMK-0613 | Central Java | Jawa Tengah | Demak | -6.90943055555556 | 110.633 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-DMK-0613 | Supernode Demak | 0 |  | MBH Central Java Ring 12 | PAG-JTDMK0613-01H | 10.219.36.17 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 4 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-16 | 42 | October |  | 2026 | 2025-11-03 | 2025-11-03 | Approved | 2025-11-07 |  | Submitted | Approved | 2025-11-16 |  | Done | Done | 2025-11-08 | DOEID251107OC | 2025-11-15 | 2025-11-17 | Done | Done | Done | Done | Done | Done | Mingze | 2025-11-15 | 46 | 2025-11-16 |  | 2025-11-10 | XLWO-20251112-00001205 |  | 2025-11-18 | 2025-11-17 | 2025-11-18 | 47 | 2025-11-18 | 47 | TRUE | 2025-11-17 | 47 | 2025-11-17 | 2025-11-17 | NY | #N/A | #N/A | November | 2025-11-19
1 | 2 | CLEAR | Swap_JAW-JT-PTI-1520_2 | Swap_JAW-JT-PTI-1520 | JAW-JT-PTI-1520 | Central Java | Jawa Tengah | Pati | -6.7188 | 111.1446 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-PTI-1520 | Juana | Protelindo |  | MBH Central Java Ring 12 | PAG-JTPTI1520-01H | 10.219.36.18 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep | 4 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-11-13 | 46 |  |  | 2026 | 2025-11-07 | 2025-10-29 02:50:38 | Reviewing |  |  | Submitted | Approved | 2025-11-16 |  | Done | Done | 2025-11-08 | DOEID251107OE | 2025-11-15 | 2025-11-17 | Done | Done | Done | Done | Done | Done | Mingze | 2025-11-15 | 46 | 2025-11-17 |  | 2025-11-10 | XLWO-20251112-00001205 |  | 2025-11-18 | 2025-11-17 | 2025-11-18 | 47 | 2025-11-18 | 47 | TRUE | 2025-11-17 | 47 | 2025-11-17 | 2025-11-17 | Done | #N/A | #N/A | November | 2025-11-19
1 | 2 | CLEAR | Swap_JAW-JT-MGG-1158_2 | Swap_JAW-JT-MGG-1158 | JAW-JT-MGG-1158 | Central Java | Jawa Tengah | Kota Magelang | -7.4796 | 110.2269 | Swap | Swap Only | Swap | Type C | PAG | JAW-JT-MGG-1158 | Mpls - Magelang | Protelindo |  | MBH Central Java Ring 13 | PAG-JTMGG1158-01H | 10.219.36.10 | ATN910C | Huawei | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GIT | 2025-10-15 | 42 | October |  | 2026 | 2025-10-28 |  |  |  |  | Submitted | Approved | [31 empty] | #N/A |  | NY | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-SMG-2406_2 | Swap_JAW-JT-SMG-2406 | JAW-JT-SMG-2406 | Central Java | Jawa Tengah | Kota Semarang | -6.9856 | 110.4079 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-SMG-2406 | Simpang Lima | DMT |  | MBH Central Java Ring 2 | PAG-JTSMG2406-01H | 10.219.36.27 | ATN910C | Huawei | New Purchase | HRAN Upgrade | Keep | 11 | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December | GIT | 2025-10-14 | 42 | October |  | 2026 | 2025-10-16 | [37 empty] | #N/A |  | NY | #N/A | #N/A
1 | 2 | CLEAR | Swap_JAW-JT-SMG-2526_2 | Swap_JAW-JT-SMG-2526 | JAW-JT-SMG-2526 | Central Java | Jawa Tengah | Kota Semarang | -6.9978 | 110.4478 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-SMG-2526 | Gayamsari | Others |  | MBH Central Java Ring 2 | PAG-JTSMG2526-01H | 10.219.36.28 | ATN910C | Huawei | New Purchase | HRAN Upgrade | Keep | 11 | TypeC 6120H-S Bundle | PT IFORTE SOLUSI INFOTEK | [7 empty] | 2025-11-09 | #N/A |  |  | 2025-End Nov | Plan Swap December |  | 2026-02-02 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SMG-2424_1 | Swap_JAW-JT-SMG-2424 | JAW-JT-SMG-2424 | Central Java | Jawa Tengah | Kota Semarang | -6.9839 | 110.413 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SMG-2424 | Dp Mall Semarang | Others |  | MBH Central Java Ring 2B | MA-JTSMG2424-01H | 10.206.30.175 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 11 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December |  | 2026-02-02 | 6 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SMG-2432_1 | Swap_JAW-JT-SMG-2432 | JAW-JT-SMG-2432 | Central Java | Jawa Tengah | Kota Semarang | -6.9743 | 110.4142 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SMG-2432 | Imam Bonjol Poncol | DMT |  | MBH Central Java Ring 2B | MA-JTSMG2432-01H | 10.219.37.157 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 11 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December |  | 2026-02-02 | 6 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SMG-2487_1 | Swap_JAW-JT-SMG-2487 | JAW-JT-SMG-2487 | Central Java |  |  | #N/A | #N/A | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SMG-2487 | #N/A | #N/A |  | MBH Central Java Ring 2B | MA-JTSMG2487-01H | 10.219.37.21 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 11 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A | [5 empty] | 2026-02-02 | 6 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SMG-2483_1 | Swap_JAW-JT-SMG-2483 | JAW-JT-SMG-2483 | Central Java | Jawa Tengah | Kota Semarang | -6.9814 | 110.427 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SMG-2483 | Loyola Karang Saru (Colocated With Nts) | Protelindo |  | MBH Central Java Ring 2B | MA-JTSMG2483-01H | 10.219.37.161 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 11 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December |  | 2026-02-02 | 6 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SMG-2528_1 | Swap_JAW-JT-SMG-2528 | JAW-JT-SMG-2528 | Central Java | Jawa Tengah | Kota Semarang | -6.9763 | 110.4491 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SMG-2528 | Muktiharjo | Centratama |  | MBH Central Java Ring 2B | MA-JTSMG2528-01H | 10.219.37.23 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 11 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December |  | 2026-02-03 | 6 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SMG-2458_1 | Swap_JAW-JT-SMG-2458 | JAW-JT-SMG-2458 | Central Java | Jawa Tengah | Kota Semarang | -6.9847 | 110.425 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SMG-2458 | Bugangan Relocation | Centratama |  | MBH Central Java Ring 2B | MA-JTSMG2458-01H | 10.219.37.160 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 11 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December |  | 2026-02-03 | 6 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-SMG-2497_1 | Swap_JAW-JT-SMG-2497 | JAW-JT-SMG-2497 | Central Java | Jawa Tengah | Kota Semarang | -6.9841 | 110.432 | Swap | Swap Only | Swap | Type B | MA | JAW-JT-SMG-2497 | Kebon Agung | Protelindo |  | MBH Central Java Ring 2B | MA-JTSMG2497-01H | 10.219.37.22 | ATN910C | Huawei | New Purchase | Swap impact Stitch | Keep | 11 | TypeB 6120H-SC Chassis Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December |  | 2026-02-03 | 6 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | TAKEOUT | Swap_JAW-JB-CBN-2036_1 | Swap_JAW-JB-CBN-2036 | JAW-JB-CBN-2036 | Central Java | Jawa Barat | Kota Cirebon | -6.7411 | 108.576 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JB-CBN-2036 | PEGAMBIRAN | #N/A |  | West Java Ring 14 | PAG-BD2313-01H | 10.219.221.120 | NE40E-X2-M8A | Huawei | New Purchase | Linknet NNI,PAG1 | #N/A |  | TypeC 6120H-S Bundle | [9 empty] | #N/A | [5 empty] | 2026-02-03 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | TAKEOUT | Swap_JAW-JB-CBN-2013_1 | Swap_JAW-JB-CBN-2013 | JAW-JB-CBN-2013 | Central Java | Jawa Barat | Kota Cirebon | -6.7058 | 108.554 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JB-CBN-2013 | PANCURAN CIREBON | #N/A |  | West Java Ring 14 | PAG-BD2314-03H | 10.219.221.119 | NE40E-X2-M8A | Huawei | New Purchase | Linknet NNI,PAG2 | #N/A |  | TypeC 6120H-S Bundle | [9 empty] | #N/A | [5 empty] | 2026-02-03 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | CLEAR | Swap_JAW-JT-CLP-0403_1 | Swap_JAW-JT-CLP-0403 | JAW-JT-CLP-0403 | Central Java | Jawa Tengah | Cilacap | -7.4834 | 108.7923 | Swap&Upgrade | Swap+Upgrade site | Swap | Type C | PAG | JAW-JT-CLP-0403 | Sidareja | Centratama |  | Central Java Ring 16 | PAG-BD2300-01H | 10.219.27.161 | ATN910C-B | Huawei | New Purchase | HRAN Upgrade | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | CCSI | 2026-02-04 | 6 |  |  | 2026 | 2025-10-25 | 2025-10-30 | Approved | 2025-11-07 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 1 | TAKEOUT | Swap_JAW-JB-PWK-1747_1 | Swap_JAW-JB-PWK-1747 | JAW-JB-PWK-1747 | Central Java | Jawa Barat | Purwakarta | -6.5207 | 107.4336 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JB-PWK-1747 | MARACANG PURWAKARTA | #N/A |  | West Java Ring 32 | PAG-BD2175-01H | 10.219.208.209 | NE40E-M2K-B | Huawei | New Purchase | Linknet NNI,PAG1 | #N/A |  | TypeC 6120H-S Bundle | [9 empty] | #N/A | [5 empty] | 2026-02-04 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | TAKEOUT | Swap_JAW-JB-PWK-1787_1 | Swap_JAW-JB-PWK-1787 | JAW-JB-PWK-1787 | Central Java | Jawa Barat | Purwakarta | -6.5222 | 107.458 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JB-PWK-1787 | CISEUREH | #N/A |  | West Java Ring 32 | PAG-BD1951-01H | 10.219.208.210 | NE40E-M2K-B | Huawei | New Purchase | Linknet NNI,PAG2 | #N/A |  | TypeC 6120H-S Bundle | [9 empty] | #N/A | [5 empty] | 2026-02-04 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 1 | HOLD | Swap__1 | Swap_ |  | Central Java |  |  | #N/A | #N/A | Swap | Swap Only | Swap | Type C | PAG |  |  | #N/A |  | CENTRAL Ring 12B | CENTRAL Ring 12B-PAG1 | #N/A | #N/A | #N/A | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A | [5 empty] | 2026-02-04 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 2 | HOLD | Swap__2 | Swap_ |  | Central Java |  |  | #N/A | #N/A | Swap | Swap Only | Swap | Type C | PAG |  |  | #N/A |  | CENTRAL Ring 12B | CENTRAL Ring 12B-PAG2 | #N/A | #N/A | #N/A | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A | [5 empty] | 2026-02-04 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 3 | HOLD | Swap__3 | Swap_ |  | Central Java |  |  | #N/A | #N/A | Swap | Swap Only | Swap | Type C | PAG |  |  | #N/A |  | CENTRAL Ring 13F | CENTRAL Ring 13F-PAG1 | #N/A | #N/A | #N/A | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A | [5 empty] | 2026-02-05 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 4 | HOLD | Swap__4 | Swap_ |  | Central Java |  |  | #N/A | #N/A | Swap | Swap Only | Swap | Type C | PAG |  |  | #N/A |  | CENTRAL Ring 13F | CENTRAL Ring 13F-PAG2 | #N/A | #N/A | #N/A | New Purchase | Swap impact Stitch (PAG Part） | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A | [5 empty] | 2026-02-05 | 6 |  |  | 2026 | [38 empty] | #N/A |  |  | #N/A | #N/A
1 | 4 | CLEAR | Swap_JAW-JT-KDL-3487_4 | Swap_JAW-JT-KDL-3487 | JAW-JT-KDL-3487 | Central Java | Jawa Tengah | Kendal | -6.96536111111111 | 110.270188888889 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | MA | JAW-JT-KDL-3487 | Supernode Mangkang | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | New Purchase | New Ring 001 | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  |  |  | GPA | 2025-10-20 | 43 | October |  | 2026 | 2025-11-10 | 2025-11-10 | Approved | 2025-11-17 |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 3 | CLEAR | Swap_JAW-JT-SMG-2526_3 | Swap_JAW-JT-SMG-2526 | JAW-JT-SMG-2526 | Central Java | Jawa Tengah | Kota Semarang | -6.9978 | 110.4478 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-SMG-2526 | Gayamsari | Others |  | #N/A | #N/A | #N/A | #N/A | #N/A | New Purchase | New Ring 010 | Keep |  | TypeC 6120H-S Bundle | PT IFORTE SOLUSI INFOTEK | [7 empty] | 2025-11-09 | #N/A |  |  | 2025-End Nov | Plan Swap December |  | 2026-02-05 | 6 |  |  | 2026 | [5 empty] | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 3 | CLEAR | Swap_JAW-JT-SMG-2406_3 | Swap_JAW-JT-SMG-2406 | JAW-JT-SMG-2406 | Central Java | Jawa Tengah | Kota Semarang | -6.9856 | 110.4079 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-SMG-2406 | Simpang Lima | DMT |  | #N/A | #N/A | #N/A | #N/A | #N/A | New Purchase | New Ring 010 | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2025-End Nov | Plan Swap December | GIT | 2025-10-14 | 42 | October |  | 2026 | 2025-10-16 |  |  |  |  | Submitted | Approved | [31 empty] | #N/A |  | NY | #N/A | #N/A
1 | 3 | CLEAR | Swap_JAW-JT-KDS-0925_3 | Swap_JAW-JT-KDS-0925 | JAW-JT-KDS-0925 | Central Java | Jawa Tengah | Kudus | -6.8057 | 110.8798 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | #N/A | JAW-JT-KDS-0925 | Ngembal Kulon | Centratama |  | #N/A | #N/A | #N/A | #N/A | #N/A | New Purchase | New Ring 011 | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2026 | Plan Swap December | GIT | 2026-02-06 | 6 |  |  | 2026 | 2025-11-13 |  |  |  |  | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 5 | CLEAR | Swap_JAW-JT-DMK-0612_5 | Swap_JAW-JT-DMK-0612 | JAW-JT-DMK-0612 | Central Java | Jawa Tengah | Demak | -6.8503 | 110.8054 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | PAG | JAW-JT-DMK-0612 | Karanganyar Demak | Centratama |  | #N/A | #N/A | #N/A | #N/A | #N/A | New Purchase | New Ring 011 | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2026 | Plan Swap December | GPA | 2025-10-16 | 42 | October |  | 2026 |  |  | Not Started |  |  | Submitted | Approved | [31 empty] | #N/A |  | Done | #N/A | #N/A
1 | 4 | CLEAR | Swap_JAW-JT-KDS-0925_4 | Swap_JAW-JT-KDS-0925 | JAW-JT-KDS-0925 | Central Java | Jawa Tengah | Kudus | -6.8057 | 110.8798 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | #N/A | JAW-JT-KDS-0925 | Ngembal Kulon | Centratama |  | #N/A | #N/A | #N/A | #N/A | #N/A | New Purchase | New Ring 012 | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2026 | Plan Swap December | GIT | 2026-02-06 | 6 |  |  | 2026 | 2025-11-13 |  |  |  |  | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
1 | 3 | CLEAR | Swap_JAW-JT-KDS-0942_3 | Swap_JAW-JT-KDS-0942 | JAW-JT-KDS-0942 | Central Java | Jawa Tengah | Kudus | -6.7958 | 110.9612 | Swap&Upgrade | Swap+Upgrade Link | Swap | Type C | #N/A | JAW-JT-KDS-0942 | Jekulo | Protelindo |  | #N/A | #N/A | #N/A | #N/A | #N/A | New Purchase | New Ring 012 | Keep |  | TypeC 6120H-S Bundle | [9 empty] | #N/A |  |  | 2026 | Plan Swap December | GIT | 2026-02-06 | 6 |  |  | 2026 | 2025-11-12 |  |  |  |  | Submitted | Approved | [31 empty] | #N/A |  |  | #N/A | #N/A
Formulas:
Survey Week = WEEKNUM([Survey Plan],1)
MOS Plan = [Install Plan]
MOS Plan = [Install Actual]-1
Install Plan = [Integration Plan]-3
Install Plan = [Install Actual]-1
Weekly Install = WEEKNUM([Install Plan],2)
Integration Plan = [Migration Plan]
Weekly Mig = WEEKNUM([Migration Plan],2)
New Weekly Mig = WEEKNUM([New Mig Plan],2)
New Week Plan 2 = WEEKNUM([New Plan 2],2)
RFS Week Plan = WEEKNUM([RFS Plan],2)
MOS Actual = [Install Plan]-1
Note on Q759: 10333988: 与0613配对
Note on Q761: 10333988: 与2526配对